## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | Blockwork Checklist |  |  |  |  | Yes | Blockwork Checklist | 17955318-59ef-418a-a687-3e332e10aacc
checkpoint-status |  |  | checkpoint | Take delivery, stored correctly
checkpoint-status |  |  | checkpoint | Correct Block type, colour, grade
checkpoint-status |  |  | checkpoint | Scaffold situation suitable
checkpoint-status |  |  | checkpoint | Correct steel size, tied and placed
checkpoint-status |  |  | checkpoint | Washouts clean & clear of mortar
checkpoint-status |  |  | checkpoint | Block lintels correct steel type & position
checkpoint-status |  |  | checkpoint | Mortar - Quantities & consistancy correct
checkpoint-status |  |  | checkpoint | Block fill correct Mpa & additives if specified
label | 66b267e7-53c0-5ebf-8ada-9053b457d967 |  | note | See Delivery Dockets (attached)
checkpoint-status |  |  | checkpoint | Area damage Free
checkpoint-status |  |  | checkpoint | Work area left clean & tidy
checkpoint-status |  |  | checkpoint | Joints uniform & clean
checkpoint-status |  |  | checkpoint | Final check to ensure no other trades have damaged the block work
checklist-flat |  |  | checklist | Brickwork for Area: |  |  |  |  | Yes | QA - Brickwork | 203783e8-1292-43bd-b992-4c4a29c286ea
checkpoint-status |  |  | checkpoint | Substrate Acceptable and Ready
boolean | 324e51ee-ee39-5b1e-bc5a-11d976138a42 |  | tickbox | Take delivery, stored correctly
boolean | 80a0ab07-07f9-5d03-ab8e-4a3d651a7fe5 |  | tickbox | Correct brick type, colour, grade
boolean | 6cb32a3e-73f8-58ad-ba5a-d36e64a8dcf7 |  | tickbox | Scaffold situation suitable
checkpoint-status |  |  | checkpoint | Correct cavity size, Cavity clean & clear of mortar
checkpoint-status |  |  | checkpoint | Brick ties, correct fixings grade and spacings
checkpoint-status |  |  | checkpoint | Wire to joint reinforcement
checkpoint-status |  |  | checkpoint | Lintels correct type & position
checkpoint-status |  |  | checkpoint | Brick shelf angles correct type & position
label | 429aa49e-b2c7-5a2c-84e3-edc99571ecde |  | note | Fixings to angles correct type, size & position
checkpoint-status |  |  | checkpoint | DPC to windows
checkpoint-status |  |  | checkpoint | Mortar - Quantities & consistancy correct
checkpoint-status |  |  | checkpoint | Weep, breathing holes in place, clear, vent gaps
checkpoint-status |  |  | checkpoint | Vermin stop in place
checkpoint-status |  |  | checkpoint | Work area left clean & damage free
boolean | a8bca07e-49ff-59ae-bd8f-fc8c50f83621 |  | tickbox | Joints uniform & clean
boolean | bd605406-b7af-5bbf-9ad1-4fd62be61004 |  | tickbox | Raked
checkpoint-status |  |  | checkpoint | Final check to ensure no other trades have damaged the brick work
checklist-flat |  |  | checklist | Variation / Day Works |  |  |  |  | Yes | Variation / Day Works | 6c5bfb8a-fe99-4fbe-98a3-9ac61bfc9822
checkpoint-status |  |  | checkpoint | Variation / SI Details Entered
label | e63d1fb1-ffb4-504c-911e-a1d9924a46d0 |  | note | Please take before photos
text | 0e5fdbad-2ab3-5c87-8eb3-9aeb0d4476ac |  | textbox | Attention:
text | b1d9be82-b3be-5b9b-8568-f780a9836ea9 |  | textbox | Area/Location
text | 3901e99b-a7cc-593b-afa6-917d7e1c6d57 |  | textbox | Date
text | bdcef86b-e792-5b1e-aa3a-903ca1aea735 |  | textbox | Scope of work
text | 4ada19de-3596-5ac4-9d55-d3de0e5f42d9 |  | textbox | Normal Hours
text | cf0cfcfd-2e46-5ccb-a6da-0aa38503e2c2 |  | textbox | Overtime Hours
text | f4913d82-df8c-5492-8be7-d7f3d3eb9139 |  | textbox | Material to Complete Task
checkpoint-status |  |  | checkpoint | Reference/SI Number Entered
text | 73e94ef3-2005-5d76-b994-d862cfd2b5d5 |  | textbox | Reference/SI Number
checkpoint-status |  |  | checkpoint | Variation / SI Work Completed
holdpoint |  |  | signoff | Add Signature Here if Required
checkpoint-status |  |  | checkpoint | Values Added (Office use only)
text | 7d5d7a2f-a0cf-5484-af02-e95b7752c866 |  | textbox | Labour Value
text | 5140e1dd-6e51-5396-b76c-a243db5e124a |  | textbox | Material Value
text | 7815189b-e371-5bba-98a8-855b80af3a62 |  | textbox | Measured Items
text | 36da11ee-bfdc-55f2-adaa-26ee3d1804bf |  | textbox | Total Variation Value