## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | DS2672-ITP-S109 - EW and Drainage Material - Rev 1 | itp |  |  |  |  | DS2672-ITP-S109 - EW and Drainage Material - Rev 1
section | 4.01 General
checkpoint | 4.01.01 - IANZ Laboratory
note | Acceptance / Conformance Criteria - The laboratory shall be IANZ accredited for the specific testing required. The nominated Contractor shall submit details (including certificates, etc) of intended personnel and equipment for approval at least one week prior to the commencement of earthworks.
note | Standard / Specification - 14AED/AD4-C - 030.18.1 / 30.17
note | Verifying Document - IANZ Certification
note | Frequency - One Week Prior to Earthworks
note | Activity - R
note | By - PE
checkpoint | 4.01.02 - NDM Operator and Equipment
note | Acceptance / Conformance Criteria - Submit details (including certificates, etc) of intended personnel and equipment for approval at least one week prior to the commencement of earthworks.
note | Standard / Specification - 14AED/AD4-C - 030.18.1
note | Verifying Document - Training Records
note | Frequency - One week prior to the commencement of earthworks.
note | Activity - HP
note | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.01.03 - Earthworks Supervisor
note | Acceptance / Conformance Criteria - Nominated Contractor shall appoint an experienced full-time earthworks supervisor, whose duties shall include the control of filling operations in accordance with this specification.
note | Standard / Specification - 14AED/AD4-C - 30.17
note | Verifying Document - Approval
note | Frequency - Prior to Works
note | Activity - R
note | By - PE
section | 4.02 Buttress Fill Materials
checkpoint | 4.02.01 - Buttress Fill Sieve Analysis
note | Acceptance / Conformance Criteria - Buttress fill shall be granular material obtained on-site either from undercut or from borrow areas.
note | Standard / Specification - 14AED/AD4-C - 030.13.1 / 030.18.1
note | Verifying Document - IANZ PSD
note | Frequency - 1 set from the first lift, and 1 set per 500 m3 thereafter.
note | Activity - R
note | By - PE
checkpoint | 4.02.02 - Buttress Fill MDD
note | Acceptance / Conformance Criteria - Buttress fill shall be tested for Heavy Compaction test (Proctor Test). Where appropriate, an oversize correction shall be applied to the target density derived from laboratory compaction tests.
note | Standard / Specification - 14AED/AD4-C - 030.18.1
note | Verifying Document - IANZ MDD
note | Frequency - 2 sets at commencement of project.
note | Activity - R
note | By - PE
section | 4.03 Drainage Materials
checkpoint | 4.03.01 - HDPE Welder
note | Acceptance / Conformance Criteria - HDPE pipes shall be joined using the electro-fusion method. To ensure the full strength of the pipe is achieved and the connections are of a consistent quality, installers must be properly trained and certified.
note | Standard / Specification - 14AED/AD4-C - 040.5.1
note | Verifying Document - Training Records
note | Frequency - Prior to Welding
note | Activity - R
note | By - PE
checkpoint | 4.03.02 - HDPE Welding Equipment
note | Acceptance / Conformance Criteria - The HDPE Welder and power supply used for the fusion couplers shall be of a high quality and have the capability of readily fusing pipes of the specified diameter and wall thickness.
note | Standard / Specification - 14AED/AD4-C - 040.5.1
note | Verifying Document - Datasheets
note | Frequency - Prior to Welding
note | Activity - R
note | By - PE
checkpoint | 4.03.03 - Filter / Drainage F1, F2, F3 Weathering Resistance
note | Acceptance / Conformance Criteria - Zone F1, F2, F3 shall be tested for Weathering quality index
note | Standard / Specification - 14AED/AD4-C - 030.18.1
note | Verifying Document - IANZ Weathering Report
note | Frequency - 1 test for each material type
note | Activity - R
note | By - PE
checkpoint | 4.03.04 - Filter / Drainage Zone F1 Sieve Analysis
note | Acceptance / Conformance Criteria - Filter / drainage Zone F1 shall be tested for Sieve Analysis and fines testing
note | Standard / Specification - 14AED/AD4-C - 030.18.1 / 030.13.2
note | Verifying Document - IANZ PSD / Fines Test
note | Frequency - 1 pre-construction. 1 on initial placement. 2 further samples during placement.
note | Activity - R
note | By - PE
checkpoint | 4.03.05 - Filter / Drainage Zone F2 Sieve Analysis
note | Acceptance / Conformance Criteria - Filter / drainage Zone F2 shall be tested for Sieve Analysis and fines testing
note | Standard / Specification - 14AED/AD4-C - 030.18.1 / 030.13.3
note | Verifying Document - IANZ PSD / Fines Test
note | Frequency - 1 pre-construction. 1 on initial placement. 5 further samples during placement.
note | Activity - R
note | By - PE
checkpoint | 4.03.06 - Filter / Drainage Zone F3 Sieve Analysis
note | Acceptance / Conformance Criteria - Filter / drainage Zone F3 shall be tested for Sieve Analysis and fines testing
note | Standard / Specification - 14AED/AD4-C - 030.18.1 / 030.13.4
note | Verifying Document - IANZ PSD / Fines Test
note | Frequency - 1 pre-construction. 1 on initial placement. 3 further samples during placement.
note | Activity - R
note | By - PE
checkpoint | 4.03.07 - Subsoil Drain Pipes
note | Acceptance / Conformance Criteria - Subsoil drain pipes shall be DN200 HDPE PN10 pipe. Five rows of 5mm holes shall be drilled at 75mm spacing along the length of the pipe, with the perforated portion of the pipe laid upwards.
note | Standard / Specification - 14AED/AD4-C - 040.4.1
note | Verifying Document - Datasheet / Inspection
note | Frequency - Prior to Works
note | Activity - R
note | By - PE
checkpoint | 4.03.08 - Drainage Outlet Pipe
note | Acceptance / Conformance Criteria - Where shown on the drawings, all outlet pipes shall be DN630 HDPE PN12.5 pipe with standard dimension ratios as indicated.
note | Standard / Specification - 14AED/AD4-C - 040.4.2
note | Verifying Document - Datasheet
note | Frequency - Prior to Works
note | Activity - R
note | By - PE
section | 4.04 Rip Rap Materials
checkpoint | 4.04.01 - Rip Rap Source
note | Acceptance / Conformance Criteria - Only hard, sound rock of uniform quality not subject to deterioration or breakdown will be acceptable. The rock shall be free of defined cleavage planes and should not be adversely affected by wetting and drying.
note | Standard / Specification - 14AED/AD4-C - 030.13.5
note | Verifying Document - Source Properties / Investigation
note | Frequency - Prior to use
note | Activity - R
note | By - PE
checkpoint | 4.04.02 - Rip Rap Grading
note | Acceptance / Conformance Criteria - Rock riprap shall not be single sized but shall be a well graded mixture designed to ensure that all interstices between large rocks are filled with rock of progressively smaller size.
note | Standard / Specification - 14AED/AD4-C - 030.13.5
note | Verifying Document - On Site PSD / Investigation
note | Frequency - Prior to use
note | Activity - R
note | By - PE
checkpoint | 4.04.03 - Rip Rap Rock Shape
note | Acceptance / Conformance Criteria - Rock should preferably be predominantly angular in shaped with not more than 25% of rocks, distributed through the gradation, having a length more than twice the breadth or thickness.
note | Standard / Specification - 14AED/AD4-C - 030.13.5
note | Verifying Document - On Site PSD / Investigation
note | Frequency - Prior to use
note | Activity - R
note | By - PE
section | 4.05 River Diversion Materials
checkpoint | 4.05.01 - Site Derived Granular Fill
note | Acceptance / Conformance Criteria - River Diversion shall be Site Derived Granular Fill
note | Standard / Specification - DWG - 14AED-AD4-111
note | Verifying Document - Site Records
note | Frequency - Prior to use
note | Activity - R
note | By - PE
checkpoint | 4.05.02 - Bidim
note | Acceptance / Conformance Criteria - River Diversion Bidim shall be A39 filter fabric.
note | Standard / Specification - DWG - 14AED-AD4-111
note | Verifying Document - Datasheet
note | Frequency - Prior to Works
note | Activity - R
note | By - PE