## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | DS2672-ITP-S110 - EW General and Setup - Rev 1 | itp |  |  |  |  | DS2672-ITP-S110 - EW General and Setup - Rev 1
section | 3.01 Site Requirements
checkpoint | 3.01.01 - Construction Pack
note | Acceptance / Conformance Criteria - Submit a Construction Pack including a Methodology and JESA to the Engineer before works
note | Standard / Specification - Downer
note | Verifying Document - Construction Pack
note | Frequency - Submit Prior to commencement of works
note | Activity - H
note | By - PE
checkpoint | 3.01.02 - Survey Setout
note | Acceptance / Conformance Criteria - Survey Set out as per contract drawings and specification, capturing pre-construction levels where needed.
note | Standard / Specification - Downer
note | Verifying Document - Survey Records
note | Frequency - Prior to Works
note | Activity - H
note | By - SV
checkpoint | 3.01.03 - Service Location
note | Acceptance / Conformance Criteria - Complete the Excavation permit process to identify, locate and protect all services.
note | Standard / Specification - Downer
note | Verifying Document - Excavation Permit
note | Frequency - Prior to Excavation
note | Activity - H
note | By - SE
checkpoint | 3.01.04 - Internal Permits
note | Acceptance / Conformance Criteria - Complete internal Permits as required to complete works including but not limited to: Hot works, concrete saw, lift, confined space, working at height etc.
note | Standard / Specification - Downer
note | Verifying Document - Internal Permits
note | Frequency - Prior to Excavation
note | Activity - H
note | By - SE
checkpoint | 3.01.05 - External Permits
note | Acceptance / Conformance Criteria - Obtain External Permits as required to complete works including but not limited to: Close approach, Worksafe Notice etc.
note | Standard / Specification - Downer
note | Verifying Document - External Permits
note | Frequency - Prior to Excavation
note | Activity - H
note | By - PE
checkpoint | 3.01.06 - Approved Construction Drawings
note | Acceptance / Conformance Criteria - Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version.
note | Standard / Specification - Downer
note | Verifying Document - IFC Drawings
note | Frequency - Prior to works start
note | Activity - H
note | By - PE
section | 3.02 Hold Points
checkpoint | 3.02.03 - Diversion Notice
note | Acceptance / Conformance Criteria - The Consent Holder shall inform a Compliance Officer of the Consent Authority at least five working days prior to any diversion taking place to allow an inspection of the works to be undertaken.
note | Standard / Specification - P&G 14
note | Verifying Document - Notice
note | Frequency - At least five working days prior to any diversion
note | Activity - HP
note | By - ENG
holdpoint | AUTHORITY HOLDPOINT
section | 5.01 Erosion and Sediment Controls
checkpoint | 5.01.01 - Certification
note | Acceptance / Conformance Criteria - Prior to bulk earthworks commencing, the nominated Contractor shall submit asbuilt drawings to the Engineer for approval, and to confirm the erosion and sediment controls have been constructed in accordance with the approved E&SCP and Resource Consent conditions.
note | Standard / Specification - 14AED/AD4-C - 020.5.7
note | Verifying Document - Jet-Grouting Asbuilt Drawings
note | Frequency - Prior to Bulk Earthworks
note | Activity - HP
note | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.01.02 - Seasonal Restriction
note | Acceptance / Conformance Criteria - No vegetation removal or earthworks on the site shall be undertaken between 30 April and 1 October in any year, without the written approval of the Engineer. Earthworks in this regard refers to bulk earthworks (cut/fill/waste) associated with the site.
note | Standard / Specification - 14AED/AD4-C - 020.5.9
note | Verifying Document - Hold Point Release
note | Frequency - Each Occurrence
note | Activity - HP
note | By - ENG
holdpoint | AUTHORITY HOLDPOINT
section | 5.02 Diversion
checkpoint | 5.02.01 - Diversion Management Plan
note | Acceptance / Conformance Criteria - The nominated contractor shall prepare a management plan covering all work below river level and submit it to the Engineer for review.
note | Standard / Specification - 14AED/AD4-C - 030.4
note | Verifying Document - Management Plan
note | Frequency - Prior to Works
note | Activity - HP
note | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.02.02 - Diversion Bund Methodology
note | Acceptance / Conformance Criteria - The Diversion bund shall be constructed using site-derived granular soils, with rock rip-rap on both the upstream and downstream shoulders. The nominated Contractor shall provide a method statement for construction of the bund for the approval of the Engineer.
note | Standard / Specification - 14AED/AD4-C - 030.13.6
note | Verifying Document - Methodology
note | Frequency - Prior to Works
note | Activity - HP
note | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.02.03 - Completed spillway strengthening works
note | Acceptance / Conformance Criteria - Completed spillway strengthening works (by others) prior to commencement of diversion works must be inspected by the Engineer prior to further work being carried out in the area.
note | Standard / Specification - 14AED/AD4-C - 030.3
note | Verifying Document - Hold Point Release
note | Frequency - 48 Hours Notice Prior to Each Occurrence
note | Activity - HP
note | By - ENG
holdpoint | AUTHORITY HOLDPOINT
section | 5.03 Clearing, Stripping, and Excavation
checkpoint | 5.03.01 - Excavation of Upper Dam Shoulder Inspection
note | Acceptance / Conformance Criteria - Excavation of upper dam shoulder at interface with spillway block and cut-off wall, placement of filter and drainage materials: full-time designer site presence must be inspected by the Engineer prior to further work being carried out in the area.
note | Standard / Specification - 14AED/AD4-C - 030.3
note | Verifying Document - Hold Point Release
note | Frequency - 48 Hours Notice Prior to Each Occurrence
note | Activity - HP
note | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.03.02 - Excavated upper dam shoulder Inspection
note | Acceptance / Conformance Criteria - Excavated upper dam shoulder, each subsequent 20m wide section prior to placement of filter and drainage materials must be inspected by the Engineer prior to further work being carried out in the area.
note | Standard / Specification - 14AED/AD4-C - 030.3
note | Verifying Document - Hold Point Release
note | Frequency - 48 Hours Notice Prior to each subsequent 20m wide section
note | Activity - HP
note | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.03.03 - Organic Material Removal
note | Acceptance / Conformance Criteria - All organic material shall be removed from the areas subject to excavation or filling. Turf, topsoil, and any scrub shall be removed to expose soil containing insignificant amounts of organic material.
note | Standard / Specification - 14AED/AD4-C - 030.7.1
note | Verifying Document - Site Records / Photos
note | Frequency - When encountered
note | Activity - A
note | By - PE
checkpoint | 5.03.04 - Topsoil Stockpiling
note | Acceptance / Conformance Criteria - All significant volumes of topsoil shall be stockpiled for later re-use. Materials containing insufficient amounts of topsoil for practical separation shall be disposed of in dump areas to be designated by the Engineer.
note | Standard / Specification - 14AED/AD4-C - 030.7.1
note | Verifying Document - Site Records / Photos
note | Frequency - When encountered
note | Activity - A
note | By - PE
checkpoint | 5.03.05 - Tree and Bush Clearing
note | Acceptance / Conformance Criteria - No trees or bush shall be cleared without approval from the Engineer.
note | Standard / Specification - 14AED/AD4-C - 030.7.2
note | Verifying Document - Hold Point Release
note | Frequency - Prior to Removal
note | Activity - HP
note | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.03.06 - Surface Drainage Control
note | Acceptance / Conformance Criteria - All earthworks shall be carried out in the dry. Both cut and fill areas shall be sloped adequately during construction so that they do not pond water and temporary drains shall be provided as necessary to ensure the effective removal of stormwater from the areas of operation into the site drainage system.
note | Standard / Specification - 14AED/AD4-C - 030.7.3
note | Verifying Document - Site Records / Photos
note | Frequency - During Works
note | Activity - R
note | By - SE
checkpoint | 5.03.07 - Unsuitable Material Removal
note | Acceptance / Conformance Criteria - Unsuitable material shall be excluded from the construction works and be placed in a disposal area as directed by the Engineer in loose layer thicknesses not exceeding 500 mm and be track rolled with a minimum of two passes.
note | Standard / Specification - 14AED/AD4-C - 030.14.7
note | Verifying Document - Site Records / Photos
note | Frequency - When encountered
note | Activity - R
note | By - SE
checkpoint | 5.03.08 - Water in Excavation
note | Acceptance / Conformance Criteria - The excavation shall be free of water at all times
note | Standard / Specification - 14AED/AD4-C - 030.10
note | Verifying Document - Site Records / Photos
note | Frequency - Daily
note | Activity - M
note | By - SE
checkpoint | 5.03.09 - Dewatering Sump Backfilling
note | Acceptance / Conformance Criteria - Sumps formed for the purposes of dewatering shall be backfilled and compacted in layers with suitable fill to the approval of the Engineer.
note | Standard / Specification - 14AED/AD4-C - 030.10
note | Verifying Document - Site Records / Photos
note | Frequency - Each Sump
note | Activity - HP
note | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.03.10 - Bulk Excavation
note | Acceptance / Conformance Criteria - Excavation within the buttress footprint shall be to intact rock, which is anticipated to be weak siltstone.
note | Standard / Specification - 14AED/AD4-C - 030.8
note | Verifying Document - Site Records / Photos
note | Frequency - During Works
note | Activity - I
note | By - SE
checkpoint | 5.03.11 - Bulk Excavation Protection
note | Acceptance / Conformance Criteria - No compaction or trafficking on the exposed rock shall be undertaken, as it is likely that the surface will be sensitive to disturbance and deterioration.
note | Standard / Specification - 14AED/AD4-C - 030.8
note | Verifying Document - Site Records / Photos
note | Frequency - During Works
note | Activity - R
note | By - SE
checkpoint | 5.03.12 - Subgrade Inspection
note | Acceptance / Conformance Criteria - On completion of the bulk excavation, inspection and testing of the subgrade shall be performed by the Engineer.
note | Standard / Specification - 14AED/AD4-C - 030.8
note | Verifying Document - Hold Point Release
note | Frequency - 48 Hours Notice Prior to Each Occurrence
note | Activity - HP
note | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.03.13 - Inspection Prior to Filling
note | Acceptance / Conformance Criteria - Before fill is placed in any area, the Engineer shall be notified so that he may inspect the stripping and/or removal of unsuitable materials to see that this prior work meets with the specified requirements. No filling shall be undertaken until inspections have been made and the Engineer has approved the commencement to fill.
note | Standard / Specification - 14AED/AD4-C - 030.11
note | Verifying Document - Hold Point Release
note | Frequency - Prior to Filling
note | Activity - HP
note | By - ENG
holdpoint | AUTHORITY HOLDPOINT
section | 10.01 Site Post Construction Activities
checkpoint | 10.01.01 - Construction Record Compilation
note | Acceptance / Conformance Criteria - Compile construction records for final submission ensuring defects (NCRs) / Snags / missing records are captured or closed out, all tests have been received and passed, and changes / omissions have been noted.
note | Standard / Specification - Downer
note | Verifying Document - Records
note | Frequency - Post construction
note | Activity - H
note | By - SE
checkpoint | 10.01.02 - Survey Records
note | Acceptance / Conformance Criteria - Ensure all items have been surveyed and records are assembled for asbuilting
note | Standard / Specification - Downer P&G 20.1
note | Verifying Document - Records
note | Frequency - Post construction
note | Activity - H
note | By - SV
checkpoint | 10.01.03 - Redline Drawings
note | Acceptance / Conformance Criteria - Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in red pen. Red-pen mark-up copies of the Drawings and Specifications and other design documentation showing any deviations from the specified details and requirements produced in accordance with industry good practice.
note | Standard / Specification - Downer P&G 20.1
note | Verifying Document - Redlines
note | Frequency - Post construction
note | Activity - H
note | By - PE
checkpoint | 10.01.04 - Defect, Snag and Punch List
note | Acceptance / Conformance Criteria - Update the project Defect, Snag and Punch List Register
note | Standard / Specification - Downer
note | Verifying Document - Register
note | Frequency - Post construction
note | Activity - H
note | By - PE