## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | DS2672-ITP-S111 - Drainage - Rev 1 | itp |  |  |  |  | DS2672-ITP-S111 - Drainage - Rev 1
section | 5.04 Placement and Compaction of Fill General
checkpoint | 5.04.01 - Retaining Wall foundation Inspection
note | Acceptance / Conformance Criteria - Excavated natural ground in foundation area of retaining wall upgrade/extension works prior to placement of fill or concrete must be inspected by the Engineer prior to further work being carried out in the area.
note | Standard / Specification - 14AED/AD4-C - 030.3
note | Verifying Document - Hold Point Release
note | Frequency - 48 Hours Notice Prior to Each Occurrence
note | Activity - HP
note | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.04.02 - Earthwork Drainage
note | Acceptance / Conformance Criteria - Cut and fill areas shall be sloped and graded adequately so that they do not pond stormwater, and drains shall be installed as necessary on a regular basis to deflect run off from the areas of operation, or to drain ponded water as soon as ponds are seen to develop.
note | Standard / Specification - 14AED/AD4-C - 034.14.1
note | Verifying Document - Site Records / Photos
note | Frequency - Daily
note | Activity - R
note | By - SE
checkpoint | 5.04.03 - Wet Weather
note | Acceptance / Conformance Criteria - No fill shall be placed during periods of wet weather.
note | Standard / Specification - 14AED/AD4-C - 034.14.1
note | Verifying Document - Site Records / Photos
note | Frequency - Daily
note | Activity - M
note | By - SE
checkpoint | 5.04.04 - Extended Wet Weather Resumption Approval
note | Acceptance / Conformance Criteria - In the event of fill operations ceasing in any area on account of wet weather or for more than one week for any reason, the nominated Contractor shall obtain the Engineer’s approval of the conditions of the fill surface before recommencing fill operations.
note | Standard / Specification - 14AED/AD4-C - 034.14.1
note | Verifying Document - Hold Point Release
note | Frequency - Each Occurrence
note | Activity - HP
note | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.04.05 - Compaction Adjacent to Retaining Structures
note | Acceptance / Conformance Criteria - Rollers shall not be operated within 2m of retaining walls with placement of fill in 200mm maximum thickness lifts and compaction shall be via hand equipment or a small roller without vibration.
note | Standard / Specification - 14AED/AD4-C - 034.14.3
note | Verifying Document - Site Records / Photos
note | Frequency - Each Structure
note | Activity - V
note | By - SE
section | 5.05 F1, F2 and F3 Placement and Compaction
checkpoint | 5.05.01 - Preparation of stripped ground surface inspection
note | Acceptance / Conformance Criteria - Preparation of stripped ground surface prior to placement of site concrete must be inspected by the Engineer prior to further work being carried out in the area.
note | Standard / Specification - 14AED/AD4-C - 030.3
note | Verifying Document - Hold Point Release
note | Frequency - 48 Hours Notice Prior to Each Occurrence
note | Activity - HP
note | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.05.02 - Excavated lower dam shoulder / foundation Inspection
note | Acceptance / Conformance Criteria - Excavated lower dam shoulder/foundation, each 20m wide section prior to placement of filter and drainage materials must be inspected by the Engineer prior to further work being carried out in the area.
note | Standard / Specification - 14AED/AD4-C - 030.3
note | Verifying Document - Hold Point Release
note | Frequency - 48 Hours Notice Prior to Each Occurrence
note | Activity - HP
note | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.05.03 - Placement of filter and drainage material Inspection at Upper dam shoulder
note | Acceptance / Conformance Criteria - Placement of filter and drainage material, a full-time designer site presence must be inspected by the Engineer prior to further work being carried out in the area.
note | Standard / Specification - 14AED/AD4-C - 030.3
note | Verifying Document - Hold Point Release
note | Frequency - 48 Hours Notice Prior to Each Occurrence
note | Activity - HP
note | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.05.04 - Placement of Drainage Material
note | Acceptance / Conformance Criteria - Filter/drainage material shall be placed in a way which prevents segregation, contamination or breakdown of particles with the maximum loose lift thickness for filter/drainage materials is 200mm.
note | Standard / Specification - 14AED/AD4 -C -034.14.5
note | Verifying Document - Site Records / Photos
note | Frequency - Each Layer
note | Activity - C
note | By - SE
checkpoint | 5.05.05 - Compaction of Drainage Material
note | Acceptance / Conformance Criteria - Where space constraints allow, compaction shall comprise two passes with a self-propelled smooth-drum roller without vibration. In areas where space constraints prevent the use of a roller, compaction shall comprise two passes with a vibrating plate compactor or similar.
note | Standard / Specification - 14AED/AD4 -C -034.14.5
note | Verifying Document - Site Records / Photos
note | Frequency - Each Layer
note | Activity - C
note | By - SE
checkpoint | 5.05.06 - Excessive Compaction of Drainage Material
note | Acceptance / Conformance Criteria - The nominated Contractor shall ensure excessive compaction is avoided as this may reduce drain permeability. The nominated Contractor shall avoid damage to pipes. If pipes are damaged, they shall be removed and replaced.
note | Standard / Specification - 14AED/AD4 -C -034.14.5
note | Verifying Document - Site Records / Photos
note | Frequency - Each Layer
note | Activity - M
note | By - SE
checkpoint | 5.05.07 - Surface Drainage
note | Acceptance / Conformance Criteria - Construction of drainage works shall be staged such that sub-surface drains do not act as surface drains or can be otherwise contaminated by siltation or vehicle trafficking prior to placement of buttressing bulk fill.
note | Standard / Specification - 14AED/AD4 -C -034.14.5
note | Verifying Document - Construction Pack
note | Frequency - Prior to works
note | Activity - M
note | By - SE
section | 5.06 Subsoil Drainage
checkpoint | 5.06.01 - Subsoil Drainage Timing
note | Acceptance / Conformance Criteria - The subsoil drainage system shall be installed prior to the commencement of filling operations.
note | Standard / Specification - 14AED/AD4-C - 030.12
note | Verifying Document - Site Records / Photos
note | Frequency - Prior to the commencement of filling
note | Activity - R
note | By - PE
checkpoint | 5.06.02 - Installation of all new drainage pipes Inspection
note | Acceptance / Conformance Criteria - Installation of all new drainage pipes in buttress, prior to backfilling must be inspected by the Engineer prior to further work being carried out in the area.
note | Standard / Specification - 14AED/AD4-C - 030.3 / 040.4.1
note | Verifying Document - Hold Point Release
note | Frequency - 48 Hours Notice Prior to Each Occurrence
note | Activity - HP
note | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.06.03 - Subsoil Drainage Grading
note | Acceptance / Conformance Criteria - The subsoil drains and collector pipe shall be uniformly graded to ensure they do not hold water and evenly jointed to ensure unimpeded flow.
note | Standard / Specification - 14AED/AD4-C - 030.12
note | Verifying Document - Survey Records
note | Frequency - During Installation
note | Activity - D
note | By - SV
checkpoint | 5.06.04 - Bedding for Pipes
note | Acceptance / Conformance Criteria - Embedment material for drainage pipes within the buttress shall comprise Zone F3 drainage material.
note | Standard / Specification - 14AED/AD4-C - 040.4.3
note | Verifying Document - Site Records / Photos
note | Frequency - Each Pipe
note | Activity - I
note | By - SE
checkpoint | 5.06.05 - HDPE Jointing
note | Acceptance / Conformance Criteria - HDPE pipes shall be joined using the electro-fusion method ensuring the internal diameters are within 3mm and are not out of roundness along the length of the pipe.
note | Standard / Specification - 14AED/AD4-C - 040.5.1
note | Verifying Document - Welding Checksheet
note | Frequency - Each Weld
note | Activity - I
note | By - SE