## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | DS2672-ITP-S112 - Buttress Fill - Rev 1 | itp |  |  |  |  | DS2672-ITP-S112 - Buttress Fill - Rev 1
section | 5.04 Placement and Compaction of Fill General
checkpoint | 5.04.01 - Retaining Wall foundation Inspection
note | Acceptance / Conformance Criteria - Excavated natural ground in foundation area of retaining wall upgrade/extension works prior to placement of fill or concrete must be inspected by the Engineer prior to further work being carried out in the area.
note | Standard / Specification - 14AED/AD4-C - 030.3
note | Verifying Document - Hold Point Release
note | Frequency - 48 Hours Notice Prior to Each Occurrence
note | Activity - HP
note | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.04.02 - Earthwork Drainage
note | Acceptance / Conformance Criteria - Cut and fill areas shall be sloped and graded adequately so that they do not pond stormwater, and drains shall be installed as necessary on a regular basis to deflect run off from the areas of operation, or to drain ponded water as soon as ponds are seen to develop.
note | Standard / Specification - 14AED/AD4-C - 034.14.1
note | Verifying Document - Site Records / Photos
note | Frequency - Daily
note | Activity - R
note | By - SE
checkpoint | 5.04.03 - Wet Weather
note | Acceptance / Conformance Criteria - No fill shall be placed during periods of wet weather.
note | Standard / Specification - 14AED/AD4-C - 034.14.1
note | Verifying Document - Site Records / Photos
note | Frequency - Daily
note | Activity - M
note | By - SE
checkpoint | 5.04.04 - Extended Wet Weather Resumption Approval
note | Acceptance / Conformance Criteria - In the event of fill operations ceasing in any area on account of wet weather or for more than one week for any reason, the nominated Contractor shall obtain the Engineer’s approval of the conditions of the fill surface before recommencing fill operations.
note | Standard / Specification - 14AED/AD4-C - 034.14.1
note | Verifying Document - Hold Point Release
note | Frequency - Each Occurrence
note | Activity - HP
note | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.04.05 - Compaction Adjacent to Retaining Structures
note | Acceptance / Conformance Criteria - Rollers shall not be operated within 2m of retaining walls with placement of fill in 200mm maximum thickness lifts and compaction shall be via hand equipment or a small roller without vibration.
note | Standard / Specification - 14AED/AD4-C - 034.14.3
note | Verifying Document - Site Records / Photos
note | Frequency - Each Structure
note | Activity - V
note | By - SE
section | 5.07 Buttress Fill Placement and Compaction
checkpoint | 5.07.01 - Start of the buttress filling Inspection
note | Acceptance / Conformance Criteria - Start of the buttress filling operation must be inspected by the Engineer prior to further work being carried out in the area.
note | Standard / Specification - 14AED/AD4-C - 030.3
note | Verifying Document - Hold Point Release
note | Frequency - 48 Hours Notice Prior to Each Occurrence
note | Activity - HP
note | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.07.02 - Compaction Effort
note | Acceptance / Conformance Criteria - Compaction of granular earthfill shall be carried out using a 10-tonne (minimum static weight), smooth steel drum vibrating roller, or approved equivalent and shall be demonstrated and conformance confirmed via a compaction trial.
note | Standard / Specification - 14AED/AD4-C - 034.14.2
note | Verifying Document - Compaction Trail
note | Frequency - Prior to Works
note | Activity - H
note | By - PE
checkpoint | 5.07.03 - Buttress Fill
note | Acceptance / Conformance Criteria - Each fill layer for dam fill shall be given the higher of the trail result or four passes with vibration, even if the acceptance standard is met with fewer passes. No pumping of weaving of granular fill is permitted.
note | Standard / Specification - 14AED/AD4 -C - 034.14.4 / 034.14.1
note | Verifying Document - Site Records / Photos
note | Frequency - Each layer
note | Activity - V
note | By - SE
checkpoint | 5.07.04 - Borrow Fill Moisture Content
note | Acceptance / Conformance Criteria - Prior to removal of material from a borrow area wet or dry the material to a uniform moisture content close to optimum for the material.
note | Standard / Specification - 14AED/AD4-C - 034.14.2
note | Verifying Document - Site Records / Photos
note | Frequency - Daily
note | Activity - C
note | By - SE
checkpoint | 5.07.05 - Placement and Compaction of Dam Fill
note | Acceptance / Conformance Criteria - Spread out the fill in a layer of uniform loose thickness. Loose layer thickness shall not exceed 300mm for granular earthfill.
note | Standard / Specification - 14AED/AD4-C - 034.14.2
note | Verifying Document - Site Records / Photos
note | Frequency - Each layer
note | Activity - V
note | By - SE
checkpoint | 5.07.06 - Buttress Fill Compaction
note | Acceptance / Conformance Criteria - Buttress Fill shall be compacted to an average density to 97%MDD and a minimum of 95%MDD for any one test over 10 consecutive test sets. A set of tests shall comprise two or more individual tests made within an area of 0.5m². In-situ moisture/ density (NDM method with laboratory moisture content)
note | Standard / Specification - 14AED/AD4-C - 034.14.4 / 030.18.1 /
note | Verifying Document - NDM Records
note | Frequency - 10 tests (5 sets) per 500mm placed
note | Activity - I
note | By - SE
note | Comments / Closeout Details - RFI With Kerry B.
checkpoint | 5.07.07 - Buttress Fill Proof Rolling
note | Acceptance / Conformance Criteria - The deflection of the compacted fill surface for any lift during a proof roll with a 10t smooth drum roller shall be less than 7mm.
note | Standard / Specification - 14AED/AD4-C - 034.14.4 / 030.18.1
note | Verifying Document - Proof Roll
note | Frequency - Each layer
note | Activity - I
note | By - SE
checkpoint | 5.07.08 - Steep Slope Key
note | Acceptance / Conformance Criteria - Where dam fill abuts sloping ground steeper than 18º (1V:3H), the natural ground or fill being filled against shall be keyed in. The horizontal width of the key shall be equal to the thickness of the compacted layer.
note | Standard / Specification - 14AED/AD4-C - 034.14.2
note | Verifying Document - Site Records / Photos
note | Frequency - Each Occurrence
note | Activity - C
note | By - SE
checkpoint | 5.07.09 - Overfilling dam embankments
note | Acceptance / Conformance Criteria - During construction, the batters shall be overfilled by a minimum of 1m (horizontal), and this overfill should be pulled up by digger, and used as the final lift(s) of fill on the dam crest.
note | Standard / Specification - 14AED/AD4-C - 034.14.2
note | Verifying Document - Site Records / Photos
note | Frequency - Final Embankment Layer
note | Activity - C
note | By - SE
checkpoint | 5.07.10 - Dam Fill Tolerances and Profiles
note | Acceptance / Conformance Criteria - The finished tolerances for the dam crest level is -0/+200mm. For upstream and downstream batters finished tolerances are –100/+200mm (vertical height), and the surface shall be visually regular.
note | Standard / Specification - 14AED/AD4-C - 030.14.8
note | Verifying Document - Survey Records
note | Frequency - Finished Fill
note | Activity - D
note | By - SV
checkpoint | 5.07.11 - Completed buttressing works Inspection
note | Acceptance / Conformance Criteria - Completion of buttressing works to final level must be inspected by the Engineer prior to further work being carried out in the area.
note | Standard / Specification - 14AED/AD4-C - 030.3
note | Verifying Document - Hold Point Release
note | Frequency - 48 Hours Notice Prior to Each Occurrence
note | Activity - HP
note | By - ENG
holdpoint | AUTHORITY HOLDPOINT