## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | DS2672-ITP-S113 - Rip Rap - Rev 1 | itp |  |  |  |  | DS2672-ITP-S113 - Rip Rap - Rev 1
section | 5.08 Rip Rap Installation
checkpoint | 5.08.01 - Foundation inspection
note | Acceptance / Conformance Criteria - Prior to the placement of RIPRAP the foundation must be inspected by the Engineer prior to further work being carried out in the area.
note | Standard / Specification - DOWNER
note | Verifying Document - Hold Point Release
note | Frequency - 48 Hours Notice Prior to Each Occurrence
note | Activity - HP
note | By - ENG
note | Comments / Closeout Details - Is this Required
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.08.02 - Placement of Rip Rap
note | Acceptance / Conformance Criteria - Rip rap shall be machine placed such that segregation of breakage of stone does not occur. Dumping and spreading of rock shall not be permitted. Stone shall be released as close to is final position as practical to minimise dragging and rehandling.
note | Standard / Specification - 14AED/AD4-C - 030.14.6
note | Verifying Document - Site Records / Photos
note | Frequency - Each Layer
note | Activity - C
note | By - SE
checkpoint | 5.08.03 - Rip Rap Voids
note | Acceptance / Conformance Criteria - Rip Rap shall have no significant voids occur in the rock blanket through which underlying material could be washed out.
note | Standard / Specification - 14AED/AD4-C - 030.13.5
note | Verifying Document - Site Records / Photos
note | Frequency - Each Layer
note | Activity - C
note | By - SE
checkpoint | 5.08.04 - Rip Rap Loose rocks
note | Acceptance / Conformance Criteria - Rip Rap shall create an interlocking mass of rock in which no individual rock is free to move by itself; and
note | Standard / Specification - 14AED/AD4-C - 030.13.5
note | Verifying Document - Site Records / Photos
note | Frequency - Each Layer
note | Activity - C
note | By - SE
checkpoint | 5.08.05 - Rip Rap Protruding Rocks
note | Acceptance / Conformance Criteria - Rip Rap shall create a shielding effect on the surface of the rock, which avoids high drag forces that occur when individual rocks protrude into the flow.
note | Standard / Specification - 14AED/AD4-C - 030.13.5
note | Verifying Document - Site Records / Photos
note | Frequency - Each Layer
note | Activity - C
note | By - SE
checkpoint | 5.08.06 - Rip Rap Post Installation PSD
note | Acceptance / Conformance Criteria - The particle size distribution after handling and placement shall conform to the limits set in 030.13.5.
note | Standard / Specification - 14AED/AD4-C - 030.13.5
note | Verifying Document - Site Records / Photos
note | Frequency - Each Layer
note | Activity - I
note | By - SE