## ITP Cover Page
[16 empty] | Insitu Concrete Construction Inspection and Test Plan | [7 empty] | Subordinate Inspection and Test Plan
Project: Peacocke Whatukooruru Drive
Number and Revision: DS1205 - 103 - Rev D
SECTION 1 – GENERAL DETAILS
Project Name: |  |  | Peacocke Whatukooruru Drive |  |  |  |  | ITP Number: |  |  | 103 | [5 empty] | Subordinate ITP Cover page UPDATE
Project Number: |  |  | DS1205 |  |  |  |  | ITP Status: |  |  | Draft For Approval
ITP Description: |  |  | Insitu Concrete Construction |  |  |  |  | Revision: | 1000 |  | D
Contract Number: |  |  | Peacocke Whatukooruru Drive |  |  |  |  | Drawing Sets:
Customer: |  |  | Hamilton City Council |  |  |  |  | Specification: |  |  | Project Specification and Appendices.
Quality Specified: |  |  | NZTA Z/1
Review / Update History | [9 empty] | Verification Activity | [6 empty] | Subordinate Inspection and Test Plan Details
Rev: | Status: | Date: |  | Reviewed By: |  | Revision Details: |  |  |  | Activity Key |  |  | Responsibilities Key |  |  |  | Construction Pack Number: |  |  | CP##
A | Draft for Approval |  |  |  |  | First Revieion for Review and Approval |  |  |  | A | Action |  | ENG | Engineer / Engineer's Rep |  |  | Work Area / Chainage / Lot: | [5 empty] | SUB ITP NO. S-
[10 empty] | B | Report by Breach |  | CR | Customer Rep
B | Draft for Approval |  |  |  |  | In response to Engineer's comments on 15 February 2023 for Review and Approval |  |  |  | C | Check |  | PD | Project Director
[10 empty] | D | Dimension Inspection |  | PM | Project Manager |  |  | Master ITP Details:
C | Draft for Approval |  |  |  |  | In response to Engineer's comments on 11 May 2023 for Review and Approval |  |  |  | E | Examine |  | OP | Operations Manager |  |  | Review / Update History
[10 empty] | HP | Hold Point (Engineer) |  | HSE | HSE Manager / Rep |  |  | Rev: | Status: | Date: |  | Reviewed By: | Revision Details:
D | Draft for Approval |  |  |  |  | In response to Engineer's comments on 19 May 2023 for Review and Approval |  |  |  | H | Hold Point (Internal) |  | QM | QA Manager / Rep |  |  | A |  |  |  |  | Subordinate ITP Creation for
[10 empty] | I | Inspection |  | PE | Project Engineer
[10 empty] | M | Monitor on Random Basis |  | SE | Site Engineer
[10 empty] | O | Operation |  | QE | Quality Engineer
[10 empty] | R | Review |  | SUP | Superintendent / Supervisor |  |  | SUB ITP Instructions: 0. Master ITP to be Approved and Accepted 1. Extract Cover page (this page) and Body page to new Workbook 2. Drag and drop the two white cell blocs above into the cover page 3. Assign an ITP Number in Mater ITP Register tab 4. Populate Title Page Details 5. Remove all Inspection points in the Body which do not relate to works 6. Review for approval, submitting to Client / Engineer once internally approved
[10 empty] | S | Subcontractor |  | SV | Surveyor
[10 empty] | V | Visual Verification |  | ITP | Third Party Inspector
[10 empty] | W | Witness Point |  | SPEC | Specialist
SECTION 2A – Master ITP Approval | [7 empty] | SECTION 2B – ITP CLOSEOUT
Position |  | Name: |  |  | Signature: |  | Date: | Position |  | Name: |  | Signature: |  |  | Date:
Downer PM | [7 empty] | Downer PM
Downer QM | [7 empty] | Downer QM
Client (If Applicable) | [7 empty] | Client (If Applicable)

## In-situ Concrete Construction
Insitu Concrete Construction Inspection and Test Plan
Project: Peacocke Whatukooruru Drive
Number and Revision: DS1205 - 103 - Rev D
Item No. | Inspection and Test Point | Acceptance / Conformance Criteria | Standard / Specification | Verifying Document | Frequency | Verification Activity
[6 empty] | Activity | By
SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
1.01 | Site Requirements
1.01.01 | Construction Pack | Construction Pack including a Methodology and JESA to be assembled , uploaded and transmitted on InEight before works commence. | Downer | Construction Pack | Prior to Works | H | PE
1.01.02 | Survey Setout | The Contractor shall verify the setting out position, level and line of the bridge, prior to commencing construction. The Contractor shall advise the Engineer of any apparent anomalies identified. | Downer PS - 11.2 | Survey Records | Prior to Works | H | PE
1.01.03 | Internal Permits | Complete internal Permits as required to complete works including but not limited to: Hot works, concrete saw, lift, confined space, working at height etc. | Downer | Internal Permits | Prior to activity being undertaken | H | SE
1.01.04 | External Permits | Obtain External Permits as required to complete works including but not limited to: Close approach, Worksafe Notice etc. | Downer | External Permits | Prior to commencment of activity | H | SE
1.01.05 | Approved Construction Drawings | Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version. | Downer | IFC Drawings | Prior to works start | H | PE
1.01.06 | Construction Methodology | The Contractor must submit their proposed construction methodology and justification to the Engineer for review at least 10 Working Days prior to commencement of bridge construction. The Engineer’s review will be limited to conceptual assessment of any potential impact on critical elements of the structure. | PS - 11.3 SS 2146 - 3 | Methodology | At least 10 Working Days prior to commencement | HP | ENG
1.01.07 | Stakeholder | Inform stakeholder of upcoming pours. Special considerations to early morning pours, potential for noise monitoring requirements being triggered. *Forward correspondence around notifications of early morning pours to the Engineer and HCC before pours are carried out. | CNVMO / CCCP | correspondence with stake holders | per pour | H | PE
SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
2.01 | Temporary Works
2.01.01 | Chartered Engineer | The Contractor shall employ or retain a Chartered Engineer registered with Engineering New Zealand and experienced in the design of temporary works and erection engineering activities to design and provide construction oversight for all temporary works as specified in these Contract Documents and/or as may be necessary to complete the Physical Works. | PS - 11.14 | Chartered Engineer Details | Prior to Temporary Works | HP | PE
2.01.02 | Drawings and calculations | The drawings and calculations for the temporary works and/or erection engineering activities prepared by the Contractor shall be submitted to the Engineer for review in advance of proceeding with any temporary works covered by the drawings and calculations to facilitate construction. In no case shall construction commence until the Engineer has reviewed and accepted the drawings and calculations. | PS - 11.14 | Approved Drawings and calculations | Prior to Temporary Works | HP | ENG
2.02 | Concrete
2.02.01 | Concrete Mix Design | Concrete mix design to be completed and reviewed by the contractor prior use on site. The following criteria are to be satisfied: • Strength: 40Mpa • Normal maximum aggregate size: 20mm • Basic drying shrinkage strain 720 microstain • Concrete materials and manufacturing are to comply with NZS3109 • All concrete shall contain a minimum of 25kg/m3 of micro silica for enhanced durability. • Only one brand of cement shall be used throughout the works without prior Engineer’s written acceptance. • Details of the types and rates of application of the admixtures proposed are to be supplied to the Engineer for acceptance. • Trials undertaken in advance of production to verify outcomes are being achieved in accordance with mix design expectations. This is to include if the mixes will be pumped. • The Contractor shall identify appropriate preventive measures and to justify those measures to the Engineer to minimise the risk of Alkali Silica Reaction (ASR). | PS - 11.5 SS 2140 - 3, 4, 9, 6.1, 6.3, 6.5 | Concrete Mix Design | All Mix Designs | H | PE
2.02.02 | Concrete Mix Design Checklist | Each mix design shall have a completed concrete checklist with supporting data including Trial Results, submitted at least 5 Working Days prior to production of that mix design, for the Engineer’s review and acceptance. | PS - 11.5 SS 2140 - 9 | Concrete Checklist | 5 Working Days prior to production of that mix design | HP | ENG
2.03 | Reinforcement
2.03.01 | Reinforcement | 3D modelling completed, bar bending schedule checked against latest construction drawings and submitted to the Engineeer for review | Downer | Reinforcment shop drawings | Each batch of reinforcement | H | PE
2.03.02 | Reinforcement | Mill & test certificates for each batch of reinforcement used to be provided to the Engineer. Unless specifically nominated otherwise on the Drawings, only Grade 500E reinforcement manufactured using the micro-alloyed process is acceptable. | SS 2142 - 3 PS - 11.6 | Mill Certs | Each Batch assigned to Each Pour | R | ENG
2.03.03 | Welding reinforcing | Prior to welding reinforcement, approval from the Engineer must be obtained. The person undertaking the weld must hold the relevant certification. | SS 2142 - 9 | Approval | Prior to welding (if required) | HP | ENG
2.03.04 | Steel supply | Certificate of origin for all steel reinforcing supplied | NA | Certificate | Each batch of reinforcment | R | ENG
SECTION 3 – CONSTRUCTION ACTIVITY
3.01 | Pre pour
3.01.01 | Temporary Works | Temporary works to be installed as per design drawings. Permit to load to be issued by temporary works inspector prior to loading element | Downer | Permit to load | As defined in the temporary works design | H | PE
3.01.02 | Reciept of Reinforcment | Reinforcement checked against bending schedule. Bars correct length, size, shape, grade, and free of defects. | IFC Drawings SS 2142 | Photos / delivery dockets | Each pour | I | SE
3.01.03 | Reinforcing Welding and NDT Inspections | All reinforcing steel welding should comply with AS/NZS 1554.3; and all welded splices shall also conform with NZS 3109 Clause 3.7.2 or 3.7.3. | SS 2142 - 9 AS/NZS 1554:3 NZS 3109 Cl 3.7.2 or 3.7.3 | TPI Report | Each weld prior to installation | H | TPI
3.01.04 | Pre pour inspection | Pre-pour inspection checklist undertaken by the Site Engineer and captured on the ConQA web app. All aspects of the element to be checked against latest construction drawings and specification requirements. | Downer | Pre Pour | Each Pour | H | SE
3.01.05 | Engineers Inspection | The Contractor shall advise the Engineer when he intends to commence placing concrete. No concrete shall be placed until the Engineer is satisfied that the requirements of this Specification and the Drawings relating to formwork, reinforcement and construction joints have been complied with entirely. No concrete shall be placed in the absence of the Engineer without prior acceptance. | SS 2146 - 6 PS - 2.2.16 | Hold Point Release | Min 48h Notice | HP | ENG
3.01.06 | ESCP | All erosion and sediment control measures are to be installed and maintained in accordance with Site Specific ESCP | Site Specific ESCP | Acceptance | Each pour | I | SE
3.01.07 | Concrete Cover | Concrete Cover: 75mm - all concrete cast in contact with the ground 50mm - where protected from soil contact during casting by formwork or by a suitable damp-proof membrane 40mm - standard unless noted otherwise on the drawings Tolerances: i) In slabs and walls ...... +10, -0mm ii) In beams and columns ...... +10, -0mm iii) At ends of members ....... +25, -0mm | IFC Drawing NZS 3109 Secion 3.9 | Approval | Before concreting | I | SE
3.02 | Concrete Pour
3.02.01 | Unfavourable Conditions - Cold Weather | Concrete shall not be placed in conditions where temperature is below 5°C with temperature decreasing or below 2°C with temperature increasing. | PS - 11.5 NZS3901 cl 7.2 | Pre Pour | Each Pour | R | SE
3.02.02 | Unfavourable Conditions - Hot Weather | Concrete shall not be placed in excessively hot dry conditions. Concrete temperature should not be higher than 30°C | NZS3901 Cl. 7.2.1 & Cl. 7.2.2 | Pre Pour | Each Pour | R | SE
3.02.03 | Unfavourable Conditions - Rain | Concrete shall not be commenced when heavy rains is falling or threathening and if rain commences during a pour, the work shall be protected as directed to prevent damage to the concrete or to any newly finished surfaces until the concrete has set to such a stage as to withstand leaching of the cement. | BBO SS2146 | Pre / During Pour | Each Pour | R | SE
3.02.04 | Construction Joints | Where a concrete surface is to act as a construction joint to receive infill over or adjacent, the contact surface interface shall be prepared to the Engineer’s satisfaction to be clean, free of laitance, and with a peak to trough roughness of not less than 5mm to ensure compliance with Type B construction joints as defined by NZS3109 Section 5.6. | PS - 11.5 NZS3109 Section 5.6 | Pre / Post Pour | Each Pour | I | SE
3.02.05 | Delivery dockets | Each batch delivered shall be accompanied by a delivery docket certifying the cement type, maximum aggregate size, specified strength, slump or spread, date, time mixing completed, and time water added at the plant. | SS 2140 - 4 | Dockets | Each Delivery | R | SE
3.02.06 | Slump tests and spread tests | Slump tests or spread tests shall be taken for each delivery of concrete and the results recorded by the Contractor | SS 2140 - 7 NZS3109 Table 9.1 | Photos or slumps and on-site records | Each Delivery | I | SE
3.02.07 | Time Limits | Concrete not placed and vibrated in forms after 90 minutes have lapsed from the stated time that water was added at the plant, or within 30 minutes after discharge from the mixer or agitator truck, may be rejected by the Engineer. Concrete not placed in its final position in the forms before initial set has occurred shall not be used. For concrete mixes containing set accelerating admixtures the above times shall be halved. | SS 2146 - 7 | Site Notes Batching record Delivery dockets | Each Delivery | R | SE
3.02.08 | Compression Testing | Compression testing shall be carried out at an independent laboratory accepted by the Engineer. A set of specimens for compression tests shall consist of four specimens for each concrete pour, one of which is to be tested at 7 days and the remainder at 28 days. Cylinders are to be cast on-site straight from the truck, not at the batching plant. Larger pours greater than 75m^3 will require an additional set of cylunders to be taken. | SS 2140 - 4 SS 2140 - 7 | Compression Tests | Each pour | R | SE
3.02.09 | Concrete finishes | Concrete finish are to be as specified by NZS3114, scheduled as follows: Barriers: F5 Precast elements - exterior faces : F5, connecting faces to other elements: Type B construction joints to NZS3109 Exposed concrete : F5 Element below ground: F2/U2 Top surface of desk: U5 | NZS3114 NZS3109 | Approval | Post concreting | R | ENG
3.02.10 | Curing | Minium of 7 days wet curing for all concrete including prestressed concrete after completion of accelerated curing | SS2146 -11 Construction Drawing | Acceptance / Repair Details | post concreting | H | SE
3.03 | Post Pour
3.03.01 | Falsework and Formwork Removal | Formwork shall not be removed until minimum periods set down in Table 5.3 of NZS3109 have elapsed. The stripping time may be reduced if it is shown by field-cured tests that compressive strength has been attained of twice the stress to which the member will be subjected at the time of stripping or as directed by the temporary works engineer. | SS 2144 - 10 NZS3109 Table 5.3 Downer | Approval | Before removal of Falsework and Formwork | H | SE
3.03.02 | Post Pour Inspection | Post pour inspection undertaken by the site engineer and captured in the ConQA web app. Engineer notified of any defects. | Downer | Site Photos | Each pour | H | SE
3.03.03 | Concrete Repair | Repair of any minor surface defect or structural defect of concrete shall only be carried out with the Engineer’s acceptance. All repaired concrete shall have the same strength, durability and surface finish as the parent concrete unless otherwise accepted by the Engineer. | SS 2146 - 11 PS - 11.5 | Acceptance / Repair Details | Prior to Each Repair | HP | ENG
SECTION 4 – POST CONSTRUCTION
4.01 | Site Post Construction Activities
4.01.01 | Construction Record Compilation | Compile construction records for final submission ensuring defects (NCRs) / Snags / missing records are captured or closed out, all tests have been received and passed, and changes / omissions have been noted. | Downer | Records | Post construction | H | SE
4.01.02 | Survey Records | Ensure all items have been surveyed and records are assembled for asbuilting | Downer | Records | Post construction | H | SV
4.01.03 | Redline Drawings | Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in red pen. | Downer | Redlines | Post construction | H | SE
4.01.04 | Defect, Snag and Punch List | Update the project Defect, Snag and Punch List Register | Downer | Register | Post construction | H | SE
4.01.05 | Delivery dockets | At the completion of the Contract a schedule of delivery docket numbers for all concrete supplied shall be forwarded to the Engineer. | SS 2140 - 4 | Dockets | Post construction | H | SE