## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP - Insitu Concrete Construction - Rev D | itp |  |  |  |  | ITP - Insitu Concrete Construction - Rev D
section | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements
checkpoint | 1.01.01 - Construction Pack
note | Acceptance / Conformance Criteria - Construction Pack including a Methodology and JESA to be assembled , uploaded and transmitted on InEight before works commence.
note | Standard / Specification - Downer
note | Verifying Document - Construction Pack
note | Frequency - Prior to Works
note | Activity - H
note | By - PE
checkpoint | 1.01.02 - Survey Setout
note | Acceptance / Conformance Criteria - The Contractor shall verify the setting out position, level and line of the bridge, prior to commencing construction. The Contractor shall advise the Engineer of any apparent anomalies identified.
note | Standard / Specification - Downer PS - 11.2
note | Verifying Document - Survey Records
note | Frequency - Prior to Works
note | Activity - H
note | By - PE
checkpoint | 1.01.03 - Internal Permits
note | Acceptance / Conformance Criteria - Complete internal Permits as required to complete works including but not limited to: Hot works, concrete saw, lift, confined space, working at height etc.
note | Standard / Specification - Downer
note | Verifying Document - Internal Permits
note | Frequency - Prior to activity being undertaken
note | Activity - H
note | By - SE
checkpoint | 1.01.04 - External Permits
note | Acceptance / Conformance Criteria - Obtain External Permits as required to complete works including but not limited to: Close approach, Worksafe Notice etc.
note | Standard / Specification - Downer
note | Verifying Document - External Permits
note | Frequency - Prior to commencment of activity
note | Activity - H
note | By - SE
checkpoint | 1.01.05 - Approved Construction Drawings
note | Acceptance / Conformance Criteria - Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version.
note | Standard / Specification - Downer
note | Verifying Document - IFC Drawings
note | Frequency - Prior to works start
note | Activity - H
note | By - PE
checkpoint | 1.01.06 - Construction Methodology
note | Acceptance / Conformance Criteria - The Contractor must submit their proposed construction methodology and justification to the Engineer for review at least 10 Working Days prior to commencement of bridge construction.
note | • The Engineer’s review will be limited to conceptual assessment of any potential impact on critical elements of the structure.
note | Standard / Specification - PS - 11.3, SS 2146 - 3
note | Verifying Document - Methodology
note | Frequency - At least 10 Working Days prior to commencement
note | Activity - HP
note | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.01.07 - Stakeholder
note | Acceptance / Conformance Criteria - Inform stakeholder of upcoming pours. Special considerations to early morning pours, potential for noise monitoring requirements being triggered.
note | *Forward correspondence around notifications of early morning pours to the Engineer and HCC before pours are carried out.
note | Standard / Specification - CNVMO / CCCP
note | Verifying Document - correspondence with stake holders
note | Frequency - per pour
note | Activity - H
note | By - PE
section | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works
checkpoint | 2.01.01 - Chartered Engineer
note | Acceptance / Conformance Criteria - The Contractor shall employ or retain a Chartered Engineer registered with Engineering New Zealand and experienced in the design of temporary works and erection engineering activities to design and provide construction oversight for all temporary works as specified in these Contract Documents and/or as may be necessary to complete the Physical Works.
note | Standard / Specification - PS - 11.14
note | Verifying Document - Chartered Engineer Details
note | Frequency - Prior to Temporary Works
note | Activity - HP
note | By - PE
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.01.02 - Drawings and calculations
note | Acceptance / Conformance Criteria - The drawings and calculations for the temporary works and/or erection engineering activities prepared by the Contractor shall be submitted to the Engineer for review in advance of proceeding with any temporary works covered by the drawings and calculations to facilitate construction. In no case shall construction commence until the Engineer has reviewed and accepted the drawings and calculations.
note | Standard / Specification - PS - 11.14
note | Verifying Document - Approved Drawings and calculations
note | Frequency - Prior to Temporary Works
note | Activity - HP
note | By - ENG
holdpoint | AUTHORITY HOLDPOINT
section | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete
checkpoint | 2.02.01 - Concrete Mix Design
note | Acceptance / Conformance Criteria - Concrete mix design to be completed and reviewed by the contractor prior use on site. The following criteria are to be satisfied:
note | • Strength: 40Mpa
note | • Normal maximum aggregate size: 20mm
note | • Basic drying shrinkage strain 720 microstain
note | • Concrete materials and manufacturing are to comply with NZS3109
note | • All concrete shall contain a minimum of 25kg/m3 of micro silica for enhanced durability.
note | • Only one brand of cement shall be used throughout the works without prior Engineer’s written acceptance.
note | • Details of the types and rates of application of the admixtures proposed are to be supplied to the Engineer for acceptance.
note | • Trials undertaken in advance of production to verify outcomes are being achieved in accordance with mix design expectations. This is to include if the mixes will be pumped.
note | • The Contractor shall identify appropriate preventive measures and to justify those measures to the Engineer to minimise the risk of Alkali Silica Reaction (ASR).
note | Standard / Specification - PS - 11.5, SS 2140 - 3, 4, 9, 6.1, 6.3, 6.5
note | Verifying Document - Concrete Mix Design
note | Frequency - All Mix Designs
note | Activity - H
note | By - PE
checkpoint | 2.02.02 - Concrete Mix Design Checklist
note | Acceptance / Conformance Criteria - Each mix design shall have a completed concrete checklist with supporting data including Trial Results, submitted at least 5 Working Days prior to production of that mix design, for the Engineer’s review and acceptance.
note | Standard / Specification - PS - 11.5, SS 2140 - 9
note | Verifying Document - Concrete Checklist
note | Frequency - 5 Working Days prior to production of that mix design
note | Activity - HP
note | By - ENG
holdpoint | AUTHORITY HOLDPOINT
section | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement
checkpoint | 2.03.01 - Reinforcement
note | Acceptance / Conformance Criteria - 3D modelling completed, bar bending schedule checked against latest construction drawings and submitted to the Engineeer for review
note | Standard / Specification - Downer
note | Verifying Document - Reinforcment shop drawings
note | Frequency - Each batch of reinforcement
note | Activity - H
note | By - PE
checkpoint | 2.03.02 - Reinforcement
note | Acceptance / Conformance Criteria - Mill & test certificates for each batch of reinforcement used to be provided to the Engineer. Unless specifically nominated otherwise on the Drawings, only Grade 500E reinforcement manufactured using the micro-alloyed process is acceptable.
note | Standard / Specification - SS 2142 - 3, PS - 11.6
note | Verifying Document - Mill Certs
note | Frequency - Each Batch assigned to Each Pour
note | Activity - R
note | By - ENG
checkpoint | 2.03.03 - Welding reinforcing
note | Acceptance / Conformance Criteria - Prior to welding reinforcement, approval from the Engineer must be obtained. The person undertaking the weld must hold the relevant certification.
note | Standard / Specification - SS 2142 - 9
note | Verifying Document - Approval
note | Frequency - Prior to welding (if required)
note | Activity - HP
note | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.03.04 - Steel supply
note | Acceptance / Conformance Criteria - Certificate of origin for all steel reinforcing supplied
note | Standard / Specification - NA
note | Verifying Document - Certificate
note | Frequency - Each batch of reinforcment
note | Activity - R
note | By - ENG
section | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour
checkpoint | 3.01.01 - Temporary Works
note | Acceptance / Conformance Criteria - Temporary works to be installed as per design drawings. Permit to load to be issued by temporary works inspector prior to loading element
note | Standard / Specification - Downer
note | Verifying Document - Permit to load
note | Frequency - As defined in the temporary works design
note | Activity - H
note | By - PE
checkpoint | 3.01.02 - Reciept of Reinforcment
note | Acceptance / Conformance Criteria - Reinforcement checked against bending schedule. Bars correct length, size, shape, grade, and free of defects.
note | Standard / Specification - IFC Drawings, SS 2142
note | Verifying Document - Photos / delivery dockets
note | Frequency - Each pour
note | Activity - I
note | By - SE
checkpoint | 3.01.03 - Reinforcing Welding and NDT Inspections
note | Acceptance / Conformance Criteria - All reinforcing steel welding should comply with AS/NZS 1554.3; and all welded splices shall also conform with NZS 3109 Clause 3.7.2 or 3.7.3.
note | Standard / Specification - SS 2142 - 9, AS/NZS 1554:3, NZS 3109 Cl 3.7.2 or 3.7.3
note | Verifying Document - TPI Report
note | Frequency - Each weld prior to installation
note | Activity - H
note | By - TPI
checkpoint | 3.01.04 - Pre pour inspection
note | Acceptance / Conformance Criteria - Pre-pour inspection checklist undertaken by the Site Engineer and captured on the ConQA web app. All aspects of the element to be checked against latest construction drawings and specification requirements.
note | Standard / Specification - Downer
note | Verifying Document - Pre Pour
note | Frequency - Each Pour
note | Activity - H
note | By - SE
checkpoint | 3.01.05 - Engineers Inspection
note | Acceptance / Conformance Criteria - The Contractor shall advise the Engineer when he intends to commence placing concrete. No concrete shall be placed until the Engineer is satisfied that the requirements of this Specification and the Drawings relating to formwork, reinforcement and construction joints have been complied with entirely.
note | • No concrete shall be placed in the absence of the Engineer without prior acceptance.
note | Standard / Specification - SS 2146 - 6, PS - 2.2.16
note | Verifying Document - Hold Point Release
note | Frequency - Min 48h Notice
note | Activity - HP
note | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.01.06 - ESCP
note | Acceptance / Conformance Criteria - All erosion and sediment control measures are to be installed and maintained in accordance with Site Specific ESCP
note | Standard / Specification - Site Specific ESCP
note | Verifying Document - Acceptance
note | Frequency - Each pour
note | Activity - I
note | By - SE
checkpoint | 3.01.07 - Concrete Cover
note | Acceptance / Conformance Criteria - Concrete Cover:
note | • 75mm - all concrete cast in contact with the ground
note | • 50mm - where protected from soil contact during casting by formwork or by a suitable damp-proof membrane
note | • 40mm - standard unless noted otherwise on the drawings
note | ○ Tolerances:
note | i) In slabs and walls ...... +10, -0mm
note | ii) In beams and columns ...... +10, -0mm
note | iii) At ends of members ....... +25, -0mm
note | Standard / Specification - IFC Drawing, NZS 3109 Secion 3.9
note | Verifying Document - Approval
note | Frequency - Before concreting
note | Activity - I
note | By - SE
section | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour
checkpoint | 3.02.01 - Unfavourable Conditions - Cold Weather
note | Acceptance / Conformance Criteria - Concrete shall not be placed in conditions where temperature is below 5°C with temperature decreasing or below 2°C with temperature increasing.
note | Standard / Specification - PS - 11.5, NZS3901 cl 7.2
note | Verifying Document - Pre Pour
note | Frequency - Each Pour
note | Activity - R
note | By - SE
checkpoint | 3.02.02 - Unfavourable Conditions - Hot Weather
note | Acceptance / Conformance Criteria - Concrete shall not be placed in excessively hot dry conditions. Concrete temperature should not be higher than 30°C
note | Standard / Specification - NZS3901 Cl. 7.2.1 & Cl. 7.2.2
note | Verifying Document - Pre Pour
note | Frequency - Each Pour
note | Activity - R
note | By - SE
checkpoint | 3.02.03 - Unfavourable Conditions - Rain
note | Acceptance / Conformance Criteria - Concrete shall not be commenced when heavy rains is falling or threathening and if rain commences during a pour, the work shall be protected as directed to prevent damage to the concrete or to any newly finished surfaces until the concrete has set to such a stage as to withstand leaching of the cement.
note | Standard / Specification - BBO SS2146
note | Verifying Document - Pre / During Pour
note | Frequency - Each Pour
note | Activity - R
note | By - SE
checkpoint | 3.02.04 - Construction Joints
note | Acceptance / Conformance Criteria - Where a concrete surface is to act as a construction joint to receive infill over or adjacent, the contact surface interface shall be prepared to the Engineer’s satisfaction to be clean, free of laitance, and with a peak to trough roughness of not less than 5mm to ensure compliance with Type B construction joints as defined by NZS3109 Section 5.6.
note | Standard / Specification - PS - 11.5, NZS3109 Section 5.6
note | Verifying Document - Pre / Post Pour
note | Frequency - Each Pour
note | Activity - I
note | By - SE
checkpoint | 3.02.05 - Delivery dockets
note | Acceptance / Conformance Criteria - Each batch delivered shall be accompanied by a delivery docket certifying the cement type, maximum aggregate size, specified strength, slump or spread, date, time mixing completed, and time water added at the plant.
note | Standard / Specification - SS 2140 - 4
note | Verifying Document - Dockets
note | Frequency - Each Delivery
note | Activity - R
note | By - SE
checkpoint | 3.02.06 - Slump tests and spread tests
note | Acceptance / Conformance Criteria - Slump tests or spread tests shall be taken for each delivery of concrete and the results recorded by the Contractor
note | – – – – – – – – –
note | Table 9.1 - Tolerances for nominated slump
note | Nominated slump (mm) ¦¦ Tolerance for snatch sample (mm)
note | – – – – – – – – –
note | 60 or less ¦¦ ±20
note | 70 - 110 ¦¦ ±30
note | Greater than 110 ¦¦ ±40
note | – – – – – – – – –
note | Standard / Specification - SS 2140 - 7, NZS3109 Table 9.1
note | Verifying Document - Photos or slumps and on-site records
note | Frequency - Each Delivery
note | Activity - I
note | By - SE
checkpoint | 3.02.07 - Time Limits
note | Acceptance / Conformance Criteria - Concrete not placed and vibrated in forms after 90 minutes have lapsed from the stated time that water was added at the plant, or within 30 minutes after discharge from the mixer or agitator truck, may be rejected by the Engineer.
note | • Concrete not placed in its final position in the forms before initial set has occurred shall not be used. For concrete mixes containing set accelerating admixtures the above times shall be halved.
note | Standard / Specification - SS 2146 - 7
note | Verifying Document - Site Notes, Batching record, Delivery dockets
note | Frequency - Each Delivery
note | Activity - R
note | By - SE
checkpoint | 3.02.08 - Compression Testing
note | Acceptance / Conformance Criteria - Compression testing shall be carried out at an independent laboratory accepted by the Engineer.
note | • A set of specimens for compression tests shall consist of four specimens for each concrete pour, one of which is to be tested at 7 days and the remainder at 28 days. Cylinders are to be cast on-site straight from the truck, not at the batching plant.
note | • Larger pours greater than 75m^3 will require an additional set of cylunders to be taken.
note | Standard / Specification - SS 2140 - 4, SS 2140 - 7
note | Verifying Document - Compression Tests
note | Frequency - Each pour
note | Activity - R
note | By - SE
checkpoint | 3.02.09 - Concrete finishes
note | Acceptance / Conformance Criteria - Concrete finish are to be as specified by NZS3114, scheduled as follows:
note | • Barriers: F5
note | • Precast elements - exterior faces : F5, connecting faces to other elements: Type B construction joints to NZS3109
note | • Exposed concrete : F5
note | • Element below ground: F2/U2
note | • Top surface of desk: U5
note | Standard / Specification - NZS3114, NZS3109
note | Verifying Document - Approval
note | Frequency - Post concreting
note | Activity - R
note | By - ENG
checkpoint | 3.02.10 - Curing
note | Acceptance / Conformance Criteria - Minium of 7 days wet curing for all concrete including prestressed concrete after completion of accelerated curing
note | Standard / Specification - SS2146 -11 Construction Drawing
note | Verifying Document - Acceptance / Repair Details
note | Frequency - post concreting
note | Activity - H
note | By - SE
section | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour
checkpoint | 3.03.01 - Falsework and Formwork Removal
note | Acceptance / Conformance Criteria - Formwork shall not be removed until minimum periods set down in Table 5.3 of NZS3109 have elapsed.
note | • The stripping time may be reduced if it is shown by field-cured tests that compressive strength has been attained of twice the stress to which the member will be subjected at the time of stripping or as directed by the temporary works engineer.
note | Standard / Specification - SS 2144 - 10, NZS3109 Table 5.3 Downer
note | Verifying Document - Approval
note | Frequency - Before removal of Falsework and Formwork
note | Activity - H
note | By - SE
checkpoint | 3.03.02 - Post Pour Inspection
note | Acceptance / Conformance Criteria - Post pour inspection undertaken by the site engineer and captured in the ConQA web app. Engineer notified of any defects.
note | Standard / Specification - Downer
note | Verifying Document - Site Photos
note | Frequency - Each pour
note | Activity - H
note | By - SE
checkpoint | 3.03.03 - Concrete Repair
note | Acceptance / Conformance Criteria - Repair of any minor surface defect or structural defect of concrete shall only be carried out with the Engineer’s acceptance. All repaired concrete shall have the same strength, durability and surface finish as the parent concrete unless otherwise accepted by the Engineer.
note | Standard / Specification - SS 2146 - 11, PS - 11.5
note | Verifying Document - Acceptance / Repair Details
note | Frequency - Prior to Each Repair
note | Activity - HP
note | By - ENG
holdpoint | AUTHORITY HOLDPOINT
section | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities
checkpoint | 4.01.01 - Construction Record Compilation
note | Acceptance / Conformance Criteria - Compile construction records for final submission ensuring defects (NCRs) / Snags / missing records are captured or closed out, all tests have been received and passed, and changes / omissions have been noted.
note | Standard / Specification - Downer
note | Verifying Document - Records
note | Frequency - Post construction
note | Activity - H
note | By - SE
checkpoint | 4.01.02 - Survey Records
note | Acceptance / Conformance Criteria - Ensure all items have been surveyed and records are assembled for asbuilting
note | Standard / Specification - Downer
note | Verifying Document - Records
note | Frequency - Post construction
note | Activity - H
note | By - SV
checkpoint | 4.01.03 - Redline Drawings
note | Acceptance / Conformance Criteria - Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in red pen.
note | Standard / Specification - Downer
note | Verifying Document - Redlines
note | Frequency - Post construction
note | Activity - H
note | By - SE
checkpoint | 4.01.04 - Defect, Snag and Punch List
note | Acceptance / Conformance Criteria - Update the project Defect, Snag and Punch List Register
note | Standard / Specification - Downer
note | Verifying Document - Register
note | Frequency - Post construction
note | Activity - H
note | By - SE
checkpoint | 4.01.05 - Delivery dockets
note | Acceptance / Conformance Criteria - At the completion of the Contract a schedule of delivery docket numbers for all concrete supplied shall be forwarded to the Engineer.
note | Standard / Specification - SS 2140 - 4
note | Verifying Document - Dockets
note | Frequency - Post construction
note | Activity - H
note | By - SE