## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-099 - NPD - Universal Building | itp |  |  |  |  | ITP-099 - NPD - Universal Building Rev1
section | 1 - Design and Submissions
checkpoint | 1.1 Check for correct documentation
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
label | – using the correct and complete set of drawings
label | – all drawings are the latest revision
label | REFERENCE DOCUMENTS: Drawings and drawing registers
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: This ITP signed
label | HP*
label | RESPONSIBILITY: Fulton Hogan Engineer
text | Date Completed:
checkpoint | 1.2 Implementation of all measures and controls
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WP
label | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed
label | HP*
label | RESPONSIBILITY: Fulton Hogan Engineer
text | Date Completed:
checkpoint | 1.3 Approval of material
label | FREQUENCY: Prior to works commencing
label | ACCEPTANCE CRITERIA: At least one week prior to works commencing, submit details of materials and material approval to client.
label | REFERENCE DOCUMENTS: Contract Drawings
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed
label | HP
label | RESPONSIBILITY: Fulton Hogan/ Superintendent
text | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 2 - Subcontractor ITP
checkpoint | 2.1 Works/Activity
label | FREQUENCY: As works are being carried out
label | ACCEPTANCE CRITERIA: ITP to be followed and compeleted while works are happening. To be signed off by sub-contrcator, then checked and signed by responsible Fulton Hogan person.
label | REFERENCE DOCUMENTS: Signed and executed Subcontractor ITP
label | INSPECTION/TEST METHOD: Inspect
label | RECORD OF CONFORMITY: This ITP signed
label | HP*
label | RESPONSIBILITY: Fulton Hogan Engineer
text | Date Completed:
section | 3 - Post-Work details and Survey
checkpoint | 5.3 Building Surveyor sign off
label | FREQUENCY: As required
label | ACCEPTANCE CRITERIA: Designer/Building Surveyor to complete inspection report and give verification that construction has been carried out as per design.
label | REFERENCE DOCUMENTS: Report
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed
label | IP
label | RESPONSIBILITY: Fulton Hogan
text | Date Completed:
checkpoint | 5.5 As Built Drawings
label | FREQUENCY: Prior to lot closure
label | ACCEPTANCE CRITERIA: Recorded of as-built drawings
label | REFERENCE DOCUMENTS: Fulton Hogan Procedure
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed
label | IP
label | RESPONSIBILITY: Fulton Hogan
text | Date Completed:
checkpoint | Final Inspection
note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
textbox | Date: