## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | External Balcony ITP |  |  |  |  | Yes | External Balcony ITP | 0ad8a4b4-3187-4a25-9504-ec43b17211dd
checkpoint-status |  |  | checkpoint | Area accessible and ready (If failed please take a photo)
checkpoint-status |  |  | checkpoint | Surface has been checked and confirmed acceptable
checkpoint-status |  |  | checkpoint | Has a bucket test been completed by others to ensure compliance falls to waste
label | a99c3be9-bddb-5f2d-bcca-5df3e9ddaf3b |  | note | GCP Silcor 560
holdpoint |  |  | signoff | Signed Tight Seal
checkpoint-status |  |  | checkpoint | Primer (Ensure photo is taken)
checkpoint-status |  |  | checkpoint | Correct curing time allowed 1hr (Primer)
checkpoint-status |  |  | checkpoint | Ensure joints are treated in accordance with post completion movement tolerances
checkpoint-status |  |  | checkpoint | Caulking Preparation
checkpoint-status |  |  | checkpoint | 1st Coat (Ensure photo is taken)
checkpoint-status |  |  | checkpoint | Correct curing time allowed 12hr (1st Coat)
checkpoint-status |  |  | checkpoint | 2nd Coat (Ensure photo is taken)
checkpoint-status |  |  | checkpoint | Correct curing time allowed 12hr (2nd Coat)
checkpoint-status |  |  | checkpoint | Detailed areas such as pipe penetrations, pits, joints, pile capping installed as per specification
checkpoint-status |  |  | checkpoint | Application to correct DFT (Ensure photo is taken)
checkpoint-status |  |  | checkpoint | UV Stable top coat applied (Ensure photo is taken)
checkpoint-status |  |  | checkpoint | Correct curing time allowed 12hr (UV Stable)
checkpoint-status |  |  | checkpoint | Ensure all penetrations by others are sealed to ensure works are not compromised.
holdpoint |  |  | signoff | Signed Tight Seal
checklist-sectioned |  |  | checklist | Internal Liquid Waterproofing ITP |  |  |  |  | Yes | Internal Liquid Waterproofing ITP | 58cb0f0c-3632-4636-9669-fe52e2f33c29
checkpoint-group |  |  | section | Below screed membrane
checkpoint-status |  |  | checkpoint | Area accessible and ready (If failed please take a photo)
checkpoint-status |  |  | checkpoint | Surface has been checked and confirmed acceptable
checkpoint-status |  |  | checkpoint | Floors are scraped, vaccum and puddle flanges exposed
checkpoint-status |  |  | checkpoint | Has a bucket test been completed by others to ensure compliance falls to waste
holdpoint |  |  | signoff | Signed Tight Seal
checkpoint-status |  |  | checkpoint | Ensure moisture content of slab is under 4.5%(Ensure photo is taken)
label | 74c0f738-3973-57fa-9020-efae9274088b |  | note | GCP Silcor 560 Floors 1.5mm
checkpoint-status |  |  | checkpoint | Primer (Ensure photo is taken) - SILCOR Primer BS
checkpoint-status |  |  | checkpoint | Correct curing time allowed 1hr (Primer)
checkpoint-status |  |  | checkpoint | Ensure angles are installed as per metre mark
checkpoint-status |  |  | checkpoint | Caulking Preparation
checkpoint-status |  |  | checkpoint | Detailed areas such as pipe penetrations, pits, joints, pile capping installed as per specification
checkpoint-status |  |  | checkpoint | 1st Coat (Ensure photo is taken)
checkpoint-status |  |  | checkpoint | Correct curing time allowed 12hr (1st Coat)
checkpoint-status |  |  | checkpoint | 2nd Coat (Ensure photo is taken)
checkpoint-status |  |  | checkpoint | Correct curing time allowed 12hr (2nd Coat)
checkpoint-status |  |  | checkpoint | Tie / Broadcast coat applied (Ensure photo is taken) - Silcor 575 - Sand will be applied with Tie coat
checkpoint-status |  |  | checkpoint | Correct curing time allowed 12hr (Tie / Broadcast coat)
checkpoint-status |  |  | checkpoint | Application to correct DFT (Ensure photo is taken) - DFT required for walls (1 mm) and floor (1.5mm)
checkpoint-status |  |  | checkpoint | Flood Test 24 hours (Ensure photo is taken)
holdpoint |  |  | signoff | Signed Tight Seal
checklist-flat |  |  | checklist | External Step Downs |  |  |  |  | Yes | External Step Downs | a3f0e103-ca28-4676-86e3-5e332a285a8d
checkpoint-status |  |  | checkpoint | Area accessible & ready (If failed please take a photo)
checkpoint-status |  |  | checkpoint | Surface has been checked and confirmed acceptable
checkpoint-status |  |  | checkpoint | Has a bucket test been completed by others to ensure compliance falls to waste
label | 71ff84e8-1630-58f7-9013-578dc9327254 |  | note | GCP Silcor 560
checkpoint-status |  |  | checkpoint | Angles have been installed
checkpoint-status |  |  | checkpoint | Primer (Ensure photo is taken)
checkpoint-status |  |  | checkpoint | Correct curing time allowed 1hr (Primer)
checkpoint-status |  |  | checkpoint | Ensure joints are treated in accordance with post completion movement tolerances
checkpoint-status |  |  | checkpoint | Caulking Preparation
checkpoint-status |  |  | checkpoint | 1st Coat (Ensure photo is taken)
checkpoint-status |  |  | checkpoint | Correct curing time allowed 12hr (1st Coat)
checkpoint-status |  |  | checkpoint | 2nd Coat (Ensure photo is taken)
checkpoint-status |  |  | checkpoint | Correct curing time allowed 12hr (2nd Coat)
checkpoint-status |  |  | checkpoint | Detailed areas such as pipe penetrations, pits, joints, pile capping installed as per specification
checkpoint-status |  |  | checkpoint | Application to correct DFT (Ensure photo is taken)
checkpoint-status |  |  | checkpoint | Correct curing time allowed 12hr (UV Stable)
checkpoint-status |  |  | checkpoint | Ensure all penetrations by others are sealed to ensure works are not compromised.
holdpoint |  |  | signoff | Signed Tight Seal