## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | Floor Finishes ITP |  |  |  |  | Yes | Floor Finishes ITP | 58c1e9ff-df71-4ae0-b3b8-6fa89ccdc947
checkpoint-group |  |  | section | Subfloor, Floor Preparation, Adhesive
checkpoint-status |  |  | checkpoint | Confirm area of work is accessible & acceptable to commence (If not comment below)
checkpoint-status |  |  | checkpoint | Subfloor mechanically diamond ground
checkpoint-status |  |  | checkpoint | Moisture Barrier installed to concrete substrate - Mapei Mapeproof Turbo
checkpoint-status |  |  | checkpoint | Floor preparation product installed in accordance with manufacturer's instructions
button | 20b0959c-fed3-5326-a167-46636705bbf2 |  | button | Product: | Mapei Ultraplan Trade, Mapei Planiprep, Mapei Nivorapid
text | a06a7d76-95e3-574f-8416-3c7aeda1114c |  | textbox | Average thickness: | 3mm
checkpoint-status |  |  | checkpoint | Correct adhesive used
button | e9070dfa-d3b8-591e-a886-cbbd94e25a6a |  | button | Adhesive: | Roberts R2000 Vinyl Adhesive, Roberts R656
checkpoint-group |  |  | section | Carpet / Vinyl
checkpoint-status |  |  | checkpoint | Confirm area of work is accessible & acceptable to commence (If not comment below)
text | 3d83a05d-a381-5540-a391-8e9767cca97e |  | textbox | Drawing & revision number(s)
checkpoint-status |  |  | checkpoint | Vinyl installed as per plan
select | cc63d90d-0bcf-5349-9365-37d66c228aaf |  | dropdown | Material: | FLVY-007 - TARKETT IQ SURFACE CONTRAST AIRY 21089083 (CUSTOM EMINENT), FLVY-007.1.1 - TARKETT ECLIPSE PREMIUM COLOUR LIGHT PURE GREY 21020963, FLVY-007.2.1 - TARKETT ECLIPSE PREMIUM SPECTRA COLOUR PASTEL SKY BLUE 21081079, FLVY-007.2.2 - TARKETT PRIMO PREMIUM COLOUR OCEAN BLUE 21010638, FLVY-007.2.3 - TARKETT ECLIPSE PREMIUM COLOUR MIDNIGHT BLUE 21020775, FLVY-007.3.1 - TARKETT PRIMO PREMIUM COLOUR LIGHT GREEN 21010679, FLVY-007.3.2 - TARKETT PRIMO PREMIUM COLOUR MEDIUM GREEN 21020680, FLVY-007.4.1 - TARKETT ECLIPSE PREMIUM SPECTRA COLOUR PASTEL YELLOW 21081076, FLVY-007.4.2 - TARKETT PRIMO PREMIUM COLOUR SOFT ORANGE 21010667, FLVY-007.4.3 - TARKETT ECLIPSE PREMIUM COLOUR ORANGE 21020784, FLVY-007.2.5 - TARKETT IQ EMINENT UNISENSE COLOUR DUSTY BLUE 21030 907, FLVY-007.5.1 - TARKETT ECLIPSE PREMIUM SPECTRA COLOUR PASTEL BLUE 21081 082, FLVY-007.5.2 - TARKETT ECLIPSE PREMIUM COLOUR LIGHT BLUE 21020978, FLVY-007.6.3 - TARKETT ECLISPE PREMIUM COLOUR PREMIUM YELLOW 21020732, FLVY-009 - TARKETT IQ GRANIT SAFE T COLOUR DARK GREY 3052698, FLVY-009.2.3 - TARKETT IQ GRANIT SAFE T COLOUR BLUE 3052 695, FLVY-009.4.2 - TARKETT IQ GRANIT SAFE T COLOUR TERRACOTTA 3052693, FLVY-501 - TARKETT ACCZENT EXCELLENCE 80 COLOUR OAK LONGSTRIPE NATURAL 25127002, FLSK-500 - IQ EMINENT UNISENSE COLOUR WHITE 21030904, FLVY-001 - TARKETT PRIMO SD DARK COOL GREY 21012 563, FLVY-508.3 - TARKETT IQ EMINENT UNISENSE COLOUR DUSTY GREEN 21030 925
checkpoint-status |  |  | checkpoint | Carpet installed as per plan
select | 427576d1-ea88-5ff2-80a9-e6eb1a605c51 |  | dropdown | Material: | FLCP-5001.1 - INTERFACE ESCARPMENT COMMON GROUND COLOUR DESERT NEUTRAL, FLCP-5002.2 - INTERFACE ESCARPMENT COMMON GROUND COLOUR SEAWATER DEPTH, FLCP-500.3.2 - INTERFACE ESCARPMENT COMMON GROUND COLOUR DESERT SHRUB, FLCP-500.4.2 - INTERFACE ESCARPMENT COMMON GROUND COLOUR DESERT SANDS
text | f0232344-14ac-5c0c-bc35-b4d349a16c32 |  | textbox | Other colour:
checkpoint-status |  |  | checkpoint | Joints sealed with heat welded seams and mitres as per AS 1884-2020
select | 8dc2403c-54ff-545b-8a4e-79e7c07cdba6 |  | dropdown | Vinyl skirting Type | Vinyl coved 150mm up perimeter walls, Vinyl border cove installed 150mm up perimeter walls
text | 4a4a84ec-ec78-563a-9139-089a5c931067 |  | textbox | Custom height:
checkpoint-status |  |  | checkpoint | Add-Floors Sign Off
checkpoint-group |  |  | section | Walls
checkpoint-status |  |  | checkpoint | Confirm area of work is accessible & acceptable to commence (If not comment below)
text | f31d0dbb-cd11-5ec6-9bda-a85e6c60f7b8 |  | textbox | Drawing & revision number(s)
checkpoint-status |  |  | checkpoint | Wall Finish installed as per plan
select | 713999cf-7fe6-5a77-a4ec-3b96cb7e2673 |  | dropdown | Material: | TARKETT WALLGARD 2MM SNOWFLAKE 3105025
checkpoint-status |  |  | checkpoint | Joints sealed with heat welded seams and mitres as per AS 1884-2020
checkpoint-status |  |  | checkpoint | Add-Floors Sign Off
checkpoint-group |  |  | section | Protection and Handover
checkpoint-status |  |  | checkpoint | Installation complete, checked and reviewed - as per specification
text | 5159c19f-67b8-5de0-b4ab-81e487d59bec |  | textbox | General comments / observations
checkpoint-status |  |  | checkpoint | Vinyl protected with Bubbleweave and/or MDF floor protection
checkpoint-status |  |  | checkpoint | Add-Floors Sign Off: Protection installed as per manufacturer's instructions
checklist-sectioned |  |  | checklist | Area Ready Checklist |  |  |  |  | Yes | Area Ready Checklist | 8e48972c-b642-4889-99c2-40eb5cdeac19
checkpoint-group |  |  | section | Substrate
checkpoint-status |  |  | checkpoint | Substrate Acceptable
checkpoint-status |  |  | checkpoint | Wet Area Screed Installed
checkpoint-group |  |  | section | Walls / Ceiling
checkpoint-status |  |  | checkpoint | Ceiling Installed
checkpoint-status |  |  | checkpoint | Gyprock
checkpoint-status |  |  | checkpoint | Plastered
checkpoint-status |  |  | checkpoint | Plaster Sanded
checkpoint-status |  |  | checkpoint | Painted
checklist-sectioned |  |  | checklist | Daily Pre Start |  |  |  |  | Yes | Daily Pre Start | e8138c80-1953-4cbc-87ea-c80b443377a5
checkpoint-group |  |  | section | Details
checkpoint-status |  |  | checkpoint | Supervisor Leading Meeting
date | 803df22f-2b49-53f0-a67d-c3c96043fba7 |  | date | Date
text | aad6650c-0ccc-59ab-86b3-3a1db8872bb0 |  | textbox | Time
checkpoint-status |  |  | checkpoint | 1. Issues arising from previous day
text | aa7524ef-5c36-55f9-bc7a-fbb3fb14049a |  | textbox | Issues arising from previous day
label | 6904ec9c-829d-587f-99dd-e60fbdf5cad8 |  | note | NOTE: If this requires a change to the SWMS then please ensure this is captured and relevant personnel inducted.
checkpoint-status |  |  | checkpoint | 2. Planned work / activities being carried out today
boolean | 3c254474-0d52-5b2f-8c26-b8be41a88a49 |  | tickbox | Carpet and resilient finishes
boolean | 4774e8fb-6706-5235-b162-7b099a49bc81 |  | tickbox | Other:
text | c4b4d29a-4c36-5da3-a00e-d9a804863289 |  | textbox
text | aa237c6f-6970-5f45-a40a-c636d1b1d106 |  | textbox
text | e42701e5-2b2d-5700-9cae-6d776fb50e2a |  | textbox
text | ab78bcdd-99b4-508b-8bfd-01d823fcb55d |  | textbox
checkpoint-status |  |  | checkpoint | 3. Is a SWMS in place for ALL high risk construction work and work procedures in place for all other works?
label | a72c0907-86ec-5390-832d-0efc92c09bf9 |  | note | If FAIL, stop and develop
checkpoint-status |  |  | checkpoint | 4. Are you subcontracting out any works today and will you be interacting with other trades?
text | 9f782889-4840-5487-aad1-9ed69327d086 |  | textbox | If PASS, please list
checkpoint-status |  |  | checkpoint | 5. Permits in place for today’s Activities - Stating Permit No. and Description
button | c27837ce-4c4a-5a41-bc41-eed8da0fa277 |  | button | Hot Works | No,Yes
text | e2a16422-9ef0-54fc-bdd9-458882f53e20 |  | textbox | Number:
text | b746f3af-4b9c-592d-85ba-7d5bec666593 |  | textbox | Number / Description:
text | ce2c5180-d1e4-5891-be1b-14c87d99552b |  | textbox | Number / Description:
text | 2a8f9a5f-945b-58ff-9744-5a0ecebf3c84 |  | textbox | Number / Description:
checkpoint-status |  |  | checkpoint | 6. Hazardous Substances being used, or will be brought to/or stored on site today?
boolean | 9e3a950c-2528-5607-b79f-43af5860a056 |  | tickbox | Flooring adhesives
boolean | a55bdb5e-0e8a-5f99-814e-7b5dc515eff9 |  | tickbox | Floor preparation materials
boolean | 190e59a4-558f-55fb-8920-4a5b5f67b44c |  | tickbox | Gas cylinders
text | b51686a2-6d86-519b-9b9d-3a3bf1f81e03 |  | textbox | Other:
checkpoint-status |  |  | checkpoint | 7. Is there an MSDS on site for ALL the above listed substances (less than 5 years old)
checkpoint-status |  |  | checkpoint | 8. What controls are in place to manage environmental risk on site, specific for today; e.g. Wash out areas, maintenance of sediment fences and drains, monitoring of dust? List
boolean | 0b350280-4596-53ac-ae2f-1692a14044fa |  | tickbox | New self igniting gas guns fitted and exclusion barriers set up
boolean | fc360ee8-90bc-5ca1-9f6f-e17a67fbdfaf |  | tickbox | Vacuums to control dust, Wash out bays provided used for cleaning, Bins provided used for waste
text | 3d9df010-bbcf-51b9-9fec-4be179afcbd3 |  | textbox | Other:
text | 21486ece-4d92-542d-ad4c-f00ace106f03 |  | textbox | Other:
text | 6939e3b9-bfc4-5569-b41e-ff2675d86ea6 |  | textbox | Other:
text | 0cdadb47-fef8-58e5-bc32-f626f02b7172 |  | textbox | Other:
checkpoint-status |  |  | checkpoint | 9. Checklist for activities complete
label | e024c8d1-864c-5f7f-8269-021f85bb31d2 |  | note | Complete activities or issues must be detailed in Notes section below
button | 69e4a53d-4c86-59dd-af67-086bbc9b2e7f |  | button | Daily Risk Assessment Completed | No,Yes
button | ef60828c-93a3-5d62-899b-6d6deae62c22 |  | button | Work area inspected and safe for staff to enter and work in today | No,Yes
text | 1969a76f-c230-5929-a73d-fe615bbfd6a6 |  | textbox | Indicate number of people in your work group
button | d5538436-b48d-556c-9431-da6f52680e5f |  | button | Qualifications/training of staff adequate for work activities | No,Yes
button | ea8d81c2-30fe-5cc7-9be5-d6d8f2b7823b |  | button | Appropriate and adequate PPE supplied to work teams (SWMS/SDS) | No,Yes
text | c67b5b05-a4f0-56c6-9d19-6f2eed02cead |  | textbox | Indicate number of workers allocated for today's clean up
button | 948d852a-0f60-5a9d-9c84-b9a8a480ee07 |  | button | Plant and equipment on/off site | No,Yes
button | 8ab4123e-115f-544a-94ba-67ea98a7df4a |  | button | Equipment safe to use | No,Yes
button | 30eafbab-2005-582c-bc83-47c0819d5a76 |  | button | Weather conditions for work to be conducted / assessed | No,Yes
button | a4964fb3-89bd-50eb-a0b0-a0591e7a1d80 |  | button | Pre-start communicated to all work teams including all trades and subcontractors listed in section 4. | No,Yes
checkpoint-status |  |  | checkpoint | Builder's Briefing Notes reviewed and understood by all workers
text | 13af4d28-9369-563f-81ad-3dde2e743a2e |  | textbox
checkpoint-status |  |  | checkpoint | General Notes
text | 13fdee53-2c75-5b1e-bc34-ad42b0e34e44 |  | textbox
text | 45bc68b0-b57f-5f33-97bf-3ce451c98b7b |  | textbox
text | dd046df5-c0f6-5fb4-8560-0c33826c1f36 |  | textbox
text | 86d78792-9e39-54d8-a64d-da78bd232f56 |  | textbox
checkpoint-status |  |  | checkpoint | Attendees noted (add as comment)
checklist-sectioned |  |  | checklist | Variation Details - |  |  |  |  | Yes | Variation Details - | f412743c-a92b-4c39-9ba7-dc2b25ef62db
checkpoint-group |  |  | section | Details
checkpoint-status |  |  | checkpoint | Variation Details Approved
text | 57973e1f-e013-56c8-a1d5-d3356b74d281 |  | textbox | Reference/Drawing/Instruction Number
text | d7436a91-0db0-58da-b00d-c526c5f1e516 |  | textbox | Variation Area
text | c221f62b-d2c4-5f61-997f-c837fbe0dff4 |  | textbox | Materials & labour breakdown
holdpoint |  |  | signoff | Request Variation Acknowledgement
checkpoint-status |  |  | checkpoint | Variation Completed
holdpoint |  |  | signoff | Request Variation Signoff
checklist-sectioned |  |  | checklist | Delivery Checklist |  |  |  |  | Yes | Delivery Checklist | f55b5d9c-4d7a-401d-82ed-523dcbf8f230
checkpoint-group |  |  | section | Details
checkpoint-status |  |  | checkpoint | Delivery details input
date | 5dbf789f-0020-5611-b0fe-5e7c98d4c47a |  | date | Date
text | 4e954b2c-cac6-5cfd-9f85-7d4738e9030e |  | textbox | Delivered by
text | e340dacd-93a6-5849-bcbc-8626bed572a0 |  | textbox | From
text | a4b393f1-fcd2-558f-a337-7af0b1a7060b |  | textbox | Description
text | a95fa838-4716-5cb9-844b-416ee5d83ffd |  | textbox | Comments
text | a84e3bf9-5843-5887-aad0-37ac4f8c600e |  | textbox | Stored where
checkpoint-status |  |  | checkpoint | Materials checked
boolean | 1b9ffc84-aaf6-50e6-a59f-c93557614845 |  | tickbox | Materials in good order
boolean | a5682d99-323f-5804-97da-c7c00b4b0f56 |  | tickbox | Photo of materials
boolean | fb74a07a-71a8-5c7a-87a6-d386ab7f2af1 |  | tickbox | Photo of Con Note
boolean | d0370d81-7438-5840-aaca-026b494164db |  | tickbox | Photo Packing Slip / Slips
text | 58f4bcfa-2dfb-5fcc-b0d4-428125788d4f |  | textbox | Comments