## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | CST - S - Completion Documents |  |  |  |  | Yes | SYS - CST - S - Completion Documents (old version) | 609ee4f4-797b-4cf7-b5d3-d534f5d53f96
checkpoint-status |  |  | checkpoint | All relevant Compliance Documentation completed and attached above
button | 3ac909c1-84d5-5822-8a55-2e9af463f8c6 | DataPoint is missing 'button' values | button | LBP Memorandum/ Record of works filled out, signed and attached
button | e43e74db-1b9d-594b-a963-aaaa78846c53 | DataPoint is missing 'button' values | button | Any Additional Compliance Documentation - Completed and Attached
label | d9d2d616-e583-52ac-9bc6-01e3737bf50d |  | note | Do not select "Pass" HERE until all requirements have been marked as "Yes" & attached or you have selected "N/A"
holdpoint |  |  | signoff | Request Signoff
checklist-flat |  |  | checklist | POST - S - Joinery and Cabinets Installation - Kitchen, Ensuite, Bathroom and Wardrobes |  |  |  |  | Yes | POST - S - Joinery and Cabinets Installation - Kitchen, Ensuite, Bathroom and Wardrobes | dbea6869-acca-4d51-b41d-0a054ddbf435
checkpoint-status |  |  | checkpoint | All units & scribers in apartment
checkpoint-status |  |  | checkpoint | Joinery free from damage pre install
checkpoint-status |  |  | checkpoint | Joinery installed free from defect and damage
checkpoint-status |  |  | checkpoint | Silicone installed, correct colour & clean and tidy
checkpoint-status |  |  | checkpoint | Joinery and Cabinets installation completed - specified level of finish achieved
checklist-flat |  |  | checklist | CST - S - Completion Documents |  |  |  |  | Yes | CST - S - Completion Documents | e6819aa3-716c-4877-b0fe-83340a369421
checkpoint-status |  |  | checkpoint | All relevant Compliance Documentation completed and attached above
button | ee4dc75f-6f74-574d-acb4-a47caf293d07 |  | button | Any Additional Compliance Documentation (Required under Section C and by Consultants) - Completed and Attached | Yes,N/A
label | 5e06cd59-2097-577d-8c1b-f4b667121eca |  | note | Do not select "Pass" HERE until all requirements have been marked as "Yes" & attached or you have selected "N/A"
holdpoint |  |  | signoff | Request Signoff