## Project Structure
Folder Structure |  |  |  | Checklists | #NAME?
Site QA
Inground services
External ducting
|  |  | Mains incoming trench | Inground services
|  |  | Sub main ducts to MSB | Inground services
|  |  | pit | Inground services
|  |  | telecom duct | Inground services
Switchboard's
Ground Floor
|  |  | Main Switchboard | Switchboards
First Fix
Ground Floor
|  |  | Cold store 1 | First Fix Electrical
|  |  | Cold store 2 | First Fix Electrical
|  |  | Retail packing | First Fix Electrical
|  |  | Dried goods size reduction | First Fix Electrical
|  |  | form processing 1 | First Fix Electrical
|  |  | form processing 2 | First Fix Electrical
|  |  | Load in/out packing store | First Fix Electrical
|  |  | ante room | First Fix Electrical
|  |  | cleaning room | First Fix Electrical
Second Fix
Ground Floor
|  |  | Cold store 1 | Second Fix
|  |  | Cold store 2 | Second Fix
|  |  | Retail packing | Second Fix
|  |  | Dried goods size reduction | Second Fix
|  |  | form processing 1 | Second Fix
|  |  | form processing 2 | Second Fix
|  |  | Load in/out packing store | Second Fix
|  |  | ante room | Second Fix
|  |  | cleaning room | Second Fix
FEL SM Weekly Site Checklist
| 2024-03-18 |  |  | FEL SM Weekly Site Checklist
| 2024-03-25 |  |  | FEL SM Weekly Site Checklist
| 2024-04-01 |  |  | FEL SM Weekly Site Checklist
| 2024-04-08 |  |  | FEL SM Weekly Site Checklist
| 2024-04-15 |  |  | FEL SM Weekly Site Checklist
| 2024-04-22 |  |  | FEL SM Weekly Site Checklist
| 2024-04-29 |  |  | FEL SM Weekly Site Checklist
| 2024-05-06 |  |  | FEL SM Weekly Site Checklist
| 2024-05-13 |  |  | FEL SM Weekly Site Checklist
| 2024-05-20 |  |  | FEL SM Weekly Site Checklist
| 2024-05-27 |  |  | FEL SM Weekly Site Checklist
| 2024-06-03 |  |  | FEL SM Weekly Site Checklist
| 2024-06-10 |  |  | FEL SM Weekly Site Checklist
| 2024-06-17 |  |  | FEL SM Weekly Site Checklist
| 2024-06-24 |  |  | FEL SM Weekly Site Checklist
| 2024-07-01 |  |  | FEL SM Weekly Site Checklist
| 2024-07-08 |  |  | FEL SM Weekly Site Checklist
| 2024-07-15 |  |  | FEL SM Weekly Site Checklist
| 2024-07-22 |  |  | FEL SM Weekly Site Checklist
| 2024-07-29 |  |  | FEL SM Weekly Site Checklist
| 2024-08-05 |  |  | FEL SM Weekly Site Checklist
| 2024-08-12 |  |  | FEL SM Weekly Site Checklist
| 2024-08-19 |  |  | FEL SM Weekly Site Checklist
| 2024-08-26 |  |  | FEL SM Weekly Site Checklist

## Inground services
type | name
checklist | Inground Services
section | Ducts and Conduits
checkpoint | Correct size installed
checkpoint | Start and finish locations correct as per plan
checkpoint | separation from other services
checkpoint | Clean inside and in good condition
section | Electrical Pits
checkpoint | Set out correct
checkpoint | Correct size installed
checkpoint | Duct entry holes sealed / water proofed
checkpoint | Pits installed to correct height and level
checkpoint | Clean inside and in good condition
section | Light Pole Foundations
checkpoint | Set out correct
checkpoint | Ducting in correct position - centre of cage
checkpoint | Correct Cage Installed
checkpoint | Cage installed to correct height / level
checkpoint | Ground Plant pole installed to correct height / level
section | Photos

## First Fix Electrical
type | name
checklist | QA - First Fix
section | Flush Boxes
checkpoint | Fire Rated or Acoustic
checkpoint | Height as per plan
checkpoint | Location as per plan
checkpoint | Intumescent Pad In Place
section | Cabling
checkpoint | Power cables installed correctly
checkpoint | Lighting cables installed correctly
checkpoint | Equipment cables installed correctly
checkpoint | Circuits clearly labelled
checkpoint | Separation between Data and Power at 300mm or as specified
checkpoint | All cables secured via cable ties with ends cut
section | Cable Ladder
checkpoint | Minimum 25% spare capacity left on cable tray
section | QA - Lights
checkpoint | Setout Correct
checkpoint | Cabling in correct location
checkpoint | Emergency/ Exit Lighting
checkpoint | Nogging installed for Electrical Services
section | Seismic Bracing
checkpoint | For Lighting
checkpoint | Cable Tray
checkpoint | Switchboard
section | Conduits
checkpoint | Correct size installed
checkpoint | Location as per plan
checkpoint | All conduits glued & watertight
checkpoint | Clean inside and in good condition
checkpoint | Stainless screws used
section | Photos

## Cable Tray
Section | Cable Ladder
Checkpoint | Unistrutt Filed & Painted
Checkpoint | Hangers Spaced as Specified
Checkpoint | Correct Size Ladder Installed
Checkpoint | Ladder Joined Correctly
Checkpoint | Hangers Sceismicly Restrained as per Design
Checkpoint | Ladder Fastened to Hangers
Checkpoint | Correct Anchors used fixing to Ceiling / Walls
Checkpoint | Cable Ladder Bonded
section | Photos

## Switchboards
section | Switchboard
checkpoint | Spatial certificate signed if required
checkpoint | Fixings installed in wall correctly if board is wall mounted
checkpoint | All clearances sighted to ensure location is compliant
checkpoint | All cables correctly installed in protection device and earth and neutral bars and fully secured
checkpoint | Cables neatly dressed
checkpoint | Phase tabs on chassy covered
checkpoint | All earths and neutrals labelled to match phase numbers
checkpoint | Switchboard is clean on the inside and outside
checkpoint | Masking blanks installed
checkpoint | DB legend installed
checkpoint | Feisst label on the door installed
section | Photos

## Second Fix Electrical
type | name | values
checklist | QA - Second fix
section | Power Outlets
checkpoint | Correct type installed
checkpoint | Correctly installed with terminations all secured properly
checkpoint | Outlet Installed level
checkpoint | Circuit Tested and results recorded
checkpoint | Description Labelled on the outlet face with vivid and with dymo labeller on cover plate and ensure label is level
section | Light Switches
checkpoint | Correct type installed
checkpoint | Correctly installed with terminations all secured properly
checkpoint | Light switch Installed level
checkpoint | Circuit Tested and results recorded
checkpoint | Description Labelled on the outlet face with vivid and with dymo labeller on cover plate and ensure label is level
section | Light Fixtures
checkpoint | Correct type installed
checkpoint | Correctly installed with terminations all secured properly
checkpoint | Tested for operation
checkpoint | Correctly installed with stainless screws & 90 / 45 angle
section | Photos

## SM Weekly Checklist
type | name
checklist | FEL SM Weekly Site Checklist
section | Monday
checkpoint | Prestart Meeting with Team
checkpoint | Health Check
checkpoint | Review Tasks for the week
checkpoint | Identify Targets Including Hours
checkpoint | Approve hours by 9AM for previous week
checkpoint | Sign off Subcontractor Hours & Submit
checkpoint | Review SWMS
checkpoint | Site Toolbox Meeting
checkpoint | SSSP in Order
section | Tuesday
checkpoint | Follow up outstanding RFI's with PM
section | Wednesday
checkpoint | Review Roadblocks & Follow Up if still unresolved
checkpoint | QAs up to date
section | Thursday
checkpoint | Weekly planner filled out for week ahead
checkpoint | Roadblocks identified and actioned
checkpoint | Materials organized for week ahead
checkpoint | Plans printed with any relevant notes added
section | Friday
checkpoint | Submit Toolbox minutes to main contractor and FEL office
checkpoint | Job Cards up to date and submitted
checkpoint | Team tasks for week ahead filled out on whiteboard