## Sheet1
SECTION | DETAILS
Checkpoint | Attach any relevant documents or photos
text | ITP No.
text | Revision No. & Date
text | Prepared By
text | Reviewed By
text | Approved By
text | Suppoting documentations - e.g location, CIDD alerts etc.
SECTION | BATCH DETAIL NUMBER OF PRODUCTS - EACH LOCATION
Checkpoint | Enviro Shield
Label | Records - Photograph
Label | surveillance point
Checkpoint | Enviro Flex FC/ Sika Flex FC
Label | Records - Photograph
Label | surveillance point
Checkpoint | Enviro Clad
Label | Records - Photograph
Label | surveillance point
SECTION | PRE COMMENCEMENT - EACH LOCATION
Checkpoint | Sample Submissions
Label | Submit samples for approval as per Specific Material Requirements.
Label | Record Submissions
Checkpoint | First Of Type Inspection
Label | First of type of inspection conducted by builder prior to commencment of works taking place.
Label | Record Submissions
Checkpoint | Material Management & Storage - Envirosystems TDS
Label | Store materials in a dry, clean place away from direct sunlight as per TDS
Label | Records - Photograph
Label | Witness Point
Checkpoint | Acceptance of Substrate - AS 4654 .2.2012 Section 2.5
Label | Obtain clearance for work initiation. Ensure a smooth substrate without protrusions, voids, or formwork distortions. The substrate should be free of honeycombing/bug holes. Patching products must be fully cured as per TDS prior to application
Label | Records - Photograph
Label | Witness Point
Checkpoint | Falls in Substrate- AS3740- 2021 Section 2.3 and AS 4654.2
Label | Builder to confirm compliant falls; minimum 1-100 falls
Label | Hold Point
Checkpoint | Cracks in Substrate - AS2870 Table C2
Label | Ensure no substrate cracks greater than 1.6mm.
Label | Cracks of 1.6mm and over, movement structural joints, cold joints and Live cracks are to be referred to engineers for treatment methodology.
Label | Records - Photograph
Label | Witness Point
SECTION | SUBSTRATE PREPERATION - EACH LOCATION
Checkpoint | Substrate Preperation - AS 4654.2-2012
Label | Ensure Surface is prepared to receive primer application. Clean substrate so that it is free of mould, paint, sealers, coatings, curing agents, loose particles and other contamination or foreign matter that may interfere with the adhesion. Achieve CSP2 and CSP3 Concrete finish profile. Remove all sharp edges including screws, nails and concrete/mortar projection. Steel surfaces should be treated with appropriate degreasers, then grit blasted and/or wire brushed where necessary.
Label | Records - Photograph
Label | Witness Point
SECTION | PRIME COAT- EACH LOCATION
Checkpoint | Moisture Content - Enviro Shield Product TDS
Label | Check Moisture content of substrate, not to exceed 6% (Min.1 test per 10m2).
Label | Records - Photograph
Label | surveillance point
Checkpoint | Weather/RH - Enviro Shield Product TDS
Label | Apply within 10-35°C RH must be 0-85%
Label | Screenshot - Temperature and weather forecast
Label | Witness Point
Checkpoint | Mixing - Enviro Shield Product TDS
Label | Add Enviro Shield Part B (grey liquid hardener) to the Enviro Shield Part A (base Thoroughly mix with a mechanical mixer at low speed (less than 400 RPM) prior to application. Mix for 5 minutes or until uniform. Allow to stand 5 minutes after mixing and then mix again for a minute.
Label | Witness Point
Checkpoint | Application - Enviro Shield Product TDS
Label | Apply primer using a brush or roller.
Label | Applications of excessive build should be avoided, and material must not be allowed to pool on the substrate surface.
Label | Ensure Primer is dry and tack free (within 24 hours) prior to next coat.
Label | Records - Photograph
Label | Witness Point
SECTION | BOND BREAKER- EACH LOCATION
Checkpoint | Caulking - AS 3740 2021 & AS 4654.1
Label | Apply compatible sealant to form smooth flexible cove to all internal corners, penetrations and joints. This is to be a 12mm x 12mm coved fillet as per AS3740 class III membrane requirements for internal areas and 15mm x 15mm coved fillet as per AS4654.1 class III membrane requirements for external areas. Bond breaker to be tack free prior to coating.
Label | Records - Photograph
Label | Records - Thickness testing with fillet gauge
Label | Witness Point
SECTION | FIRST BASE COAT - EACH LOCATION
Checkpoint | Weather/RH - Enviro Clad Product TDS
Label | Apply within 10-35°C RH must be 0-85%
Label | Screenshot - Temperature and weather forecast
Label | surveillance point
Checkpoint | Mixing - Enviro Clad Product TDS
Label | • Enviro Clad should be thoroughly mixed with a mechanical mixer at low speed (less than 400 RPM) prior to application.
Label | Witness Point
Checkpoint | Application - Enviro Clad Product TDS
Label | • Enviro Clad to be applied by roller on substrate and detailed with a brush
Label | Coating to achieve a wet film thickness of 600 micirons
Label | Allow membrane to dry for 24 Hours before proceeding to the second coat.
Label | Records - Photograph
Label | Witness Point
SECTION | SECOND BASE COAT- EACH LOCATION
Checkpoint | Weather/RH - Enviro Clad Product TDS
Label | Apply within 10-35°C RH must be 0-85%
Label | Screenshot - Temperature and weather forecast
Label | surveillance point
Checkpoint | Mixing - Enviro Clad Product TDS
Label | • Enviro Clad should be thoroughly mixed with a mechanical mixer at low speed (less than 400 RPM) prior to application.
Label | Witness Point
Checkpoint | Application - Enviro Clad Product TDS
Label | • Enviro Clad to be applied by roller on substrate and detailed with a brush
Label | Coating to achieve a wet film thickness of 600 micirons
Label | Allow membrane to dry for 24 Hours before proceeding to the second coat.
Label | Records - Photograph
Label | Witness Point
Section | QA TESTING - EACH LOCATION
Checkpoint | Inspection
Label | Inspect after installation of reinforcement/finishes to check for any damage to waterproofing and rectify as required.
Label | Records - Photograph
Label | Witness Point
Checkpoint | Thickness Testing - Delfasco Positector
Label | Thickness testing of application to the recommended DFT of 1.5mm to manufacturers instructions.( 1 test per 10m2)
Label | Records - Photograph
Label | Hold Point
SECTION | SIGN OFFS
Checkpoint | Polyseal ITP acceptance Sign off
SIGNOFF | Subcontractor inspection sign off
Checkpoint | Site Engineer/foreman ITP accceptance Sign off
SIGNOFF | Site Engineer/foreman inspection sign off