## Sheet1
Enviro Systems Checklist - Enviro B-LV+HP1200+900PUR+800TC
SECTION | DETAILS
Checkpoint | Attach any relevant documents or photos
text | ITP No.
text | Revision No. & Date
text | Prepared By
text | Reviewed By
text | Approved By
text | Suppoting documentations - e.g location, CIDD alerts etc.
SECTION | BATCH DETAIL NUMBER OF PRODUCTS - EACH LOCATION
Checkpoint | Enviro B-LV
Label | Records - Photograph
Label | surveillance point
Checkpoint | Sika Flex FC/ Enviro Flex FC
Label | Records - Photograph
Label | surveillance point
Checkpoint | Enviro HP1200
Label | Records - Photograph
Label | surveillance point
Checkpoint | Enviro 800TC
Label | Records - Photograph
Label | surveillance point
SECTION | PRE COMMENCEMENT - EACH LOCATION
Checkpoint | Sample Submissions
Label | Submit samples for approval as per Specific Material Requirements.
Label | Record Submissions
Checkpoint | First Of Type Inspection
Label | First of type of inspection conducted by builder prior to commencment of works taking place.
Label | Record Submissions
Checkpoint | Material Management & Storage - Envirosystems TDS
Label | Store materials in a dry, clean place away from direct sunlight as per TDS
Label | Records - Photograph
Label | Witness Point
Checkpoint | Acceptance of Substrate - AS 4654 .2.2012 Section 2.5
Label | Obtain clearance for work initiation. Ensure a smooth substrate without protrusions, voids, or formwork distortions. The substrate should be free of honeycombing/bug holes. Patching products must be fully cured as per TDS prior to application
Label | Records - Photograph
Label | Witness Point
Checkpoint | Falls in Substrate- AS3740- 2021 Section 2.3 and AS 4654.2
Label | Builder to confirm compliant falls; minimum 1-100 falls
Label | Hold Point
Checkpoint | Cracks in Substrate - AS2870 Table C2
Label | Ensure no substrate cracks greater than 1.6mm.
Label | Cracks of 1.6mm and over, movement structural joints, cold joints and Live cracks are to be referred to engineers for treatment methodology.
Label | Records - Photograph
Label | Witness Point
SECTION | SUBSTRATE PREPERATION: AS 4654.2-2012
Checkpoint | Substrate Preperation - AS 4654.2-2012
Label | Ensure Surface is prepared to receive primer application. Clean substrate so that it is free of mould, paint, sealers, coatings, curing agents, loose particles and other contamination or foreign matter that may interfere with the adhesion. Achieve CSP2 and CSP3 Concrete finish profile. Remove all sharp edges including screws, nails and concrete/mortar projection. Steel surfaces should be treated with appropriate degreasers, then grit blasted and/or wire brushed where necessary.
Label | Records - Photograph
Label | Witness Point
SECTION | PRIME COAT- EACH LOCATION
Checkpoint | Moisture Content - Enviro Epoxy B-LV Product TDS
Label | Check moisture content of substrate, not to exceed 6% (Min.1 test per 10m2).
Label | Records - Photograph
Label | surveillance point
Checkpoint | Weather/RH - Enviro Epoxy BL-V Product TDS
Label | Apply within 5-35°C RH must be 0-85%
Label | Screenshot - Temperature and weather forecast
Label | Witness Point
Checkpoint | Product Mixing - Enviro Epoxy BL-V Product TDS
Label | Mix Part A (12L) and Part B (6L) seperately add Part B, liquid hardener, to the Enviro Epoxy B-LV Part A base. Enviro Epoxy B-LV should be thoroughly mixed with a mechanical mixer at low speed with a suitable mixing paddle attached. Mix for 3 minutes or until uniform with a mechanical mixer at low speed (less than 400 RPM) prior to application.
Label | Witness Point
Checkpoint | Application - Enviro Epoxy BL-V Product TDS
Label | Apply primer using a brush or roller and casting aggregate for every 5 m2 applied. Applications of excessive build should be avoided, and material must not be allowed to pool on the substrate surface Ensure Primer is dry and tack free (within 24 hours) prior to next coat.
Label | Records - Photograph
Label | Witness Point
SECTION | BOND BREAKER- EACH LOCATION
Checkpoint | Caulking - AS 3740 2021 & AS 4654.1
Label | Apply compatible sealant to form smooth flexible cove to all internal corners, penetrations and joints. This is to be a 12mm x 12mm coved fillet as per AS3740 class III membrane requirements for internal areas and 15mm x 15mm coved fillet as per AS4654.1 class III membrane requirements for external areas. Bond breaker to be tack free prior to coating.
Label | Records - Photograph
Label | Records - Thickness testing with fillet gauge
Label | Witness Point
SECTION | BASE COAT - EACH LOCATION
Checkpoint | Weather/RH - HP1200 Product TDS
Label | Apply within 5-35°C RH must be 0-85%
Label | Screenshot - Temperature and weather forecast
Label | surveillance point
Checkpoint | Product Mixing - HP1200 Product TDS
Label | Mixing by way of 1:1 mix ratio (by volume) in heated plural component. Mix Part B thoroughly with a mechanical power mixer before use
Label | Witness Point
Checkpoint | Application- HP1200 Product TDS
Label | HP1200 must be sprayed using high pressue plural component dispensing equipment - Drums of component must be pre-heated to at least 25C prior to mixing or dispensing
Label | Records - Photograph
Label | Witness Point
Section | QA TESTING - EACH LOCATION
Checkpoint | Inspection
Label | Inspect after installation of reinforcement/finishes to check for any damage to waterproofing and rectify as required.
Label | Records - Photograph
Label | Witness Point
Checkpoint | Thickness Testing - Delfasco Positector
Label | Thickness testing of application to the recommended DFT of 1.0mm to manufacturers instructions.( 1 test per 10m2)
Label | Records - Photograph
Label | Hold Point
Checkpoint | ELT Testing - Delfasco Holiday Tester
Label | Conduct Electronic Leak Testing ( ELT) on area membraned
Label | Records - Photograph
Label | Hold point
SECTION | WEAR COAT- EACH LOCATION
Checkpoint | Weather/RH - Enviro 900 product TDS
Label | Apply within 5-35°C RH must be 0-85%
Label | Screenshot - Temperature and weather forecast
Label | surveillance point
Checkpoint | Mixing of Product - Enviro 900 product TDS
Label | Mix Part A and Part B separately, before combining. Enviro 900 should be thoroughly mixed with a mechanical mixer at low speed (less than 400 RPM) for a minimum of thirty seconds prior to application.
Label | Witness Point
Checkpoint | Application - Enviro 900 product TDS
Label | Enviro 900 to be applied by squeegee, roller or brush to finished membrane. Aggregate should be uniformly broadcasted to the wet Enviro 900 within 10 minutes.
Label | Records - Photograph
Label | Witness Point
SECTION | FIRST TOP COAT - EACH LOCATION
Checkpoint | Weather/RH - Enviro 800 product TDS
Label | Apply within 10-35°C RH must be 0-85%
Label | Screenshot - Temperature and weather forecast
Label | surveillance point
Checkpoint | Mixing - Enviro 800 product TDS
Label | Mixing by way of 4:1 mix ratio (A:B) by volume. Enviro 800 TC should be thoroughly mixed with a mechanical mixer at low speed (less than 400 RPM) prior to application. Add Part B to Part A and mix to a uniform colour and consistency of a minimum 3 minutes - allow to react for 10 minutes before application.
Label | Witness Point
Checkpoint | Application - Enviro 800 product TDS
Label | Enviro 800TC to be applied by roller or brush to finished membrane. Allow coat to sufficiently dry ( 24H) before proceeding to the next coat.
Label | Records - Photograph
Label | Witness Point
SECTION | SECOND TOP COAT - EACH LOCATION
Checkpoint | Weather/RH - Enviro 800 product TDS
Label | Apply within 10-35°C RH must be 0-85%
Label | Screenshot - Temperature and weather forecast
Label | surveillance point
Checkpoint | Mixing - Enviro 800 product TDS
Label | Mixing by way of 4:1 mix ratio (A:B) by volume. Enviro 800 TC should be thoroughly mixed with a mechanical mixer at low speed (less than 400 RPM) prior to application. Add Part B to Part A and mix to a uniform colour and consistency of a minimum 3 minutes - allow to react for 10 minutes before application.
Label | Witness Point
Checkpoint | Application - Enviro 800 product TDS
Label | Enviro 800TC to be applied by roller or brush to finished membrane. Allow coat to sufficiently dry ( 24H) before proceeding to the next coat.
Label | Records - Photograph
Label | Witness Point
SECTION | DETAILING- EACH LOCATION
CHECKPOINT | Vertical Termination Detailing - AS 4654.2
Label | Ensure Vertical terminations of membrane on a building element are provided with a pressure seal, reglet or by being overcoated with a waterproof or water resistant material to protect the membrane edge.
Label | Records - Photograph
Label | Witness Point
SECTION | SIGN OFFS
Checkpoint | Polyseal ITP acceptance Sign off
SIGNOFF | Subcontractor inspection sign off
Checkpoint | Site Engineer/foreman ITP accceptance Sign off
SIGNOFF | Site Engineer/foreman inspection sign off