## Sheet1
PVC Waterstop Plate
SECTION | DETAILS
Checkpoint | Attach any relevant documents or photos
text | ITP No.
text | Revision No. & Date
text | Prepared By
text | Reviewed By
text | Approved By
text | Suppoting documentations - e.g location, CIDD alerts etc.
SECTION | BATCH DETAIL NUMBER OF PRODUCTS - EACH LOCATION
Checkpoint | PVC Waterstop
Label | Records - Photograph
Label | surveillance point
SECTION | PRE COMMENCEMENT- EACH LOCATION
Checkpoint | Inspection of waterstop
Label | Inspect waterstop and review specification as per TDS
Label | surveillance point
Checkpoint | Samples Submitted
Label | Submit samples for approval as per Specific Material Requirements.
Label | Record Submissions
Checkpoint | First Of Type Inspection
Label | First of type of inspection conducted by builder prior to commencment of works taking place.
Label | Record Submissions
SECTION | APPLICATION - EACH LOCATION
Checkpoint | Quality assurance of bonding
Label | Check butt-welded joints making sure they don’t have defects such as Visible porosity in the weld,Charred or burnt material, Bubbles or inadequate bonding and Visible signs of splice separation when cooled splice
Checkpoint | installation of waterstops at Joints
Waterstop is positioned to ensure proper distance from steel reinforcing bars to prevent rock pockets and honeycomb. Waterstop is centred on joint, with approximately one-half of waterstop width to be embedded in concrete on each side of the joint. Waterstop to be cable tied to Reo
SECTION | SIGN OFFS
Checkpoint | Polyseal ITP acceptance Sign off
SIGNOFF | Subcontractor inspection sign off
Checkpoint | Site Engineer/foreman ITP accceptance Sign off
SIGNOFF | Site Engineer/foreman inspection sign off