## _res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | BLV + 700X + 250NS V1.1 | [5 empty] | BLV + 700X + 250NS V1.1 | bcb4f837-1851-407e-84d1-81e00e510de2
section | DETAILS
checkpoint | Attach any relevant documents or photos
text | ITP No.
text | Revision No. & Date
text | Prepared By
text | Reviewed By
text | Approved By
Text | Supporting documentations - e.g location, CIDD alerts etc.
section | BATCH DETAIL NUMBER OF PRODUCTS - EACH LOCATION
checkpoint | Enviro Flex FC/ Sika Flex Pro
label | Records - Photograph
label | Surveillance point
checkpoint | Enviro B-LV
label | Records - Photograph
label | Surveillance point
checkpoint | Enviro 700X
label | Records - Photograph
label | Surveillance point
checkpoint | Enviro 250NS
label | Records - Photograph
label | Surveillance point
section | PRE COMMENCEMENT - EACH LOCATION
checkpoint | Sample Submissions
label | Submit samples for approval as per Specific Material Requirements.
label | Record Submissions
checkpoint | First Of Type Inspection
label | First of type of inspection conducted by builder prior to commencment of works taking place.
label | Record Submissions
checkpoint | Material Management & Storage - Envirosystems TDS
label | Store materials in a dry, clean place away from direct sunlight as per TDS
label | Records - Photograph
label | Witness Point
checkpoint | Acceptance of Substrate - AS 4654 .2.2012 Section 2.5
label | Obtain clearance for work initiation.
label | Ensure a smooth substrate without protrusions, voids, or formwork distortions. The substrate should be free of honeycombing/bug holes.
label | Patching products must be fully cured as per TDS prior to application
label | Records - Photograph
label | Witness Point
checkpoint | Falls in Substrate- AS3740- 2021 Section 2.3 and AS 4654.2
label | Builder to confirm compliant falls; minimum 1-100 falls
label | Hold Point
checkpoint | Cracks in Substrate - AS2870 Table C2
label | Ensure no substrate cracks greater than 1.6mm.
label | Cracks of 1.6mm and over, movement structural joints, cold joints and Live cracks are to be referred to engineers for treatment methodology.
label | Records - Photograph
label | Witness Point
section | SUBSTRATE PREPERATION: AS 4654.2-2012
checkpoint | Substrate Preperation - AS 4654.2-2012
label | Ensure Surface is prepared to receive primer application.
label | Clean substrate so that it is free of mould, paint, sealers, coatings, curing agents, loose particles and other contamination or foreign matter that may interfere with the adhesion.
label | Achieve CSP2 and CSP3 Concrete finish profile.
label | Remove all sharp edges including screws, nails and concrete/mortar projection.
label | Steel surfaces should be treated with appropriate degreasers, then grit blasted and/or wire brushed where necessary.
label | Records - Photograph
label | Witness Point
section | PRIME COAT- EACH LOCATION
checkpoint | Moisture Content - Enviro Epoxy B-LV Product TDS
label | Check moisture content of substrate, not to exceed 6% (Min.1 test per 10m2).
label | Records - Photograph
label | Surveillance point
checkpoint | Weather/RH - Enviro Epoxy BL-V Product TDS
label | Apply within 5-35°C RH must be 0-85%
label | Screenshot - Temperature and weather forecast
label | Witness Point
checkpoint | Product Mixing - Enviro Epoxy BL-V Product TDS
label | Mix Part A (12L) and Part B (6L) seperately add Part B, liquid hardener, to the Enviro Epoxy B-LV Part A base.
label | Enviro Epoxy B-LV should be thoroughly mixed with a mechanical mixer at low speed with a suitable mixing paddle attached.
label | Mix for 3 minutes or until uniform with a mechanical mixer at low speed (less than 400 RPM) prior to application.
label | Witness Point
checkpoint | Application - Enviro Epoxy BL-V Product TDS
label | Apply primer using a brush or roller and casting aggregate for every 5 m2 applied.
label | Applications of excessive build should be avoided, and material must not be allowed to pool on the substrate surface
label | Ensure Primer is dry and tack free (within 24 hours) prior to next coat.
label | Records - Photograph
label | Witness Point
section | BOND BREAKER- EACH LOCATION
checkpoint | Caulking - AS 3740 2021 & AS 4654.1
label | Apply compatible sealant to form smooth flexible cove to all internal corners, penetrations and joints.
label | This is to be a 12mm x 12mm coved fillet as per AS3740 class III membrane requirements for internal areas and 15mm x 15mm coved fillet as per AS4654.1 class III membrane requirements for external areas.
label | Bond breaker to be tack free prior to coating.
label | Records - Photograph
label | Records - Thickness testing with fillet gauge
label | Witness Point
section | FIRST BASE COAT - EACH LOCATION
checkpoint | Weather/RH - 700X Product TDS
label | Apply within 5-35°C
label | RH must be 0-85%
label | Screenshot - Temperature and weather forecast
label | Surveillance point
checkpoint | Product Mixing - 700X Product TDS
label | ○ Product should be thoroughly mixed with a mechanical mixer at low speed (less than 400 RPM) prior to application.
label | Witness Point
checkpoint | Application - 700X Product TDS
label | ○ 700X to be applied by roller vertically on substrate and terminating min 150mm with brush.
label | Minimum application requirements set forth relevant Australian Standards to be followed
label | Allow membrane to dry for 24 Hours before proceeding to the second coat.
label | Records - Photograph
label | Witness Point
section | ENVIRO 700X - SECOND COAT
checkpoint | Weather/RH - 700X Product TDS
label | Apply within 5-35°C
label | RH must be 0-85%
label | Screenshot - Temperature and weather forecast
label | Surveillance point
checkpoint | Product Mixing - 700X Product TDS
label | ○ Product should be thoroughly mixed with a mechanical mixer at low speed (less than 400 RPM) prior to application.
label | Witness Point
checkpoint | Application - 700X Product TDS
label | ○ 700X to be applied by roller Horizontally on substrate and terminating min 150mm with brush.
label | Minimum application requirements set forth relevant Australian Standards to be followed
label | Allow membrane to dry for 24 Hours before proceeding to the second coat.
label | Records - Photograph
label | Witness Point
section | QA TESTING - EACH LOCATION
checkpoint | Inspection
label | Inspect after installation of reinforcement/finishes to check for any damage to waterproofing and rectify as required.
label | Records - Photograph
label | Witness Point
checkpoint | Thickness Testing - Delfasco Positector
label | Thickness testing of application to the recommended DFT of 1.5mm to manufacturers instructions. (1 test per 10m2)
label | Records - Photograph
label | Hold Point
checkpoint | ELT Testing - Delfasco Holiday Tester
label | Conduct Electronic Leak Testing ( ELT) on area membraned
label | Records - Photograph
label | Hold Point
section | DETAILING- EACH LOCATION
checkpoint | Vertical Termination Detailing - AS 4654.2
label | Ensure Vertical terminations of membrane on a building element are provided with a pressure seal, reglet or by being overcoated with a waterproof or water resistant material to protect the membrane edge.
label | Records - Photograph
label | Witness Point
section | FIRST TOP COAT - EACH LOCATION
checkpoint | Weather/RH - 250NS PRODUCT TDS
label | Apply within 5-35°C
label | RH must be 35-85%
label | Screenshot - Temperature and weather forecast
label | Surveillance point
checkpoint | Mixing- 250NS PRODUCT TDS
label | ○ Enviro 250NS should be thoroughly mixed with a mechanical mixer at low speed (less that 400 RPM) prior to application.
label | Witness Point
checkpoint | APPLICATION - 250NS PRODUCT TDS
label | ○ 250NS to be applied using roller and brush.
label | ○ Ensure Product is cured for 24 hours prior to second coat.
label | Records - Photograph
label | Witness Point
section | SECOND TOP COAT - EACH LOCATION
checkpoint | Weather/RH - 250NS PRODUCT TDS
label | Apply within 5-35°C
label | RH must be 35-85%
label | Screenshot - Temperature and weather forecast
label | Surveillance point
checkpoint | Mixing- 250NS PRODUCT TDS
label | ○ Enviro 250NS should be thoroughly mixed with a mechanical mixer at low speed (less that 400 RPM) prior to application.
label | Witness Point
checkpoint | APPLICATION - 250NS PRODUCT TDS
label | ○ 250NS to be applied using roller and brush.
label | Records - Photograph
label | Witness Point
section | SIGN OFFS
checkpoint | Polyseal ITP acceptance Sign off
holdpoint | Subcontractor inspection sign off
checkpoint | Site Engineer/foreman ITP accceptance Sign off
holdpoint | Site Engineer/foreman inspection sign off
checklist | Enviro BSM V1.1 | [5 empty] | Enviro BSM V1.1 | cbb72f06-380d-41d8-995c-c666be1d4551
section | DETAILS
checkpoint | Attach any relevant documents or photos
text | ITP No.
text | Revision No. & Date
text | Prepared By
text | Reviewed By
text | Approved By
text | Supporting documentations - e.g location, CIDD alerts etc.
section | BATCH DETAIL NUMBER OF PRODUCTS - EACH LOCATION
checkpoint | Enviro BSM
label | Records - Photograph
label | Surveillance point
checkpoint | Enviro Epoxy Grout 100
label | Records - Photograph
label | Surveillance point
checkpoint | Enviro 700X
label | Records - Photograph
label | Surveillance point
checkpoint | Envro Flex FC/ Sika FC
label | Records - Photograph
label | Surveillance point
section | PRE COMMENCEMENT- EACH LOCATION
checkpoint | Material Management & Storage
label | Enviro BSM to be stored upright in dry, cool conditions out of direct UV and weather. Maximum storage temperature is 45°C.
label | Records - Photograph
label | Witness Point
checkpoint | Acceptance of Substrate
label | The substrate should be sound and even, thus preventing movement or subsidence during concrete placement.
label | The substrate in which BSM is to be installed should have no protrusions, gaps or voids greater than 10mm. Penetrations such as plumbing and electrical pipes should be stabilized to prevent movement during membrane and concrete placement.
label | For horizontal membrane placement, ensure that the substrate is sound, especially when installing over compacted fill so to avoid displacement from traffic or pouring of concrete.
label | For vertical placement, ensure substrate is sound to provide required support for membrane during concrete placement.
label | Records - Photograph
label | Witness Point
checkpoint | Samples Submitted
label | Submit samples for approval as per Specific Material Requirements.
label | Record Submissions
checkpoint | First Of Type Inspection
label | First of type of inspection conducted by builder prior to commencment of works taking place.
label | Record Submissions
section | APPLICATION - EACH LOCATION
checkpoint | Horizontal application
label | For horizontal applications, Enviro BSM should be placed with the coloured protective layer facing upwards and the white HDPE layer facing the substrate. Stagger end laps of each run to avoid a build-up of layers.
label | Overlap each previous sheet by 75mm ensuring membranes overlap edge is positioned correctly. Ensure the back of each subsequent roll is clean prior to overlapping and once in place remove the plastic film (on the overlap section) to bond the sheets together.
label | Ensure a complete bond with no creases by using a heavy roller across overlap areas. Once overlap bond is complete the plastic film can be completely removed.
label | Records - Photograph
label | Witness Point
checkpoint | Vertical application - Witness Point
label | Enviro BSM should be mechanically fixed to the substrate using (substrate dependent) fixings with the coloured protective layer facing the concrete pour.
label | These fixings should only be placed in the overlap section of the membrane and have a low-profile head so that the sheet overlaps can lay flat and rolled evenly for optimum adhesion.
label | Overlapping in vertical applications should be done in the same manner as horizontal applications ensuring subsequent sheet is overlapped by 75mm, adhered, and mechanically fixed correctly before proceeding with the next.
label | The plastic film can be removed immediately in vertical applications. All cut edges and roll ends should be overlapped by 75mm, be clean and dry and sealed with Enviro BSM SeamTape.
label | Records - Photograph
label | Witness Point
section | DETAILING - EACH LOCATION
checkpoint | Reo Bars
label | Ensure bars are chemset and fully cured prior to detailing.
label | Use Flex FC/ Sikaflex FC to caulk around reo bars and overcoat with Enviro 700X.
label | Membrane to return out minimum 50mm.
label | Records - Photograph
label | Witness Point
checkpoint | Pile Caps
label | Pile cap to be encapsulated with Enviro epoxy grout 100 achieving minimum 50mm finished height.
label | Records - Photograph
label | Witness Point
checkpoint | Sub columns
label | Sub columns joints to be caulked and overcoated with Enviro 700X terminated minimum 100mm high and 100mm lapping on BSM sheet.
label | Records - Photograph
label | Witness Point
checkpoint | Service Penetrations
label | Service penetrations to be caulked around with Enviro flex FC/ SIka FC.
label | Records - Photograph
label | Witness Point
section | SIGN OFFS
checkpoint | Polyseal ITP acceptance Sign off
holdpoint | Subcontractor inspection sign off
checkpoint | Site Engineer/foreman ITP accceptance Sign off
holdpoint | Site Engineer/foreman inspection sign off
checklist | Enviro Clad V1.1 | [5 empty] | Enviro Clad V1.1 | 11fb1bdb-1bec-4919-bac2-37968efa3dbb
section | DETAILS
checkpoint | Attach any relevant documents or photos
text | ITP No.
text | Revision No. & Date
text | Prepared By
text | Reviewed By
text | Approved By
text | Supporting documentations - e.g location, CIDD alerts etc.
section | BATCH DETAIL NUMBER OF PRODUCTS - EACH LOCATION
checkpoint | Enviro Shield
label | Records - Photograph
label | Surveillance point
checkpoint | Enviro Flex FC/ Sika Flex FC
label | Records - Photograph
label | Surveillance point
checkpoint | Enviro Clad
label | Records - Photograph
label | Surveillance point
section | PRE COMMENCEMENT - EACH LOCATION
checkpoint | Sample Submissions
label | Submit samples for approval as per Specific Material Requirements.
label | Record Submissions
checkpoint | First Of Type Inspection
label | First of type of inspection conducted by builder prior to commencment of works taking place.
label | Record Submissions
checkpoint | Material Management & Storage - Envirosystems TDS
label | Store materials in a dry, clean place away from direct sunlight as per TDS
label | Records - Photograph
label | Witness Point
checkpoint | Acceptance of Substrate - AS 4654 .2.2012 Section 2.5
label | Obtain clearance for work initiation.
label | Ensure a smooth substrate without protrusions, voids, or formwork distortions. The substrate should be free of honeycombing/bug holes.
label | Patching products must be fully cured as per TDS prior to application
label | Records - Photograph
label | Witness Point
checkpoint | Falls in Substrate- AS3740- 2021 Section 2.3 and AS 4654.2
label | Builder to confirm compliant falls; minimum 1-100 falls
label | Hold Point
checkpoint | Cracks in Substrate - AS2870 Table C2
label | Ensure no substrate cracks greater than 1.6mm.
label | Cracks of 1.6mm and over, movement structural joints, cold joints and Live cracks are to be referred to engineers for treatment methodology.
label | Records - Photograph
label | Witness Point
section | SUBSTRATE PREPERATION - EACH LOCATION
checkpoint | Substrate Preperation - AS 4654.2-2012
label | Ensure Surface is prepared to receive primer application.
label | Clean substrate so that it is free of mould, paint, sealers, coatings, curing agents, loose particles and other contamination or foreign matter that may interfere with the adhesion.
label | Achieve CSP2 and CSP3 Concrete finish profile.
label | Remove all sharp edges including screws, nails and concrete/mortar projection.
label | Steel surfaces should be treated with appropriate degreasers, then grit blasted and/or wire brushed where necessary.
label | Records - Photograph
label | Witness Point
section | PRIME COAT- EACH LOCATION
checkpoint | Moisture Content - Enviro Shield Product TDS
label | Check Moisture content of substrate, not to exceed 6% (Min.1 test per 10m2).
label | Records - Photograph
label | Surveillance point
checkpoint | Weather/RH - Enviro Shield Product TDS
label | Apply within 10-35°C
label | RH must be 0-85%
label | Screenshot - Temperature and weather forecast
label | Witness Point
checkpoint | Mixing - Enviro Shield Product TDS
label | Add Enviro Shield Part B (grey liquid hardener) to the Enviro Shield Part A (base Thoroughly mix with a mechanical mixer at low speed (less than 400 RPM) prior to application.
label | Mix for 5 minutes or until uniform.
label | Allow to stand 5 minutes after mixing and then mix again for a minute.
label | Witness Point
checkpoint | Application - Enviro Shield Product TDS
label | Apply primer using a brush or roller.
label | Applications of excessive build should be avoided, and material must not be allowed to pool on the substrate surface.
label | Ensure Primer is dry and tack free (within 24 hours) prior to next coat.
label | Records - Photograph
label | Witness Point
section | BOND BREAKER- EACH LOCATION
checkpoint | Caulking - AS 3740 2021 & AS 4654.1
label | Apply compatible sealant to form smooth flexible cove to all internal corners, penetrations and joints.
label | This is to be a 12mm x 12mm coved fillet as per AS3740 class III membrane requirements for internal areas and 15mm x 15mm coved fillet as per AS4654.1 class III membrane requirements for external areas.
label | Bond breaker to be tack free prior to coating.
label | Records - Photograph
label | Records - Thickness testing with fillet gauge
label | Witness Point
section | FIRST BASE COAT - EACH LOCATION
checkpoint | Weather/RH - Enviro Clad Product TDS
label | Apply within 10-35°C
label | RH must be 0-85%
label | Screenshot - Temperature and weather forecast
label | Surveillance point
checkpoint | Mixing - Enviro Clad Product TDS
label | ○ Enviro Clad should be thoroughly mixed with a mechanical mixer at low speed (less than 400 RPM) prior to application.
label | Witness Point
checkpoint | Application - Enviro Clad Product TDS
label | ○ Enviro Clad to be applied by roller on substrate and detailed with a brush
label | Coating to achieve a wet film thickness of 600 micirons
label | Allow membrane to dry for 24 Hours before proceeding to the second coat.
label | Records - Photograph
label | Witness Point
section | SECOND BASE COAT- EACH LOCATION
checkpoint | Weather/RH - Enviro Clad Product TDS
label | Apply within 10-35°C
label | RH must be 0-85%
label | Screenshot - Temperature and weather forecast
label | Surveillance point
checkpoint | Mixing - Enviro Clad Product TDS
label | ○ Enviro Clad should be thoroughly mixed with a mechanical mixer at low speed (less than 400 RPM) prior to application.
label | Witness Point
checkpoint | Application - Enviro Clad Product TDS
label | ○ Enviro Clad to be applied by roller on substrate and detailed with a brush
label | Coating to achieve a wet film thickness of 600 micirons
label | Allow membrane to dry for 24 Hours before proceeding to the second coat.
label | Records - Photograph
label | Witness Point
section | QA TESTING - EACH LOCATION
checkpoint | Inspection
label | Inspect after installation of reinforcement/finishes to check for any damage to waterproofing and rectify as required.
label | Records - Photograph
label | Witness Point
checkpoint | Thickness Testing - Delfasco Positector
label | Thickness testing of application to the recommended DFT of 1.5mm to manufacturers instructions. (1 test per 10m2)
label | Records - Photograph
label | Hold Point
section | SIGN OFFS
checkpoint | Polyseal ITP acceptance Sign off
holdpoint | Subcontractor inspection sign off
checkpoint | Site Engineer/foreman ITP accceptance Sign off
holdpoint | Site Engineer/foreman inspection sign off
checklist | Enviro P2 + 700X V1.1 | [5 empty] | Enviro P2 + 700X V1.1 | 300506d5-3c6f-4a19-823e-30a30b36ebc6
section | DETAILS
checkpoint | Attach any relevant documents or photos
text | ITP No.
text | Revision No. & Date
text | Prepared By
text | Reviewed By
text | Approved By
text | Supporting documentations - e.g location, CIDD alerts etc.
section | BATCH DETAIL NUMBER OF PRODUCTS - EACH LOCATION
checkpoint | Enviro Flex FC/ Sika Flex Pro
label | Records - Photograph
label | Surveillance point
checkpoint | Enviro P2
label | Records - Photograph
label | Surveillance point
checkpoint | Enviro 700X
label | Records - Photograph
label | Surveillance point
section | PRE COMMENCEMENT - EACH LOCATION
checkpoint | Sample Submissions
label | Submit samples for approval as per Specific Material Requirements.
label | Record Submissions
checkpoint | First Of Type Inspection
label | First of type of inspection conducted by builder prior to commencment of works taking place.
label | Record Submissions
checkpoint | Material Management & Storage - Envirosystems TDS
label | Store materials in a dry, clean place away from direct sunlight as per TDS
label | Records - Photograph
label | Witness Point
checkpoint | Acceptance of Substrate - AS 4654 .2.2012 Section 2.5
label | Obtain clearance for work initiation.
label | Ensure a smooth substrate without protrusions, voids, or formwork distortions. The substrate should be free of honeycombing/bug holes.
label | Patching products must be fully cured as per TDS prior to application
label | Records - Photograph
label | Witness Point
checkpoint | Falls in Substrate- AS3740- 2021 Section 2.3 and AS 4654.2
label | Builder to confirm compliant falls; minimum 1-100 falls
label | Hold Point
checkpoint | Cracks in Substrate - AS2870 Table C2
label | Ensure no substrate cracks greater than 1.6mm.
label | Cracks of 1.6mm and over, movement structural joints, cold joints and Live cracks are to be referred to engineers for treatment methodology.
label | Records - Photograph
label | Witness Point
section | SUBSTRATE PREPERATION: AS 4654.2-2012
checkpoint | Substrate Preperation - AS 4654.2-2012
label | Ensure Surface is prepared to receive primer application.
label | Clean substrate so that it is free of mould, paint, sealers, coatings, curing agents, loose particles and other contamination or foreign matter that may interfere with the adhesion.
label | Achieve CSP2 and CSP3 Concrete finish profile.
label | Remove all sharp edges including screws, nails and concrete/mortar projection.
label | Steel surfaces should be treated with appropriate degreasers, then grit blasted and/or wire brushed where necessary.
label | Records - Photograph
label | Witness Point
section | PRIME COAT- EACH LOCATION
checkpoint | Moisture Content - Enviro P2 Product TDS
label | Check moisture content of substrate, not to exceed 6% (Min.1 test per 10m2).
label | Records - Photograph
label | Surveillance point
checkpoint | Weather/RH - Enviro P2 Product TDS
label | Apply within 5-35°C
label | RH must be 0-85%
label | Screenshot - Temperature and weather forecast
label | Witness Point
checkpoint | Product Mixing - Enviro Epoxy P2 Product TDS
label | Mix Part A (12L) and Part B (6L) seperately add Part B, liquid hardener, to the Enviro P2 Part A base.
label | Enviro P2 should be thoroughly mixed with a mechanical mixer at low speed with a suitable mixing paddle attached.
label | Mix for 3 minutes or until uniform with a mechanical mixer at low speed (less than 400 RPM) prior to application.
label | Witness Point
checkpoint | Application - Enviro P2 Product TDS
label | Apply primer using a brush or roller and casting aggregate for every 5 m2 applied.
label | Applications of excessive build should be avoided, and material must not be allowed to pool on the substrate surface
label | Ensure Primer is dry and tack free (within 24 hours) prior to next coat.
label | Records - Photograph
label | Witness Point
section | BOND BREAKER- EACH LOCATION
checkpoint | Caulking - AS 3740 2021 & AS 4654.1
label | Apply compatible sealant to form smooth flexible cove to all internal corners, penetrations and joints.
label | This is to be a 12mm x 12mm coved fillet as per AS3740 class III membrane requirements for internal areas and 15mm x 15mm coved fillet as per AS4654.1 class III membrane requirements for external areas.
label | Bond breaker to be tack free prior to coating.
label | Records - Photograph
label | Records - Thickness testing with fillet gauge
label | Witness Point
section | FIRST BASE COAT - EACH LOCATION
checkpoint | Weather/RH - 700X Product TDS
label | Apply within 5-35°C
label | RH must be 0-85%
label | Screenshot - Temperature and weather forecast
label | Surveillance point
checkpoint | Product Mixing - 700X Product TDS
label | ○ Product should be thoroughly mixed with a mechanical mixer at low speed (less than 400 RPM) prior to application.
label | Witness Point
checkpoint | Application - 700X Product TDS
label | ○ 700X to be applied by roller vertically on substrate and terminating min 150mm with brush.
label | Minimum application requirements set forth relevant Australian Standards to be followed
label | Allow membrane to dry for 24 Hours before proceeding to the second coat.
label | Records - Photograph
label | Witness Point
section | SECOND BASE COAT - EACH LOCATION
checkpoint | Weather/RH - 700X Product TDS
label | Apply within 5-35°C
label | RH must be 0-85%
label | Screenshot - Temperature and weather forecast
label | Surveillance point
checkpoint | Product Mixing - 700X Product TDS
label | ○ Product should be thoroughly mixed with a mechanical mixer at low speed (less than 400 RPM) prior to application.
label | Witness Point
checkpoint | Application - 700X Product TDS
label | ○ 700X to be applied by roller Horizontally on substrate and terminating min 150mm with brush.
label | Minimum application requirements set forth relevant Australian Standards to be followed
label | Allow membrane to dry for 24 Hours before proceeding to the second coat.
label | Records - Photograph
label | Witness Point
section | QA TESTING - EACH LOCATION
checkpoint | Inspection
label | Inspect after installation of reinforcement/finishes to check for any damage to waterproofing and rectify as required.
label | Records - Photograph
label | Witness Point
checkpoint | Thickness Testing - Delfasco Positector
label | Thickness testing of application to the recommended DFT of 1.5mm to manufacturers instructions. (1 test per 10m2)
label | Records - Photograph
label | Hold Point
checkpoint | ELT Testing - Delfasco Holiday Tester
label | Conduct Electronic Leak Testing ( ELT) on area membraned
label | Records - Photograph
label | Hold Point
label | Records - time stamped photograph
section | DETAILING- EACH LOCATION
checkpoint | Vertical Termination Detailing - AS 4654.2
label | Ensure Vertical terminations of membrane on a building element are provided with a pressure seal, reglet or by being overcoated with a waterproof or water resistant material to protect the membrane edge.
label | Records - Photograph
label | Witness Point
section | SIGN OFFS
checkpoint | Polyseal ITP acceptance Sign off
holdpoint | Subcontractor inspection sign off
checkpoint | Site Engineer/foreman ITP accceptance Sign off
holdpoint | Site Engineer/foreman inspection sign off
checklist | Enviro Ultra Tuff V1.1 | [5 empty] | Enviro Ultra Tuff V1.1 | 0bcfe49a-de1e-4679-9f79-d37e12fd3e3d
section | DETAILS
checkpoint | Attach any relevant documents or photos
text | ITP No.
text | Revision No. & Date
text | Prepared By
text | Reviewed By
text | Approved By
text | Supporting documentations - e.g location, CIDD alerts etc.
section | BATCH DETAIL NUMBER OF PRODUCTS - EACH LOCATION
checkpoint | Enviro B-LV
label | Records - Photograph
label | Surveillance point
checkpoint | Enviro Ultra Tuff
label | Records - Photograph
label | Surveillance point
section | PRE COMMENCEMENT - EACH LOCATION
checkpoint | Sample Submissions
label | Submit samples for approval as per Specific Material Requirements.
label | Record Submissions
checkpoint | First Of Type Inspection
label | First of type of inspection conducted by builder prior to commencment of works taking place.
label | Record Submissions
checkpoint | Material Management & Storage - Envirosystems TDS
label | Store materials in a dry, clean place away from direct sunlight as per TDS
label | Records - Photograph
label | Witness Point
checkpoint | Acceptance of Substrate - AS 4654 .2.2012 Section 2.5
label | Obtain clearance for work initiation.
label | Ensure a smooth substrate without protrusions, voids, or formwork distortions. The substrate should be free of honeycombing/bug holes.
label | Patching products must be fully cured as per TDS prior to application
label | Records - Photograph
label | Witness Point
checkpoint | Falls in Substrate- AS3740- 2021 Section 2.3 and AS 4654.2
label | Builder to confirm compliant falls; minimum 1-100 falls
label | Hold Point
checkpoint | Cracks in Substrate - AS2870 Table C2
label | Ensure no substrate cracks greater than 1.6mm.
label | Cracks of 1.6mm and over, movement structural joints, cold joints and Live cracks are to be referred to engineers for treatment methodology.
label | Records - Photograph
label | Witness Point
section | SUBSTRATE PREPERATION: AS 4654.2-2012
checkpoint | Substrate Preperation - AS 4654.2-2012
label | Ensure Surface is prepared to receive primer application.
label | Clean substrate so that it is free of mould, paint, sealers, coatings, curing agents, loose particles and other contamination or foreign matter that may interfere with the adhesion.
label | Achieve CSP2 and CSP3 Concrete finish profile.
label | Remove all sharp edges including screws, nails and concrete/mortar projection.
label | Steel surfaces should be treated with appropriate degreasers, then grit blasted and/or wire brushed where necessary.
label | Records - Photograph
label | Witness Point
section | PRIME COAT- EACH LOCATION
checkpoint | Moisture Content - Enviro Epoxy B-LV Product TDS
label | Check moisture content of substrate, not to exceed 6% (Min.1 test per 10m2).
label | Records - Photograph
label | Surveillance point
checkpoint | Weather/RH - Enviro Epoxy BL-V Product TDS
label | Apply within 5-35°C RH must be 0-85%
label | Screenshot - Temperature and weather forecast
label | Witness Point
checkpoint | Product Mixing - Enviro Epoxy BL-V Product TDS
label | Mix Part A (12L) and Part B (6L) seperately add Part B, liquid hardener, to the Enviro Epoxy B-LV Part A base.
label | Enviro Epoxy B-LV should be thoroughly mixed with a mechanical mixer at low speed with a suitable mixing paddle attached.
label | Mix for 3 minutes or until uniform with a mechanical mixer at low speed (less than 400 RPM) prior to application.
label | Witness Point
checkpoint | Application - Enviro Epoxy BL-V Product TDS
label | Apply primer using a brush or roller and casting aggregate for every 5 m2 applied.
label | Applications of excessive build should be avoided, and material must not be allowed to pool on the substrate surface
label | Ensure Primer is dry and tack free (within 24 hours) prior to next coat.
label | Records - Photograph
label | Witness Point
section | EPOXY COVING - EACH LOCATION
checkpoint | Coving - Enviro Epoxy B product data sheet
label | Mix Sand plus Epoxy B according to the works' design specifications to create minimum 75mm coving
label | Records - Photograph
label | Witness Point
section | FIRST EPOXY COAT - EACH LOCATION
checkpoint | Weather/RH - Enviro Ultra Tuff Product TDS
label | Apply within 5-35°C
label | RH must be 0-85%
label | Screenshot - Temperature and weather forecast
label | Surveillance point
checkpoint | Product Mixing - Enviro Ultra Tuff Product TDS
label | When using a colour pack add to Part A and mechanically mix until uniform. Add Part B and re-mix until components are uniformly mixed. Colour Packs Rations: 1 pack to make a 8L kit and 2 for the 16L kit.
label | Product should be thoroughly mixed with a mechanical mixer at low speed (less than 400 RPM) for 3mins prior to application.
label | Witness Point
checkpoint | Application - Enviro Ultra Tuff Product TDS
label | Enviro Ultra Tuff can be applied by brush or roller to minimum dry film thickness of 250 Microns
label | Broadcast selected aggregate and allow to cure for 24 hours prior to second coat
label | Records - Photograph
label | Witness Point
section | SECOND EPOXY COAT - EACH LOCATION
checkpoint | Weather/RH - Enviro Ultra Tuff Product TDS
label | Apply within 5-35°C
label | RH must be 0-85%
label | Records - Photograph
label | Surveillance point
checkpoint | Product Mixing - Enviro Ultra Tuff Product TDS
label | When using a colour pack add to Part A and mechanically mix until uniform. Add Part B and re-mix until components are uniformly mixed. Colour Packs Rations: 1 pack to make a 8L kit and 2 for the 16L kit.
label | Product should be thoroughly mixed with a mechanical mixer at low speed (less than 400 RPM) for 3mins prior to application.
label | Witness Point
checkpoint | Application - Enviro Ultra Tuff Product TDS
label | Enviro Ultra Tuff can be applied by brush or roller to minimum dry film thickness of 250 Microns
label | Records - Photograph
label | Witness Point
section | QA TESTING - EACH LOCATION
checkpoint | Inspection
label | Inspect after installation of reinforcement/finishes to check for any damage to coating and rectify as required.
label | Records - Photograph
label | Witness Point
section | SIGN OFFS
checkpoint | Polyseal ITP acceptance Sign off
holdpoint | Subcontractor inspection sign off
checkpoint | Site Engineer/foreman ITP accceptance Sign off
holdpoint | Site Engineer/foreman inspection sign off
checklist | HP1200 v1.1 | [5 empty] | HP1200 v1.1 | b8ff14f3-7840-47e2-aa62-60598c3705fb
section | DETAILS
checkpoint | Attach any relevant documents or photos
text | ITP No.
text | Revision No. & Date
text | Prepared By
text | Reviewed By
text | Approved By
text | Supporting documentations - e.g location, CIDD alerts etc.
section | BATCH DETAIL NUMBER OF PRODUCTS - EACH LOCATION
checkpoint | Enviro B-LV
label | Records - Photograph
label | Surveillance point
checkpoint | Sika Flex FC/ Enviro Flex FC
label | Records - Photograph
label | Surveillance point
checkpoint | Enviro HP1200
label | Records - Photograph
label | Surveillance point
section | PRE COMMENCEMENT - EACH LOCATION
checkpoint | Sample Submissions
label | Submit samples for approval as per Specific Material Requirements.
label | Record Submissions
checkpoint | First Of Type Inspection
label | First of type of inspection conducted by builder prior to commencment of works taking place.
label | Record Submissions
checkpoint | Material Management & Storage - Envirosystems TDS
label | Store materials in a dry, clean place away from direct sunlight as per TDS
label | Records - Photograph
label | Witness Point
checkpoint | Acceptance of Substrate - AS 4654 .2.2012 Section 2.5
label | Obtain clearance for work initiation.
label | Ensure a smooth substrate without protrusions, voids, or formwork distortions. The substrate should be free of honeycombing/bug holes.
label | Patching products must be fully cured as per TDS prior to application
label | Records - Photograph
label | Witness Point
checkpoint | Falls in Substrate- AS3740- 2021 Section 2.3 and AS 4654.2
label | Builder to confirm compliant falls; minimum 1-100 falls
label | Hold Point
checkpoint | Cracks in Substrate - AS2870 Table C2
label | Ensure no substrate cracks greater than 1.6mm.
label | Cracks of 1.6mm and over, movement structural joints, cold joints and Live cracks are to be referred to engineers for treatment methodology.
label | Records - Photograph
label | Witness Point
section | SUBSTRATE PREPERATION: AS 4654.2-2012
checkpoint | Substrate Preperation - AS 4654.2-2012
label | Ensure Surface is prepared to receive primer application.
label | Clean substrate so that it is free of mould, paint, sealers, coatings, curing agents, loose particles and other contamination or foreign matter that may interfere with the adhesion.
label | Achieve CSP2 and CSP3 Concrete finish profile.
label | Remove all sharp edges including screws, nails and concrete/mortar projection.
label | Steel surfaces should be treated with appropriate degreasers, then grit blasted and/or wire brushed where necessary.
label | Records - Photograph
label | Witness Point
section | PRIME COAT- EACH LOCATION
checkpoint | Moisture Content - Enviro Epoxy B-LV Product TDS
label | Check moisture content of substrate, not to exceed 6% (Min.1 test per 10m2).
label | Records - Photograph
label | Surveillance point
checkpoint | Weather/RH - Enviro Epoxy BL-V Product TDS
label | Apply within 5-35°C
label | RH must be 0-85%
label | Screenshot - Temperature and weather forecast
label | Witness Point
checkpoint | Product Mixing - Enviro Epoxy BL-V Product TDS
label | Mix Part A (12L) and Part B (6L) seperately add Part B, liquid hardener, to the Enviro Epoxy B-LV Part A base.
label | Enviro Epoxy B-LV should be thoroughly mixed with a mechanical mixer at low speed with a suitable mixing paddle attached.
label | Mix for 3 minutes or until uniform with a mechanical mixer at low speed (less than 400 RPM) prior to application.
label | Witness Point
checkpoint | Application - Enviro Epoxy BL-V Product TDS
label | Apply primer using a brush or roller and casting aggregate for every 5 m2 applied.
label | Applications of excessive build should be avoided, and material must not be allowed to pool on the substrate surface
label | Ensure Primer is dry and tack free (within 24 hours) prior to next coat.
label | Records - Photograph
label | Witness Point
section | BOND BREAKER- EACH LOCATION
checkpoint | Caulking - AS 3740 2021 & AS 4654.1
label | Apply compatible sealant to form smooth flexible cove to all internal corners, penetrations and joints.
label | This is to be a 12mm x 12mm coved fillet as per AS3740 class III membrane requirements for internal areas and 15mm x 15mm coved fillet as per AS4654.1 class III membrane requirements for external areas.
label | Bond breaker to be tack free prior to coating.
label | Records - Photograph
label | Records - Thickness testing with fillet gauge
label | Witness Point
section | BASE COAT - EACH LOCATION
checkpoint | Weather/RH - HP1200 Product TDS
label | Apply within 5-35°C
label | RH must be 0-85%
label | Screenshot - Temperature and weather forecast
label | Surveillance point
checkpoint | Product Mixing - HP1200 Product TDS
label | Mixing by way of 1:1 mix ratio (by volume) in heated plural component.
label | Mix Part B thoroughly with a mechanical power mixer before use
label | Witness Point
checkpoint | Application - HP1200 Product TDS
label | HP1200 must be sprayed using high pressue plural component dispensing equipment - Drums of component must be pre-heated to at least 25C prior to mixing or dispensing
label | Records - Photograph
label | Witness Point
section | QA TESTING - EACH LOCATION
checkpoint | Inspection
label | Inspect after installation of reinforcement/finishes to check for any damage to waterproofing and rectify as required.
label | Records - Photograph
label | Witness Point
checkpoint | Thickness Testing - Delfasco Positector
label | Thickness testing of application to the recommended DFT of 1.5mm to manufacturers instructions. (1 test per 10m2)
label | Records - Photograph
label | Witness Point
checkpoint | ELT Testing - Delfasco Holiday Tester
label | Conduct Electronic Leak Testing ( ELT) on area membraned
label | Records - Photograph
label | Witness Point
section | DETAILING- EACH LOCATION
checkpoint | Vertical Termination Detailing - AS 4654.2
label | Ensure Vertical terminations of membrane on a building element are provided with a pressure seal, reglet or by being overcoated with a waterproof or water resistant material to protect the membrane edge.
label | Records - Photograph
label | Witness Point
section | SIGN OFFS
checkpoint | Polyseal ITP acceptance Sign off
holdpoint | Subcontractor inspection sign off
checkpoint | Site Engineer/foreman ITP accceptance Sign off
holdpoint | Site Engineer/foreman inspection sign off
checklist | HP1200 + 800TC V1.1 | [5 empty] | HP1200 + 800TC V1.1 | 1b4a2d1e-9087-4f76-a560-0fbd8d7b23cb
section | DETAILS
checkpoint | Attach any relevant documents or photos
text | ITP No.
text | Revision No. & Date
text | Prepared By
text | Reviewed By
text | Approved By
text | Supporting documentations - e.g location, CIDD alerts etc.
section | BATCH DETAIL NUMBER OF PRODUCTS - EACH LOCATION
checkpoint | Enviro B-LV
label | Records - Photograph
label | Surveillance point
checkpoint | Sika Flex FC/ Enviro Flex FC
label | Records - Photograph
label | Surveillance point
checkpoint | Enviro HP1200
label | Records - Photograph
label | Surveillance point
checkpoint | Enviro 800TC
label | Records - Photograph
label | Surveillance point
section | PRE COMMENCEMENT - EACH LOCATION
checkpoint | Sample Submissions
label | Submit samples for approval as per Specific Material Requirements.
label | Record Submissions
checkpoint | First Of Type Inspection
label | First of type of inspection conducted by builder prior to commencment of works taking place.
label | Record Submissions
checkpoint | Material Management & Storage - Envirosystems TDS
label | Store materials in a dry, clean place away from direct sunlight as per TDS
label | Records - Photograph
label | Witness Point
checkpoint | Acceptance of Substrate - AS 4654 .2.2012 Section 2.5
label | Obtain clearance for work initiation.
label | Ensure a smooth substrate without protrusions, voids, or formwork distortions. The substrate should be free of honeycombing/bug holes.
label | Patching products must be fully cured as per TDS prior to application
label | Records - Photograph
label | Witness Point
checkpoint | Falls in Substrate- AS3740- 2021 Section 2.3 and AS 4654.2
label | Builder to confirm compliant falls; minimum 1-100 falls
label | Hold Point
checkpoint | Cracks in Substrate - AS2870 Table C2
label | Ensure no substrate cracks greater than 1.6mm.
label | Cracks of 1.6mm and over, movement structural joints, cold joints and Live cracks are to be referred to engineers for treatment methodology.
label | Records - Photograph
label | Witness Point
section | SUBSTRATE PREPERATION: AS 4654.2-2012
checkpoint | Substrate Preperation - AS 4654.2-2012
label | Ensure Surface is prepared to receive primer application.
label | Clean substrate so that it is free of mould, paint, sealers, coatings, curing agents, loose particles and other contamination or foreign matter that may interfere with the adhesion.
label | Achieve CSP2 and CSP3 Concrete finish profile.
label | Remove all sharp edges including screws, nails and concrete/mortar projection.
label | Steel surfaces should be treated with appropriate degreasers, then grit blasted and/or wire brushed where necessary.
label | Records - Photograph
label | Witness Point
section | PRIME COAT- EACH LOCATION
checkpoint | Moisture Content - Enviro Epoxy B-LV Product TDS
label | Check moisture content of substrate, not to exceed 6% (Min.1 test per 10m2).
label | Records - Photograph
label | Surveillance point
checkpoint | Weather/RH - Enviro Epoxy BL-V Product TDS
label | Apply within 5-35°C RH must be 0-85%
label | Screenshot - Temperature and weather forecast
label | Witness Point
checkpoint | Product Mixing - Enviro Epoxy BL-V Product TDS
label | Mix Part A (12L) and Part B (6L) seperately add Part B, liquid hardener, to the Enviro Epoxy B-LV Part A base.
label | Enviro Epoxy B-LV should be thoroughly mixed with a mechanical mixer at low speed with a suitable mixing paddle attached.
label | Mix for 3 minutes or until uniform with a mechanical mixer at low speed (less than 400 RPM) prior to application.
label | Witness Point
checkpoint | Application - Enviro Epoxy BL-V Product TDS
label | Apply primer using a brush or roller and casting aggregate for every 5 m2 applied.
label | Applications of excessive build should be avoided, and material must not be allowed to pool on the substrate surface
label | Ensure Primer is dry and tack free (within 24 hours) prior to next coat.
label | Records - Photograph
label | Witness Point
section | BOND BREAKER- EACH LOCATION
checkpoint | Caulking - AS 3740 2021 & AS 4654.1
label | Apply compatible sealant to form smooth flexible cove to all internal corners, penetrations and joints.
label | This is to be a 12mm x 12mm coved fillet as per AS3740 class III membrane requirements for internal areas and 15mm x 15mm coved fillet as per AS4654.1 class III membrane requirements for external areas.
label | Bond breaker to be tack free prior to coating.
label | Records - Photograph
label | Records - Thickness testing with fillet gauge
label | Witness Point
section | BASE COAT - EACH LOCATION
checkpoint | Weather/RH - HP1200 Product TDS
label | Apply within 5-35°C
label | RH must be 0-85%
label | Screenshot - Temperature and weather forecast
label | Surveillance point
checkpoint | Product Mixing - HP1200 Product TDS
label | Mixing by way of 1:1 mix ratio (by volume) in heated plural component.
label | Mix Part B thoroughly with a mechanical power mixer before use
label | Witness Point
checkpoint | Application - HP1200 Product TDS
label | HP1200 must be sprayed using high pressue plural component dispensing equipment - Drums of component must be pre-heated to at least 25C prior to mixing or dispensing
label | Records - Photograph
label | Witness Point
section | QA TESTING - EACH LOCATION
checkpoint | Inspection
label | Inspect after installation of reinforcement/finishes to check for any damage to waterproofing and rectify as required.
label | Records - Photograph
label | Witness Point
checkpoint | Thickness Testing - Delfasco Positector
label | Thickness testing of application to the recommended DFT of 1.5mm to manufacturers instructions. (1 test per 10m2)
label | Records - Photograph
label | Hold Point
checkpoint | ELT Testing - Delfasco Holiday Tester
label | Conduct Electronic Leak Testing ( ELT) on area membraned
label | Records - Photograph
label | Hold point
section | WEAR COAT- EACH LOCATION
checkpoint | Weather/RH - Enviro 900 product TDS
label | Apply within 5-35°C
label | RH must be 0-85%
label | Screenshot - Temperature and weather forecast
label | Surveillance point
checkpoint | Mixing of Product - Enviro 900 product TDS
label | Mix Part A and Part B separately, before combining.
label | Enviro 900 should be thoroughly mixed with a mechanical mixer at low speed (less than 400 RPM) for a minimum of thirty seconds prior to application.
label | Witness Point
checkpoint | Application - Enviro 900 product TDS
label | Enviro 900 to be applied by squeegee, roller or brush to finished membrane.
label | Aggregate should be uniformly broadcasted to the wet Enviro 900 within 10 minutes.
label | Records - Photograph
label | Witness Point
section | FIRST TOP COAT - EACH LOCATION
checkpoint | Weather/RH - Enviro 800 product TDS
label | Apply within 10-35°C
label | RH must be 0-85%
label | Screenshot - Temperature and weather forecast
label | Surveillance point
checkpoint | Mixing - Enviro 800 product TDS
label | Mixing by way of 4:1 mix ratio (A:B) by volume.
label | Enviro 800 TC should be thoroughly mixed with a mechanical mixer at low speed (less than 400 RPM) prior to application.
label | Add Part B to Part A and mix to a uniform colour and consistency of a minimum 3 minutes - allow to react for 10 minutes before application.
label | Witness Point
checkpoint | Application - Enviro 800 product TDS
label | Enviro 800TC to be applied by roller or brush to finished membrane.
label | Allow coat to sufficiently dry ( 24H) before proceeding to the next coat.
label | Records - Photograph
label | Witness Point
section | SECOND TOP COAT - EACH LOCATION
checkpoint | Weather/RH - Enviro 800 product TDS
label | Apply within 10-35°C
label | RH must be 0-85%
label | Screenshot - Temperature and weather forecast
label | Surveillance point
checkpoint | Mixing - Enviro 800 product TDS
label | Mixing by way of 4:1 mix ratio (A:B) by volume.
label | Enviro 800 TC should be thoroughly mixed with a mechanical mixer at low speed (less than 400 RPM) prior to application.
label | Add Part B to Part A and mix to a uniform colour and consistency of a minimum 3 minutes - allow to react for 10 minutes before application.
label | Witness Point
checkpoint | Application - Enviro 800 product TDS
label | Enviro 800TC to be applied by roller or brush to finished membrane.
label | Allow coat to sufficiently dry ( 24H) before proceeding to the next coat.
label | Records - Photograph
label | Witness Point
section | DETAILING- EACH LOCATION
checkpoint | Vertical Termination Detailing - AS 4654.2
label | Ensure Vertical terminations of membrane on a building element are provided with a pressure seal, reglet or by being overcoated with a waterproof or water resistant material to protect the membrane edge.
label | Records - Photograph
label | Witness Point
section | SIGN OFFS
checkpoint | Polyseal ITP acceptance Sign off
holdpoint | Subcontractor inspection sign off
checkpoint | Site Engineer/foreman ITP accceptance Sign off
holdpoint | Site Engineer/foreman inspection sign off
checklist | Sealer V1.1 | [5 empty] | Sealer V1.1 | abfda6e1-3062-4777-8465-3392cfdb040c
section | DETAILS
checkpoint | Attach any relevant documents or photos
text | ITP No.
text | Revision No. & Date
text | Prepared By
text | Reviewed By
text | Approved By
text | Supporting documentations - e.g location, CIDD alerts etc.
section | BATCH DETAIL NUMBER OF PRODUCTS - EACH LOCATION
checkpoint | Enviro Seal WB
label | Records - Photograph
label | Surveillance point
checkpoint | Enviro CSH
label | Records - Photograph
label | Surveillance point
section | PRE COMMENCEMENT - EACH LOCATION
checkpoint | Sample Submissions
label | Submit samples for approval as per Specific Material Requirements.
label | Record Submissions
checkpoint | First Of Type Inspection
label | First of type of inspection conducted by builder prior to commencment of works taking place.
label | Record Submissions
checkpoint | Material Management & Storage - Envirosystems TDS
label | Store materials in a dry, clean place away from direct sunlight as per TDS
label | Records - Photograph
label | Witness Point
checkpoint | Acceptance of Substrate - AS 4654 .2.2012 Section 2.5
label | Obtain clearance for work initiation.
label | Ensure a smooth substrate without protrusions, voids, or formwork distortions. The substrate should be free of honeycombing/bug holes.
label | Patching products must be fully cured as per TDS prior to application
label | Records - Photograph
label | Witness Point
checkpoint | Cracks in Substrate - AS2870 C2
label | Ensure no substrate cracks greater than 1.6mm.
label | Cracks of 1.6mm and over, movement structural joints, cold joints and Live cracks are to be referred to engineers for treatment methodology.
label | Records - Photograph
label | Witness Point
select | Inspection | Surveillance point, Witness point
section | SUBSTRATE PREPERATION - EACH LOCATION
checkpoint | Substrate Preperation - AS 4654.2-2012
label | Ensure Surface is prepared to receive primer application.
label | Clean substrate so that it is free of mould, paint, sealers, coatings, curing agents, loose particles and other contamination or foreign matter that may interfere with the adhesion.
label | Achieve CSP2 and CSP3 Concrete finish profile.
label | Remove all sharp edges including screws, nails and concrete/mortar projection.
label | Steel surfaces should be treated with appropriate degreasers, then grit blasted and/or wire brushed where necessary.
label | Records - Photograph
label | Witness Point
section | FIRST SEALER COAT - EACH LOCATION
checkpoint | Application
label | Spray or roll concrete Sealer on substrate
label | Allow membrane to dry for 24 Hours before proceeding to the second coat.
label | Records - Photograph
label | Witness Point
section | SECOND SEALER COAT - EACH LOCATION
checkpoint | Application
label | Spray or roll concrete Sealer on substrate
label | Allow membrane to dry for 24 Hours before proceeding to the second coat.
label | Records - Photograph
label | Witness Point
section | SIGN OFFS
checkpoint | Polyseal ITP acceptance Sign off
holdpoint | Subcontractor inspection sign off
checkpoint | Site Engineer/foreman ITP accceptance Sign off
holdpoint | Site Engineer/foreman inspection sign off
checklist | WB Primer + Enviro 200P V1.1 | [5 empty] | WB Primer + Enviro 200P V1.1 | 2378b285-cdaa-49ab-bcf0-87c1b5210c6b
section | DETAILS
checkpoint | Attach any relevant documents or photos
text | ITP No.
text | Revision No. & Date
text | Prepared By
text | Reviewed By
text | Approved By
text | Supporting documentations - e.g location, CIDD alerts etc.
section | BATCH DETAIL NUMBER OF PRODUCTS - EACH LOCATION
checkpoint | Enviro WB Primer
label | Records - Photograph
label | Surveillance point
checkpoint | Enviro Flex FC/ Sika Flex FC
label | Records - Photograph
label | Surveillance point
checkpoint | Enviro 200P Ultra
label | Records - Photograph
label | Surveillance point
section | PRE COMMENCEMENT - EACH LOCATION
checkpoint | Samples Submitted
label | Submit samples for approval as per Specific Material Requirements.
label | Record Submissions
checkpoint | First Of Type Inspection
label | First of type of inspection conducted by builder prior to commencment of works taking place.
label | Record Submissions
checkpoint | Material Management & Storage - Envirosystems TDS
label | Store materials in a dry, clean place away from direct sunlight as per TDS
label | Records - Photograph
label | Witness Point
checkpoint | Acceptance of Substrate - AS 4654 .2.2012 Section 2.5
label | Obtain clearance for work initiation.
label | Ensure a smooth substrate without protrusions, voids, or formwork distortions. The substrate should be free of honeycombing/bug holes.
label | Patching products must be fully cured as per PDS before applying the membrane.
label | Records - Photograph
label | Witness Point
checkpoint | Acceptance of Puddle Flanges - AS3740-2021 Section 4.3.1
label | All Puddle flanges to be recessed into substrate to finish flush ready for waterproofing.
label | Records - Photograph
label | Witness Point
checkpoint | Acceptance of wall - AS3740- 2021 Section 4.4.4
label | FC sheeting to have max 6mm gap at floor/wall junction.
label | Sheets to be set with manufacturers base coat, including all nails, penetrations and corners.
label | Mortar in block work needs to be a flush joint, smooth and level with the blocks, no blow outs of mortar.
label | Records - Photograph
label | Witness Point
checkpoint | Falls in Substrate- AS3740- 2021 Section 2.3
label | Builder to confirm compliant falls; minimum 1-100 falls and 1-80 in showers
label | Hold Point
checkpoint | Cracks in Substrate - AS2870 C2
label | Ensure no substrate cracks greater than 1.6mm.
label | Cracks of 1.6mm and over, movement structural joints, cold joints and Live cracks are to be referred to engineers for treatment methodology.
label | Records - Photograph
label | Witness Point
section | SUBSTRATE PREPERATION - EACH LOCATION
checkpoint | Substrate Preperation - AS 4654.2-2012
label | Ensure Surface is prepared to receive primer application.
label | Clean substrate so that it is free of mould, paint, sealers, coatings, curing agents, loose particles and other contamination or foreign matter that may interfere with the adhesion.
label | Achieve CSP2 and CSP3 Concrete finish profile.
label | Remove all sharp edges including screws, nails and concrete/mortar projection.
label | Steel surfaces should be treated with appropriate degreasers, then grit blasted and/or wire brushed where necessary.
label | Records - Photograph
label | Witness Point
section | PRIME COAT- EACH LOCATION
checkpoint | Moisture Content - Enviro prime WB product TDS
label | Check moisture content of substrate, not to exceed 6% (Min.1 test per 10m2).
label | Records - Photograph
label | Surveillance point
checkpoint | Weather/RH - Enviro prime WB Product TDS
label | Apply within 10-35°C
label | RH must be 0-85%
label | Screenshot - Temperature and weather forecast
label | Witness Point
checkpoint | Mixing - Enviro prime WB TDS
label | Dilute 1 part Enviro Prime WB with 1 part water and brush/roll out over surface, ensuring a consistent coverage across entire area to be membrane. Allow to dry before proceeding with waterproofing membrane application.
label | Witness Point
checkpoint | Application - Enviro prime WB TDS
label | Apply primer using a brush or roller.
label | Applications of excessive build should be avoided, and material must not be allowed to pool on the substrate surface.
label | Ensure Primer is dry and tack free prior to next coat.
label | Records - Photograph
label | Witness Point
section | BOND BREAKER- EACH LOCATION
checkpoint | Caulking - AS 3740 2021 & AS 4654.1
label | Apply compatible sealant to form smooth flexible cove to all internal corners, penetrations and joints.
label | This is to be a 12mm x 12mm coved fillet as per AS3740 class III membrane requirements for internal areas and 15mm x 15mm coved fillet as per AS4654.1 class III membrane requirements for external areas.
label | Bond breaker to be tack free prior to coating.
label | Records - Photograph
label | Records - Thickness testing with fillet gauge
label | Witness Point
section | FIRST BASE COAT - EACH LOCATION
checkpoint | Weather/RH - 200P Ultra Product TDS
label | Apply within 10-35°C
label | RH must be 0-85%
label | Screenshot - Temperature and weather forecast
label | Surveillance point
checkpoint | Mixing - 200P Ultra Product TDS
label | ○ 200P Ultra should be thoroughly mixed with a mechanical mixer at low speed (less than 400 RPM) prior to application.
label | Witness Point
checkpoint | Application - 200P Ultra Product TDS
label | ○ 200P Ultra to be applied by roller vertically on substrate and terminating min 150mm with brush.
label | Minimum application requirements set forth relevant Australian Standards to be followed
label | Allow membrane to dry for 24 Hours before proceeding to the second coat.
label | Records - Photograph
label | Witness Point
section | SECOND BASE COAT- EACH LOCATION
checkpoint | Weather/RH - 200P Ultra Product TDS
label | Apply within 10-35°C
label | RH must be 0-85%
label | Screenshot - Temperature and weather forecast
label | Surveillance point
checkpoint | Mixing - 200P Ultra Product TDS
label | ○ 200P Ultra should be thoroughly mixed with a mechanical mixer at low speed (less than 400 RPM) prior to application.
label | Witness Point
checkpoint | Application - 200P Ultra Product TDS
label | ○ 200P Ultra to be applied by roller vertically on substrate and terminating min 150mm with brush.
label | Minimum application requirements set forth relevant Australian Standards to be followed
label | Allow membrane to dry for 24 Hours before proceeding to the second coat.
label | Records - Photograph
label | Witness Point
section | QA TESTING - EACH LOCATION
checkpoint | Inspection
label | Inspect after installation of reinforcement/finishes to check for any damage to waterproofing and rectify as required.
label | Records - Photograph
label | Witness Point
checkpoint | Thickness Testing - Delfasco Positector
label | Thickness testing of application to the recommended DFT of 1.5mm to manufacturers instructions. (1 test per 10m2)
label | Records - Photograph
label | Hold Point
checkpoint | Flood Testing
label | Mark water level and conduct a 24 hour flood test for internal wet areas
label | Records - Photograph
label | Hold Point
section | SIGN OFFS
checkpoint | Polyseal ITP acceptance Sign off
holdpoint | Subcontractor inspection sign off
checkpoint | Site Engineer/foreman ITP accceptance Sign off
holdpoint | Site Engineer/foreman inspection sign off