## Resources
type | name | value
checklist | ITR No.0 5 Rough in
Label | Drawing Rev No.
checkpoint | Area clear, tidy and accessible
checkpoint | Rough in all lighting feeds and label on plan
checkpoint | Rough in of all lighting circuits- inc Emg/Exits and sensors
checkpoint | Rough in of all external lights
checkpoint | Rough in all power feeds and label on plan
checkpoint | Rough in of all power circuits
checkpoint | Check for clashes with other services
checkpoint | Assess all relevent drawings to ensure cables are in appropriate location.
checkpoint | Ensure area is left clean
checkpoint | Make sure any junctions are left in an accessible area and clearly marked on relevent plans/uploaded to conqa
checkpoint | Power plans are uploaded with location of feeds
checkpoint | Lighting plans are uploaded with location of feeds including dali route.
checklist | ITR No.7 - Fit Off
Label | Drawing Rev No.
checkpoint | Area clear, tidy and accessible
checkpoint | Ensure danger tags have up to date contact & isolation details
checkpoint | LOCK OFF & TAG circuits that require isolation (Ensure key is with supervisor)
checkpoint | Test circuits to ensure they are isolated
checkpoint | Area clear, tidy and accessible
checkpoint | Fit off all Lights
checkpoint | Fit off all Sensors and SET TIME TO MINIMUM
checkpoint | Fit off all EX/EMG’s
checkpoint | Label all EX/EMG’s as per plan number
checkpoint | Fit off all GPOs
checkpoint | Fit off of all isolators (signs, hand dryers, hws)
checkpoint | Ensure all fit off has been ticked off on plans once completed
checkpoint | Ensure area is left clean
checklist-flat | ITR. 12 Switchboard Commissioning
checkpoint | Prior To Energising All Personnel Involved To Be Inducted Into Energisation Procedure And All Steps Undertaken To Ensurecompliance With This Procedure
checkpoint | Place all required signage and barricading and have LV rescue kit on standby.
checkpoint | Refer To As Installed Drawings
checkpoint | Obtain Copy Of Switchboard Schedule And Schematic Drawings
checkpoint | Mark Up Any Additions Or Deletions Found Whilst Commissioing
checkpoint | Complete Visual Checks
checkpoint | Refer To Mandatory Testing From As/Nzs 3000:2018 8.3.3 Below
checkpoint | Complete Mandatory Tests Using Metrel Tester, Save And Log Results On Tester
checkpoint | Any Failed Results To Be Rectified Saved And Logged On Tester
checkpoint | Ensure Correct Opertation Of All Control/Equipment Installed In Switchboard
checkpoint | Ensure Vast Witness Test Has Been Completed
checkpoint | Ensure Escutcheons, Pole Fillers, Fixing Screws Are Reinstated
checkpoint | Ensure No Access To Live Parts
checkpoint | Complete Switchboard Schedules On Vast Template, Install And Fix To Allocated Postion In Switchboard
checkpoint | Download Test Results From Metrel Tester And Save To Project Folder
checkpoint | Complete Certificate Of Electrical Safety And Save To Project Folder
checklist | ITR No.02 Cutout of Ceilings & Walls
Label | Drawing Rev No.
checkpoint | Confirm sizes off all fittings prior to cut out
checkpoint | Cut out for all sensors, EX/EMG and light fittings
checkpoint | Consult supervisor before cutting a patch of is a mistake is made
checkpoint | Cut out items on joinery to the joinery plans
checkpoint | Cut out GPO's
checkpoint | Cut out bathrooms and other wet areas to relevent wet area plans
checkpoint | Ensure kitchen outlets are in correct position (where applicable)
checkpoint | Locate all cables
checkpoint | Install Fire Boxes and hit all 4 tabs in
checkpoint | Fire caulk ( if applicable )
checkpoint | For AV power and data, consult relevent AV plans and coordinate with AV contractor
checkpoint | FIT OFF ALL 413'S + QC'S + CEILING ROSES TO LIGHT FITTINGS THAT REQUIRE THEM
checklist | ITP No. 20 Decommission Temporary Power Board
checkpoint | Determine what the temporary board is controlling and confirm what action is required before board can be decommissioned.
label | De-commission form issued to builder, 48 hours notice to be given
checkpoint | Sign off builders checklist
checkpoint | Safety Committee Inspection
checkpoint | Final approval to be given by builder
checkpoint | Perform voltage test to ensure power supply has been isolated
checkpoint | Disconnect supply cables
checkpoint | Fire sealing of penetrations
checkpoint | Remove temporary board
checkpoint | Update temporary power board register
checklist | ITP No. 29 Installion of Electrical & Communication Pits
checkpoint | Inspect pits for any damage on arrival to site
checkpoint | Mark out pit locations and alignment/arrangement
checkpoint | Check finished heights of pits against civil drawings/finished floor height
checkpoint | Erect pedestrian barricading
checkpoint | Excavate ground around pits as required
checkpoint | Place bedding material as per pit installation requirements
checkpoint | Cut out pit entry as required
checkpoint | Install pits in ground (using correct lifting equipment)
checkpoint | Check finished heights of pits against civil drawings
checkpoint | Install relevant conduits
checkpoint | Backfill and reinstatement of ground
checkpoint | Check stabilised FCR backfill 200mm below proposed road level, compacted FCR above that
checklist | ITP No. 19 Installation of Temporary Power Board
Label | Drawing Rev No.
checkpoint | Area accessible & ready
checkpoint | Locate & fix into position, bolt temporary board down with at least 2 fixings
checkpoint | Install submains cabling as appropriate eg: glands/tray/duct
checkpoint | Install lugs and terminate
checkpoint | Any cables not terminated prior to energisation must be removed from cubicle at origin and have ends covered in heat shrink. At destination cables must be covered in heat shrink and be contrained in a junction box
checkpoint | Clearly identify services
checkpoint | When ready to energise proceed in accordance with energisation procedure
checkpoint | Energise & record results on Vast RCD test sheet
checkpoint | Install A3 laminated sign on face of temp board with floor plan and where the board is fed from
checkpoint | Update Temporary Power Board register & save to project folder/design control/temp const.
label | Lodge non prescribed certificate of electrical safety
label | RCBO'S must be fully tested initially and then tested every month with results recorded and c/b’s labelled
checklist | ITP No. 14 Construction Wiring, Installation, Test and Tag & Removal
Label | Drawing Rev No.
checkpoint | Area accessible & ready
checkpoint | Refer to temporary wiring setout plan
label | CABLING MUST BE SUPPORTED AND PROTECTED FROM DAMAGE. CONSTRUCTION WIRING TAPE MUST BE FITTED AT EVERY 5 METRES. TEMPORARY WIRING MUST NOT BE INSTALLED WITH PERMANENT CABLING
checkpoint | Fit off plug base and or powerpoint/isolator
checkpoint | Install light fitting, exit/emg, power
checkpoint | Terminate cable to temp board. Ensure temp board is isolated! Test Test Test
checkpoint | Test & commission
label | Lodge non prescribed certificate of electrical safety
checklist | ITR No.09 In Slab Conduits
Label | Drawing Rev No.
checkpoint | Determine origin and destination
checkpoint | Check clear of other services, penetrations etc
checkpoint | Check cable size to verify conduit size
checkpoint | Check if expansion joints are required
checkpoint | Mark out positions of junction boxes and penerations whee necessary
checkpoint | Install bar chairs where necessary
checkpoint | Install junction boxes and penetrations where necessary
checkpoint | Install junction boxes and glue conduits
checkpoint | Tie conduits securely at all joints and midpoints
checkpoint | Ensure all conduits are 50mm above deck
checkpoint | Ensure floor boxes and conduits into the FB are secured and photos of each one are uploaded
checkpoint | Mark up drawing of conduit runs
checkpoint | Observe conduits when concrete is being poured
checklist | ITR 33. Installing Underground Services (Electrical)
checkpoint | Inspect conduit material to check that it meets material specifications
checkpoint | Check conduit alignment as per plans
checkpoint | Set out marked, and all services located
checkpoint | Erect pedetrian barricading as per plan
checkpoint | Check excavation depth against proposed road level
checkpoint | Excavate to the trench as per plan
checkpoint | Place specified bedding material in trench
checkpoint | Placement of conduit of specified size in accordance with specifications/drawings
checkpoint | Install service hangers around conduits at every 500mm intervals
checkpoint | Backfill over conduit and install ORANGE under ground tape
checkpoint | Install cover slabs over conduit
checklist | ITR 33C. Installing Underground Services (Comms)
checkpoint | Inspect conduit material to check that it meets material specifications
checkpoint | Check conduit alignment as per plans
checkpoint | Set out marked, and all services located
checkpoint | Erect pedetrian barricading as per plan
checkpoint | Check excavation depth against proposed road level
checkpoint | Excavate to the trench as per plan
checkpoint | Place specified bedding material in trench
checkpoint | Placement of conduit of specified size in accordance with specifications/drawings
checkpoint | Install service hangers around conduits at every 500mm intervals
checkpoint | Backfill over conduit and install WHITE underground tape
checklist | ITR No.14 Mains and Sub Mains
Label | Drawing Rev No.
checkpoint | Measure cable runs with appropriate accurate measuring instrument eg: tape measure, wheel, rope in conduit
checkpoint | Confirm length of cable
checkpoint | Install cable in applicable method eg: cable stands, electric winch, pulleys etc
label | Any cable not terminated immediately must have the end taped covering the bare copper
checkpoint | Trefoil (refer to details on back for all options) cables and tie cables to support system
checkpoint | Check cable requirements for cable identification and install
checklist | ITP No.07 Structured Cabling Rough In
Label | Drawing Rev No.
label | REFER APPROVED DRAWINGS AND SPECIFICATION.
checkpoint | INSTALL CABLE SUPPORT OR CONDUIT WHERE REQUIRED.
checkpoint | VERIFY CORRECT CABLE TYPE.
checkpoint | REFER TO APPROVED DRAWINGS FOR CABLE NUMBERING SEQUENCE RELEVANT TO FINAL FIT OFF SEQUENCE & RECORD
checkpoint | INSTALL CABLE WITHIN OR ON CABLE SUPPORT SYSTEMS MAINTAINING MIN SEGREGATIONS, ENSURE VELCRO CABLE TIES ARE USED AS PER SPEC
checkpoint | FORM CABLES INTO RELEVANT FIT-OFF GROUPS AT THE CABINET END.
checklist | ITR No. 18 Light and Power Fit Off
label | Bakelite & Power
checkpoint | CHECK DRAWINGS FOR QUANTITY, BRAND TYPE AND COLOUR
checkpoint | WET AREAS to be above 300 from FFL- UNDER 40L SINK to be 150mm/400mm rule- OVER 40L SINK to be 500mm/1000mm rule
checkpoint | FIT OFF AND FIX SWITCHES WITH NO MORE THAN 100mm SINGLE INSULATION BEHIND WALL
checkpoint | FIT OFF AND FIX GPO’S WITH NO MORE THAN 100mm SINGLE INSULATION BEHIND WALL
checkpoint | ALL METAL STUDS ARE EARTHED TO THE NEAREST GPO
checkpoint | FIT OFF FINAL APPLIANCES WITH PHOTOS
checkpoint | COVER PLATES (IF REQUIRED)
label | Light Fittings
checkpoint | DELIVERY CHECK FOR DAMAGE AND CORRECT QUANTITIES
checkpoint | PLUG IN OR FIT OFF LIGHT / PLUG BASE
checkpoint | INSTALL LIGHT FITTING
checkpoint | INSTALL LAMPS AND DIFFUSER
checkpoint | CLEAN FITTING, LAMP DIFFUSER
checklist | ITR No. 16 Switchboard Installation and Terminate Submains
checkpoint | DELIVERY CHECK FOR DAMAGE, PAINT FINISH, DIMENSIONS AND DOORS AGAINST APPROVED SHOP DRAWING
checkpoint | LOCATE & FIX INTO POSITION
checkpoint | INSTALL SUBMAINS CABLING AS APPROPRIATE EG. GLANDS, TRAY, DUCT
checkpoint | INSTALL LUGS AND TERMINATE ONCE INSULATION RESISTANCE AND POLARITY TESTS HAVE BEEN CONDUCTED
checkpoint | ANY CABLES NOT TERMINATED PRIOR TO ENERGISATION MUST BE REMOVED FROM CUBICLE AT ORIGIN AND HAVE ENDS COVERED IN HEATSHRINK. AT DESTINATION CABLES MUST BE COVERED IN HEATSHRINK AND BE CONTAINED IN A JUNCTION BOX
checkpoint | CLEAN & VACUUM
checkpoint | ORGANISE INPECTION BY INSPECTOR. LODGE PRESCRIBED / NON PRESCRIBED (AS APPLICABLE) CERTIFICATE OF ELECTRICAL SAFETY (IF REQUIRED).
checkpoint | CLEARLY IDENTIFY SERVICES
checkpoint | WHEN READY TO ENERGISE PROCEED IN ACCORDANCE WITH ENERGISATION PROCEDURE
checkpoint | ENERGIZE & RECORD RESULTS
checkpoint | INSTALL SUB CIRCUIT CABLING IN ACCORDANCE WITH DB SCHEDULE AND TERMINATE. if circuit not complete at the other end, it must not be terminated BUT PLACED IN A JUNCTION BOX AT FIELD END AND IN CONNECTORS AT dISTRIBUTION BOARD END.
checkpoint | CLEAN & VACUUM
checkpoint | RECORD RELEVANT INFORMATION AND ANY CHANGES ON DB SCHEDULE. AND RETURN TO ADMINISTRATOR/OFFICE FOR COMMISSIONING TEAM
checklist | ITP No. 13 SUB-CIRCUIT CABLING FIT OFF
Label | Drawing Rev No.
checkpoint | TEST & ENSURE SUB CIRCUIT CABLING IS NOT LIVE PRIOR TO FIT OFF
checkpoint | TERMINATE CABLE TO OUTLET OR PLUG BASE, CHECK CORRECT CONNECTIONS AND FIX TO SURFACE, IF CIRCUIT CAN NOT BE FULLY TERMINATED A JUNCTION BOX MUST BE INSTALLED WHERE REQUIRED
checkpoint | CLEAN AREA AS REQUIRED
checkpoint | RECORD ANY RELEVANT INFORMATION ON DRAWINGS.
checklist | ITP No. 16 EXIT & EMERGENCY INSTALLATION & TESTING
Label | Drawing Rev No.
checkpoint | DELIVERY CHECK FOR DAMAGE AND CORRECT QUANTITIES
checkpoint | COORDINATE LOCATIONS WITH OTHER SERVICES
checkpoint | PLUG IN OR FIT OFF LIGHT, FIT OFF DATA CABLE IF REQUIRED
checkpoint | INSTALL LAMP & DIFFUSER AND CLEAN FITTING
checkpoint | INSTALL EMERGENCY BARCODE TO FITTING AND TO DRAWINGS (IF REQUIRED)- UP LOAD PHOTO OF PLAN WITH LABELS
checkpoint | NUMBER FITTINGS AS PER VAST SHOP DRAWINGS.
checkpoint | UPDATE ANY CHANGES FOR AS BUILTS
checklist | ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
Label | Drawing Rev No.
checkpoint | REFER TO INSTALLED DRAWINGS
checkpoint | Test terminations using COPPER STRUCTURED CABLING tester AND LOG RESULTS
checkpoint | RECTIFY ANY FAILED RESULTS, RE-TEST AND LOG
checkpoint | LABEL FRAMES AND PATCH PANELS
checkpoint | COMPLETE PATCH PANEL SCHEDULE
checkpoint | DOWNLOAD RESULTS FROM TESTER TO PROJECT FOLDER
checklist | ITP No. 08 STRUCTURED CABLING FIT OFF
Label | Drawing Rev No.
checkpoint | VISUAL CHECK ENSURING CABLE TO BE FITTED OFF IN CORRECT POSITION.
checkpoint | SELECTION OF CORRECT TOOL TO BE USED FOR TERMINATION TYPE.
checkpoint | ENSURE CABLES ARE STRIPPED NO MORE THAN THE SPECIFIED DISTANCE. CHECK TERMINATIONS AT COMPLETION FOR COLOUR CODE AND SEQUENCE.
checkpoint | ATTACH WRAP AROUND LABEL TO CABLE NO MORE THAN 60MM FROM THE JACK. ENSURING CORRECT NUMBER SEQUENCE.
checkpoint | DRESS CABLES TO FINAL LOCATION. ENSURE VELCRO STRAPS FOR CAT 6 CABLING
checkpoint | INSTALL JACK INTO WORKSTATION OR WALL OUTLET.
checkpoint | INSTALL PATCH PANEL INTO CABINET LOOM CABLES TO THE BACK OF THE PATCH PANEL. TIE INTO POSITION USING VELCRO STRIP AND/OR CABLE TIES SUPPLIED.
checkpoint | PATCH OUTLETS TO HARDWARE DEVICES WHERE APPLICABLE AND CHECK FOR CORRECT OPERATION.
checkpoint | LABEL OUTLET ENSURING CORRECT NUMBER SEQUENCE
checkpoint | COMPLETE CERTIFICATION AS REQUIRED
checklist | ITR No. 34 Installing Light Pole Cages
checkpoint | INSPECT CAGES FOR ANY DAMAGE PROIR TO INSTALLATION
checkpoint | SET OUT LIGHT POLE LOCATION, ALIGNMENT AND HEIGHT AS SPECIFIED
checkpoint | ERECT PEDESTRIAN BARRICADING AS PER PLAN
checkpoint | EXCAVATE AS PER PLAN
checkpoint | PLACE SPECIFIED BEDDING MATERIAL AS PER REQUIREMENT
checkpoint | INSTALL LIGHT POLE CAGES AND CONDUITS AS REQUIRED
checkpoint | RE-CHECK FINSHED HEIGHT AS PER CIVIL DRAWINGS
checkpoint | POUR CONCRETE FOOTING WITH SPECIFIED MPA
checkpoint | CLEAN UP AND BARRICADE WORK AREA
checklist | ITR No.35 Installing Underground Pits
checkpoint | INSPECT PITS FOR ANY DAMAGE PROIR TO INSTALLATION
checkpoint | SET OUT PIT LOCATION, ALIGNMENT AND HEIGHT AS SPECIFIED
checkpoint | ERECT PEDESTRIAN BARRICADING AS PER PLAN
checkpoint | EXCAVATE AS PER PLAN
checkpoint | PLACE SPECIFIED BEDDING MATERIAL AS PER REQUIREMENT
checkpoint | INSTALL PIT AND CONDUITS AS REQUIRED
checkpoint | RE-CHECK FINSHED HEIGHT AS PER CIVIL DRAWINGS
checkpoint | BACKFILL AND REINSTATE GROUND AS REQUIRED
checklist | ITR No. 10 Cable Tray Installation
Label | Drawing Rev No.
checkpoint | CO-ORDINATE WITH OTHER SERVICES (CHECK FOR ANY CLASHES)
checkpoint | CONFIRM SIZE OF CABLE TRAY
checkpoint | INSTALL FIXINGS AND SUPPORTS AS NEEDED
checkpoint | INSTALL CABLE TRAY
checkpoint | COMPLETE SKETCH/MARK UP DRAWING FOR FUTURE AS BUILTS
checklist | Documents
Label | Drawing Rev No.
checklist | ITR No.41 Field Commissioning
checkpoint | Energisation permit completed prior to energisation
checkpoint | Address site at prestart and inform of no access to area under commissioning.
checkpoint | Place all relevent signage and barricading and have LV rescue kit on standby.
checkpoint | Visual check of DB serviced areas
checkpoint | Dead Testing
checkpoint | Live Testing
checkpoint | Report any issues to supervisor and generate plan to rectify (if any)
checkpoint | Perform a 2 hour test on all exit and emergency lighting (allow time for initial charging of batteries)
checklist | ITP No. 43 Lighting Control Rough In
Label | Drawing Rev No.
checkpoint | Area clear, tidy and accessible
checkpoint | Plan lighting control route in conjunction with supervisor.
checkpoint | Rough in lighting control cable to all sensors and switches.
checkpoint | All lighting control must be roughed in point to point, daisy chain style (no star points, two cables at each point only).
checkpoint | Lighting control route must be drawn clearly and precisely on dedicated plan, if there is a change or revision, a new plan must be created and superseded written on old plan.
checkpoint | Upload lighting control plan to Conqa, use this spot as a place to upload any and all plan/revision of this drawing.
checkpoint | Rough in of all booster cables applicable to the lighting control system (1.5mm2 twin active)
checkpoint | Ensure all cables are clearly labled and are to the appropriate length.
checkpoint | Ensure area is left clean
checklist | ITR No. 44 Lighting Control Fit off
Label | Drawing Rev No.
checkpoint | Area clear, tidy and accessible
checkpoint | Dediacte one person to be in charge of lighting control fitoff.
checkpoint | Always use the correct tools to fitoff the lighting control equiptment
checkpoint | Fitoff all sensors
checkpoint | Fit off all untumbra switches
checkpoint | Stick barcode of sensor/switch onto the designated plan in the location of the sensor/switch
checkpoint | Make sure all installed items are clean and undamaged.
checklist | ITR No. 45 Lighting Control Commissioning
Label | Drawing Rev No.
Label | Before lighting control programmer
checkpoint | Area clear, tidy and accessible
checkpoint | Complete testing and commissioning of general light and power.
checkpoint | Once lighting commissioning is complete, assess all sensors light up red upon registering movement.
checkpoint | Ensure all switches are illuminated.
checkpoint | Put Dali universe in flash mode, all lights on that universe should be flashing.
checkpoint | Address any issues
Label | With lighting control programmer
checkpoint | Explain which fittings are to be programmed and what they should be programmed to do
checkpoint | Walk around with programmer, show him the DB feeding the lighting and control modules.
checkpoint | Be on standby for any rectification works needed brought up by the programmer.
checkpoint | Visually see all working as intended before he leaves site.

## ETAF
Folder Structure |  |  |  |  | Checklists
Site QA
Site Induction
Undergrounds
|  | ETAF | Pit Installation |  | ITP No. 29 Installion of Electrical & Communication Pits
|  |  | Electrical Conduit Install |  | ITR 33. Installing Underground Services (Electrical)
|  |  | Communication Conduit Install |  | ITR 33C. Installing Underground Services (Comms)
Temp Boards
|  | ETAF | GROUND FLOOR |  | ITP No. 19 Installation of Temporary Power Board
|  |  | LEVEL 1 |  | ITP No. 19 Installation of Temporary Power Board
Temp Lighting
|  | ETAF | GROUND FLOOR |  | ITP No. 14 Construction Wiring, Installation, Test and Tag & Removal
|  |  | LEVEL 1 |  | ITP No. 14 Construction Wiring, Installation, Test and Tag & Removal
Mains & Sub Mains
|  | ETAF | MSB |  | ITR No.14 Mains and Sub Mains
|  |  | DB-TAF-EGF |  | ITR No.14 Mains and Sub Mains
|  |  | DB-TAF-WGF |  | ITR No.14 Mains and Sub Mains
|  |  | DB-TAF-EL1 |  | ITR No.14 Mains and Sub Mains
|  |  | DB-TAF-CAFÉ |  | ITR No.14 Mains and Sub Mains
|  |  | MSSB-01 |  | ITR No.14 Mains and Sub Mains
|  |  | MSSB-02 |  | ITR No.14 Mains and Sub Mains
|  |  | DB- LIFT EAST |  | ITR No.14 Mains and Sub Mains
|  |  | DB-LIFT WEST |  | ITR No.14 Mains and Sub Mains
|  |  | DB-TAF-POOL |  | ITR No.14 Mains and Sub Mains
|  |  | DB-TAF-SOLAR |  | ITR No.14 Mains and Sub Mains
Inslab Conduits
|  | ETAF | GROUND EAST |  | ITR No.09 In Slab Conduits
|  |  | GROUND WEST |  | ITR No.09 In Slab Conduits
|  |  | LEVEL 1 EAST |  | ITR No.09 In Slab Conduits
|  |  | LEVEL 1 WEST |  | ITR No.09 In Slab Conduits
Switchboards
|  | ETAF | MSB |  | ITR No. 16 Switchboard Installation and Terminate Submains
|  |  | DB-TAF-EGF |  | ITR No. 16 Switchboard Installation and Terminate Submains
|  |  | DB-TAF-WGF |  | ITR No. 16 Switchboard Installation and Terminate Submains
|  |  | DB-TAF-EL1 |  | ITR No. 16 Switchboard Installation and Terminate Submains
|  |  | DB-TAF-CAFÉ |  | ITR No. 16 Switchboard Installation and Terminate Submains
|  |  | DB- LIFT EAST |  | ITR No. 16 Switchboard Installation and Terminate Submains
|  |  | DB-LIFT WEST |  | ITR No. 16 Switchboard Installation and Terminate Submains
|  |  | DB-TAF-POOL |  | ITR No. 16 Switchboard Installation and Terminate Submains
|  |  | DB-TAF-SOLAR |  | ITR No. 16 Switchboard Installation and Terminate Submains
|  |  | MSSB-01 |  | ITR No. 16 Switchboard Installation and Terminate Submains
|  |  | MSSB-02 |  | ITR No. 16 Switchboard Installation and Terminate Submains
Rough in
|  | ETAF | GROUND FLOOR- ZONE A- WEST | COMMON CORRIDOR | ITR No. 10 Cable Tray Installation
ITR No.0 5 Rough in
ITP No.07 Structured Cabling Rough In
ITP No. 43 Lighting Control Rough In
|  |  |  | POOL CORRIDOR | ITR No. 10 Cable Tray Installation
ITR No.0 5 Rough in
ITP No.07 Structured Cabling Rough In
ITP No. 43 Lighting Control Rough In
|  |  |  | OFFICE 2 | ITR No.0 5 Rough in
ITP No.07 Structured Cabling Rough In
ITP No. 43 Lighting Control Rough In
|  |  |  | OFFICE 3 | ITR No.0 5 Rough in
ITP No.07 Structured Cabling Rough In
ITP No. 43 Lighting Control Rough In
|  |  |  | PHYSIO | ITR No.0 5 Rough in
ITP No.07 Structured Cabling Rough In
ITP No. 43 Lighting Control Rough In
|  |  |  | CONSULT ROOM 1 | ITR No.0 5 Rough in
ITP No.07 Structured Cabling Rough In
ITP No. 43 Lighting Control Rough In
|  |  |  | CONSULT ROOM 2 | ITR No.0 5 Rough in
ITP No.07 Structured Cabling Rough In
ITP No. 43 Lighting Control Rough In
|  |  |  | MEDICAL ROOM | ITR No.0 5 Rough in
ITP No.07 Structured Cabling Rough In
ITP No. 43 Lighting Control Rough In
|  |  |  | CARDIO/WEIGHTS/GYM | ITR No.0 5 Rough in
ITP No.07 Structured Cabling Rough In
ITP No. 43 Lighting Control Rough In
|  |  |  | PROPERTY | ITR No.0 5 Rough in
ITP No.07 Structured Cabling Rough In
ITP No. 43 Lighting Control Rough In
|  |  |  | LOADING | ITR No.0 5 Rough in
ITP No.07 Structured Cabling Rough In
ITP No. 43 Lighting Control Rough In
|  |  |  | STAIR 2 | ITR No.0 5 Rough in
ITP No. 43 Lighting Control Rough In
|  |  |  | POOL CORRIDOR | ITR No.0 5 Rough in
ITP No.07 Structured Cabling Rough In
ITP No. 43 Lighting Control Rough In
|  |  |  | POOL CHANGE ROOM 1 | ITR No.0 5 Rough in
ITP No.07 Structured Cabling Rough In
ITP No. 43 Lighting Control Rough In
|  |  |  | POOL CHANGE ROOM 2 | ITR No.0 5 Rough in
ITP No.07 Structured Cabling Rough In
ITP No. 43 Lighting Control Rough In
|  |  |  | POOL CHANGE ROOM 3 | ITR No.0 5 Rough in
ITP No.07 Structured Cabling Rough In
ITP No. 43 Lighting Control Rough In
|  |  |  | POOL CHANGE ROOM 4 | ITR No.0 5 Rough in
ITP No.07 Structured Cabling Rough In
ITP No. 43 Lighting Control Rough In
|  |  |  | POOL ACC CH 1 | ITR No.0 5 Rough in
ITP No.07 Structured Cabling Rough In
ITP No. 43 Lighting Control Rough In
|  |  |  | POOL STORE | ITR No.0 5 Rough in
ITP No.07 Structured Cabling Rough In
ITP No. 43 Lighting Control Rough In
|  |  |  | POOL PLANT | ITR No.0 5 Rough in
ITP No.07 Structured Cabling Rough In
ITP No. 43 Lighting Control Rough In
|  |  |  | MUD ROOM | ITR No.0 5 Rough in
ITP No.07 Structured Cabling Rough In
ITP No. 43 Lighting Control Rough In
|  |  |  | EXTERNAL | ITR No.0 5 Rough in
ITP No.07 Structured Cabling Rough In
ITP No. 43 Lighting Control Rough In
Rough in
|  | ETAF | GROUND FLOOR- ZONE B- EAST | COMMON CORRIDOR | ITR No. 10 Cable Tray Installation
ITR No.0 5 Rough in
ITP No.07 Structured Cabling Rough In
ITP No. 43 Lighting Control Rough In
|  |  |  | HIGH PERFORMANCE COACH | ITR No.0 5 Rough in
ITP No.07 Structured Cabling Rough In
ITP No. 43 Lighting Control Rough In
|  |  |  | OFFICE 4 | ITR No.0 5 Rough in
ITP No.07 Structured Cabling Rough In
ITP No. 43 Lighting Control Rough In
|  |  |  | OFFICE 5 | ITR No.0 5 Rough in
ITP No.07 Structured Cabling Rough In
ITP No. 43 Lighting Control Rough In
|  |  |  | PLAYER PERFORMANCE SPACE | ITR No.0 5 Rough in
ITP No.07 Structured Cabling Rough In
ITP No. 43 Lighting Control Rough In
|  |  |  | BREAK OUT AREA 2 | ITR No.0 5 Rough in
ITP No.07 Structured Cabling Rough In
ITP No. 43 Lighting Control Rough In
|  |  |  | COACHES 1 | ITR No.0 5 Rough in
ITP No.07 Structured Cabling Rough In
ITP No. 43 Lighting Control Rough In
|  |  |  | COACHES 2 | ITR No.0 5 Rough in
ITP No.07 Structured Cabling Rough In
ITP No. 43 Lighting Control Rough In
|  |  |  | OFFICE 1 | ITR No.0 5 Rough in
ITP No.07 Structured Cabling Rough In
ITP No. 43 Lighting Control Rough In
|  |  |  | WAR ROOM | ITR No.0 5 Rough in
ITP No.07 Structured Cabling Rough In
ITP No. 43 Lighting Control Rough In
|  |  |  | PLAYERS & STAFF AREA | ITR No.0 5 Rough in
ITP No.07 Structured Cabling Rough In
ITP No. 43 Lighting Control Rough In
|  |  |  | SERVERY | ITR No.0 5 Rough in
ITP No.07 Structured Cabling Rough In
ITP No. 43 Lighting Control Rough In
|  |  |  | KITCHEN | ITR No.0 5 Rough in
ITP No.07 Structured Cabling Rough In
ITP No. 43 Lighting Control Rough In
|  |  |  | FOCUS ROOM | ITR No.0 5 Rough in
ITP No.07 Structured Cabling Rough In
ITP No. 43 Lighting Control Rough In
|  |  |  | PSYCH ROOM | ITR No.0 5 Rough in
ITP No.07 Structured Cabling Rough In
ITP No. 43 Lighting Control Rough In
|  |  |  | AFLW OFFICE | ITR No.0 5 Rough in
ITP No.07 Structured Cabling Rough In
ITP No. 43 Lighting Control Rough In
|  |  |  | OPEN WORK SPACE | ITR No.0 5 Rough in
ITP No.07 Structured Cabling Rough In
ITP No. 43 Lighting Control Rough In
|  |  |  | RECRUITMENT ROOM | ITR No.0 5 Rough in
ITP No.07 Structured Cabling Rough In
ITP No. 43 Lighting Control Rough In
|  |  |  | REC MTG | ITR No.0 5 Rough in
ITP No.07 Structured Cabling Rough In
ITP No. 43 Lighting Control Rough In
|  |  |  | LINE 1 | ITR No.0 5 Rough in
ITP No.07 Structured Cabling Rough In
ITP No. 43 Lighting Control Rough In
|  |  |  | LINE 2 | ITR No.0 5 Rough in
ITP No.07 Structured Cabling Rough In
ITP No. 43 Lighting Control Rough In
|  |  |  | LINE 3 | ITR No.0 5 Rough in
ITP No.07 Structured Cabling Rough In
ITP No. 43 Lighting Control Rough In
|  |  |  | ACC WC 3 | ITR No.0 5 Rough in
ITP No.07 Structured Cabling Rough In
ITP No. 43 Lighting Control Rough In
|  |  |  | STAFF MALE WC | ITR No.0 5 Rough in
ITP No.07 Structured Cabling Rough In
ITP No. 43 Lighting Control Rough In
|  |  |  | STAFF FEMALE WC | ITR No.0 5 Rough in
ITP No.07 Structured Cabling Rough In
ITP No. 43 Lighting Control Rough In
|  |  |  | AMB WC | ITR No.0 5 Rough in
ITP No.07 Structured Cabling Rough In
ITP No. 43 Lighting Control Rough In
|  |  |  | ACC WC1 | ITR No.0 5 Rough in
ITP No.07 Structured Cabling Rough In
ITP No. 43 Lighting Control Rough In
|  |  |  | ACC WC2 | ITR No.0 5 Rough in
ITP No.07 Structured Cabling Rough In
ITP No. 43 Lighting Control Rough In
|  |  |  | MERCH STORE | ITR No.0 5 Rough in
ITP No.07 Structured Cabling Rough In
ITP No. 43 Lighting Control Rough In
|  |  |  | RETAIL & MUSEUM | ITR No.0 5 Rough in
ITP No.07 Structured Cabling Rough In
ITP No. 43 Lighting Control Rough In
|  |  |  | HISTORY ROOM | ITR No.0 5 Rough in
ITP No.07 Structured Cabling Rough In
ITP No. 43 Lighting Control Rough In
|  |  |  | PAST PLAYER OFFICE | ITR No.0 5 Rough in
ITP No.07 Structured Cabling Rough In
ITP No. 43 Lighting Control Rough In
|  |  |  | PAST PLAYER BOARD ROOM | ITR No.0 5 Rough in
ITP No.07 Structured Cabling Rough In
ITP No. 43 Lighting Control Rough In
|  |  |  | UTILITIES | ITR No.0 5 Rough in
ITP No.07 Structured Cabling Rough In
ITP No. 43 Lighting Control Rough In
|  |  |  | THEATRE | ITR No.0 5 Rough in
ITP No.07 Structured Cabling Rough In
ITP No. 43 Lighting Control Rough In
|  |  |  | EXTERNAL | ITR No.0 5 Rough in
ITP No.07 Structured Cabling Rough In
ITP No. 43 Lighting Control Rough In
|  |  |  | FIP | ITR No.0 5 Rough in
Rough in
|  | ETAF | LEVEL 1- ZONE A- WEST | COMMON CORRIDOR | ITR No. 10 Cable Tray Installation
ITR No.0 5 Rough in
ITP No.07 Structured Cabling Rough In
ITP No. 43 Lighting Control Rough In
|  |  |  | POOL | ITR No.0 5 Rough in
|  |  |  | SLEEP ROOM | ITR No.0 5 Rough in
ITP No.07 Structured Cabling Rough In
ITP No. 43 Lighting Control Rough In
|  |  |  | YOGA ROOM | ITR No.0 5 Rough in
ITP No.07 Structured Cabling Rough In
ITP No. 43 Lighting Control Rough In
|  |  |  | STORAGE YOGA ROOM | ITR No.0 5 Rough in
ITP No.07 Structured Cabling Rough In
ITP No. 43 Lighting Control Rough In
|  |  |  | ACC CHANGE | ITR No.0 5 Rough in
ITP No.07 Structured Cabling Rough In
ITP No. 43 Lighting Control Rough In
|  |  |  | COMMS ROOM | ITR No.0 5 Rough in
ITP No.07 Structured Cabling Rough In
ITP No. 43 Lighting Control Rough In
|  |  |  | MASSAGE | ITR No.0 5 Rough in
ITP No.07 Structured Cabling Rough In
ITP No. 43 Lighting Control Rough In
|  |  |  | STORAGE MASSAGE | ITR No.0 5 Rough in
ITP No.07 Structured Cabling Rough In
ITP No. 43 Lighting Control Rough In
|  |  |  | MENS TOILETS | ITR No.0 5 Rough in
ITP No.07 Structured Cabling Rough In
ITP No. 43 Lighting Control Rough In
|  |  |  | MENS ENTRY & CHANGE ROOM | ITR No.0 5 Rough in
ITP No.07 Structured Cabling Rough In
ITP No. 43 Lighting Control Rough In
|  |  |  | WOMENS TOILET | ITR No.0 5 Rough in
ITP No.07 Structured Cabling Rough In
ITP No. 43 Lighting Control Rough In
|  |  |  | WOMENS ENTRY & CHANGE ROOM | ITR No.0 5 Rough in
ITP No.07 Structured Cabling Rough In
ITP No. 43 Lighting Control Rough In
|  |  |  | PLAYER RECREATION | ITR No.0 5 Rough in
ITP No.07 Structured Cabling Rough In
ITP No. 43 Lighting Control Rough In
|  |  |  | COURTYARD | ITR No.0 5 Rough in
ITP No.07 Structured Cabling Rough In
ITP No. 43 Lighting Control Rough In
|  |  |  | INDOOR TRAINING | ITR No.0 5 Rough in
ITP No.07 Structured Cabling Rough In
ITP No. 43 Lighting Control Rough In
|  |  |  | EXTERNAL CANOPY | ITR No.0 5 Rough in
ITP No.07 Structured Cabling Rough In
ITP No. 43 Lighting Control Rough In
Rough in
|  | ETAF | LEVEL 1- ZONE B- EAST | COMMON CORRIDOR | ITR No. 10 Cable Tray Installation
ITR No.0 5 Rough in
ITP No.07 Structured Cabling Rough In
ITP No. 43 Lighting Control Rough In
|  |  |  | PLAYER RECREATION | ITR No.0 5 Rough in
ITP No.07 Structured Cabling Rough In
ITP No. 43 Lighting Control Rough In
|  |  |  | PLAYER DEV | ITR No.0 5 Rough in
ITP No.07 Structured Cabling Rough In
ITP No. 43 Lighting Control Rough In
|  |  |  | FOCUS 4 | ITR No.0 5 Rough in
ITP No.07 Structured Cabling Rough In
ITP No. 43 Lighting Control Rough In
|  |  |  | PLAYER EDUCATION | ITR No.0 5 Rough in
ITP No.07 Structured Cabling Rough In
ITP No. 43 Lighting Control Rough In
|  |  |  | OFFICE 5 | ITR No.0 5 Rough in
ITP No.07 Structured Cabling Rough In
ITP No. 43 Lighting Control Rough In
|  |  |  | OFFICE 6 | ITR No.0 5 Rough in
ITP No.07 Structured Cabling Rough In
ITP No. 43 Lighting Control Rough In
|  |  |  | OFFICE 7 | ITR No.0 5 Rough in
ITP No.07 Structured Cabling Rough In
ITP No. 43 Lighting Control Rough In
|  |  |  | OPEN WORK SPACE | ITR No.0 5 Rough in
ITP No.07 Structured Cabling Rough In
ITP No. 43 Lighting Control Rough In
|  |  |  | KITCHEN | ITR No.0 5 Rough in
ITP No.07 Structured Cabling Rough In
ITP No. 43 Lighting Control Rough In
|  |  |  | BOARD ROOM | ITR No.0 5 Rough in
ITP No.07 Structured Cabling Rough In
ITP No. 43 Lighting Control Rough In
|  |  |  | MEETING 1 | ITR No.0 5 Rough in
ITP No.07 Structured Cabling Rough In
ITP No. 43 Lighting Control Rough In
|  |  |  | MEETING 2 | ITR No.0 5 Rough in
ITP No.07 Structured Cabling Rough In
ITP No. 43 Lighting Control Rough In
|  |  |  | BALCONY | ITR No.0 5 Rough in
ITP No.07 Structured Cabling Rough In
ITP No. 43 Lighting Control Rough In
|  |  |  | EXTERNAL CANOPY | ITR No.0 5 Rough in
ITP No.07 Structured Cabling Rough In
ITP No. 43 Lighting Control Rough In
|  |  |  | WAITING AREA | ITR No.0 5 Rough in
ITP No.07 Structured Cabling Rough In
ITP No. 43 Lighting Control Rough In
|  |  |  | STUDIO | ITR No.0 5 Rough in
ITP No.07 Structured Cabling Rough In
ITP No. 43 Lighting Control Rough In
|  |  |  | EXECUTIVE AREA | ITR No.0 5 Rough in
ITP No.07 Structured Cabling Rough In
ITP No. 43 Lighting Control Rough In
|  |  |  | BREAK OUT 4 & 5 | ITR No.0 5 Rough in
ITP No.07 Structured Cabling Rough In
ITP No. 43 Lighting Control Rough In
|  |  |  | UTILITIES | ITR No.0 5 Rough in
ITP No.07 Structured Cabling Rough In
ITP No. 43 Lighting Control Rough In
|  |  |  | COMMS ROOM | ITR No.0 5 Rough in
ITP No.07 Structured Cabling Rough In
ITP No. 43 Lighting Control Rough In
|  |  |  | STORE | ITR No.0 5 Rough in
ITP No.07 Structured Cabling Rough In
ITP No. 43 Lighting Control Rough In
|  |  |  | MEETING 3 | ITR No.0 5 Rough in
ITP No.07 Structured Cabling Rough In
ITP No. 43 Lighting Control Rough In
|  |  |  | FOCUS 1 | ITR No.0 5 Rough in
ITP No.07 Structured Cabling Rough In
ITP No. 43 Lighting Control Rough In
|  |  |  | FOCUS 2 | ITR No.0 5 Rough in
ITP No.07 Structured Cabling Rough In
ITP No. 43 Lighting Control Rough In
|  |  |  | FOCUS 3 | ITR No.0 5 Rough in
ITP No.07 Structured Cabling Rough In
ITP No. 43 Lighting Control Rough In
|  |  |  | OFFICE 8 | ITR No.0 5 Rough in
ITP No.07 Structured Cabling Rough In
ITP No. 43 Lighting Control Rough In
|  |  |  | MEMBERSHIP | ITR No.0 5 Rough in
ITP No.07 Structured Cabling Rough In
ITP No. 43 Lighting Control Rough In
|  |  |  | ACC 2 | ITR No.0 5 Rough in
ITP No.07 Structured Cabling Rough In
ITP No. 43 Lighting Control Rough In
|  |  |  | LOCKERS | ITR No.0 5 Rough in
ITP No.07 Structured Cabling Rough In
ITP No. 43 Lighting Control Rough In
|  |  |  | WELLNESS ROOM 1 | ITR No.0 5 Rough in
ITP No.07 Structured Cabling Rough In
ITP No. 43 Lighting Control Rough In
|  |  |  | WELLNESS ROOM 2 | ITR No.0 5 Rough in
ITP No.07 Structured Cabling Rough In
ITP No. 43 Lighting Control Rough In
|  |  |  | FEMALE TOILET | ITR No.0 5 Rough in
ITP No.07 Structured Cabling Rough In
ITP No. 43 Lighting Control Rough In
|  |  |  | MALE TOILET | ITR No.0 5 Rough in
ITP No.07 Structured Cabling Rough In
ITP No. 43 Lighting Control Rough In
|  |  |  | OFFICE 1 | ITR No.0 5 Rough in
ITP No.07 Structured Cabling Rough In
ITP No. 43 Lighting Control Rough In
|  |  |  | OFFICE 2 | ITR No.0 5 Rough in
ITP No.07 Structured Cabling Rough In
ITP No. 43 Lighting Control Rough In
|  |  |  | OFFICE 4 | ITR No.0 5 Rough in
ITP No.07 Structured Cabling Rough In
ITP No. 43 Lighting Control Rough In
|  |  |  | BREAK OUT AREA | ITR No.0 5 Rough in
ITP No.07 Structured Cabling Rough In
ITP No. 43 Lighting Control Rough In
Cut Out
|  | ETAF | GROUND FLOOR- ZONE A- WEST | COMMON CORRIDOR | ITR No.02 Cutout of Ceilings & Walls
|  |  |  | POOL CORRIDOR | ITR No.02 Cutout of Ceilings & Walls
|  |  |  | OFFICE 2 | ITR No.02 Cutout of Ceilings & Walls
|  |  |  | OFFICE 3 | ITR No.02 Cutout of Ceilings & Walls
|  |  |  | PHYSIO | ITR No.02 Cutout of Ceilings & Walls
|  |  |  | CONSULT ROOM 1 | ITR No.02 Cutout of Ceilings & Walls
|  |  |  | CONSULT ROOM 2 | ITR No.02 Cutout of Ceilings & Walls
|  |  |  | MEDICAL ROOM | ITR No.02 Cutout of Ceilings & Walls
|  |  |  | CARDIO/WEIGHTS/GYM | ITR No.02 Cutout of Ceilings & Walls
|  |  |  | PROPERTY | ITR No.02 Cutout of Ceilings & Walls
|  |  |  | LOADING | ITR No.02 Cutout of Ceilings & Walls
|  |  |  | STAIR 2 | ITR No.02 Cutout of Ceilings & Walls
|  |  |  | POOL CORRIDOR | ITR No.02 Cutout of Ceilings & Walls
|  |  |  | POOL CHANGE ROOM 1 | ITR No.02 Cutout of Ceilings & Walls
|  |  |  | POOL CHANGE ROOM 2 | ITR No.02 Cutout of Ceilings & Walls
|  |  |  | POOL CHANGE ROOM 3 | ITR No.02 Cutout of Ceilings & Walls
|  |  |  | POOL CHANGE ROOM 4 | ITR No.02 Cutout of Ceilings & Walls
|  |  |  | POOL ACC CH 1 | ITR No.02 Cutout of Ceilings & Walls
|  |  |  | POOL STORE | ITR No.02 Cutout of Ceilings & Walls
|  |  |  | POOL PLANT | ITR No.02 Cutout of Ceilings & Walls
|  |  |  | MUD ROOM | ITR No.02 Cutout of Ceilings & Walls
|  |  |  | EXTERNAL | ITR No.02 Cutout of Ceilings & Walls
Cut Out
|  | ETAF | GROUND FLOOR- ZONE B- EAST | COMMON CORRIDOR | ITR No.02 Cutout of Ceilings & Walls
|  |  |  | HIGH PERFORMANCE COACH | ITR No.02 Cutout of Ceilings & Walls
|  |  |  | OFFICE 4 | ITR No.02 Cutout of Ceilings & Walls
|  |  |  | OFFICE 5 | ITR No.02 Cutout of Ceilings & Walls
|  |  |  | PLAYER PERFORMANCE SPACE | ITR No.02 Cutout of Ceilings & Walls
|  |  |  | BREAK OUT AREA 2 | ITR No.02 Cutout of Ceilings & Walls
|  |  |  | COACHES 1 | ITR No.02 Cutout of Ceilings & Walls
|  |  |  | COACHES 2 | ITR No.02 Cutout of Ceilings & Walls
|  |  |  | OFFICE 1 | ITR No.02 Cutout of Ceilings & Walls
|  |  |  | WAR ROOM | ITR No.02 Cutout of Ceilings & Walls
|  |  |  | PLAYERS & STAFF AREA | ITR No.02 Cutout of Ceilings & Walls
|  |  |  | SERVERY | ITR No.02 Cutout of Ceilings & Walls
|  |  |  | KITCHEN | ITR No.02 Cutout of Ceilings & Walls
|  |  |  | FOCUS ROOM | ITR No.02 Cutout of Ceilings & Walls
|  |  |  | PSYCH ROOM | ITR No.02 Cutout of Ceilings & Walls
|  |  |  | AFLW OFFICE | ITR No.02 Cutout of Ceilings & Walls
|  |  |  | OPEN WORK SPACE | ITR No.02 Cutout of Ceilings & Walls
|  |  |  | RECRUITMENT ROOM | ITR No.02 Cutout of Ceilings & Walls
|  |  |  | REC MTG | ITR No.02 Cutout of Ceilings & Walls
|  |  |  | LINE 1 | ITR No.02 Cutout of Ceilings & Walls
|  |  |  | LINE 2 | ITR No.02 Cutout of Ceilings & Walls
|  |  |  | LINE 3 | ITR No.02 Cutout of Ceilings & Walls
|  |  |  | ACC WC 3 | ITR No.02 Cutout of Ceilings & Walls
|  |  |  | STAFF MALE WC | ITR No.02 Cutout of Ceilings & Walls
|  |  |  | STAFF FEMALE WC | ITR No.02 Cutout of Ceilings & Walls
|  |  |  | AMB WC | ITR No.02 Cutout of Ceilings & Walls
|  |  |  | ACC WC1 | ITR No.02 Cutout of Ceilings & Walls
|  |  |  | ACC WC2 | ITR No.02 Cutout of Ceilings & Walls
|  |  |  | MERCH STORE | ITR No.02 Cutout of Ceilings & Walls
|  |  |  | RETAIL & MUSEUM | ITR No.02 Cutout of Ceilings & Walls
|  |  |  | HISTORY ROOM | ITR No.02 Cutout of Ceilings & Walls
|  |  |  | PAST PLAYER OFFICE | ITR No.02 Cutout of Ceilings & Walls
|  |  |  | PAST PLAYER BOARD ROOM | ITR No.02 Cutout of Ceilings & Walls
|  |  |  | UTILITIES | ITR No.02 Cutout of Ceilings & Walls
|  |  |  | THEATRE | ITR No.02 Cutout of Ceilings & Walls
|  |  |  | EXTERNAL | ITR No.02 Cutout of Ceilings & Walls
|  |  |  | FIP | ITR No.02 Cutout of Ceilings & Walls
Cut Out
|  | ETAF | LEVEL 1- ZONE A- WEST | COMMON CORRIDOR | ITR No.02 Cutout of Ceilings & Walls
|  |  |  | POOL | ITR No.02 Cutout of Ceilings & Walls
|  |  |  | SLEEP ROOM | ITR No.02 Cutout of Ceilings & Walls
|  |  |  | YOGA ROOM | ITR No.02 Cutout of Ceilings & Walls
|  |  |  | STORAGE YOGA ROOM | ITR No.02 Cutout of Ceilings & Walls
|  |  |  | ACC CHANGE | ITR No.02 Cutout of Ceilings & Walls
|  |  |  | COMMS ROOM | ITR No.02 Cutout of Ceilings & Walls
|  |  |  | MASSAGE | ITR No.02 Cutout of Ceilings & Walls
|  |  |  | STORAGE MASSAGE | ITR No.02 Cutout of Ceilings & Walls
|  |  |  | MENS TOILETS | ITR No.02 Cutout of Ceilings & Walls
|  |  |  | MENS ENTRY & CHANGE ROOM | ITR No.02 Cutout of Ceilings & Walls
|  |  |  | WOMENS TOILET | ITR No.02 Cutout of Ceilings & Walls
|  |  |  | WOMENS ENTRY & CHANGE ROOM | ITR No.02 Cutout of Ceilings & Walls
|  |  |  | PLAYER RECREATION | ITR No.02 Cutout of Ceilings & Walls
|  |  |  | COURTYARD | ITR No.02 Cutout of Ceilings & Walls
|  |  |  | INDOOR TRAINING | ITR No.02 Cutout of Ceilings & Walls
|  |  |  | EXTERNAL CANOPY | ITR No.02 Cutout of Ceilings & Walls
Cut Out
|  | ETAF | LEVEL 1- ZONE B- EAST | COMMON CORRIDOR | ITR No.02 Cutout of Ceilings & Walls
|  |  |  | PLAYER RECREATION | ITR No.02 Cutout of Ceilings & Walls
|  |  |  | PLAYER DEV | ITR No.02 Cutout of Ceilings & Walls
|  |  |  | FOCUS 4 | ITR No.02 Cutout of Ceilings & Walls
|  |  |  | PLAYER EDUCATION | ITR No.02 Cutout of Ceilings & Walls
|  |  |  | OFFICE 5 | ITR No.02 Cutout of Ceilings & Walls
|  |  |  | OFFICE 6 | ITR No.02 Cutout of Ceilings & Walls
|  |  |  | OFFICE 7 | ITR No.02 Cutout of Ceilings & Walls
|  |  |  | OPEN WORK SPACE | ITR No.02 Cutout of Ceilings & Walls
|  |  |  | KITCHEN | ITR No.02 Cutout of Ceilings & Walls
|  |  |  | BOARD ROOM | ITR No.02 Cutout of Ceilings & Walls
|  |  |  | MEETING 1 | ITR No.02 Cutout of Ceilings & Walls
|  |  |  | MEETING 2 | ITR No.02 Cutout of Ceilings & Walls
|  |  |  | BALCONY | ITR No.02 Cutout of Ceilings & Walls
|  |  |  | EXTERNAL CANOPY | ITR No.02 Cutout of Ceilings & Walls
|  |  |  | WAITING AREA | ITR No.02 Cutout of Ceilings & Walls
|  |  |  | STUDIO | ITR No.02 Cutout of Ceilings & Walls
|  |  |  | EXECUTIVE AREA | ITR No.02 Cutout of Ceilings & Walls
|  |  |  | BREAK OUT 4 & 5 | ITR No.02 Cutout of Ceilings & Walls
|  |  |  | UTILITIES | ITR No.02 Cutout of Ceilings & Walls
|  |  |  | COMMS ROOM | ITR No.02 Cutout of Ceilings & Walls
|  |  |  | STORE | ITR No.02 Cutout of Ceilings & Walls
|  |  |  | MEETING 3 | ITR No.02 Cutout of Ceilings & Walls
|  |  |  | FOCUS 1 | ITR No.02 Cutout of Ceilings & Walls
|  |  |  | FOCUS 2 | ITR No.02 Cutout of Ceilings & Walls
|  |  |  | FOCUS 3 | ITR No.02 Cutout of Ceilings & Walls
|  |  |  | OFFICE 8 | ITR No.02 Cutout of Ceilings & Walls
|  |  |  | MEMBERSHIP | ITR No.02 Cutout of Ceilings & Walls
|  |  |  | ACC 2 | ITR No.02 Cutout of Ceilings & Walls
|  |  |  | LOCKERS | ITR No.02 Cutout of Ceilings & Walls
|  |  |  | WELLNESS ROOM 1 | ITR No.02 Cutout of Ceilings & Walls
|  |  |  | WELLNESS ROOM 2 | ITR No.02 Cutout of Ceilings & Walls
|  |  |  | FEMALE TOILET | ITR No.02 Cutout of Ceilings & Walls
|  |  |  | MALE TOILET | ITR No.02 Cutout of Ceilings & Walls
|  |  |  | OFFICE 1 | ITR No.02 Cutout of Ceilings & Walls
|  |  |  | OFFICE 2 | ITR No.02 Cutout of Ceilings & Walls
|  |  |  | OFFICE 4 | ITR No.02 Cutout of Ceilings & Walls
|  |  |  | BREAK OUT AREA | ITR No.02 Cutout of Ceilings & Walls
Fit Off
|  | ETAF | GROUND FLOOR- ZONE A- WEST | COMMON CORRIDOR | ITR No. 18 Light and Power Fit Off
ITP No. 08 STRUCTURED CABLING FIT OFF
ITR No. 44 Lighting Control Fit off
|  |  |  | POOL CORRIDOR | ITR No. 18 Light and Power Fit Off
ITP No. 08 STRUCTURED CABLING FIT OFF
ITR No. 44 Lighting Control Fit off
|  |  |  | OFFICE 2 | ITR No. 18 Light and Power Fit Off
ITP No. 08 STRUCTURED CABLING FIT OFF
ITR No. 44 Lighting Control Fit off
|  |  |  | OFFICE 3 | ITR No. 18 Light and Power Fit Off
ITP No. 08 STRUCTURED CABLING FIT OFF
ITR No. 44 Lighting Control Fit off
|  |  |  | PHYSIO | ITR No. 18 Light and Power Fit Off
ITP No. 08 STRUCTURED CABLING FIT OFF
ITR No. 44 Lighting Control Fit off
|  |  |  | CONSULT ROOM 1 | ITR No. 18 Light and Power Fit Off
ITP No. 08 STRUCTURED CABLING FIT OFF
ITR No. 44 Lighting Control Fit off
|  |  |  | CONSULT ROOM 2 | ITR No. 18 Light and Power Fit Off
ITP No. 08 STRUCTURED CABLING FIT OFF
ITR No. 44 Lighting Control Fit off
|  |  |  | MEDICAL ROOM | ITR No. 18 Light and Power Fit Off
ITP No. 08 STRUCTURED CABLING FIT OFF
ITR No. 44 Lighting Control Fit off
|  |  |  | CARDIO/WEIGHTS/GYM | ITR No. 18 Light and Power Fit Off
ITP No. 08 STRUCTURED CABLING FIT OFF
ITR No. 44 Lighting Control Fit off
|  |  |  | PROPERTY | ITR No. 18 Light and Power Fit Off
ITP No. 08 STRUCTURED CABLING FIT OFF
ITR No. 44 Lighting Control Fit off
|  |  |  | LOADING | ITR No. 18 Light and Power Fit Off
ITP No. 08 STRUCTURED CABLING FIT OFF
ITR No. 44 Lighting Control Fit off
|  |  |  | STAIR 2 | ITR No. 18 Light and Power Fit Off
ITR No. 44 Lighting Control Fit off
|  |  |  | POOL CORRIDOR | ITR No. 18 Light and Power Fit Off
ITP No. 08 STRUCTURED CABLING FIT OFF
ITR No. 44 Lighting Control Fit off
|  |  |  | POOL CHANGE ROOM 1 | ITR No. 18 Light and Power Fit Off
ITP No. 08 STRUCTURED CABLING FIT OFF
ITR No. 44 Lighting Control Fit off
|  |  |  | POOL CHANGE ROOM 2 | ITR No. 18 Light and Power Fit Off
ITP No. 08 STRUCTURED CABLING FIT OFF
ITR No. 44 Lighting Control Fit off
|  |  |  | POOL CHANGE ROOM 3 | ITR No. 18 Light and Power Fit Off
ITP No. 08 STRUCTURED CABLING FIT OFF
ITR No. 44 Lighting Control Fit off
|  |  |  | POOL CHANGE ROOM 4 | ITR No. 18 Light and Power Fit Off
ITP No. 08 STRUCTURED CABLING FIT OFF
ITR No. 44 Lighting Control Fit off
|  |  |  | POOL ACC CH 1 | ITR No. 18 Light and Power Fit Off
ITP No. 08 STRUCTURED CABLING FIT OFF
ITR No. 44 Lighting Control Fit off
|  |  |  | POOL STORE | ITR No. 18 Light and Power Fit Off
ITP No. 08 STRUCTURED CABLING FIT OFF
ITR No. 44 Lighting Control Fit off
|  |  |  | POOL PLANT | ITR No. 18 Light and Power Fit Off
ITP No. 08 STRUCTURED CABLING FIT OFF
ITR No. 44 Lighting Control Fit off
|  |  |  | MUD ROOM | ITR No. 18 Light and Power Fit Off
ITP No. 08 STRUCTURED CABLING FIT OFF
ITR No. 44 Lighting Control Fit off
|  |  |  | EXTERNAL | ITR No. 18 Light and Power Fit Off
ITP No. 08 STRUCTURED CABLING FIT OFF
ITR No. 44 Lighting Control Fit off
Fit Off
|  | ETAF | GROUND FLOOR- ZONE B- EAST | COMMON CORRIDOR | ITR No. 18 Light and Power Fit Off
ITP No. 08 STRUCTURED CABLING FIT OFF
ITR No. 44 Lighting Control Fit off
|  |  |  | HIGH PERFORMANCE COACH | ITR No. 18 Light and Power Fit Off
ITP No. 08 STRUCTURED CABLING FIT OFF
ITR No. 44 Lighting Control Fit off
|  |  |  | OFFICE 4 | ITR No. 18 Light and Power Fit Off
ITP No. 08 STRUCTURED CABLING FIT OFF
ITR No. 44 Lighting Control Fit off
|  |  |  | OFFICE 5 | ITR No. 18 Light and Power Fit Off
ITP No. 08 STRUCTURED CABLING FIT OFF
ITR No. 44 Lighting Control Fit off
|  |  |  | PLAYER PERFORMANCE SPACE | ITR No. 18 Light and Power Fit Off
ITP No. 08 STRUCTURED CABLING FIT OFF
ITR No. 44 Lighting Control Fit off
|  |  |  | BREAK OUT AREA 2 | ITR No. 18 Light and Power Fit Off
ITP No. 08 STRUCTURED CABLING FIT OFF
ITR No. 44 Lighting Control Fit off
|  |  |  | COACHES 1 | ITR No. 18 Light and Power Fit Off
ITP No. 08 STRUCTURED CABLING FIT OFF
ITR No. 44 Lighting Control Fit off
|  |  |  | COACHES 2 | ITR No. 18 Light and Power Fit Off
ITP No. 08 STRUCTURED CABLING FIT OFF
ITR No. 44 Lighting Control Fit off
|  |  |  | OFFICE 1 | ITR No. 18 Light and Power Fit Off
ITP No. 08 STRUCTURED CABLING FIT OFF
ITR No. 44 Lighting Control Fit off
|  |  |  | WAR ROOM | ITR No. 18 Light and Power Fit Off
ITP No. 08 STRUCTURED CABLING FIT OFF
ITR No. 44 Lighting Control Fit off
|  |  |  | PLAYERS & STAFF AREA | ITR No. 18 Light and Power Fit Off
ITP No. 08 STRUCTURED CABLING FIT OFF
ITR No. 44 Lighting Control Fit off
|  |  |  | SERVERY | ITR No. 18 Light and Power Fit Off
ITP No. 08 STRUCTURED CABLING FIT OFF
ITR No. 44 Lighting Control Fit off
|  |  |  | KITCHEN | ITR No. 18 Light and Power Fit Off
ITP No. 08 STRUCTURED CABLING FIT OFF
ITR No. 44 Lighting Control Fit off
|  |  |  | FOCUS ROOM | ITR No. 18 Light and Power Fit Off
ITP No. 08 STRUCTURED CABLING FIT OFF
ITR No. 44 Lighting Control Fit off
|  |  |  | PSYCH ROOM | ITR No. 18 Light and Power Fit Off
ITP No. 08 STRUCTURED CABLING FIT OFF
ITR No. 44 Lighting Control Fit off
|  |  |  | AFLW OFFICE | ITR No. 18 Light and Power Fit Off
ITP No. 08 STRUCTURED CABLING FIT OFF
ITR No. 44 Lighting Control Fit off
|  |  |  | OPEN WORK SPACE | ITR No. 18 Light and Power Fit Off
ITP No. 08 STRUCTURED CABLING FIT OFF
ITR No. 44 Lighting Control Fit off
|  |  |  | RECRUITMENT ROOM | ITR No. 18 Light and Power Fit Off
ITP No. 08 STRUCTURED CABLING FIT OFF
ITR No. 44 Lighting Control Fit off
|  |  |  | REC MTG | ITR No. 18 Light and Power Fit Off
ITP No. 08 STRUCTURED CABLING FIT OFF
ITR No. 44 Lighting Control Fit off
|  |  |  | LINE 1 | ITR No. 18 Light and Power Fit Off
ITP No. 08 STRUCTURED CABLING FIT OFF
ITR No. 44 Lighting Control Fit off
|  |  |  | LINE 2 | ITR No. 18 Light and Power Fit Off
ITP No. 08 STRUCTURED CABLING FIT OFF
ITR No. 44 Lighting Control Fit off
|  |  |  | LINE 3 | ITR No. 18 Light and Power Fit Off
ITP No. 08 STRUCTURED CABLING FIT OFF
ITR No. 44 Lighting Control Fit off
|  |  |  | ACC WC 3 | ITR No. 18 Light and Power Fit Off
ITP No. 08 STRUCTURED CABLING FIT OFF
ITR No. 44 Lighting Control Fit off
|  |  |  | STAFF MALE WC | ITR No. 18 Light and Power Fit Off
ITP No. 08 STRUCTURED CABLING FIT OFF
ITR No. 44 Lighting Control Fit off
|  |  |  | STAFF FEMALE WC | ITR No. 18 Light and Power Fit Off
ITP No. 08 STRUCTURED CABLING FIT OFF
ITR No. 44 Lighting Control Fit off
|  |  |  | AMB WC | ITR No. 18 Light and Power Fit Off
ITP No. 08 STRUCTURED CABLING FIT OFF
ITR No. 44 Lighting Control Fit off
|  |  |  | ACC WC1 | ITR No. 18 Light and Power Fit Off
ITP No. 08 STRUCTURED CABLING FIT OFF
ITR No. 44 Lighting Control Fit off
|  |  |  | ACC WC2 | ITR No. 18 Light and Power Fit Off
ITP No. 08 STRUCTURED CABLING FIT OFF
ITR No. 44 Lighting Control Fit off
|  |  |  | MERCH STORE | ITR No. 18 Light and Power Fit Off
ITP No. 08 STRUCTURED CABLING FIT OFF
ITR No. 44 Lighting Control Fit off
|  |  |  | RETAIL & MUSEUM | ITR No. 18 Light and Power Fit Off
ITP No. 08 STRUCTURED CABLING FIT OFF
ITR No. 44 Lighting Control Fit off
|  |  |  | HISTORY ROOM | ITR No. 18 Light and Power Fit Off
ITP No. 08 STRUCTURED CABLING FIT OFF
ITR No. 44 Lighting Control Fit off
|  |  |  | PAST PLAYER OFFICE | ITR No. 18 Light and Power Fit Off
ITP No. 08 STRUCTURED CABLING FIT OFF
ITR No. 44 Lighting Control Fit off
|  |  |  | PAST PLAYER BOARD ROOM | ITR No. 18 Light and Power Fit Off
ITP No. 08 STRUCTURED CABLING FIT OFF
ITR No. 44 Lighting Control Fit off
|  |  |  | UTILITIES | ITR No. 18 Light and Power Fit Off
ITP No. 08 STRUCTURED CABLING FIT OFF
ITR No. 44 Lighting Control Fit off
|  |  |  | THEATRE | ITR No. 18 Light and Power Fit Off
ITP No. 08 STRUCTURED CABLING FIT OFF
ITR No. 44 Lighting Control Fit off
|  |  |  | EXTERNAL | ITR No. 18 Light and Power Fit Off
ITP No. 08 STRUCTURED CABLING FIT OFF
ITR No. 44 Lighting Control Fit off
|  |  |  | FIP | ITR No. 18 Light and Power Fit Off
Fit Off
|  | ETAF | LEVEL 1- ZONE A- WEST | COMMON CORRIDOR | ITR No. 18 Light and Power Fit Off
ITP No. 08 STRUCTURED CABLING FIT OFF
ITR No. 44 Lighting Control Fit off
|  |  |  | POOL | ITR No. 18 Light and Power Fit Off
ITP No. 08 STRUCTURED CABLING FIT OFF
ITR No. 44 Lighting Control Fit off
|  |  |  | SLEEP ROOM | ITR No. 18 Light and Power Fit Off
ITP No. 08 STRUCTURED CABLING FIT OFF
ITR No. 44 Lighting Control Fit off
|  |  |  | YOGA ROOM | ITR No. 18 Light and Power Fit Off
ITP No. 08 STRUCTURED CABLING FIT OFF
ITR No. 44 Lighting Control Fit off
|  |  |  | STORAGE YOGA ROOM | ITR No. 18 Light and Power Fit Off
ITP No. 08 STRUCTURED CABLING FIT OFF
ITR No. 44 Lighting Control Fit off
|  |  |  | ACC CHANGE | ITR No. 18 Light and Power Fit Off
ITP No. 08 STRUCTURED CABLING FIT OFF
ITR No. 44 Lighting Control Fit off
|  |  |  | COMMS ROOM | ITR No. 18 Light and Power Fit Off
ITP No. 08 STRUCTURED CABLING FIT OFF
ITR No. 44 Lighting Control Fit off
|  |  |  | MASSAGE | ITR No. 18 Light and Power Fit Off
ITP No. 08 STRUCTURED CABLING FIT OFF
ITR No. 44 Lighting Control Fit off
|  |  |  | STORAGE MASSAGE | ITR No. 18 Light and Power Fit Off
ITP No. 08 STRUCTURED CABLING FIT OFF
ITR No. 44 Lighting Control Fit off
|  |  |  | MENS TOILETS | ITR No. 18 Light and Power Fit Off
ITP No. 08 STRUCTURED CABLING FIT OFF
ITR No. 44 Lighting Control Fit off
|  |  |  | MENS ENTRY & CHANGE ROOM | ITR No. 18 Light and Power Fit Off
ITP No. 08 STRUCTURED CABLING FIT OFF
ITR No. 44 Lighting Control Fit off
|  |  |  | WOMENS TOILET | ITR No. 18 Light and Power Fit Off
ITP No. 08 STRUCTURED CABLING FIT OFF
ITR No. 44 Lighting Control Fit off
|  |  |  | WOMENS ENTRY & CHANGE ROOM | ITR No. 18 Light and Power Fit Off
ITP No. 08 STRUCTURED CABLING FIT OFF
ITR No. 44 Lighting Control Fit off
|  |  |  | PLAYER RECREATION | ITR No. 18 Light and Power Fit Off
ITP No. 08 STRUCTURED CABLING FIT OFF
ITR No. 44 Lighting Control Fit off
|  |  |  | COURTYARD | ITR No. 18 Light and Power Fit Off
ITP No. 08 STRUCTURED CABLING FIT OFF
ITR No. 44 Lighting Control Fit off
|  |  |  | INDOOR TRAINING | ITR No. 18 Light and Power Fit Off
ITP No. 08 STRUCTURED CABLING FIT OFF
ITR No. 44 Lighting Control Fit off
|  |  |  | EXTERNAL CANOPY | ITR No. 18 Light and Power Fit Off
ITP No. 08 STRUCTURED CABLING FIT OFF
| Fit Off |  |  |  | ITR No. 44 Lighting Control Fit off
|  | ETAF | LEVEL 1- ZONE B- EAST
|  |  |  | COMMON CORRIDOR | ITR No. 18 Light and Power Fit Off
ITP No. 08 STRUCTURED CABLING FIT OFF
ITR No. 44 Lighting Control Fit off
|  |  |  | PLAYER RECREATION | ITR No. 18 Light and Power Fit Off
ITP No. 08 STRUCTURED CABLING FIT OFF
ITR No. 44 Lighting Control Fit off
|  |  |  | PLAYER DEV | ITR No. 18 Light and Power Fit Off
ITP No. 08 STRUCTURED CABLING FIT OFF
ITR No. 44 Lighting Control Fit off
|  |  |  | FOCUS 4 | ITR No. 18 Light and Power Fit Off
ITP No. 08 STRUCTURED CABLING FIT OFF
ITR No. 44 Lighting Control Fit off
|  |  |  | PLAYER EDUCATION | ITR No. 18 Light and Power Fit Off
ITP No. 08 STRUCTURED CABLING FIT OFF
ITR No. 44 Lighting Control Fit off
|  |  |  | OFFICE 5 | ITR No. 18 Light and Power Fit Off
ITP No. 08 STRUCTURED CABLING FIT OFF
ITR No. 44 Lighting Control Fit off
|  |  |  | OFFICE 6 | ITR No. 18 Light and Power Fit Off
ITP No. 08 STRUCTURED CABLING FIT OFF
ITR No. 44 Lighting Control Fit off
|  |  |  | OFFICE 7 | ITR No. 18 Light and Power Fit Off
ITP No. 08 STRUCTURED CABLING FIT OFF
ITR No. 44 Lighting Control Fit off
|  |  |  | OPEN WORK SPACE | ITR No. 18 Light and Power Fit Off
ITP No. 08 STRUCTURED CABLING FIT OFF
ITR No. 44 Lighting Control Fit off
|  |  |  | KITCHEN | ITR No. 18 Light and Power Fit Off
ITP No. 08 STRUCTURED CABLING FIT OFF
ITR No. 44 Lighting Control Fit off
|  |  |  | BOARD ROOM | ITR No. 18 Light and Power Fit Off
ITP No. 08 STRUCTURED CABLING FIT OFF
ITR No. 44 Lighting Control Fit off
|  |  |  | MEETING 1 | ITR No. 18 Light and Power Fit Off
ITP No. 08 STRUCTURED CABLING FIT OFF
ITR No. 44 Lighting Control Fit off
|  |  |  | MEETING 2 | ITR No. 18 Light and Power Fit Off
ITP No. 08 STRUCTURED CABLING FIT OFF
ITR No. 44 Lighting Control Fit off
|  |  |  | BALCONY | ITR No. 18 Light and Power Fit Off
ITP No. 08 STRUCTURED CABLING FIT OFF
ITR No. 44 Lighting Control Fit off
|  |  |  | EXTERNAL CANOPY | ITR No. 18 Light and Power Fit Off
ITP No. 08 STRUCTURED CABLING FIT OFF
ITR No. 44 Lighting Control Fit off
|  |  |  | WAITING AREA | ITR No. 18 Light and Power Fit Off
ITP No. 08 STRUCTURED CABLING FIT OFF
ITR No. 44 Lighting Control Fit off
|  |  |  | STUDIO | ITR No. 18 Light and Power Fit Off
ITP No. 08 STRUCTURED CABLING FIT OFF
ITR No. 44 Lighting Control Fit off
|  |  |  | EXECUTIVE AREA | ITR No. 18 Light and Power Fit Off
ITP No. 08 STRUCTURED CABLING FIT OFF
ITR No. 44 Lighting Control Fit off
|  |  |  | BREAK OUT 4 & 5 | ITR No. 18 Light and Power Fit Off
ITP No. 08 STRUCTURED CABLING FIT OFF
ITR No. 44 Lighting Control Fit off
|  |  |  | UTILITIES | ITR No. 18 Light and Power Fit Off
ITP No. 08 STRUCTURED CABLING FIT OFF
ITR No. 44 Lighting Control Fit off
|  |  |  | COMMS ROOM | ITR No. 18 Light and Power Fit Off
ITP No. 08 STRUCTURED CABLING FIT OFF
ITR No. 44 Lighting Control Fit off
|  |  |  | STORE | ITR No. 18 Light and Power Fit Off
ITP No. 08 STRUCTURED CABLING FIT OFF
ITR No. 44 Lighting Control Fit off
|  |  |  | MEETING 3 | ITR No. 18 Light and Power Fit Off
ITP No. 08 STRUCTURED CABLING FIT OFF
ITR No. 44 Lighting Control Fit off
|  |  |  | FOCUS 1 | ITR No. 18 Light and Power Fit Off
ITP No. 08 STRUCTURED CABLING FIT OFF
ITR No. 44 Lighting Control Fit off
|  |  |  | FOCUS 2 | ITR No. 18 Light and Power Fit Off
ITP No. 08 STRUCTURED CABLING FIT OFF
ITR No. 44 Lighting Control Fit off
|  |  |  | FOCUS 3 | ITR No. 18 Light and Power Fit Off
ITP No. 08 STRUCTURED CABLING FIT OFF
ITR No. 44 Lighting Control Fit off
|  |  |  | OFFICE 8 | ITR No. 18 Light and Power Fit Off
ITP No. 08 STRUCTURED CABLING FIT OFF
ITR No. 44 Lighting Control Fit off
|  |  |  | MEMBERSHIP | ITR No. 18 Light and Power Fit Off
ITP No. 08 STRUCTURED CABLING FIT OFF
ITR No. 44 Lighting Control Fit off
|  |  |  | ACC 2 | ITR No. 18 Light and Power Fit Off
ITP No. 08 STRUCTURED CABLING FIT OFF
ITR No. 44 Lighting Control Fit off
|  |  |  | LOCKERS | ITR No. 18 Light and Power Fit Off
ITP No. 08 STRUCTURED CABLING FIT OFF
ITR No. 44 Lighting Control Fit off
|  |  |  | WELLNESS ROOM 1 | ITR No. 18 Light and Power Fit Off
ITP No. 08 STRUCTURED CABLING FIT OFF
ITR No. 44 Lighting Control Fit off
|  |  |  | WELLNESS ROOM 2 | ITR No. 18 Light and Power Fit Off
ITP No. 08 STRUCTURED CABLING FIT OFF
ITR No. 44 Lighting Control Fit off
|  |  |  | FEMALE TOILET | ITR No. 18 Light and Power Fit Off
ITP No. 08 STRUCTURED CABLING FIT OFF
ITR No. 44 Lighting Control Fit off
|  |  |  | MALE TOILET | ITR No. 18 Light and Power Fit Off
ITP No. 08 STRUCTURED CABLING FIT OFF
ITR No. 44 Lighting Control Fit off
|  |  |  | OFFICE 1 | ITR No. 18 Light and Power Fit Off
ITP No. 08 STRUCTURED CABLING FIT OFF
ITR No. 44 Lighting Control Fit off
|  |  |  | OFFICE 2 | ITR No. 18 Light and Power Fit Off
ITP No. 08 STRUCTURED CABLING FIT OFF
ITR No. 44 Lighting Control Fit off
|  |  |  | OFFICE 4 | ITR No. 18 Light and Power Fit Off
ITP No. 08 STRUCTURED CABLING FIT OFF
ITR No. 44 Lighting Control Fit off
|  |  |  | BREAK OUT AREA | ITR No. 18 Light and Power Fit Off
ITP No. 08 STRUCTURED CABLING FIT OFF
ITR No. 44 Lighting Control Fit off
Commissioning
| MAINS | ETAF | MSB |  | ITR. 12 Switchboard Commissioning
|  |  | DB-TAF-EGF |  | ITR. 12 Switchboard Commissioning
|  |  | DB-TAF-WGF |  | ITR. 12 Switchboard Commissioning
|  |  | DB-TAF-EL1 |  | ITR. 12 Switchboard Commissioning
|  |  | DB-TAF-CAFÉ |  | ITR. 12 Switchboard Commissioning
|  |  | DB- LIFT EAST |  | ITR. 12 Switchboard Commissioning
|  |  | DB-LIFT WEST |  | ITR. 12 Switchboard Commissioning
|  |  | DB-TAF-POOL |  | ITR. 12 Switchboard Commissioning
|  |  | DB-TAF-SOLAR |  | ITR. 12 Switchboard Commissioning
|  |  | MSSB-01 |  | ITR. 12 Switchboard Commissioning
|  |  | MSSB-02 |  | ITR. 12 Switchboard Commissioning
FIELD
|  | ETAF | GROUND FLOOR- ZONE A- WEST | COMMON CORRIDOR | ITR No.41 Field Commissioning
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
|  |  |  | POOL CORRIDOR | ITR No.41 Field Commissioning
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
|  |  |  | OFFICE 2 | ITR No.41 Field Commissioning
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
|  |  |  | OFFICE 3 | ITR No.41 Field Commissioning
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
|  |  |  | PHYSIO | ITR No.41 Field Commissioning
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
|  |  |  | CONSULT ROOM 1 | ITR No.41 Field Commissioning
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
|  |  |  | CONSULT ROOM 2 | ITR No.41 Field Commissioning
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
|  |  |  | MEDICAL ROOM | ITR No.41 Field Commissioning
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
|  |  |  | CARDIO/WEIGHTS/GYM | ITR No.41 Field Commissioning
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
|  |  |  | PROPERTY | ITR No.41 Field Commissioning
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
|  |  |  | LOADING | ITR No.41 Field Commissioning
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
|  |  |  | STAIR 2 | ITR No.41 Field Commissioning
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
|  |  |  | POOL CORRIDOR | ITR No.41 Field Commissioning
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
|  |  |  | POOL CHANGE ROOM 1 | ITR No.41 Field Commissioning
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
|  |  |  | POOL CHANGE ROOM 2 | ITR No.41 Field Commissioning
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
|  |  |  | POOL CHANGE ROOM 3 | ITR No.41 Field Commissioning
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
|  |  |  | POOL CHANGE ROOM 4 | ITR No.41 Field Commissioning
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
|  |  |  | POOL ACC CH 1 | ITR No.41 Field Commissioning
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
|  |  |  | POOL STORE | ITR No.41 Field Commissioning
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
|  |  |  | POOL PLANT | ITR No.41 Field Commissioning
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
|  |  |  | MUD ROOM | ITR No.41 Field Commissioning
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
|  |  |  | EXTERNAL | ITR No.41 Field Commissioning
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
Commissioning
FIELD
|  | ETAF | GROUND FLOOR- ZONE B- EAST | COMMON CORRIDOR | ITR No.41 Field Commissioning
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
|  |  |  | HIGH PERFORMANCE COACH | ITR No.41 Field Commissioning
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
|  |  |  | OFFICE 4 | ITR No.41 Field Commissioning
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
|  |  |  | OFFICE 5 | ITR No.41 Field Commissioning
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
Remove boxed items and create and add in each room name per level / area - as per below example.
|  |  |  | PLAYER PERFORMANCE SPACE | ITR No.41 Field Commissioning
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
|  |  |  | BREAK OUT AREA 2 | ITR No.41 Field Commissioning
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
|  |  |  | COACHES 1 | ITR No.41 Field Commissioning
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
|  |  |  | COACHES 2 | ITR No.41 Field Commissioning
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
|  |  |  | OFFICE 1 | ITR No.41 Field Commissioning
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
|  |  |  | WAR ROOM | ITR No.41 Field Commissioning
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
|  |  |  | PLAYERS & STAFF AREA | ITR No.41 Field Commissioning
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
|  |  |  | SERVERY | ITR No.41 Field Commissioning
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
|  |  |  | KITCHEN | ITR No.41 Field Commissioning
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
|  |  |  | FOCUS ROOM | ITR No.41 Field Commissioning
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
|  |  |  | PSYCH ROOM | ITR No.41 Field Commissioning
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
|  |  |  | AFLW OFFICE | ITR No.41 Field Commissioning
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
|  |  |  | OPEN WORK SPACE | ITR No.41 Field Commissioning
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
|  |  |  | RECRUITMENT ROOM | ITR No.41 Field Commissioning
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
|  |  |  | REC MTG | ITR No.41 Field Commissioning
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
|  |  |  | LINE 1 | ITR No.41 Field Commissioning
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
|  |  |  | LINE 2 | ITR No.41 Field Commissioning
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
|  |  |  | LINE 3 | ITR No.41 Field Commissioning
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
|  |  |  | ACC WC 3 | ITR No.41 Field Commissioning
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
|  |  |  | STAFF MALE WC | ITR No.41 Field Commissioning
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
|  |  |  | STAFF FEMALE WC | ITR No.41 Field Commissioning
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
|  |  |  | AMB WC | ITR No.41 Field Commissioning
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
|  |  |  | ACC WC1 | ITR No.41 Field Commissioning
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
|  |  |  | ACC WC2 | ITR No.41 Field Commissioning
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
|  |  |  | MERCH STORE | ITR No.41 Field Commissioning
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
|  |  |  | RETAIL & MUSEUM | ITR No.41 Field Commissioning
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
|  |  |  | HISTORY ROOM | ITR No.41 Field Commissioning
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
|  |  |  | PAST PLAYER OFFICE | ITR No.41 Field Commissioning
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
|  |  |  | PAST PLAYER BOARD ROOM | ITR No.41 Field Commissioning
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
|  |  |  | UTILITIES | ITR No.41 Field Commissioning
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
|  |  |  | THEATRE | ITR No.41 Field Commissioning
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
|  |  |  | EXTERNAL | ITR No.41 Field Commissioning
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
|  |  |  | FIP | ITR No.41 Field Commissioning
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
Commissioning
FIELD
|  | ETAF | LEVEL 1- ZONE A- WEST | COMMON CORRIDOR | ITR No.41 Field Commissioning
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
|  |  |  | POOL | ITR No.41 Field Commissioning
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
|  |  |  | SLEEP ROOM | ITR No.41 Field Commissioning
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
|  |  |  | YOGA ROOM | ITR No.41 Field Commissioning
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
|  |  |  | STORAGE YOGA ROOM | ITR No.41 Field Commissioning
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
|  |  |  | ACC CHANGE | ITR No.41 Field Commissioning
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
|  |  |  | COMMS ROOM | ITR No.41 Field Commissioning
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
|  |  |  | MASSAGE | ITR No.41 Field Commissioning
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
|  |  |  | STORAGE MASSAGE | ITR No.41 Field Commissioning
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
|  |  |  | MENS TOILETS | ITR No.41 Field Commissioning
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
|  |  |  | MENS ENTRY & CHANGE ROOM | ITR No.41 Field Commissioning
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
|  |  |  | WOMENS TOILET | ITR No.41 Field Commissioning
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
|  |  |  | WOMENS ENTRY & CHANGE ROOM | ITR No.41 Field Commissioning
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
|  |  |  | PLAYER RECREATION | ITR No.41 Field Commissioning
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
|  |  |  | COURTYARD | ITR No.41 Field Commissioning
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
|  |  |  | INDOOR TRAINING | ITR No.41 Field Commissioning
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
|  |  |  | EXTERNAL CANOPY | ITR No.41 Field Commissioning
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
Commissioning
FIELD
|  | ETAF | LEVEL 1- ZONE B- EAST
|  |  |  | COMMON CORRIDOR | ITR No.41 Field Commissioning
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
|  |  |  | PLAYER RECREATION | ITR No.41 Field Commissioning
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
|  |  |  | PLAYER DEV | ITR No.41 Field Commissioning
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
|  |  |  | FOCUS 4 | ITR No.41 Field Commissioning
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
|  |  |  | PLAYER EDUCATION | ITR No.41 Field Commissioning
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
|  |  |  | OFFICE 5 | ITR No.41 Field Commissioning
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
|  |  |  | OFFICE 6 | ITR No.41 Field Commissioning
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
ITR No.41 Field Commissioning
|  |  |  | OFFICE 7 | ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
ITR No.41 Field Commissioning
|  |  |  | OPEN WORK SPACE | ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
ITR No.41 Field Commissioning
|  |  |  | KITCHEN | ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
ITR No.41 Field Commissioning
|  |  |  | BOARD ROOM | ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
ITR No.41 Field Commissioning
|  |  |  | MEETING 1 | ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
ITR No.41 Field Commissioning
|  |  |  | MEETING 2 | ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
ITR No.41 Field Commissioning
|  |  |  | BALCONY | ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
|  |  |  | EXTERNAL CANOPY | ITR No.41 Field Commissioning
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
|  |  |  | WAITING AREA | ITR No.41 Field Commissioning
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
|  |  |  | STUDIO | ITR No.41 Field Commissioning
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
|  |  |  | EXECUTIVE AREA | ITR No.41 Field Commissioning
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
|  |  |  | BREAK OUT 4 & 5 | ITR No.41 Field Commissioning
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
|  |  |  | UTILITIES | ITR No.41 Field Commissioning
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
|  |  |  | COMMS ROOM | ITR No.41 Field Commissioning
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
|  |  |  | STORE | ITR No.41 Field Commissioning
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
|  |  |  | MEETING 3 | ITR No.41 Field Commissioning
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
|  |  |  | FOCUS 1 | ITR No.41 Field Commissioning
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
|  |  |  | FOCUS 2 | ITR No.41 Field Commissioning
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
|  |  |  | FOCUS 3 | ITR No.41 Field Commissioning
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
|  |  |  | OFFICE 8 | ITR No.41 Field Commissioning
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
|  |  |  | MEMBERSHIP | ITR No.41 Field Commissioning
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
|  |  |  | ACC 2 | ITR No.41 Field Commissioning
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
|  |  |  | LOCKERS | ITR No.41 Field Commissioning
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
|  |  |  | WELLNESS ROOM 1 | ITR No.41 Field Commissioning
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
|  |  |  | WELLNESS ROOM 2 | ITR No.41 Field Commissioning
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
|  |  |  | FEMALE TOILET | ITR No.41 Field Commissioning
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
|  |  |  | MALE TOILET | ITR No.41 Field Commissioning
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
|  |  |  | OFFICE 1 | ITR No.41 Field Commissioning
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
|  |  |  | OFFICE 2 | ITR No.41 Field Commissioning
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
|  |  |  | OFFICE 4 | ITR No.41 Field Commissioning
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
|  |  |  | BREAK OUT AREA | ITR No.41 Field Commissioning
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM

## PAVILLION
Folder Structure |  |  |  |  | Checklists
Site QA
Site Induction
Undergrounds
|  | PAVILLION | Pit Installation |  | ITP No. 29 Installion of Electrical & Communication Pits
|  |  | Electrical Conduit Install |  | ITR 33. Installing Underground Services (Electrical)
|  |  | Communication Conduit Install |  | ITR 33C. Installing Underground Services (Comms)
Temp Boards
|  | PAVILLION | GROUND |  | ITP No. 19 Installation of Temporary Power Board
|  |  | LEVEL 1 |  | ITP No. 19 Installation of Temporary Power Board
|  |  | LEVEL 2 |  | ITP No. 19 Installation of Temporary Power Board
Temp Lighting
|  | PAVILLION | GROUND |  | ITP No. 14 Construction Wiring, Installation, Test and Tag & Removal
|  |  | LEVEL 1 |  | ITP No. 14 Construction Wiring, Installation, Test and Tag & Removal
|  |  | LEVEL 2 |  | ITP No. 14 Construction Wiring, Installation, Test and Tag & Removal
Mains & Sub Mains
|  | PAVILLION | MSB |  | ITR No.14 Mains and Sub Mains
|  |  | DB-PAV-GF |  | ITR No.14 Mains and Sub Mains
|  |  | DB-PAV-1F |  | ITR No.14 Mains and Sub Mains
|  |  | DB-PAV-2F |  | ITR No.14 Mains and Sub Mains
|  |  | DB-LIFT |  | ITR No.14 Mains and Sub Mains
|  |  | MSSB-01 |  | ITR No.14 Mains and Sub Mains
|  |  | DB-PAV-FB-L1-2 |  | ITR No.14 Mains and Sub Mains
|  |  | DB-B/CAST-LTG-A |  | ITR No.14 Mains and Sub Mains
|  |  | DB-B/CAST-LTG-B |  | ITR No.14 Mains and Sub Mains
|  |  | DB-PAV-OB |  | ITR No.14 Mains and Sub Mains
Inslab Conduits
|  | PAVILLION | GROUND EAST |  | ITR No.09 In Slab Conduits
|  |  | GROUND WEST |  | ITR No.09 In Slab Conduits
|  |  | LEVEL 1 EAST |  | ITR No.09 In Slab Conduits
|  |  | LEVEL 1 WEST |  | ITR No.09 In Slab Conduits
|  |  | LEVEL 2 EAST |  | ITR No.09 In Slab Conduits
|  |  | LEVEL 2 WEST |  | ITR No.09 In Slab Conduits
Switchboards
|  | PAVILLION | MSB |  | ITR No. 16 Switchboard Installation and Terminate Submains
|  |  | DB-PAV-GF |  | ITR No. 16 Switchboard Installation and Terminate Submains
|  |  | DB-PAV-1F |  | ITR No. 16 Switchboard Installation and Terminate Submains
|  |  | DB-PAV-2F |  | ITR No. 16 Switchboard Installation and Terminate Submains
|  |  | DB-LIFT |  | ITR No. 16 Switchboard Installation and Terminate Submains
|  |  | DB-PAV-FB-L1-2 |  | ITR No. 16 Switchboard Installation and Terminate Submains
|  |  | DB-B/CAST-LTG-A |  | ITR No. 16 Switchboard Installation and Terminate Submains
|  |  | DB-B/CAST-LTG-B |  | ITR No. 16 Switchboard Installation and Terminate Submains
|  |  | DB-PAV-OB |  | ITR No. 16 Switchboard Installation and Terminate Submains
|  |  | MSSB-01 |  | ITR No. 16 Switchboard Installation and Terminate Submains
Rough in
|  | PAVILLION | GROUND | COMMON CORRIDOR | ITR No. 10 Cable Tray Installation
ITR No.0 5 Rough in
ITP No.07 Structured Cabling Rough In
ITP No. 43 Lighting Control Rough In
|  |  |  | PLAYERS BENCH WEST | ITR No.0 5 Rough in
ITP No.07 Structured Cabling Rough In
ITP No. 43 Lighting Control Rough In
|  |  |  | OFFICIALS BENCH | ITR No.0 5 Rough in
ITP No.07 Structured Cabling Rough In
ITP No. 43 Lighting Control Rough In
|  |  |  | PLAYERS BENCH EAST | ITR No.0 5 Rough in
ITP No.07 Structured Cabling Rough In
ITP No. 43 Lighting Control Rough In
|  |  |  | DOCTORS ROOM 2 | ITR No.0 5 Rough in
ITP No.07 Structured Cabling Rough In
ITP No. 43 Lighting Control Rough In
|  |  |  | PLAYER BRIEFING ROOM | ITR No.0 5 Rough in
ITP No.07 Structured Cabling Rough In
ITP No. 43 Lighting Control Rough In
|  |  |  | MASSAGE STRAPPING | ITR No.0 5 Rough in
ITP No.07 Structured Cabling Rough In
ITP No. 43 Lighting Control Rough In
|  |  |  | TEAM CHANGE ROOM 1 | ITR No.0 5 Rough in
ITP No.07 Structured Cabling Rough In
ITP No. 43 Lighting Control Rough In
|  |  |  | COMMUNITY CHANGE 1 | ITR No.0 5 Rough in
ITP No.07 Structured Cabling Rough In
ITP No. 43 Lighting Control Rough In
|  |  |  | UMPIRE COMMON | ITR No.0 5 Rough in
ITP No.07 Structured Cabling Rough In
ITP No. 43 Lighting Control Rough In
|  |  |  | UMPIRE CHANGE 1 | ITR No.0 5 Rough in
ITP No.07 Structured Cabling Rough In
ITP No. 43 Lighting Control Rough In
|  |  |  | UMPIRE CHANGE 2 | ITR No.0 5 Rough in
ITP No.07 Structured Cabling Rough In
ITP No. 43 Lighting Control Rough In
|  |  |  | DRUG TEST | ITR No.0 5 Rough in
ITP No.07 Structured Cabling Rough In
ITP No. 43 Lighting Control Rough In
|  |  |  | ACC CH | ITR No.0 5 Rough in
ITP No.07 Structured Cabling Rough In
ITP No. 43 Lighting Control Rough In
|  |  |  | WELLNESS ROOM | ITR No.0 5 Rough in
ITP No.07 Structured Cabling Rough In
ITP No. 43 Lighting Control Rough In
|  |  |  | FOYER | ITR No.0 5 Rough in
ITP No.07 Structured Cabling Rough In
ITP No. 43 Lighting Control Rough In
|  |  |  | FIRST AID | ITR No.0 5 Rough in
ITP No.07 Structured Cabling Rough In
ITP No. 43 Lighting Control Rough In
|  |  |  | INTERVIEW ROOM | ITR No.0 5 Rough in
ITP No.07 Structured Cabling Rough In
ITP No. 43 Lighting Control Rough In
|  |  |  | COMMS ROOM | ITR No.0 5 Rough in
ITP No.07 Structured Cabling Rough In
ITP No. 43 Lighting Control Rough In
|  |  |  | COMMUNITY CHANGE 2 | ITR No.0 5 Rough in
ITP No.07 Structured Cabling Rough In
ITP No. 43 Lighting Control Rough In
|  |  |  | TEAM CHANGE 2 | ITR No.0 5 Rough in
ITP No.07 Structured Cabling Rough In
ITP No. 43 Lighting Control Rough In
|  |  |  | MASSAGE STRAPPING | ITR No.0 5 Rough in
ITP No.07 Structured Cabling Rough In
ITP No. 43 Lighting Control Rough In
|  |  |  | PLAYERS BRIEFING | ITR No.0 5 Rough in
ITP No.07 Structured Cabling Rough In
ITP No. 43 Lighting Control Rough In
|  |  |  | DOCTORS ROOM 1 | ITR No.0 5 Rough in
ITP No.07 Structured Cabling Rough In
ITP No. 43 Lighting Control Rough In
Rough in
|  | PAVILLION | LEVEL 1 | COMMON CORRIDOR | ITR No. 10 Cable Tray Installation
ITR No.0 5 Rough in
ITP No.07 Structured Cabling Rough In
ITP No. 43 Lighting Control Rough In
|  |  |  | FUNCTION ROOM | ITR No.0 5 Rough in
ITP No.07 Structured Cabling Rough In
ITP No. 43 Lighting Control Rough In
|  |  |  | FUNCTION BAR | ITR No.0 5 Rough in
ITP No.07 Structured Cabling Rough In
ITP No. 43 Lighting Control Rough In
|  |  |  | FUNCTION KITCHEN & STORE | ITR No.0 5 Rough in
ITP No.07 Structured Cabling Rough In
ITP No. 43 Lighting Control Rough In
|  |  |  | PARENTS ROOM | ITR No.0 5 Rough in
ITP No.07 Structured Cabling Rough In
ITP No. 43 Lighting Control Rough In
|  |  |  | MALE TOILETS | ITR No.0 5 Rough in
ITP No.07 Structured Cabling Rough In
ITP No. 43 Lighting Control Rough In
|  |  |  | FEMALE TOILETS | ITR No.0 5 Rough in
ITP No.07 Structured Cabling Rough In
ITP No. 43 Lighting Control Rough In
|  |  |  | KIOSK | ITR No.0 5 Rough in
ITP No.07 Structured Cabling Rough In
ITP No. 43 Lighting Control Rough In
Rough in
|  | PAVILLION | LEVEL 2 | COMMON CORRIDOR | ITR No. 10 Cable Tray Installation
ITR No.0 5 Rough in
ITP No.07 Structured Cabling Rough In
ITP No. 43 Lighting Control Rough In
|  |  |  | COACHES BOX 1 | ITR No.0 5 Rough in
ITP No.07 Structured Cabling Rough In
ITP No. 43 Lighting Control Rough In
|  |  |  | PRINT & ONLINE MEDIA | ITR No.0 5 Rough in
ITP No.07 Structured Cabling Rough In
ITP No. 43 Lighting Control Rough In
|  |  |  | RADIO BOX 1 | ITR No.0 5 Rough in
ITP No.07 Structured Cabling Rough In
ITP No. 43 Lighting Control Rough In
|  |  |  | RADIO BOX 2 | ITR No.0 5 Rough in
ITP No.07 Structured Cabling Rough In
ITP No. 43 Lighting Control Rough In
|  |  |  | TV & BROADCAST BOX | ITR No.0 5 Rough in
ITP No.07 Structured Cabling Rough In
ITP No. 43 Lighting Control Rough In
|  |  |  | UMPIRE OBS | ITR No.0 5 Rough in
ITP No.07 Structured Cabling Rough In
ITP No. 43 Lighting Control Rough In
|  |  |  | TIME KEEPER | ITR No.0 5 Rough in
ITP No.07 Structured Cabling Rough In
ITP No. 43 Lighting Control Rough In
|  |  |  | AFL CHAMPION DATA ROOM | ITR No.0 5 Rough in
ITP No.07 Structured Cabling Rough In
ITP No. 43 Lighting Control Rough In
|  |  |  | COACHES BOX 2 | ITR No.0 5 Rough in
ITP No.07 Structured Cabling Rough In
ITP No. 43 Lighting Control Rough In
|  |  |  | DISABLED TOILET | ITR No.0 5 Rough in
ITP No.07 Structured Cabling Rough In
ITP No. 43 Lighting Control Rough In
|  |  |  | MALE TOILET | ITR No.0 5 Rough in
ITP No.07 Structured Cabling Rough In
ITP No. 43 Lighting Control Rough In
|  |  |  | FEMALE TOILET | ITR No.0 5 Rough in
ITP No.07 Structured Cabling Rough In
ITP No. 43 Lighting Control Rough In
|  |  |  | COMMS | ITR No.0 5 Rough in
ITP No.07 Structured Cabling Rough In
ITP No. 43 Lighting Control Rough In
|  |  |  | KITCHENETTE | ITR No.0 5 Rough in
ITP No.07 Structured Cabling Rough In
ITP No. 43 Lighting Control Rough In
|  |  |  | MULTI PURPOSE ROOM | ITR No.0 5 Rough in
ITP No.07 Structured Cabling Rough In
ITP No. 43 Lighting Control Rough In
Cut Out
|  | PAVILLION | GROUND | COMMON CORRIDOR | ITR No.02 Cutout of Ceilings & Walls
|  |  |  | PLAYERS BENCH WEST | ITR No.02 Cutout of Ceilings & Walls
|  |  |  | OFFICIALS BENCH | ITR No.02 Cutout of Ceilings & Walls
|  |  |  | PLAYERS BENCH EAST | ITR No.02 Cutout of Ceilings & Walls
|  |  |  | DOCTORS ROOM 2 | ITR No.02 Cutout of Ceilings & Walls
|  |  |  | PLAYER BRIEFING ROOM | ITR No.02 Cutout of Ceilings & Walls
|  |  |  | MASSAGE STRAPPING | ITR No.02 Cutout of Ceilings & Walls
|  |  |  | TEAM CHANGE ROOM 1 | ITR No.02 Cutout of Ceilings & Walls
|  |  |  | COMMUNITY CHANGE 1 | ITR No.02 Cutout of Ceilings & Walls
|  |  |  | UMPIRE COMMON | ITR No.02 Cutout of Ceilings & Walls
|  |  |  | UMPIRE CHANGE 1 | ITR No.02 Cutout of Ceilings & Walls
|  |  |  | UMPIRE CHANGE 2 | ITR No.02 Cutout of Ceilings & Walls
|  |  |  | DRUG TEST | ITR No.02 Cutout of Ceilings & Walls
|  |  |  | ACC CH | ITR No.02 Cutout of Ceilings & Walls
|  |  |  | WELLNESS ROOM | ITR No.02 Cutout of Ceilings & Walls
|  |  |  | FOYER | ITR No.02 Cutout of Ceilings & Walls
|  |  |  | FIRST AID | ITR No.02 Cutout of Ceilings & Walls
|  |  |  | INTERVIEW ROOM | ITR No.02 Cutout of Ceilings & Walls
|  |  |  | COMMS ROOM | ITR No.02 Cutout of Ceilings & Walls
|  |  |  | COMMUNITY CHANGE 2 | ITR No.02 Cutout of Ceilings & Walls
|  |  |  | TEAM CHANGE 2 | ITR No.02 Cutout of Ceilings & Walls
|  |  |  | MASSAGE STRAPPING | ITR No.02 Cutout of Ceilings & Walls
|  |  |  | PLAYERS BRIEFING | ITR No.02 Cutout of Ceilings & Walls
|  |  |  | DOCTORS ROOM 1 | ITR No.02 Cutout of Ceilings & Walls
Cut Out
|  | PAVILLION | LEVEL 1 | COMMON CORRIDOR | ITR No.02 Cutout of Ceilings & Walls
|  |  |  | FUNCTION ROOM | ITR No.02 Cutout of Ceilings & Walls
|  |  |  | FUNCTION BAR | ITR No.02 Cutout of Ceilings & Walls
|  |  |  | FUNCTION KITCHEN & STORE | ITR No.02 Cutout of Ceilings & Walls
|  |  |  | PARENTS ROOM | ITR No.02 Cutout of Ceilings & Walls
|  |  |  | MALE TOILETS | ITR No.02 Cutout of Ceilings & Walls
|  |  |  | FEMALE TOILETS | ITR No.02 Cutout of Ceilings & Walls
|  |  |  | KIOSK | ITR No.02 Cutout of Ceilings & Walls
Cut Out
|  | PAVILLION | LEVEL 2 | COMMON CORRIDOR | ITR No.02 Cutout of Ceilings & Walls
|  |  |  | COACHES BOX 1 | ITR No.02 Cutout of Ceilings & Walls
|  |  |  | PRINT & ONLINE MEDIA | ITR No.02 Cutout of Ceilings & Walls
|  |  |  | RADIO BOX 1 | ITR No.02 Cutout of Ceilings & Walls
|  |  |  | RADIO BOX 2 | ITR No.02 Cutout of Ceilings & Walls
|  |  |  | TV & BROADCAST BOX | ITR No.02 Cutout of Ceilings & Walls
|  |  |  | UMPIRE OBS | ITR No.02 Cutout of Ceilings & Walls
|  |  |  | TIME KEEPER | ITR No.02 Cutout of Ceilings & Walls
|  |  |  | AFL CHAMPION DATA ROOM | ITR No.02 Cutout of Ceilings & Walls
|  |  |  | COACHES BOX 2 | ITR No.02 Cutout of Ceilings & Walls
|  |  |  | DISABLED TOILET | ITR No.02 Cutout of Ceilings & Walls
|  |  |  | MALE TOILET | ITR No.02 Cutout of Ceilings & Walls
|  |  |  | FEMALE TOILET | ITR No.02 Cutout of Ceilings & Walls
|  |  |  | COMMS | ITR No.02 Cutout of Ceilings & Walls
|  |  |  | KITCHENETTE | ITR No.02 Cutout of Ceilings & Walls
|  |  |  | MULTI PURPOSE ROOM | ITR No.02 Cutout of Ceilings & Walls
Fit Off
|  | PAVILLION | GROUND
|  |  |  | COMMON CORRIDOR | ITR No. 18 Light and Power Fit Off
ITP No. 08 STRUCTURED CABLING FIT OFF
ITR No. 44 Lighting Control Fit off
|  |  |  | PLAYERS BENCH WEST | ITR No. 18 Light and Power Fit Off
ITP No. 08 STRUCTURED CABLING FIT OFF
ITR No. 44 Lighting Control Fit off
|  |  |  | OFFICIALS BENCH | ITR No. 18 Light and Power Fit Off
ITP No. 08 STRUCTURED CABLING FIT OFF
ITR No. 44 Lighting Control Fit off
|  |  |  | PLAYERS BENCH EAST | ITR No. 18 Light and Power Fit Off
ITP No. 08 STRUCTURED CABLING FIT OFF
ITR No. 44 Lighting Control Fit off
|  |  |  | DOCTORS ROOM 2 | ITR No. 18 Light and Power Fit Off
ITP No. 08 STRUCTURED CABLING FIT OFF
ITR No. 44 Lighting Control Fit off
|  |  |  | PLAYER BRIEFING ROOM | ITR No. 18 Light and Power Fit Off
ITP No. 08 STRUCTURED CABLING FIT OFF
ITR No. 44 Lighting Control Fit off
|  |  |  | MASSAGE STRAPPING | ITR No. 18 Light and Power Fit Off
ITP No. 08 STRUCTURED CABLING FIT OFF
ITR No. 44 Lighting Control Fit off
|  |  |  | TEAM CHANGE ROOM 1 | ITR No. 18 Light and Power Fit Off
ITP No. 08 STRUCTURED CABLING FIT OFF
ITR No. 44 Lighting Control Fit off
|  |  |  | COMMUNITY CHANGE 1 | ITR No. 18 Light and Power Fit Off
ITP No. 08 STRUCTURED CABLING FIT OFF
ITR No. 44 Lighting Control Fit off
|  |  |  | UMPIRE COMMON | ITR No. 18 Light and Power Fit Off
ITP No. 08 STRUCTURED CABLING FIT OFF
ITR No. 44 Lighting Control Fit off
|  |  |  | UMPIRE CHANGE 1 | ITR No. 18 Light and Power Fit Off
ITP No. 08 STRUCTURED CABLING FIT OFF
ITR No. 44 Lighting Control Fit off
|  |  |  | UMPIRE CHANGE 2 | ITR No. 18 Light and Power Fit Off
ITP No. 08 STRUCTURED CABLING FIT OFF
ITR No. 44 Lighting Control Fit off
|  |  |  | DRUG TEST | ITR No. 18 Light and Power Fit Off
ITP No. 08 STRUCTURED CABLING FIT OFF
ITR No. 44 Lighting Control Fit off
|  |  |  | ACC CH | ITR No. 18 Light and Power Fit Off
ITP No. 08 STRUCTURED CABLING FIT OFF
ITR No. 44 Lighting Control Fit off
|  |  |  | WELLNESS ROOM | ITR No. 18 Light and Power Fit Off
ITP No. 08 STRUCTURED CABLING FIT OFF
ITR No. 44 Lighting Control Fit off
|  |  |  | FOYER | ITR No. 18 Light and Power Fit Off
ITP No. 08 STRUCTURED CABLING FIT OFF
ITR No. 44 Lighting Control Fit off
|  |  |  | FIRST AID | ITR No. 18 Light and Power Fit Off
ITP No. 08 STRUCTURED CABLING FIT OFF
ITR No. 44 Lighting Control Fit off
|  |  |  | INTERVIEW ROOM | ITR No. 18 Light and Power Fit Off
ITP No. 08 STRUCTURED CABLING FIT OFF
ITR No. 44 Lighting Control Fit off
|  |  |  | COMMS ROOM | ITR No. 18 Light and Power Fit Off
ITP No. 08 STRUCTURED CABLING FIT OFF
ITR No. 44 Lighting Control Fit off
|  |  |  | COMMUNITY CHANGE 2 | ITR No. 18 Light and Power Fit Off
ITP No. 08 STRUCTURED CABLING FIT OFF
ITR No. 44 Lighting Control Fit off
|  |  |  | TEAM CHANGE 2 | ITR No. 18 Light and Power Fit Off
ITP No. 08 STRUCTURED CABLING FIT OFF
ITR No. 44 Lighting Control Fit off
|  |  |  | MASSAGE STRAPPING | ITR No. 18 Light and Power Fit Off
ITP No. 08 STRUCTURED CABLING FIT OFF
ITR No. 44 Lighting Control Fit off
|  |  |  | PLAYERS BRIEFING | ITR No. 18 Light and Power Fit Off
ITP No. 08 STRUCTURED CABLING FIT OFF
ITR No. 44 Lighting Control Fit off
|  |  |  | DOCTORS ROOM 1 | ITR No. 18 Light and Power Fit Off
ITP No. 08 STRUCTURED CABLING FIT OFF
ITR No. 44 Lighting Control Fit off
Fit Off
|  | PAVILLION | LEVEL 1
|  |  |  | COMMON CORRIDOR | ITR No. 18 Light and Power Fit Off
ITP No. 08 STRUCTURED CABLING FIT OFF
ITR No. 44 Lighting Control Fit off
|  |  |  | FUNCTION ROOM | ITR No. 18 Light and Power Fit Off
ITP No. 08 STRUCTURED CABLING FIT OFF
ITR No. 44 Lighting Control Fit off
|  |  |  | FUNCTION BAR | ITR No. 18 Light and Power Fit Off
ITP No. 08 STRUCTURED CABLING FIT OFF
ITR No. 44 Lighting Control Fit off
|  |  |  | FUNCTION KITCHEN & STORE | ITR No. 18 Light and Power Fit Off
ITP No. 08 STRUCTURED CABLING FIT OFF
ITR No. 44 Lighting Control Fit off
|  |  |  | PARENTS ROOM | ITR No. 18 Light and Power Fit Off
ITP No. 08 STRUCTURED CABLING FIT OFF
ITR No. 44 Lighting Control Fit off
|  |  |  | MALE TOILETS | ITR No. 18 Light and Power Fit Off
ITP No. 08 STRUCTURED CABLING FIT OFF
ITR No. 44 Lighting Control Fit off
|  |  |  | FEMALE TOILETS | ITR No. 18 Light and Power Fit Off
ITP No. 08 STRUCTURED CABLING FIT OFF
ITR No. 44 Lighting Control Fit off
|  |  |  | KIOSK | ITR No. 18 Light and Power Fit Off
ITP No. 08 STRUCTURED CABLING FIT OFF
ITR No. 44 Lighting Control Fit off
Fit Off
|  | PAVILLION | LEVEL 2
|  |  |  | COMMON CORRIDOR | ITR No. 18 Light and Power Fit Off
ITP No. 08 STRUCTURED CABLING FIT OFF
ITR No. 44 Lighting Control Fit off
|  |  |  | COACHES BOX 1 | ITR No. 18 Light and Power Fit Off
ITP No. 08 STRUCTURED CABLING FIT OFF
ITR No. 44 Lighting Control Fit off
|  |  |  | PRINT & ONLINE MEDIA | ITR No. 18 Light and Power Fit Off
ITP No. 08 STRUCTURED CABLING FIT OFF
ITR No. 44 Lighting Control Fit off
|  |  |  | RADIO BOX 1 | ITR No. 18 Light and Power Fit Off
ITP No. 08 STRUCTURED CABLING FIT OFF
ITR No. 44 Lighting Control Fit off
|  |  |  | RADIO BOX 2 | ITR No. 18 Light and Power Fit Off
ITP No. 08 STRUCTURED CABLING FIT OFF
ITR No. 44 Lighting Control Fit off
|  |  |  | TV & BROADCAST BOX | ITR No. 18 Light and Power Fit Off
ITP No. 08 STRUCTURED CABLING FIT OFF
ITR No. 44 Lighting Control Fit off
|  |  |  | UMPIRE OBS | ITR No. 18 Light and Power Fit Off
ITP No. 08 STRUCTURED CABLING FIT OFF
ITR No. 44 Lighting Control Fit off
|  |  |  | TIME KEEPER | ITR No. 18 Light and Power Fit Off
ITP No. 08 STRUCTURED CABLING FIT OFF
ITR No. 44 Lighting Control Fit off
|  |  |  | AFL CHAMPION DATA ROOM | ITR No. 18 Light and Power Fit Off
ITP No. 08 STRUCTURED CABLING FIT OFF
ITR No. 44 Lighting Control Fit off
|  |  |  | COACHES BOX 2 | ITR No. 18 Light and Power Fit Off
ITP No. 08 STRUCTURED CABLING FIT OFF
ITR No. 44 Lighting Control Fit off
|  |  |  | DISABLED TOILET | ITR No. 18 Light and Power Fit Off
ITP No. 08 STRUCTURED CABLING FIT OFF
ITR No. 44 Lighting Control Fit off
|  |  |  | MALE TOILET | ITR No. 18 Light and Power Fit Off
ITP No. 08 STRUCTURED CABLING FIT OFF
ITR No. 44 Lighting Control Fit off
|  |  |  | FEMALE TOILET | ITR No. 18 Light and Power Fit Off
ITP No. 08 STRUCTURED CABLING FIT OFF
ITR No. 44 Lighting Control Fit off
|  |  |  | COMMS | ITR No. 18 Light and Power Fit Off
ITP No. 08 STRUCTURED CABLING FIT OFF
ITR No. 44 Lighting Control Fit off
|  |  |  | KITCHENETTE | ITR No. 18 Light and Power Fit Off
ITP No. 08 STRUCTURED CABLING FIT OFF
ITR No. 44 Lighting Control Fit off
|  |  |  | MULTI PURPOSE ROOM | ITR No. 18 Light and Power Fit Off
ITP No. 08 STRUCTURED CABLING FIT OFF
ITR No. 44 Lighting Control Fit off
Commissioning
MAINS
|  | PAVILLION | MSB |  | ITR. 12 Switchboard Commissioning
|  |  | DB-PAV-GF |  | ITR. 12 Switchboard Commissioning
|  |  | DB-PAV-1F |  | ITR. 12 Switchboard Commissioning
|  |  | DB-PAV-2F |  | ITR. 12 Switchboard Commissioning
|  |  | DB-LIFT |  | ITR. 12 Switchboard Commissioning
|  |  | DB-PAV-FB-L1-2 |  | ITR. 12 Switchboard Commissioning
|  |  | DB-B/CAST-LTG-A |  | ITR. 12 Switchboard Commissioning
|  |  | DB-B/CAST-LTG-B |  | ITR. 12 Switchboard Commissioning
|  |  | DB-PAV-OB |  | ITR. 12 Switchboard Commissioning
|  |  | MSSB-01 |  | ITR. 12 Switchboard Commissioning
FIELD
|  | PAVILLION | GROUND
|  |  |  | COMMON CORRIDOR | ITR No.41 Field Commissioning
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
|  |  |  | PLAYERS BENCH WEST | ITR No.41 Field Commissioning
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
|  |  |  | OFFICIALS BENCH | ITR No.41 Field Commissioning
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
|  |  |  | PLAYERS BENCH EAST | ITR No.41 Field Commissioning
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
|  |  |  | DOCTORS ROOM 2 | ITR No.41 Field Commissioning
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
|  |  |  | PLAYER BRIEFING ROOM | ITR No.41 Field Commissioning
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
|  |  |  | MASSAGE STRAPPING | ITR No.41 Field Commissioning
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
|  |  |  | TEAM CHANGE ROOM 1 | ITR No.41 Field Commissioning
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
|  |  |  | COMMUNITY CHANGE 1 | ITR No.41 Field Commissioning
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
|  |  |  | UMPIRE COMMON | ITR No.41 Field Commissioning
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
|  |  |  | UMPIRE CHANGE 1 | ITR No.41 Field Commissioning
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
|  |  |  | UMPIRE CHANGE 2 | ITR No.41 Field Commissioning
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
|  |  |  | DRUG TEST | ITR No.41 Field Commissioning
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
|  |  |  | ACC CH | ITR No.41 Field Commissioning
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
|  |  |  | WELLNESS ROOM | ITR No.41 Field Commissioning
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
|  |  |  | FOYER | ITR No.41 Field Commissioning
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
|  |  |  | FIRST AID | ITR No.41 Field Commissioning
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
|  |  |  | INTERVIEW ROOM | ITR No.41 Field Commissioning
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
|  |  |  | COMMS ROOM | ITR No.41 Field Commissioning
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
|  |  |  | COMMUNITY CHANGE 2 | ITR No.41 Field Commissioning
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
|  |  |  | TEAM CHANGE 2 | ITR No.41 Field Commissioning
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
|  |  |  | MASSAGE STRAPPING | ITR No.41 Field Commissioning
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
|  |  |  | PLAYERS BRIEFING | ITR No.41 Field Commissioning
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
|  |  |  | DOCTORS ROOM 1 | ITR No.41 Field Commissioning
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
FIELD
|  | PAVILLION | LEVEL 1
|  |  |  | COMMON CORRIDOR | ITR No.41 Field Commissioning
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
ITR No.41 Field Commissioning
|  |  |  | FUNCTION ROOM | ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
ITR No.41 Field Commissioning
|  |  |  | FUNCTION BAR | ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
|  |  |  | FUNCTION KITCHEN & STORE | ITR No.41 Field Commissioning
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
|  |  |  | PARENTS ROOM | ITR No.41 Field Commissioning
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
|  |  |  | MALE TOILETS | ITR No.41 Field Commissioning
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
|  |  |  | FEMALE TOILETS | ITR No.41 Field Commissioning
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
|  |  |  | KIOSK | ITR No.41 Field Commissioning
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
FIELD
|  | PAVILLION | LEVEL 2
|  |  |  | COMMON CORRIDOR | ITR No.41 Field Commissioning
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
|  |  |  | COACHES BOX 1 | ITR No.41 Field Commissioning
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
|  |  |  | PRINT & ONLINE MEDIA | ITR No.41 Field Commissioning
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
|  |  |  | RADIO BOX 1 | ITR No.41 Field Commissioning
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
|  |  |  | RADIO BOX 2 | ITR No.41 Field Commissioning
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
|  |  |  | TV & BROADCAST BOX | ITR No.41 Field Commissioning
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
|  |  |  | UMPIRE OBS | ITR No.41 Field Commissioning
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
|  |  |  | TIME KEEPER | ITR No.41 Field Commissioning
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
|  |  |  | AFL CHAMPION DATA ROOM | ITR No.41 Field Commissioning
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
|  |  |  | COACHES BOX 2 | ITR No.41 Field Commissioning
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
|  |  |  | DISABLED TOILET | ITR No.41 Field Commissioning
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
|  |  |  | MALE TOILET | ITR No.41 Field Commissioning
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
|  |  |  | FEMALE TOILET | ITR No.41 Field Commissioning
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
|  |  |  | COMMS | ITR No.41 Field Commissioning
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
|  |  |  | KITCHENETTE | ITR No.41 Field Commissioning
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM
|  |  |  | MULTI PURPOSE ROOM | ITR No.41 Field Commissioning
ITP No. 09 STRUCTURED CABLING TESTING CERTIFIED SYSTEM