## ITP
|  |  | Inspection and Test Plan - Installation of pre-cast concrete barriers. | [7 empty] | Document # 1145-C200-FUL-QAC-ITP-0014
Revision : 00
Client: | Fulton Hogan |  | Construction Process: | Inspection and Test Plan - Installation of pre-cast concrete barriers |  | Prepared by: |  | Reviewed by: |  |  | Approved by:
Project: | Craigieburn Road Upgrade |  | Specifications: | Project specification PS3050 VicRoads Spec 610 (Feb 2020) VicRoads Spec 620 (May 2009) VicRoads Spec 630 & 671 (Oct 2013) |  | Name: | Karim Habib | Name: |  | Mike Freeman | Name: | Nicola Lodo
Contract No: | 1145 |  | Structure / Component: | Pre-cast barriers & end-posts |  | Position: | Site Engineer | Position: |  | SPM | Position: | Quality Manager
|  |  | Location: | Area 2 Zone 6 |  | Date : | 19/10/2023 | Date : |  | 19/10/2023 | Date: | 26/10/2023
Lot No: |  |  | Lot Details: | [5 empty] | Lot Size/ Quantity:
Item | Task/Activity Description |  | Inspection / Controls and Verification Detail |  |  |  |  | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility | Checked by:
No. |  |  | Frequency | Acceptance Criteria | Reference Documents | Inspection / Test Method | Record of conformity |  | Project Engineer Site Engineer Superintendent Surveyor Foreman | Superintendent | Fulton Hogan | FH's Sub-contractor | Date
1 | Preliminaries
1.1 | Precast Elements |  | Each element | Precast supplier is required to provide the following Quality Assurance documentation for each element, typically this consists of: i. Certificate of Compliance / Birth Certificate ii. Compressive strength test results iii. Precast Lifting Design iv. Pre-pour check sheet / ITP v. Post-pour check sheet / ITP vi. Covermeter check record vii. Record of dimensional measurements to demonstrate compliance with dimensional tolerances of precast shown on table 610.473 | IFC Drawings 610.47 (a) Table 610.473 | Document Review | This ITP | IP | PE/SE/SPE
1.2 | Epoxy Adhesive |  | Once, for each product | Details of epoxy adhesive used to install steel bearings to bridge deck/foundation to be submitted for review to the Nominated Authority. | Fulton Hogan Quality Management Plan | Document Review | This ITP | IP | Nominated Authority
1.3 | Joint Sealant |  | Once, for each product | Details of the joint sealant used to seal around the precast element to be submitted for review to the Nominated Authority | Fulton Hogan Quality Management Plan | Document Review | This ITP | IP | Nominated Authority
1.4 | Bridge Deck / Foundation Compressive Strength |  | Each installation location | Check that the 7 day compressive strength as shown on the IFC Drawings has been achieved. | 671.03 | Document Review | This ITP | IP | SE/PE/SPE
2 | Pre-installation activities
2.1 | Survey Set-out of Precast Elements |  | Each element | Survey activities undertaken to ensure and validate that all Works meet level and location requirements within the tolerances as per the table 610.462 / 610.472 as applicable to the element. Where anchor bolts are cast in to the concrete, ensure that these are within tolerance. If the precast elements are being connected with a stitch pour, mark any clashes from protruding reinforcement with the planned locations from the precast. Note: Any clashes should be levered out of the way using a crow-bar or similar - avoid hitting with a hammer on bars with a tight radius. | IFC Drawings 610.47 (a) Table 610.472 | Measure Visual | This ITP | IP | Surveyor SE/PE/SPE
2.2 | Hold-down Bracket Levelling Bolt Bearing Plate Placement |  | Where applicable, each installation location | Mix the epoxy adhesive in accordance with the product TDS and apply to the back face of the steel bearing plates. Place the epoxied plates onto the survey marks and ensure that the area level. | IFC Drawings Product TDS | Measure Visual | This ITP | IP | Surveyor SE/PE/SPE
2.3 | Bearing Shims or Bearing Strip Placement |  | Where applicable, each installation location | Place the bearing shims, strip or variety of shims to the survey marks and to the required thickness to achieve compliance with the IFC Drawings and tolerances. Note: If the precast elements are to be grouted, the minimum and maximum thicknesses of the bearing will determine the product for the grouting activities (usually 10mm min.) | IFC Drawings | Measure Visual | This ITP | IP | Surveyor SE/PE/SPE
2.4 | Sealing Strips, Backing Rod & Bitumen Board |  | Where applicable, each installation location | Adhere any sealing strips, backing rod or bitumen impregnated fibre-board into the positions shown on the IFC Drawings or where grout or concrete ingress will affect the end use (such as around conduits). Backing rod should be compressed enough to prevent movement during the concrete or grout pouring activities. | IFC Drawings | Measure Visual | This ITP | IP | Surveyor SE/PE/SPE
2.5 | Materials Inspection Checklist |  | Each element | General inspection of precast elements for defects including cracks, damage, exposed reinforcement and where applicable, damage to coatings. Confirm that the cast in lifters (anchors or loops) are the correct size and orientation as per the Precast Lifting Design (they should be clearly labelled on the end to be connected to). Elements shall have unique identification and orientation marked (if applicable). | 620.06 620.07 Fulton Hogan Quality Management Plan | Measure Visual | This ITP | IP | SE/PE/SPE
3 | Installation activities
3.1 | Precast Handling |  | Each element | Unless otherwise specified, precast elements shall be lifted using the lifting points provided and supported with the top surface uppermost at all times. | 620.07 Crane Lift Study | Visual | This ITP | IP | SE/PE/SPE
3.2 | Precast Placement |  | Each element | Precast elements shall be placed onto the bearing shims and not released from the crane until sufficiently braced or restrained by bolted connection, in accordance with the approved temporary works design and/or IFC drawings. Make any adjustments necessary by lifting the unit and adding/removing shims or adjusting the levelling bolts so that alignment between units, overall height and position remains in tolerance. The nominal gap between elements is as per the IFC Drawings. | IFC Drawings 610.27 | Measure Visual | This ITP | IP | Surveyor SE/PE/SPE
3.3 | Draw-string in Service Ducts |  | Where applicable, each element | Place a continuous length of 3mm galvanised wire or high-strength nylon draw string so that it can be terminated at any junction boxes. | IFC Drawings 671.03 | Visual | This ITP | IP | SE/PE/SPE
3.4 | Hold-down Bracket Fastener Tightening - Snug Tight Condition (4.6/S & 8.8/S) |  | Where applicable, each bolted connection | Place washers and nuts onto the embedded thread as detailed on the IFC Drawings. Tapered washers shall be positioned if the surfaces are on a slope of 1:20 or greater. Tighten with a few impacts of an impact wrench or the full effort of a person using a podger spanner. Protrusion to be at least 1 clear thread shows beyond the nut but no greater than 12mm. | IFC Drawings 630.20 (a) & (c) AS5131 Clause 8.3 | Visual | This ITP | IP | SE/PE/SPE
3.5 | Precast Traceability |  | Each element | All manufactured precast elements shall be traced from the completion of manufacture to their final location by a unique identification number. Record: The final location of each precast element, showing individual ID and date installed onto the Red-line Drawings or Survey Report | 620.09 | Visual | This ITP | IP | SE/PE/SPE
4 | Post-installation activities
4.1 | Joint Sealant Application |  | Where applicable | The gap between each precast element or at interfaces with other structures should be sealed with an the approved sealant on top of a backing rod. | IFC Drawings | Visual | Grout Pedestals & Bearings ITP | IP | Surveyor SE/PE/SPE
4.2 | Flowable Grout Pour |  | Where applicable | Grout shall be poured at connections between elements and/or in the gap between the bottom of the precast element and top of the bridge deck/foundation following full sealant application. Complete: Grout Pedestals & Bearings ITP | IFC Drawings | Visual | Grout Pedestals & Bearings ITP | IP | Surveyor SE/PE/SPE
4.3 | Barrier Railing |  | Where applicable | Where applicable. Complete: Structural Steel Barrier Rail (Supply & Installation) ITP. | IFC Drawings | Document Review | Structural Steel Barrier Rail (Supply & Installation) ITP | IP | Surveyor SE/PE/SPE
4.4 | As-built Survey |  | Each element | Provide record of dimensional measurements to demonstrate concrete members comply with tolerances as per the table 610.462 (November 2018) or 610.472 (March/June 2019) as applicable to the element. Attach: Survey As-builts / Survey Report | IFC Drawings 610.47 (a) Table 610.472 | Document Review | This ITP | IP | Surveyor SE/PE/SPE
4.5 | Non-conformance Report (NCR) Closure |  | Once, prior to closure of this lot / element / Work area | Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs. | Fulton Hogan Quality Management Plan | Document Review | This ITP | HP* | SE/PE/SPE
Final Inspection
The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and verifies lot compliance with specifications.
| Print Name: |  | Position: |  | Signature: |  |  |  |  | Date:
Work Completed On:
Legend
HP | Hold Point | Work shall not proceed past the HP until released by the Superintendent |  |  | IP | Inspection point |  | Formal Inspection to be done and recorded
HP* | FH Hold Point | Work shall not proceed past the HP* until released by FH |  |  | TP | Test Point |  | Product compliance test to be undertaken and recorded/reported
AP | Approval Point | Written or verbal approval given by the Superintendent |  |  | SCP | Survey conformance point |  | A qualified surveyor to check product/section/structure and report
WP | Witness Point | An inspection which must be witnessed by the Superintendent