## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-014-A2-LOT-XXX - Desc | itp |  |  |  |  | ITP 0014 - INSTALLATION OF PRE-CAST CONCRETE BARRIERS
section | Lot Information
checkpoint | 1.0 Lot Information
date | Lot Created On
date | Lot Opened On
date | Work Commenced On
select | Lot Type | CIL - Civil
text | From and To Chainage
select | Construction Element | SAFE - Safety Barrier
select | Activity | CONCB - Concrete Barrier
select | Design Package No | 1145-ACM-CVD-DPK-0002, 1145-ACM-CVD-DPK-0003, 1145-ACM-CVD-DPK-0004, 1145-ACM-CVP-DPK-0001, 1145-ACM-CVP-DPK-0002, 1145-ACM-CVR-DPK-0001, 1145-ACM-CVR-DPK-0002, 1145-ACM-CVR-DPK-0003, 1145-ACM-CVR-DPK-0004, 1145-ACM-ELE-DPK-0001, 1145-ACM-ELE-DPK-0002, 1145-ACM-LDE-DPK-0001, 1145-ACM-LDE-DPK-0002, 1145-ACM-SBA-DPK-0001, 1145-ACM-STR-DPK-0001, 1145-ACM-TSI-DPK-0001, 1145-ACM-TSI-DPK-0002, 1145-ACM-TSI-DPK-0003, 1145-ACM-TSI-DPK-0004, 1145-ACM-UTL-DPK-0001, 1145-ACM-UTL-DPK-0002
select | Traffic Direction | EB - Eastbound, ME - Median, NB - Northbound, SB - Southbound, WB - Westbound
text | Engineer Responsible
text | comments
section | 1 - Preliminaries
checkpoint | 1.1 - Precast Elements
label | Frequency: Each element
label | - - - - - - - - -
label | Acceptance Criteria: Precast supplier is required to provide the following Quality Assurance documentation for each element, typically this consists of:
label | i. Certificate of Compliance / Birth Certificate
label | ii. Compressive strength test results
label | iii. Precast Lifting Design
label | iv. Pre-pour check sheet / ITP
label | v. Post-pour check sheet / ITP
label | vi. Covermeter check record
label | vii. Record of dimensional measurements to demonstrate compliance with dimensional tolerances of precast shown on table 610.473
label | - - - - - - - - -
label | Reference Documents: IFC Drawings 610.47 (a) Table 610.473
label | - - - - - - - - -
label | Inspection / Test Method: Document Review
label | - - - - - - - - -
label | Record of Conformity: This ITP
label | - - - - - - - - -
label | IP
label | - - - - - - - - -
text | Responsibility: PE/SE/SPE
checkpoint | 1.2 - Epoxy Adhesive
label | Frequency: Once, for each product
label | - - - - - - - - -
label | Acceptance Criteria: Details of epoxy adhesive used to install steel bearings to bridge deck/foundation to be submitted for review to the Nominated Authority.
label | - - - - - - - - -
label | Reference Documents: Fulton Hogan Quality Management Plan
label | - - - - - - - - -
label | Inspection / Test Method: Document Review
label | - - - - - - - - -
label | Record of Conformity: This ITP
label | - - - - - - - - -
label | IP
label | - - - - - - - - -
text | Responsibility: Nominated Authority
checkpoint | 1.3 - Joint Sealant
label | Frequency: Once, for each product
label | - - - - - - - - -
label | Acceptance Criteria: Details of the joint sealant used to seal around the precast element to be submitted for review to the Nominated Authority
label | - - - - - - - - -
label | Reference Documents: Fulton Hogan Quality Management Plan
label | - - - - - - - - -
label | Inspection / Test Method: Document Review
label | - - - - - - - - -
label | Record of Conformity: This ITP
label | - - - - - - - - -
label | IP
label | - - - - - - - - -
text | Responsibility: Nominated Authority
checkpoint | 1.4 - Bridge Deck / Foundation Compressive Strength
label | Frequency: Each installation location
label | - - - - - - - - -
label | Acceptance Criteria: Check that the 7 day compressive strength as shown on the IFC Drawings has been achieved.
label | - - - - - - - - -
label | Reference Documents: 671.03
label | - - - - - - - - -
label | Inspection / Test Method: Document Review
label | - - - - - - - - -
label | Record of Conformity: This ITP
label | - - - - - - - - -
label | IP
label | - - - - - - - - -
text | Responsibility: SE/PE/SPE
section | 2 - Pre-installation activities
checkpoint | 2.1 - Survey Set-out of Precast Elements
label | Frequency: Each element
label | - - - - - - - - -
label | Acceptance Criteria: Survey activities undertaken to ensure and validate that all Works meet level and location requirements within the tolerances as per the table 610.462 / 610.472 as applicable to the element. Where anchor bolts are cast in to the concrete, ensure that these are within tolerance. If the precast elements are being connected with a stitch pour, mark any clashes from protruding reinforcement with the planned locations from the precast.
label | Note: Any clashes should be levered out of the way using a crow-bar or similar - avoid hitting with a hammer on bars with a tight radius.
label | - - - - - - - - -
label | Reference Documents: IFC Drawings 610.47 (a) Table 610.472
label | - - - - - - - - -
label | Inspection / Test Method: Measure, Visual
label | - - - - - - - - -
label | Record of Conformity: This ITP
label | - - - - - - - - -
label | IP
label | - - - - - - - - -
text | Responsibility: Surveyor, SE/PE/SPE
checkpoint | 2.2 - Hold-down Bracket Levelling Bolt Bearing Plate Placement
label | Frequency: Where applicable, each installation location
label | - - - - - - - - -
label | Acceptance Criteria: Mix the epoxy adhesive in accordance with the product TDS and apply to the back face of the steel bearing plates. Place the epoxied plates onto the survey marks and ensure that the area level.
label | - - - - - - - - -
label | Reference Documents: IFC Drawings, Product TDS
label | - - - - - - - - -
label | Inspection / Test Method: Measure, Visual
label | - - - - - - - - -
label | Record of Conformity: This ITP
label | - - - - - - - - -
label | IP
label | - - - - - - - - -
text | Responsibility: Surveyor, SE/PE/SPE
checkpoint | 2.3 - Bearing Shims or Bearing Strip Placement
label | Frequency: Where applicable, each installation location
label | - - - - - - - - -
label | Acceptance Criteria: Place the bearing shims, strip or variety of shims to the survey marks and to the required thickness to achieve compliance with the IFC Drawings and tolerances.
label | Note: If the precast elements are to be grouted, the minimum and maximum thicknesses of the bearing will determine the product for the grouting activities (usually 10mm min.)
label | - - - - - - - - -
label | Reference Documents: IFC Drawings
label | - - - - - - - - -
label | Inspection / Test Method: Measure, Visual
label | - - - - - - - - -
label | Record of Conformity: This ITP
label | - - - - - - - - -
label | IP
label | - - - - - - - - -
text | Responsibility: Surveyor, SE/PE/SPE
checkpoint | 2.4 - Sealing Strips, Backing Rod & Bitumen Board
label | Frequency: Where applicable, each installation location
label | - - - - - - - - -
label | Acceptance Criteria: Adhere any sealing strips, backing rod or bitumen impregnated fibre-board into the positions shown on the IFC Drawings or where grout or concrete ingress will affect the end use (such as around conduits). Backing rod should be compressed enough to prevent movement during the concrete or grout pouring activities.
label | - - - - - - - - -
label | Reference Documents: IFC Drawings
label | - - - - - - - - -
label | Inspection / Test Method: Measure, Visual
label | - - - - - - - - -
label | Record of Conformity: This ITP
label | - - - - - - - - -
label | IP
label | - - - - - - - - -
text | Responsibility: Surveyor, SE/PE/SPE
checkpoint | 2.5 - Materials Inspection Checklist
label | Frequency: Each element
label | - - - - - - - - -
label | Acceptance Criteria: General inspection of precast elements for defects including cracks, damage, exposed reinforcement and where applicable, damage to coatings. Confirm that the cast in lifters (anchors or loops) are the correct size and orientation as per the Precast Lifting Design (they should be clearly labelled on the end to be connected to). Elements shall have unique identification and orientation marked (if applicable).
label | - - - - - - - - -
label | Reference Documents: 620.06, 620.07 Fulton Hogan Quality Management Plan
label | - - - - - - - - -
label | Inspection / Test Method: Measure, Visual
label | - - - - - - - - -
label | Record of Conformity: This ITP
label | - - - - - - - - -
label | IP
label | - - - - - - - - -
text | Responsibility: SE/PE/SPE
section | 3 - Installation activities
checkpoint | 3.1 - Precast Handling
label | Frequency: Each element
label | - - - - - - - - -
label | Acceptance Criteria: Unless otherwise specified, precast elements shall be lifted using the lifting points provided and supported with the top surface uppermost at all times.
label | - - - - - - - - -
label | Reference Documents: 620.07 Crane Lift Study
label | - - - - - - - - -
label | Inspection / Test Method: Visual
label | - - - - - - - - -
label | Record of Conformity: This ITP
label | - - - - - - - - -
label | IP
label | - - - - - - - - -
text | Responsibility: SE/PE/SPE
checkpoint | 3.2 - Precast Placement
label | Frequency: Each element
label | - - - - - - - - -
label | Acceptance Criteria: Precast elements shall be placed onto the bearing shims and not released from the crane until sufficiently braced or restrained by bolted connection, in accordance with the approved temporary works design and/or IFC drawings. Make any adjustments necessary by lifting the unit and adding/removing shims or adjusting the levelling bolts so that alignment between units, overall height and position remains in tolerance. The nominal gap between elements is as per the IFC Drawings.
label | - - - - - - - - -
label | Reference Documents: IFC Drawings 610.27
label | - - - - - - - - -
label | Inspection / Test Method: Measure, Visual
label | - - - - - - - - -
label | Record of Conformity: This ITP
label | - - - - - - - - -
label | IP
label | - - - - - - - - -
text | Responsibility: Surveyor, SE/PE/SPE
checkpoint | 3.3 - Draw-string in Service Ducts
label | Frequency: Where applicable, each element
label | - - - - - - - - -
label | Acceptance Criteria: Place a continuous length of 3mm galvanised wire or high-strength nylon draw string so that it can be terminated at any junction boxes.
label | - - - - - - - - -
label | Reference Documents: IFC Drawings 671.03
label | - - - - - - - - -
label | Inspection / Test Method: Visual
label | - - - - - - - - -
label | Record of Conformity: This ITP
label | - - - - - - - - -
label | IP
label | - - - - - - - - -
text | Responsibility: SE/PE/SPE
checkpoint | 3.4 - Hold-down Bracket Fastener Tightening - Snug Tight Condition (4.6/S & 8.8/S)
label | Frequency: Where applicable, each bolted connection
label | - - - - - - - - -
label | Acceptance Criteria: Place washers and nuts onto the embedded thread as detailed on the IFC Drawings. Tapered washers shall be positioned if the surfaces are on a slope of 1:20 or greater. Tighten with a few impacts of an impact wrench or the full effort of a person using a podger spanner. Protrusion to be at least 1 clear thread shows beyond the nut but no greater than 12mm.
label | - - - - - - - - -
label | Reference Documents: IFC Drawings 630.20 (a) & (c) AS5131 Clause 8.3
label | - - - - - - - - -
label | Inspection / Test Method: Visual
label | - - - - - - - - -
label | Record of Conformity: This ITP
label | - - - - - - - - -
label | IP
label | - - - - - - - - -
text | Responsibility: SE/PE/SPE
checkpoint | 3.5 - Precast Traceability
label | Frequency: Each element
label | - - - - - - - - -
label | Acceptance Criteria: All manufactured precast elements shall be traced from the completion of manufacture to their final location by a unique identification number.
label | Record: The final location of each precast element, showing individual ID and date installed onto the Red-line Drawings or Survey Report
label | - - - - - - - - -
label | Reference Documents: 620.09
label | - - - - - - - - -
label | Inspection / Test Method: Visual
label | - - - - - - - - -
label | Record of Conformity: This ITP
label | - - - - - - - - -
label | IP
label | - - - - - - - - -
text | Responsibility: SE/PE/SPE
section | 4 - Post-installation activities
checkpoint | 4.1 - Joint Sealant Application
label | Frequency: Where applicable
label | - - - - - - - - -
label | Acceptance Criteria: The gap between each precast element or at interfaces with other structures should be sealed with an the approved sealant on top of a backing rod.
label | - - - - - - - - -
label | Reference Documents: IFC Drawings
label | - - - - - - - - -
label | Inspection / Test Method: Visual
label | - - - - - - - - -
label | Record of Conformity: Grout Pedestals & Bearings ITP
label | - - - - - - - - -
label | IP
label | - - - - - - - - -
text | Responsibility: Surveyor, SE/PE/SPE
checkpoint | 4.2 - Flowable Grout Pour
label | Frequency: Where applicable
label | - - - - - - - - -
label | Acceptance Criteria: Grout shall be poured at connections between elements and/or in the gap between the bottom of the precast element and top of the bridge deck/foundation following full sealant application.
label | Complete: Grout Pedestals & Bearings ITP
label | - - - - - - - - -
label | Reference Documents: IFC Drawings
label | - - - - - - - - -
label | Inspection / Test Method: Visual
label | - - - - - - - - -
label | Record of Conformity: Grout Pedestals & Bearings ITP
label | - - - - - - - - -
label | IP
label | - - - - - - - - -
text | Responsibility: Surveyor, SE/PE/SPE
checkpoint | 4.3 - Barrier Railing
label | Frequency: Where applicable
label | - - - - - - - - -
label | Acceptance Criteria: Where applicable.
label | Complete: Structural Steel Barrier Rail (Supply & Installation) ITP.
label | - - - - - - - - -
label | Reference Documents: IFC Drawings
label | - - - - - - - - -
label | Inspection / Test Method: Document Review
label | - - - - - - - - -
label | Record of Conformity: Structural Steel Barrier Rail (Supply & Installation) ITP
label | - - - - - - - - -
label | IP
label | - - - - - - - - -
text | Responsibility: Surveyor, SE/PE/SPE
checkpoint | 4.4 - As-built Survey
label | Frequency: Each element
label | - - - - - - - - -
label | Acceptance Criteria: Provide record of dimensional measurements to demonstrate concrete members comply with tolerances as per the table 610.462 (November 2018) or 610.472 (March/June 2019) as applicable to the element.
label | Attach: Survey As-builts / Survey Report
label | - - - - - - - - -
label | Reference Documents: IFC Drawings 610.47 (a) Table 610.472
label | - - - - - - - - -
label | Inspection / Test Method: Document Review
label | - - - - - - - - -
label | Record of Conformity: This ITP
label | - - - - - - - - -
label | IP
label | - - - - - - - - -
text | Responsibility: Surveyor, SE/PE/SPE
checkpoint | 4.5 - Non-conformance Report (NCR) Closure
label | Frequency: Once, prior to closure of this lot / element / Work area
label | - - - - - - - - -
label | Acceptance Criteria: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
label | - - - - - - - - -
label | Reference Documents: Fulton Hogan Quality Management Plan
label | - - - - - - - - -
label | Inspection / Test Method: Document Review
label | - - - - - - - - -
label | Record of Conformity: This ITP
label | - - - - - - - - -
label | HP*
label | - - - - - - - - -
text | Responsibility: SE/PE/SPE
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and verifies lot compliance with specifications.
text | Print Name:
text | Position:
date | Date:
date | Work Completed On
section | Lot Verification
checkpoint | Lot Verification.
select | Is the relevant RFI attached to the Lot? | YES, NO, N/A
select | Is the relevant NCR attached to the Lot? | YES, NO, N/A
select | Are any relevant Mails/ Transmittals attached to the Lot? | YES, NO, N/A
select | Lot verified By | Babak Rudd-Project Quality Manager, Abid Hameed (Area 1 Manager), Nicola Lodo (Area 2 Manager), Nicolas Terpstra (Delivery Manager),Other:
text | Other:
select | Lot Status | OUTSTANDING, CLOSED
date | Lot Closed On
text | comments
Note on B2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Checklist name must be different from the template name. Always use the value that Martin provides on the ticket.
Note on H2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Note the full template name being different from the truncated one used for the checklist itself.
Note on B8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Use the value supplied by Martin.
Note on B10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Martin will always provide the dropdown values needed for this. Only use the ones supplied.
Note on B11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Ditto, but for Activity. As before, only use the values that Martin provides on the ticket.
Note on B12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: No need to change either of these values unless Martin specifies that their packages need to be altered.
Note on B299: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: A checkpoint for Final Inspection is always the closing checkpoint under the final item in the ITP.
Note on B305: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Lot Verification always needs to be in its own standalone section.
Note on B306: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Not a typo. Make sure there's always a period (.) at the end of Lot Verification. This is needed to prevent display issues on the matrix due to name ambiguity (the matrix pulls section progress instead of checkpoint progress if there's no period).
Note on C307: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: No need to change these dropdown values unless specified to by Martin or any other QE from FH.