## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | INF-HSEQ CC0375-ITP-009 Unbound Flexible Pavement & Checklist- Rev.5 | itp |  |  |  | Yes | INF-HSEQ CC0375-ITP-009 Unbound Flexible Pavement & Checklist- Rev.5
section | 1.0 Preliminaries
checkpoint | 1.1 - Documentation
label | Ref docs - Drawings
label | Acceptance Criteria - Check that you have the latest site and engineering drawings BEFORE starting each task/set of tasks.
button | Acceptance | Yes,No,N/A
label | Key - S
label | UGL Key - S
label | SHL Key - S
checkpoint | 1.2 - Lot Traceability
label | Ref docs - Spec. 0161 Quality (Construction) [Cl 7.6]
label | Acceptance Criteria - Prepare a lot map for traceability of the work area
button | Acceptance | Yes,No,N/A
label | Key - S
label | UGL Key - S
label | SHL Key - S
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
bool | Lot map
checkpoint | 1.3 - Material Classification and Source
label | Ref docs - Spec. 1141 Flexible Pavements [Cl 2.3, 3.0]
label | Acceptance Criteria - Is the correct material being used?
label | ○ Has the material to be used been approved by UGL (Material certificates to be provided)?
label | HOLD POINT
label | Notice: 14 days before commencing
button | Acceptance | Yes,No,N/A
label | Please tick the appropriate box:
bool | DGB20
bool | DGS20
bool | _________
textbox
label | Key - H
label | UGL Key - H
label | SHL Key - H
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
bool | Material test certificates
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.4 - Set Out
label | Acceptance Criteria - Is the work area clearly pegged out for line and level?
button | Acceptance | Yes,No,N/A
label | Key - S
label | UGL Key - S
label | SHL Key - S
section | 2.0 Pavement construction
checkpoint | 2.1 - Delivery of Material
label | Ref docs - Spec. 1141 Flexible Pavements [Cl 4.2]
label | Acceptance Criteria - Inspection of delivered materials for approval
label | WITNESS POINT
label | Notice: Before placing
button | Acceptance | Yes,No,N/A
label | Key - W
label | UGL Key - W
label | SHL Key - W
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
bool | Delivery dockets
checkpoint | 2.2 - Stockpiling of Materials (if required)
label | Ref docs - Spec. 1141 Flexible Pavements [Cl 4.2]
label | Acceptance Criteria - Is the material being stored in an approved stockpile location?
label | ○ Stockpile foundation to be clear of vegetation and extraneous matter and shaped to form a crown to drain freely.
label | ○ Stockpile total height < 4m
label | ○ Shape of batter: Side slopes not greater than 1.5H:1.0V or less than 3.0H:1.0V
label | WITNESS POINT: Ongoing
button | Acceptance | Yes,No,N/A
label | Key - W
label | UGL Key - W
label | SHL Key - W
checkpoint | 2.3 - Spreading Material
label | Ref docs - Spec. 1141 Flexible Pavements [Cl 4.3]
label | Acceptance Criteria - Prior to spreading, previous layer to be inspected by the Superintendent for approval.
label | ○ Refer to ITP of previous Layer.
label | HOLD POINT
label | Notice: Prior to spreading material
button | Acceptance | Yes,No,N/A
label | Key - H
label | UGL Key - H
label | SHL Key - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.4 - Moisture
label | Ref docs - Spec. 1141 Flexible Pavements [Cl 4.3]
label | Acceptance Criteria - Has the material maintained at optimum moisture content (60 to 90% OMC), with additional water being added if required during compaction?
button | Acceptance | Yes,No,N/A
label | Key - S
label | UGL Key - S
label | SHL Key - S
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
bool | Test reports
checkpoint | 2.5 - Compaction
label | Ref docs - Spec. 1141 Flexible Pavements [Cl 4.4]
label | Acceptance Criteria - Is compacted layer thickness between 100-150mm?
label | ○ Has the layer been adequately compacted to a minimum relative compaction of 97%?
label | HOLD POINT
label | Notice: 1 working days after getting results
button | Acceptance | Yes,No,N/A
label | Key - H
label | UGL Key - H
label | SHL Key - H
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
bool | Test reports
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.6 - Removal & Replacement
label | Ref docs - Spec. 1141 Flexible Pavements [Cl 4.7]
label | Acceptance Criteria - Superintendent to determine the extent of any rejected pavement to be removed. Before replacing the material, area to be reinspected by the superintendent
label | HOLD POINT
label | Notice: 1 working day before next activity
button | Acceptance | Yes,No,N/A
label | Key - H
label | UGL Key - H
label | SHL Key - H
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
bool | As built reports
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.7 - Maintenance of Base
label | Ref docs - Spec. 1141 Flexible Pavements [Cl 4.8]
label | Acceptance Criteria - Finished surface of the base course must be maintained and appropriately drained until the wearing course is completed.
label | ○ Cover base course with primerseal within 7 days of acceptance unless agreed otherwise with the superintendent (see 1143 Sprayed Bituminous Surfacing)
label | ○ Non-essential plant to be restricted from using the pavement until primerseal is applied unless otherwise approved.
label | WITNESS POINT
label | Notice: within 7 days of acceptance
button | Acceptance | Yes,No,N/A
label | Key - W
label | UGL Key - W
label | SHL Key - W
section | 3.0 Conformance check
checkpoint | 3.1 - Pavement finish
label | Ref docs - Spec. 1141 Flexible Pavements [Cl 4.6]
label | Acceptance Criteria - Has the pavement course been finished to a smooth and uniform surface parallel with proposed finished wearing surface?
button | Acceptance | Yes,No,N/A
label | Key - S
label | UGL Key - S
label | SHL Key - S
checkpoint | 3.2 - Width and alignment
label | Ref docs - Spec. 1141 Flexible Pavements [Cl 4.6]
label | Acceptance Criteria - Is the pavement width and alignment within tolerance: 0mm to +100mm measured from the design centreline (limited to 50mm per side)
label | HOLD POINT
label | Notice: 1 working day before next activity
button | Acceptance | Yes,No,N/A
label | Key - H
label | UGL Key - H
label | SHL Key - H
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
bool | As built reports
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.3 - Surface level of pavement courses
label | Ref docs - Spec. 1141 Flexible Pavements [Cl 4.6]
label | Acceptance Criteria - Is the pavement surface level within the following tolerances:
label | ○ Layer Surface: 0mm to +10mm
label | ○ Top Base Layer adjacent to Kerb and gutter: ± 5mm from lip level of gutter less thickness of wearing course
label | ○ Surface deviation: ± 5mm from 3m straightedge laid in any direction, after trimming and immediately prior to seal
label | HOLD POINT
label | Notice: 1 working day before next activity
button | Acceptance | Yes,No,N/A
label | Key - H
label | UGL Key - H
label | SHL Key - H
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
bool | As built reports
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.4 - Acceptance and closure of non-conforming items
label | Ref docs - Spec. 0161 Quality [Cl 3.8]
label | Acceptance Criteria - NCRs to be opened for non-conforming items and closed prior to closing construction lot.
label | HOLD POINT
button | Acceptance | Yes,No,N/A
label | Key - H
label | UGL Key - H
label | SHL Key - H
holdpoint | AUTHORITY HOLDPOINT