## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | INF-HSEQ CC0375-ITP-010 Asphalt & Checklist - Rev.3 | itp |  |  |  | Yes | INF-HSEQ CC0375-ITP-010 Asphalt & Checklist - Rev.3
section | 1.0 Preliminaries
checkpoint | 1.1 - Documentation
label | Ref docs - Issued drawings / Site copy drawings
label | Acceptance Criteria - Check that you have the latest site and engineering drawings BEFORE starting each task/set of tasks.
button | Acceptance | Yes,No,N/A
label | Key - S
label | UGL Key - S
label | SHL Key - S
checkpoint | 1.2 - Determine lot size
label | Ref docs - Spec. 0161 Quality [Cl 7.8]
label | Acceptance Criteria - Lots to be broken up accordingly and outlined on a lot map
button | Acceptance | Yes,No,N/A
label | Key - S
label | UGL Key - S
label | SHL Key - S
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
bool | Lot map
checkpoint | 1.3 - Set out
label | Ref docs - Spec. 0161 Quality [Cl 3.13], Drawings
label | Acceptance Criteria - Has the pavement been set out by an accredited Surveyor?
label | ○ Set out comply with drawings?
button | Acceptance | Yes,No,N/A
label | Key - S
label | UGL Key - S
label | SHL Key - S
checkpoint | 1.4 - Mix design approval
label | Ref docs - Spec. 1144 Asphaltic Concrete [Cl 2.4]
label | Acceptance Criteria - Provide all mix designs. Mix design is to be assessed by the Superintendent for compliance.
label | ○ Mix design to be approved by Superintendent before use.
label | Notice: 14 working days before using mix
label | HOLD POINT
button | Acceptance | Yes,No,N/A
label | Key - H
label | UGL Key - H
label | SHL Key - H
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
bool | Mix design
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.5 - Tolerances of mix production
label | Ref docs - Spec. 1144 Asphaltic Concrete [Cl 3.1]
label | Acceptance Criteria - Is the Binder within 0.3% of total mix?
label | ○ Has the daily particle size distribution been within tolerance?
label | ○ Has the daily moisture content been within tolerance – not to exceed 0.5% on completion of mixing?
button | Acceptance | Yes,No,N/A
label | Key - S
label | UGL Key - S
label | SHL Key - S
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
bool | Test report
checkpoint | 1.6 - Production temperatures
label | Ref docs - Spec. 1144 Asphaltic Concrete [Cl 3.2]
label | Acceptance Criteria - Do the temperatures listed below comply with requirements for max. temperature?
label | – Class 170, Class 320, Class AR450 Bitumen delivered into mixer – 165ºC
label | – Class 600 Bitumen delivered into mixer – 175 ºC
label | – Aggregates before binder – 200 ºC
label | – Asphalt at discharge point – 175 ºC
button | Acceptance | Yes,No,N/A
label | Key - S
label | UGL Key - S
label | SHL Key - S
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
bool | Test report
checkpoint | 1.7 - Certification of specification Compliance
label | Acceptance Criteria - Has each delivery come with a certificate of compliance?
button | Acceptance | Yes,No,N/A
label | Key - S
label | UGL Key - S
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
bool | Certificate of compliance
section | 2.0 Preparation
checkpoint | 2.1 - Conformance of previous layer
label | Acceptance Criteria - Has the previous layer passed acceptance criteria? Refer to ITP of previous layer.
button | Acceptance | Yes,No,N/A
label | Key - S
label | UGL Key - S
label | SHL Key - S
checkpoint | 2.2 - Joints
label | Ref docs - Spec. 1144 Asphaltic Concrete [Cl 3.4]
label | Acceptance Criteria - Transverse joints shall be offset by not less than 2m in adjoining paver runs and from later to layer.
label | Longitudinal joints shall meet the following requirements:
label | – Wearing course joint coincide with location of intended traffic lane lines
label | – Intermediate and base course offset from layer to layer by not less than 150mm provided that no joint is placed directly below a trafficked wheel path
label | – Parallel to traffic lanes
label | ○ Location of planned joints is a Hold Point.
label | Notice: 7 working day before commencing
label | HOLD POINT
button | Acceptance | Yes,No,N/A
label | Key - H
label | UGL Key - H
label | SHL Key - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 - Prime application rate
label | Ref docs - Spec. 1144 Asphaltic Concrete [Cl 3.4]
label | Acceptance Criteria - Unless otherwise directed, tack coat is to be applied to provide a uniform application rate of residual binder of between 0.10L/m2 and 0.20L/m2
label | ○ Is the application rate for tack coat between the following?
label | 0.15 to 0.30 litres/m 2 (60% bitumen content)
label | 0.30 to 0.60 litres/ m 2 (30% bitumen content)
button | Acceptance | Yes,No,N/A
label | Key - S
label | UGL Key - S
label | SHL Key - S
checkpoint | 2.4 - Approval to proceed
label | Ref docs - Spec. 1144 Asphaltic Concrete [Cl 2.4]
label | Acceptance Criteria - Has approval to proceed been obtained from the Superintendent?
label | Notice: 7 working days before commencing production
label | HOLD POINT
button | Acceptance | Yes,No,N/A
label | Key - H
label | UGL Key - H
label | SHL Key - H
holdpoint | AUTHORITY HOLDPOINT
section | 3.0 Placement of Asphalt
checkpoint | 3.1 - Conditions for placing
label | Ref docs - Spec. 1144 Asphaltic Concrete [Cl 3.4]
label | Acceptance Criteria - Is the area essentially dry and free of surface water?
label | ○ Does the surface temperature meet requirements?
label | – Intermediate and base courses: 5ºC
label | – Wearing course: 10ºC
button | Acceptance | Yes,No,N/A
label | Key - S
label | UGL Key - S
label | SHL Key - S
checkpoint | 3.2 - Spreading
label | Ref docs - Drawings Spec. 1144 Asphaltic Concrete [Cl 3.4]
label | Acceptance Criteria - Has the asphalt been spread in layers at compacted thicknesses as per the drawings:
label | – Wearing Course: 40mm
label | – 7mm Primer Seal
label | ○ Has all asphalt been spread with a purpose designed asphalt paving machine to form a uniformly smooth asphalt mat?
label | ○ Does the width of a single paving run not exceed 6m?
button | Acceptance | Yes,No,N/A
label | Key - S
label | UGL Key - S
label | SHL Key - S
checkpoint | 3.3 - Compaction
label | Ref docs - Spec. 1144 Asphaltic Concrete [Cl 3.4, 3.5]
label | Acceptance Criteria - Uniformly compact asphalt to below requirements as soon as the asphalt has cooled sufficiently.
label | ○ Confirm Frequency of testing and target requirements
label | ○ 6 cores per lot
label | ○ 10 nuclear density tests per lot
label | Tested to the following criteria (acceptable values to be calculated bases off formula in standard):
label | – Density ratio greater than 94% for thickness less than 50mm
label | – Density ratio greater than 96% for thickness greater than 50mm
label | Notice: Progressive
label | HOLD POINT
button | Acceptance | Yes,No,N/A
label | Key - H
label | UGL Key - H
label | SHL Key - H
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
bool | Test reports
holdpoint | AUTHORITY HOLDPOINT
section | 4.0 Finishing
checkpoint | 4.1 - Surface finish
label | Ref docs - Spec. 1144 Asphaltic Concrete [Cl 3.5]
label | Acceptance Criteria - Asphalt shall be consistent and uniform?
label | ○ Top of asphalt shall be not more than 10mm above specified level?
label | ○ Asphalt against the kerb and channel shall be flush or not more than 5mm above the lip of the channel?
label | ○ Do no points on the finished surface lie more than below (medium to light traffic roads):
label | Parallel to centreline
label | – 7mm below a 3m straight edge for wearing course
label | Transverse to centreline
label | – 10mm below a 3m straight edge for wearing course
button | Acceptance | Yes,No,N/A
label | Key - S
label | UGL Key - S
label | SHL Key - S
checkpoint | 4.2 - Survey pickup (Top layer only, N/A for all intermediate layers)
label | Ref docs - Spec. 1144 Asphaltic Concrete [Cl 3.5]
label | Acceptance Criteria - Has the prepared layer been surveyed in accordance with and verifying specified requirements?
label | ○ The horizontal location of any point on the pavement not to vary by more than ± 50mm from the corresponding points shown on the documents, expect where alignment with existing is required.
button | Acceptance | Yes,No,N/A
label | Key - S
label | UGL Key - S
label | SHL Key - S
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
bool | As built reports