## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | INF-HSEQ CC0375-ITP-014 Piles with Checklist Rev.4 | itp |  |  |  | Yes | INF-HSEQ CC0375-ITP-014 Piles with Checklist Rev.4
section | 1.0 Preliminaries
checkpoint | 1.1 - Documentation
label | Ref docs - Issued drawings / Site copy drawings
label | Acceptance Criteria - Check that you have the latest site and engineering drawings BEFORE starting each task/set of tasks.
button | Acceptance | Yes,No,N/A
label | Key - S
label | UGL Key - S
checkpoint | 1.2 - Determine lot size
label | Acceptance Criteria - Lots to be broken up accordingly and outlined on a lot map
button | Acceptance | Yes,No,N/A
label | Key - S
label | UGL Key - S
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
bool | Lot map
checkpoint | 1.3 - Geotechnical Engineer
label | Ref docs - Spec. 0003 Piling [Cl 2.7.1]
label | Acceptance Criteria - Proposed Geotechnical Engineer holds correct qualifications and Experience.
label | ○ 5+ Years Geotechnical Experience including CFA Pile installation
button | Acceptance | Yes,No,N/A
label | Key - S
label | UGL Key - S
section | 2.0 Materials & Equipment
checkpoint | 2.1 - Boring machine
label | Ref docs - Spec. 0003 Piling [Cl 3.3.2]
label | Acceptance Criteria - Details of the boring machine and any other tools that may be required shall be provided for approval by the Superintendent
label | HOLD POINT
button | Acceptance | Yes,No,N/A
label | Key - H
label | UGL Key - H
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
bool | Plant documents
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 - Approval of Concrete Mix Design
label | Ref docs - Spec. 0003 Piling [Cl 3.1.2]
label | Acceptance Criteria - Concrete Mix Code: S40/10/220 – Special Mix
label | ○ Strength: 40MPa
label | ○ Agg Size: not greater than 18mm
label | ○ Slump: not greater than 220mm
label | ○ Required to achieve 25MPa @ 7 Days
label | HOLD POINT
button | Acceptance | Yes,No,N/A
label | Key - H
label | UGL Key - H
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
bool | Mix design
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 - Pile Cage & Spacers
label | Ref docs - Drawings
label | Acceptance Criteria - Certificate of Compliance for Pile Cage
label | ○ Cage Manufactured as per approved IFC Drawings and welding to approved weld procedure LOR-CJAUTO-12/20-250/500-1
label | ○ Site splice weld as required IAW approved weld procedure WPS-CSS-014
label | HOLD POINT
button | Acceptance | Yes,No,N/A
label | Key - H
label | UGL Key - H
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
bool | Material certificates and COC
bool | Site Daily Weld Repot
holdpoint | AUTHORITY HOLDPOINT
section | 3.0 Piling
checkpoint | 3.1 - Survey Setout
label | Ref docs - Spec. 0003 Piling [3.10], Drawings
label | Acceptance Criteria - A registered surveyor shall be used to accurately located all pile locations as shown on the drawings and specifications.
button | Acceptance | Yes,No,N/A
label | Key - S
label | UGL Key - S
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
bool | Survey Report
checkpoint | 3.2 - Concrete lines primed and in good order
label | Ref docs - Wagstaff WP-MS-09.3.07 [ Cl 6.2.1]
label | Acceptance Criteria - Inspect concrete liners have no damage and are primed correctly.
button | Acceptance | Yes,No,N/A
label | Key - S
label | UGL Key - S
checkpoint | 3.3 - Excavation of bore hole
label | Ref docs - Spec. 0003 Piling [Cl 3.3], Drawings
label | Acceptance Criteria - Verify: (via Pile Rig)
label | – Inclination. +/- 4%
label | – Diameter: 900mm
label | – Depth: Refer to drawings for min. depth into socket material
label | – The tolerances on the level of the bottom of the piles shall be +0, -100mm from the RL nominated on the drawings or as directed by the Superintendent
label | – Length of pile/pile liner shall not be less than total length shown on drawings
button | Acceptance | Yes,No,N/A
label | Key - S
label | UGL Key - S
label | SHL Key - W
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
bool | Pile Log Sheets
checkpoint | 3.4 - Excavation conformance
label | Ref docs - Drawings
label | Acceptance Criteria - Check dimensions and cover are within tolerance refer to below conformance check section for details. Correct toe level as per plan. Material encountered consistent with design. Softened soil shall be removed from the bottom of the drill holes.
button | Acceptance | Yes,No,N/A
label | Key - S
label | UGL Key - S
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
bool | Pile Log Sheets
checkpoint | 3.5 - Examination of borehole
label | Ref docs - Spec. 0003 Piling [Cl 3.4]
label | Acceptance Criteria - Boreholes excavations shall be inspected as the work proceeds. When the founding level as shown on the drawings or as otherwise directed has been reached, each hole will be subject to a visual examination (or other methods of examination) by a Geotechnical Engineer appointed by the superintendent.
label | ○ The Geotechnical Engineer will advise whether a satisfactory founding level exist or whether further excavation is required.
label | HOLD POINT
button | Acceptance | Yes,No,N/A
label | Key - H
label | UGL Key - H
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
bool | Geotechnical Engineer Sign Off Sheets
bool | Pile Log Sheets
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.6 - Concrete supply
label | Ref docs - Spec. 0003 Piling [3.9]
label | Acceptance Criteria - Verify:
label | Concrete mix
label | ○ 40 MPa 10mm 220mm TREMMIE [N545526]
label | ○ 65 MPa 10mm 220mm TREMMIE [N876626]
label | A concrete delivery docket to be supplied with each batch delivered.
button | Acceptance | Yes,No,N/A
label | Key - S
label | UGL Key - W
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
bool | Material dockets
bool | Concrete Pour Records
checkpoint | 3.7 - Concrete Sampling
label | Ref docs - Spec. 0003 Piling [3.9] Spec 0002 Concrete Supply, Construction and Grouting [10.2.3]
label | Acceptance Criteria - The nominal rate of sampling shall be taken after the concrete has been discharged at site prior to handling:
label | (a) Compressive strength (1 x 7 day and 2 x 28 day cylinders): One set per pour or as otherwise directed by Superintendent;
label | (b) Slump: One per batch of concrete
label | ○ Acceptance Testing shall be done at a NATA registered laboratory
button | Acceptance | Yes,No,N/A
label | Key - S
label | UGL Key - W
checkpoint | 3.8 - Concrete Placement
label | Ref docs - Spec. 0003 Piling [3.9]
label | Acceptance Criteria - All concrete shall be placed continuously and in the dry so as to ensure the exclusion of all harmful materials and provide a well-formed dense unit of full cross-section without voids or segregation.
label | ○ All concrete shall be placed by approved methods to limit free fall of concrete to a maximum of 3.0m
label | ○ Top of 3m of concrete shall be well compacted with a high-capacity vibrator with a min. diameter of 50mm
label | Notice: 1 working day prior to placing concrete for test pile
label | WITNESS POINT
button | Acceptance | Yes,No,N/A
label | Key - S
label | UGL Key - W
label | SHL Key - W
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
bool | Concrete Pour Records
checkpoint | 3.9 - Concrete testing
label | Ref docs - Drawings
label | Acceptance Criteria - Concrete test reports achieve design requirements
button | Acceptance | Yes,No,N/A
label | Key - S
label | UGL Key - S
label | SHL Key - R
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
bool | Test reports
checkpoint | 3.10 - Placement of reinforcement cage.
label | Ref docs - Spec. 0003 Piling [Cl. 3.2.2, 3.8], Drawings
label | Acceptance Criteria - Ensure that cage is clean and straight. Plunge the cage centrally to pile hole and ensure spacers are attached at correct locations.
label | ○ Reinforcement cages and embedment to conform with drawings and specification.
label | Notice: 1 working day prior to installation of each pile
label | WITNESS POINT
button | Acceptance | Yes,No,N/A
label | Key - S
label | UGL Key - W
label | SHL Key - W
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
bool | Pile Log Sheets
checkpoint | 3.11 - Concrete RL and depth
label | Ref docs - Drawings
label | Acceptance Criteria - Bored piers depth, size, position and concrete RL as per the Piling Pile Log Sheet and Drawings.
button | Acceptance | Yes,No,N/A
label | Key - S
label | UGL Key - S
label | SHL Key - R
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
bool | Pile Log Sheets
section | 4.0 Integrity Testing - Dynamic
checkpoint | 4.1 - Pile Testing
label | Ref docs - AS 2159:2009, Spec. 0003 Piling [Cl 3.13 (5)], WP-MS-09.3.30 Low Strain Dynamic Testing
label | Acceptance Criteria - Minimum 5% sample size
label | ○ Pile Integrity testing (PIT) as per Wagstaff Procedure WP-MS-09.3.30 Low Strain Dynamic Testing.
label | Notice – 3 working days to commence testing
label | HOLD POINT
button | Acceptance | Yes,No,N/A
label | Key - H
label | UGL Key - H
label | SHL Key - R
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
bool | Integrity Test Reports
holdpoint | AUTHORITY HOLDPOINT
section | 5.0 Conformance check
checkpoint | 5.1 - Survey
label | Ref docs - Spec. 0003 Piling [3.10]
label | Acceptance Criteria - All piles shall be constructed within the tolerance specified below:
label | – The centreline at the top of the piles shall be within 50mm of the specified position
label | – The inclination of the pile shaft shall be within ± 4% of the nominated inclination
label | – The tolerance on the level of the top of the piles shall be ± 10mm
label | – The tolerances on the level of the bottom of the piles shall be +0, -100mm from the RL nominated on the drawings or as directed by the Superintendent
label | – Piles shall be constructed to the minimum diameters specified on the drawings
label | – Length of pile/pile liner shall not be less than total length shown on drawings
label | – Maximum bow of pile shall be 0.1% of length
label | – The projection of the pile cage bars above the cut-off shall be ± 25mm from the nominated level
button | Acceptance | Yes,No,N/A
label | Key - H
label | UGL Key - H
label | SHL Key - H
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
bool | As-Built Surveys
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.2 - Acceptance and closure of non-conforming items
label | Ref docs - Spec. 0161 Quality [CL 3.8]
label | Acceptance Criteria - NCRs to be opened for non-conforming items and closed prior to closing construction lot.
label | HOLD POINT
button | Acceptance | Yes,No,N/A
label | Key - H
label | UGL Key - H
label | SHL Key - H
holdpoint | AUTHORITY HOLDPOINT