## Folder Structure
Site QA
Common Areas
Building B - Hauraki
| Level 2 |  | Hobbies Lounge WC splashback | Common area Checklist
Building D - Ponui
| Level 3 | Zone 2&3 | Wind & Lift Lobby | Common area Checklist
| Level 3 | Zone 2,3&4 | Activities 1/ Activities 2/ Dinning/ Nurse Station | Common area Checklist
| Level 3 | Zone 3&4 | ACC WC1&2 | Toilet Checklist
| Level 4 | Zone 3 | ACC WC 3 | Toilet Checklist
Building E - Rangitoto
| Level 3 | Zone 2 | Hair & Beauty | Common area Checklist
| Level 3 | Zone 3 | SPA Therapy | Common area Checklist
| Level 3 | Zone 2 | Foyer 01 | Common area Checklist
| Level 3 | Zone 2 | Foyer 02 | Common area Checklist
| Level 3 | Zone 2 | Café | Common area Checklist
| Level 3 | Zone 4 | Pool Refershment Unit | Common area Checklist
| Level 4 | Zone 2 | Bar | Common area Checklist
| Level 4 | Zone 2 | Lounge Fireplace | Common area Checklist
| Level 4 | Zone 2 | Lounge seating | Common area Checklist
| Level 3 | Zone 1-3 | Female/Male Toilet, ACC WC | Toilet Checklist
| Level 4 | Zone 1-3 | Female/Male Toilet, ACC WC | Toilet Checklist
| Level 3 | Zone 3 | ACC Shower, Shower | Toilet Checklist
Apartments
Building A - Waiheke
Level 2
|  |  | AP201W | Apartment Checklist
|  |  | AP202W | Apartment Checklist
Level 3
|  |  | AP301W | Apartment Checklist
|  |  | AP302W | Apartment Checklist
|  |  | AP303W | Apartment Checklist
|  |  | AP304W | Apartment Checklist
|  |  | AP305W | Apartment Checklist
|  |  | AP306W | Apartment Checklist
|  |  | AP307W | Apartment Checklist
|  |  | AP308W | Apartment Checklist
|  |  | AP309W | Apartment Checklist
|  |  | AP310W | Apartment Checklist
|  |  | AP311W | Apartment Checklist
|  |  | AP312W | Apartment Checklist
|  |  | AP313W | Apartment Checklist
|  |  | AP314W | Apartment Checklist
Level 4
|  |  | AP401W | Apartment Checklist
|  |  | AP402W | Apartment Checklist
|  |  | AP403W | Apartment Checklist
|  |  | AP404W | Apartment Checklist
|  |  | AP405W | Apartment Checklist
|  |  | AP406W | Apartment Checklist
|  |  | AP407W | Apartment Checklist
|  |  | AP408W | Apartment Checklist
|  |  | AP409W | Apartment Checklist
|  |  | AP410W | Apartment Checklist
|  |  | AP411W | Apartment Checklist
|  |  | AP412W | Apartment Checklist
|  |  | AP413W | Apartment Checklist
|  |  | AP414W | Apartment Checklist
Level 5
|  |  | AP501W | Apartment Checklist
|  |  | AP502W | Apartment Checklist
|  |  | AP503W | Apartment Checklist
|  |  | AP504W | Apartment Checklist
|  |  | AP505W | Apartment Checklist
|  |  | AP506W | Apartment Checklist
|  |  | AP507W | Apartment Checklist
|  |  | AP508W | Apartment Checklist
|  |  | AP509W | Apartment Checklist
|  |  | AP510W | Apartment Checklist
|  |  | AP511W | Apartment Checklist
|  |  | AP512W | Apartment Checklist
Building B - Hauraki
Level 2
|  |  | AP201H | Apartment Checklist
|  |  | AP202H | Apartment Checklist
|  |  | AP203H | Apartment Checklist
|  |  | AP204H | Apartment Checklist
Level 3
|  |  | AP301H | Apartment Checklist
|  |  | AP302H | Apartment Checklist
|  |  | AP303H | Apartment Checklist
|  |  | AP304H | Apartment Checklist
|  |  | AP305H | Apartment Checklist
|  |  | AP306H | Apartment Checklist
|  |  | AP307H | Apartment Checklist
|  |  | AP308H | Apartment Checklist
Level 4
|  |  | AP401H | Apartment Checklist
|  |  | AP402H | Apartment Checklist
|  |  | AP403H | Apartment Checklist
|  |  | AP404H | Apartment Checklist
|  |  | AP405H | Apartment Checklist
|  |  | AP406H | Apartment Checklist
|  |  | AP407H | Apartment Checklist
|  |  | AP408H | Apartment Checklist
Level 5
|  |  | AP501H | Apartment Checklist
|  |  | AP502H | Apartment Checklist
|  |  | AP503H | Apartment Checklist
|  |  | AP504H | Apartment Checklist
Building D - Ponui
| Level 3 |  | CS301P | Apartment Checklist
|  |  | CS302P | Apartment Checklist
|  |  | CS303P | Apartment Checklist
|  |  | CS304P | Apartment Checklist
|  |  | CS305P | Apartment Checklist
|  |  | CS306P | Apartment Checklist
|  |  | CS307P | Apartment Checklist
|  |  | CS308P | Apartment Checklist
|  |  | CS309P | Apartment Checklist
|  |  | CS310P | Apartment Checklist
|  |  | CS311P | Apartment Checklist
|  |  | CS312P | Apartment Checklist
|  |  | CS313P | Apartment Checklist
|  |  | CS314P | Apartment Checklist
|  |  | CS315P | Apartment Checklist
|  |  | CS316P | Apartment Checklist
|  |  | CS317P | Apartment Checklist
|  |  | CS318P | Apartment Checklist
|  |  | CS319P | Apartment Checklist
Level 4
|  |  | RM401P | Apartment Checklist
|  |  | RM402P | Apartment Checklist
|  |  | RM403P | Apartment Checklist
|  |  | RM404P | Apartment Checklist
|  |  | RM405P | Apartment Checklist
|  |  | RM406P | Apartment Checklist
|  |  | RM407P | Apartment Checklist
|  |  | RM408P | Apartment Checklist
|  |  | RM409P | Apartment Checklist
|  |  | RM410P | Apartment Checklist
|  |  | RM411P | Apartment Checklist
|  |  | RM412P | Apartment Checklist
|  |  | RM413P | Apartment Checklist
|  |  | RM414P | Apartment Checklist
|  |  | RM415P | Apartment Checklist
|  |  | RM416P | Apartment Checklist
|  |  | RM417P | Apartment Checklist
|  |  | RM418P | Apartment Checklist
|  |  | RM419P | Apartment Checklist
|  |  | RM420P | Apartment Checklist
|  |  | RM421P | Apartment Checklist
|  |  | RM422P | Apartment Checklist
|  |  | RM423P | Apartment Checklist
|  |  | RM424P | Apartment Checklist
|  |  | RM425P | Apartment Checklist
|  |  | RM426P | Apartment Checklist
|  |  | RM427P | Apartment Checklist
|  |  | RM428P | Apartment Checklist
|  |  | RM429P | Apartment Checklist
|  |  | RM430P | Apartment Checklist
Level 5
|  |  | SA501P | Apartment Checklist
|  |  | SA502P | Apartment Checklist
|  |  | SA503P | Apartment Checklist
|  |  | SA504P | Apartment Checklist
|  |  | SA505P | Apartment Checklist
|  |  | SA506P | Apartment Checklist
|  |  | SA507P | Apartment Checklist
|  |  | SA508P | Apartment Checklist
|  |  | SA509P | Apartment Checklist
|  |  | SA510P | Apartment Checklist
|  |  | SA511P | Apartment Checklist
|  |  | SA512P | Apartment Checklist
|  |  | SA513P | Apartment Checklist
|  |  | SA514P | Apartment Checklist
|  |  | SA515P | Apartment Checklist
|  |  | SA516P | Apartment Checklist
|  |  | SA517P | Apartment Checklist
|  |  | SA518P | Apartment Checklist
|  |  | SA519P | Apartment Checklist
Level 6
|  |  | SA601P | Apartment Checklist
|  |  | SA602P | Apartment Checklist
|  |  | SA603P | Apartment Checklist
|  |  | SA604P | Apartment Checklist
|  |  | SA605P | Apartment Checklist
|  |  | SA606P | Apartment Checklist
|  |  | SA607P | Apartment Checklist
|  |  | SA608P | Apartment Checklist
|  |  | SA609P | Apartment Checklist
|  |  | SA610P | Apartment Checklist
|  |  | SA611P | Apartment Checklist
|  |  | SA612P | Apartment Checklist
|  |  | SA613P | Apartment Checklist
|  |  | SA614P | Apartment Checklist
|  |  | SA615P | Apartment Checklist
|  |  | SA616P | Apartment Checklist
|  |  | SA617P | Apartment Checklist
|  |  | SA618P | Apartment Checklist
|  |  | SA619P | Apartment Checklist
Level 7
|  |  | SA701P | Apartment Checklist
|  |  | SA702P | Apartment Checklist
|  |  | SA703P | Apartment Checklist
|  |  | SA704P | Apartment Checklist
|  |  | SA705P | Apartment Checklist
|  |  | SA706P | Apartment Checklist
|  |  | SA707P | Apartment Checklist
|  |  | SA708P | Apartment Checklist
|  |  | SA709P | Apartment Checklist
|  |  | SA710P | Apartment Checklist
|  |  | SA711P | Apartment Checklist
|  |  | SA712P | Apartment Checklist
|  |  | SA713P | Apartment Checklist
|  |  | SA714P | Apartment Checklist
|  |  | SA715P | Apartment Checklist
|  |  | SA716P | Apartment Checklist
|  |  | SA717P | Apartment Checklist
Building E - Rangitoto
Level 5
|  |  | AP501R | Apartment Checklist
|  |  | AP502R | Apartment Checklist
|  |  | AP503R | Apartment Checklist
|  |  | AP504R | Apartment Checklist
|  |  | AP505R | Apartment Checklist
|  |  | AP506R | Apartment Checklist
|  |  | AP507R | Apartment Checklist
Level 6
|  |  | AP601R | Apartment Checklist
|  |  | AP602R | Apartment Checklist
|  |  | AP603R | Apartment Checklist
|  |  | AP604R | Apartment Checklist
|  |  | AP605R | Apartment Checklist
|  |  | AP606R | Apartment Checklist
|  |  | AP607R | Apartment Checklist
Level 7
|  |  | AP701R | Apartment Checklist
|  |  | AP702R | Apartment Checklist
|  |  | AP703R | Apartment Checklist
|  |  | AP704R | Apartment Checklist
|  |  | AP705R | Apartment Checklist
|  |  | AP706R | Apartment Checklist
|  |  | AP707R | Apartment Checklist
Level 8
|  |  | AP801R | Apartment Checklist
|  |  | AP802R | Apartment Checklist
|  |  | AP803R | Apartment Checklist
|  |  | AP804R | Apartment Checklist
|  |  | AP805R | Apartment Checklist
Balcony
Building D - Ponui
| Level 4 |  |  | Balcony Checklist
| Level 5 |  |  | Balcony Checklist
| Level 6 |  |  | Balcony Checklist
| Level 7 |  |  | Balcony Checklist
Building E - Rangitoto
| Level 4 |  |  | Balcony Checklist
| Level 5 |  |  | Balcony Checklist
| Level 6 |  |  | Balcony Checklist
| Level 7 |  |  | Balcony Checklist
| Level 8 |  |  | Balcony Checklist

## Bathroom Checklists
checklist | Bathroom Checklist
Section | Substrate inspection
checkpoint
Substrate has no damages and sound
Floor grinded or free from any latent, contaminants or cracks
Wall Square and Plumb
Wall stopped and lined
Section | Screed works to shower floor
Checkpoint
Multiprime and A38 Slurry applied prior screeding as a bonding agent
A38 Screed to selected area
FFL and screed falls to follow construction drawings
No lose sand on top of screed
Section | Soundproofing
Primer Applied
PE Foam tape to all relevant substrate
Installed Impactamatt soundproofing using DS70
Section | Leveling after Underfloor Heating Mat being installed
Checkpoint | LQ92 / Ardex NA poured to selected area
Underfloor Heating Mat being covered properly and no cable exposed
Section | Waterproofing
Checkpoint | Primer to all relevant substrate
Apply Ardex STB to all changes plane, penetration, and floor waste area
WPM 002 waterproofing 2 coats applied
Water test performed and passed
Section | Tiling
Checkpoint | Setting out tiles according to construction drawing / Site confirmation
Primer applied prior to tiling
Full coverage of tiles with adhesive
Tile lippiness checked and to acceptable standard
Finishing trims & transition bars edge alignment
Skirting Tile Installed at 150mm
Section | Grout and Silicone
Checkpoint | Tiles adhesive cured and clean properly
Grout work properly into all joint (floor)
Silicon applied and tolled to a neat continuously finish
Section | Final check
Checkpoint | Tiling Completed
Handover

## Laundry Checklists
checklist | Laundry Checklist
Section | Substrate inspection
checkpoint
Substrate has no damages and sound
Floor grinded or free from any latent, contaminants or cracks
Wall Square and Plumb
Wall stopped and lined
Section | Screed / Leveling works to floor
Checkpoint
Multiprime and A38 Slurry applied prior screeding as a bonding agent
A38 Screed to selected area
No lose sand on top of screed
LQ92 / Ardex NA to selected area
Section | Soundproofing
Primer Applied
PE Foam tape to all relevant substrate
Installed Impactamatt soundproofing using DS70
Section | Waterproofing
Checkpoint | Primer to all relevant substrate
Apply Ardex STB to all changes plane, penetration, and floor waste area
WPM 002 waterproofing 2 coats applied
Water test performed and passed
Section | Tiling
Checkpoint | Setting out tiles according to construction drawing / Site confirmation
Primer applied prior to tiling
Full coverage of tiles with adhesive
Tile lippiness checked and to acceptable standard
Finishing trims & transition bars edge alignment
Skirting Tile Installed at 150mm
Section | Grout and Silicone
Checkpoint | Tiles adhesive cured and clean properly
Grout work properly into all joint (floor)
Silicon applied and tolled to a neat continuously finish
Section | Final check
Checkpoint | Tiling Completed
Handover

## Balcony Checklist
checklist | Balcony Checklist
section | Substrate Inspection
checkpoint | All prior works done
section | Balcony Deck Tiling
checkpoint | Setting out tiles according to construction drawing / Site confirmation
Nurajack NM used with Nurajack Maxi Leveller, Spacer and appropriated shims
Tile lippiness checked and to acceptable standard
Tile interlocked with each others, stable and not moving/rocking
Section | Final check and Sign off
Checkpoint | Tiling Completed
Sign off and Handover