## ITP-xxx
|  |  | Inspection and Test Plan - Control and Supervision of the Works | [7 empty] | Document # ITP-003
[11 empty] | Revision : 0 | Date : 13/11/2023
Client: |  | Ballarat City Council |  | Construction Process: |  | Prepared by: |  | Reviewed by : |  |  | Approved by :
Project: |  | Market Street, Ballarat Central Streetscape Redevelopment Works |  | Sub-base Construction |  | Name: | Rakib Hossain | Name: | Hugh Burns |  | Name: | Andrew Cotter
Contract No: |  | Contract No. 2022/23-183 |  | Specifications: VicRoads Specification Section 173 , 304, 812; VR Code of Practice RC 500.02, Project Specification
|  |  |  | Structure / Component: Pavement |  | Signed : | R.H. | Signed : | H.B. |  | Signed : | A.C.
|  |  |  | Location: Market Street (Red Boundary) |  | Date : | 2023-11-13 | Date : | 2023-11-13 |  | Date : | 2023-11-14
Lot No: |  |  | Lot Details: | [5 empty] | Lot Size/ Quantity:
Item | Task/Activity Description |  | Inspection / Controls and Verification Detail |  |  |  |  | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility | Checked by:
No. |  |  | Frequency | Acceptance Criteria | Reference Documents | Inspection / Test Method | Record of conformity |  | Project Engineer Site Engineer Superintendent Surveyor Foreman | Client | Fulton Hogan | FH's Sub-contractor | Date
1 | Preliminary Works
1.1 | Check for correct documentation |  | Prior to commencing any activity | Ensure that the most recent copy of the design drawings are used and have been Issued for Construction (IFC). | Drawings and drawing registers | Visual inspection | This ITP signed | WP | Site Engineer / Site Foreman | N/A |  | N/A
1.2 | Material Mix Design |  | Prior to commencing any activity | Material proposed for import as sub-base material meets the requirements of VR Section 812. Obtain material compliance data from the supplier. | Cl 812.04 RC 500.02 | Document Review | Mix Design VicRoads Approval | HP* | Site Engineer | N/A |  | N/A
1.3 | Implementation of all measures and controls |  | Prior to commencing any activity | All necessary measures and controls are being implemented, that is: SMP, PMP, EMP, QMP, TMP and SEQ documentation. | SMP, PMP, EMP, QMP, TMP and SEQ documentation. | Visual Inspection | This ITP signed | HP* | Site Engineer / Site Foreman | N/A |  | N/A
2 | Construction Works
2.1 | Transverse Joints |  | Check prior to placing material | Material should be spread to minimize number of joints Transverse joints shall be offset from one layer to next by not less than 2 metres | Cl.304.08 (a) Cl.304.08 (c) | Visual Inspection | This ITP signed off | IP | Site Engineer / Site Foreman | N/A |  | N/A
2.2 | Longitudinal Joints |  | Check prior to placing material | Material should be spread to minimise number of joints Longitudinal joints offset from one layer to next by not less than 150mm Longitudinal joints to be located within 300mm from planned traffic lane lines or within 300 mm of the centre of a traffic lane. | Cl.304.07 (a) Cl.304.08 (d) Cl.304.08 (e) | Visual Inspection | This ITP signed off | IP | Site Engineer / Site Foreman | N/A |  | N/A
2.3 | Lot Size |  | Check prior to placing material | A single lot shall be considered a single layer of 4000m2 or one days production in a single layer, whichever is lesser. | . Cl.304.09 (b)(ii) Table 304.121 | Site Inspection | Signed ITP | IP | Site Engineer / Site Foreman | N/A |  | N/A
2.4 | Layer Thickness |  | Each Lot | Sub-base shall be constructed to a maximum compacted thickness of 200mm and minimum thickness of 4 times the nominal size of the material. | Cl 304.07b | Site Inspection | Signed ITP | IP | Site Engineer | N/A |  | N/A
2.5 | Proof Rolling |  | Proof Roll each layer | No visible deformation or springing in presence of Superintendent's Rep.( Cl 173) Plant to comply with requirements of Cl 173.03. Static > 12T Pneumatic > 20T | 173.03 | Visual inspection | This ITP signed off | HP/ WP | Site Engineer / Site Foreman / Superintendent |  |  | N/A
3 | Testing Requirements
3.1 | Determine Testing Scale & Initial testing frequency |  | Prior to Testing | Initially test every lot until 3 consecutive lots of like material and/or work have achieved the standards specified in Clauses 304.09. and 304.12. If no failures, Reduced Frequency applies as specified in Table 304.121. | Cl.304.09 Cl.304.12 Table 304.121 | Document Review/ Site Inspection | Signed ITP | AP | Project Engineer | N/A |  | N/A
3.2 | Compaction Testing |  | Every Lot Every second lot (reduced frequency) | Modified Maximum Density Ratio of not less than 97% Class 3 FCR for pavement under wombat crossing as per Contract Drawings sheet 6 of 25 | Contract Drawings (sheet 06 of 25) | Test point | This ITP signed off; Test reports | TP | Site Engineer | N/A |  | N/A
Final Inspection
The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
| Print Name: | Rakib Hossain | Position: | Graduate Engineer | Signature: |  |  |  |  | Date: / /
|  | Hugh Burns |  | Project Manager
Legend
HP | Hold Point | Work shall not proceed past the HP until released by the Superintendent |  |  | IP | Inspection point |  | Formal Inspection to be done and recorded
HP* | FH Hold Point | Work shall not proceed past the HP* until released by FH |  |  | TP | Test Point |  | Product compliance test to be undertaken and recorded/reported
WP | Witness Point | An inspection which must be witnessed by the Superintendent |  |  | SCP | Survey conformance point |  | A qualified surveyor to check product/section/structure and report
AP | Approval Point | Written or verbal approval given by the Superintendent
Note on K16: Rodrigo Anchico: Write "N/A" to disable the cell.