## ITP-xxx
|  |  | Inspection and Test Plan - Control and Supervision of the Works | [7 empty] | Document # ITP-007
[11 empty] | Revision : | 2018-11-13
Client: |  | Ballarat City Council |  | Construction Process: |  | Prepared by: |  | Reviewed by : |  |  | Approved by :
Project: |  | Market Street Redevelopment |  | Sign Installation & Pavement Markings |  | Name: | Rakib Hossain | Name: | Hugh Burns |  | Name: | Andrew Cotter
Contract No: |  | 2022/23-183 |  | Specifications: VicRoads Specifications Section 721, Contract Specification
|  |  |  | Structure / Component: Sign Installation & Pavement Markings |  | Signed : | R.H | Signed : | H.B |  | Signed :
|  |  |  | Location: Market Street |  | Date : | 2023-11-13 | Date : |  |  | Date :
Lot No: |  |  | Lot Details: | [5 empty] | Lot Size/ Quantity:
Item | Task/Activity Description |  | Inspection / Controls and Verification Detail |  |  |  |  | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility | Checked by:
No. |  |  | Frequency | Acceptance Criteria | Reference Documents | Inspection / Test Method | Record of conformity |  | Project Engineer Site Engineer Superintendent Surveyor Foreman | Client | Fulton Hogan | FH's Sub-contractor | Date
1 | General
1.1 | Check for correct documentation |  | Prior to commencing any activity | Ensure that all employees and subcontractors are: - using the correct and complete set of drawings -all drawings are the latest revision | Drawings and drawing registers | Visual inspection | This ITP signed | HP* | Site Engineer / Site Foreman | N/A
1.2 | Line marking conformance |  | Prior to commencing any activity | Materials to be used must conform with the specification | Cl 721.A05 IFC Drawing | Record Review | This ITP signed | IP | Contractor Representative | N/A
1.3 | Site Preparation |  | Prior to commencing any activity | Removal of any existing unsound, obsolete or redundant pavement markings | Cl 721.A06 | Visual inspection | This ITP signed | IP | Contractor Representative | N/A
1.4 | Set-out of Pavement Markings |  | Prior to commencing any activity | Pavement markings to set-out in accordance with IFC Drawings | Cl 721.A09 | Visual inspection | This ITP signed | IP | Contractor Representative | N/A
2 | Pavement Markings
2.1 | Acceptance of Work |  | Each Lot as required | Where removal of unsuitable pavement marking is required, the method of removal shall be subject to the approval of the Superintendent before removal works commence. | 721.A12 | Visual Inspection | This ITP signed | HP | Site Engineer / Site Foreman / Superintendent |  |  | N/A
2.2 | Position of Markings |  | Each Lot as required | All markings are to be set out in accordance with the dimensions and spacings as required by the appropriate standard in Clause 721.A03. Painting/application of material shall not commence until the Superintendent has inspected the set out and given consent to proceed, unless an exemption has been granted in writing by the Superintendent. | 721.B05 | Visual Inspection | This ITP Signed | HP | Site Engineer / Site Foreman / Superintendent |  |  | N/A
2.3 | Installation of Linemarking |  | During Construction | Line marking installed as per the IFC drawings | IFC Drawings | Visual inspection | This ITP Signed | IP* | Site Engineer / Site Foreman | N/A
3 | Sign Installation
3.1 | Completion Inspection |  | Each Lot as required | Completed marking shall be uniform in appearance, texture, width and thickness and the surface shall be free from blister, air bubbles, tears, lumps, overlaps, unbeaded areas, tyre marks or other defects. Edges and cuts-offs shall be neat and sharp , and there shall be no visible run-off, overspray, dribbles, splash or spillage on to the surrounding area, or on to parked or passing vehicles. |  | Visual inspection | This ITP Signed | WP | Site Engineer / Site Foreman / Superintendent |  |  | N/A
The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
| Print Name: |  | Position: |  | Signature: |  |  |  |  | Date: / /
Legend
HP | Hold Point | Work shall not proceed past the HP until released by the Superintendent |  |  | IP | Inspection point |  | Formal Inspection to be done and recorded
HP* | FH Hold Point | Work shall not proceed past the HP* until released by FH |  |  | TP | Test Point |  | Product compliance test to be undertaken and recorded/reported
WP | Witness Point | An inspection which must be witnessed by the Superintendent |  |  | SCP | Survey conformance point |  | A qualified surveyor to check product/section/structure and report
AP | Approval Point | Written or verbal approval given by the Superintendent
Note on K16: Rodrigo Anchico: Write "N/A" to disable the cell.