## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-001 - Pre-commencement of works Rev. 3 | itp |  |  |  |  | ITP-001 - Pre-commencement of works Rev. 3
section | 1 - Construction - General
checkpoint | 1.1 - Design Drawings
label | Frequency - Prior to commencing any activity
label | Acceptance Criteria - Ensure that the most recent copy of the design drawings are used and have been Issued for Construction (IFC).
label | Reference Documents - IFC Drawings
label | Inspection / Test Method - Visual inspection
label | Record of conformity - ITP Signed
label | IHP
label | Responsibility - Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 1.2 - Service Locating / Permits
label | Frequency - Prior to commencing any activity
label | Acceptance Criteria - Lodge DBYD application prior to works commence and obtain any relevant permits applicable to the works. DBYD to be renewed every 30 days. All nominated/aﬀected services from the DBYD application must be located/potholed prior to commencement of works. Works identified within the vicinity of the powerlines to ensure distance exclusions are followed & spotter used, if required.
label | Reference Documents - DBYD Information
label | Inspection / Test Method - Visual inspection
label | Record of conformity - ITP Signed
label | IHP
label | Responsibility - Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 1.3 - Commencement of work
label | Frequency - Prior to commencing any activity
label | Acceptance Criteria - The Contractor shall not commence work on site before the following documents have been submitted to the Superintendent and the Superintendent has authorised release of the Hold Point:
label | (a) Public Liability and WorkSafe insurance conforming with the requirements of the General Conditions of Contract
label | (b) Health and Safety Co-ordination Plan
label | (c) Environmental Management Plan for initial works
label | (d) Project Management Plan
label | (e) Quality Management Plan
label | (f) Safety Management Plan
label | Reference Documents - VicRoads Standard Section 160, 166, 167, 168 & 176
label | Inspection / Test Method - Visual Inspection
label | Record of conformity - ITP Signed
label | HP
label | Responsibility - Site Engineer
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 2 - Traffic Management
checkpoint | 2.1 - Submission of the TMP to the Superintendent
label | Frequency - Prior to commencing any activity
label | Acceptance Criteria - The Traffic Management Plan shall not be implemented as a Traffic Guidance Scheme until the Superintendent has completed the review of the final Traffic Management Plan and released this Hold Point.
label | Reference Documents - TMP VicRoads Standard Section 166.08
label | Inspection / Test Method - Visual Inspection
label | Record of conformity - ITP Signed
label | HP
label | Responsibility - Site Engineer
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 - Detours and Side Tracks
label | (a) Side Tracks
label | (b) Detours
label | Frequency - Prior to commencing any activity
label | Acceptance Criteria - Traffic shall not be diverted on to any side track until permission to use such side track has been given by the Superintendent.
label | – Permission has been given by the Superintendent and Ballarat City Council.
label | ○ Where VicRoads as well as the Contractor has some responsibility for the restoration of any detours or sidetracks, the Contractor shall not commence any restoration work until the Contractor has submitted details of the work to be undertaken to the Superintendent for review.
label | Reference Documents - VicRoads Standard Section 166.17 (a) & (b)
label | Inspection / Test Method - Inspection
label | Record of conformity - ITP Signed
label | HP
label | Responsibility - Site Engineer
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 - Traffic Management Documentation
label | Frequency - Prior to commencing any activity
label | Acceptance Criteria - Ensure all TGS plans have been reviewed and deemed acceptable for the project. Obtain MoA approval for any road impacts or closures.
label | Reference Documents - VicRoads Standard Section 166
label | Inspection / Test Method - Visual Inspection
label | Record of conformity - ITP Signed
label | IHP
label | Responsibility - Site Engineer / Site Foreman
date | Date Completed:
section | 3 - Health and Safety
checkpoint | 3.1 - Occupational Health & Safety Management Implementation
label | Frequency - Prior to commencing any activity
label | Acceptance Criteria - Signed Safe Work Method Statement (SWMS) in place. All personnel including Subcontractors must complete Site Induction prior to arriving on site.
label | Reference Documents - Site Specific SWMS
label | Inspection / Test Method - Inspection
label | Record of conformity - ITP Signed SWMS
label | IHP
label | Responsibility - Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 3.2 - Health and Safety Co-ordination Plan and Declaration
label | Frequency - Prior to commencing any activity
label | Acceptance Criteria - The Contractor shall, not less than 5 working days prior to commencing work, submit to the Superintendent:
label | (a) a reviewed Health and Safety Co-ordination Plan; and
label | (b) a signed HSCP Declaration by an OH&S consultant/advisor that the HSCP meets all the necessary requirements. The Declaration shall be in accordance with the proforma included in the appendices of this Specification.
label | (c) a completed VicRoads HSCP Checklist with Contractor’s responses for each checklist item requirement.
label | Reference Documents - VicRoads Standard Section 168.05 (c)
label | Inspection / Test Method - Submission
label | Record of conformity - ITP Signed, Safety Management Plan
label | HP
label | Responsibility - Site Engineer
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 4 - Environmental Management
checkpoint | 4.1 - Environmental Impacts, Aspects & Risk Assessment Implementation
label | Frequency - Prior to commencing any activity
label | Acceptance Criteria - All environmental controls implemented in accordance with the Contract Environmental Impacts, Aspects & Risk Assessment.
label | Reference Documents - EMP & A&I
label | Inspection / Test Method - Visual Inspection
label | Record of conformity - ITP Signed
label | IHP
label | Responsibility - Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 4.2 - Environmental Management Plans
label | Frequency - Prior to commencing any activity
label | Acceptance Criteria - The Contractor shall submit to the Superintendent for review an Environmental Management Plan not less than 2 weeks prior to the commencement of work. Work shall not commence until:
label | – the Superintendent is satisfied that the Plan meets the requirements of this specification; and
label | – the controls detailed in the Plan are implemented; and
label | – the Superintendent has authorised release of the Hold Point.
label | – Limit of works identified in applicable SWMS.
label | Reference Documents - VicRoads Standard Section 176.A3, VicRoads Standard Section 177.A3
label | Inspection / Test Method - Submission
label | Record of conformity - EMP, ITP Signed
label | HP
label | Responsibility - Site Engineer
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.3 - Flora and Fauna
label | Frequency - Prior to commencing any activity
label | Acceptance Criteria - Prior to removing any vegetation or habitat, the Contractor shall arrange an on-site inspection with the Superintendent and other relevant authorities to conﬁrm and clearly identify and mark trees, vegetation or habitat to be removed. Any removal shall be consistent with the Contract drawings and any relevant permits and shall fence and sign all sites nominated as No-Go Zones.
label | Reference Documents - VicRoads Standard Section 176.I1, VicRoads Standard Section 177.I1(c)
label | Inspection / Test Method - Visual Inspection
label | Record of conformity - ITP Signed, Relevant permits, No Go Zone Signage
label | HP
label | Responsibility - Site Engineer
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.4 - Erosion and Sediment Control
label | Frequency - Prior to commencing any activity if applicable
label | Acceptance Criteria - The Contractor shall provide the necessary environmental controls as nominated on the approved Environmental Management Plan and identified on site.
label | Reference Documents - VicRoads Standard Section 177.D1(c)
label | Inspection / Test Method - Visual Inspection
label | Record of conformity - ITP Signed
label | IHP
label | Responsibility - Site Engineer / Site Foreman
date | Date Completed:
section | 5 - Stakeholder and Community Engagement
checkpoint | 5.1 - Residents have been informed
label | Frequency - Prior to commencing any activity
label | Acceptance Criteria - Residents impacted by construction works are to be notified by letter drop of the construction taking place, the timeframe of the works and information on how the works will affect them.
label | Reference Documents - Letterdrop
label | Inspection / Test Method - Visual Inspection
label | Record of conformity - ITP Signed
label | HP*
label | Responsibility - Site Engineer
date | Date Completed:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | Print Name:
text | Position:
date | Work Completed On:
date | Date:
checklist | ITP-002 - Stormwater Drainage Red Boundary Rev. 3 | itp |  |  |  |  | ITP-002 - Stormwater Drainage Red Boundary Rev. 3
section | 1 - Preliminary Works
checkpoint | 1.1 - Check for correct documentation
label | Frequency - Prior to commencing any activity
label | Acceptance Criteria - Ensure that all employees and subcontractors are using the correct and complete set of IFC Drawings.
label | Reference Documents - IFC Drawings
label | Inspection / Test Method - Visual inspection
label | Record of conformity - ITP Signed
label | IHP
label | Responsibility - Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 1.2 - Implementation of all measures and controls
label | Frequency - Prior to commencing any activity
label | Acceptance Criteria - Ensure all relevant project documentation has been submitted and approved by Superintendent including SMP, PMP, EMP, QMP, TMP and SEQ documentation.
label | Reference Documents - SMP, PMP, EMP, QMP, TMP & SEQ
label | Inspection / Test Method - Visual Inspection
label | Record of conformity - ITP Signed
label | HP
label | Responsibility - Site Engineer/ Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.3 - Purchase and delivery of pre-cast drainage components
label | Frequency - Each Delivery
label | Acceptance Criteria - Precast materials to be used for construction have been inspected and are free from defects or damage.
label | Reference Documents - VicRoads Standard Section 701.05
label | Inspection / Test Method - Visual Inspection
label | Record of conformity - ITP Signed
label | WP
label | Responsibility - Site Engineer
date | Date Completed:
checkpoint | 1.5 - Backfill material Classification
label | Frequency - Prior to start
label | Acceptance Criteria - Approved compacted backfill within bedding zone to be 20mm Class 3 Fine Crushed Rock as nominated on the IFC Design Drawings
label | Reference Documents - Dwg No. 982RD-06 Sheet 6 Note 1
label | Inspection / Test Method - Verify
label | Record of conformity - Test Reports from supplier
label | TP
label | Responsibility - Site Engineer
date | Date Completed:
checkpoint | 1.6 - Mortar material classification
label | Frequency - Prior to start
label | Acceptance Criteria - Mortar used in the laying of box culvert sections or as jointing for pipes shall comply with the requirements of clause 610.32.
label | Reference Documents - VicRoads Standard Section 701.09 (e)
label | Inspection / Test Method - Verify
label | Record of conformity - Test Reports from supplier
label | TP
label | Responsibility - Site Engineer
date | Date Completed:
section | 2 - Construction Works
checkpoint | 2.1 - Excavation Permit
label | Frequency - Each lot
label | Acceptance Criteria - An excavation permit must be issued prior to any excavation commencing. Plant and equipment shall be appropriate for the task. Excavation operations shall not disturb areas outside the limit of excavation.
label | Reference Documents - Excavation permit
label | Inspection / Test Method - Verify
label | Record of conformity - ITP Signed
label | IHP
label | Responsibility - Site Engineer
date | Date Completed:
checkpoint | 2.12 - Conformity with Drawings
label | Frequency - Prior to Excavation
label | Acceptance Criteria - Prior to commencement of excavation for the pits and drainage lines the Contractor shall conﬁrm the position of all drainage components with the Superintendent. Unless specified otherwise the tolerance on location of pipes compared to the design or a change to the design notified in accordance with this clause shall be:
label | (a) offset of entry pits required to match lines of kerbs or barriers ±20 mm
label | (b) plan location of pits other than offsets to kerb lines or barriers ±100 mm
label | (c) invert level of pipes at pits ±50 mm
label | (d) departure from design grade of pipe runs ±10 mm in 10 m provided minimum grade is not less than 1:250
label | Reference Documents - VicRoads Standard Section 701.09
label | Inspection / Test Method - Visual Inspection
label | Record of conformity - ITP Signed
label | HP
label | Responsibility - Site Engineer/ Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.13 - Excavation
label | Frequency - Each Trench
label | Acceptance Criteria - For pipe culverts, the width of trench at and below the level of the top of the pipe shall be such that the horizontal clearance from the outside of the pipe to the wall of the trench is within the limits Min 300mm and Max. 600mm.
label | Reference Documents - VicRoads Standard Section Table 701.151 Dwg No. 982RD-06 Sheet 6
label | Inspection / Test Method - Visual Inspection
label | Record of conformity - ITP Signed
label | HP
label | Responsibility - Site Engineer/ Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.14 - Compact base of trench
label | Frequency - Each Trench
label | Acceptance Criteria - The base of the trench shall be compacted to refusal using mechanical plant.
label | Reference Documents - VicRoads Standard Section 701.15
label | Inspection / Test Method - Visual Inspection
label | Record of conformity - ITP Signed
label | WP
label | Responsibility - Site Engineer
date | Date Completed:
checkpoint | 2.15 - Placement of Bedding Material
label | Frequency - Each Trench
label | Acceptance Criteria - Bedding material shall be compacted to no less than the below thickness:
label | – 100mm where D < 1500mm
label | – 150mm where D > 1500mm
label | ○ where D is the nominal pipe diameter or culvert width.
label | Reference Documents - Dwg No. 982RD-06 Sheet 6
label | Inspection / Test Method - Visual Inspection
label | Record of conformity - ITP Signed
label | WP
label | Responsibility - Site Engineer
date | Date Completed:
checkpoint | 2.16 - Laying of Pipes
label | Frequency - Each Line
label | Acceptance Criteria - Laying of pipes shall not commence until the Contractor has verified that pipe bedding complies with the lines and levels of the design drawings and that pipes are not damaged and comply with the requirements of clause 701.04 and Clause 701.05 respectively.
label | Reference Documents - VicRoads Standard Section 701.17
label | Inspection / Test Method - Visual Inspection
label | Record of conformity - ITP Signed
label | IHP
label | Responsibility - Site Engineer
date | Date Completed:
checkpoint | 2.17 - Jointing Pipe Sections
label | Frequency - Each Line
label | Acceptance Criteria - Join pipes with rubber rings in accordance with manufacturer's instructions, check that the rings are clean and undisturbed. Any disturbed rings are to be cleaned and reassembled
label | Reference Documents - VicRoads Standard Section 701.18
label | Inspection / Test Method - Visual Inspection
label | Record of conformity - ITP Signed
label | WP
label | Responsibility - Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 2.18 - Jointing to Pits
label | Frequency - Each Pit
label | Acceptance Criteria - The joints between various components such as drainage pits, access chambers and pipes shall be made watertight using a cementitious mortar in accordance with the requirements of clause 610.33.
label | Reference Documents - VicRoads Standard Section 705.15
label | Inspection / Test Method - Visual Inspection
label | Record of conformity - ITP Signed
label | WP
label | Responsibility - Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 2.19 - Place & compact backfill material over pipes
label | Frequency - Each Lot
label | Acceptance Criteria - Unless the pipe is installed through an existing paved area, selected and ordinary backﬁll shall be placed as follows under, around, and above the culvert after the sections are bedded and compacted as speciﬁed in Clause 701.15.
label | (i) Culvert Under Area not to be Paved
label | ○ The trench shall be backﬁlled with selected backﬁll material to a level 0.3 m above the top of the culvert and with ordinary backﬁll material above that level.
label | (ii) Culvert under area not to be paved
label | ○ The trench shall be backfilled with selected backfill material to a level 0.3 m above the top of the culvert and with ordinary backfill material above that level.
label | Reference Documents - VicRoads Standard Section 701.19 Dwg No. 982RD-06 Sheet 6
label | Inspection / Test Method - Visual Inspection
label | Record of conformity - ITP Signed
label | IHP
label | Responsibility - Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 2.20 - Place & compact backfill material around pits
label | Frequency - Each Pit
label | Acceptance Criteria - Backfilling around drainage pits shall be placed in layers not exceeding 300 mm loose thickness and compacted to refusal using handheld mechanical equipment
label | Reference Documents - VicRoads Standard Section 705.18
label | Inspection / Test Method - Visual Inspection
label | Record of conformity - ITP Signed
label | WP
label | Responsibility - Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 2.21 - Backfilling with cement stabilised sand
label | Frequency - Each Trench
label | Acceptance Criteria - Where approval is given from superintendent, culverts in trenches may be backfilled to half the pipe diameter or box culvert height with 3% stabilised sand with a water content sufficient to ensure penetration beneath the pipe or box culvert invert without leaving free surface water.
label | Reference Documents - VicRoads Standard Section 701.19 (c)
label | Inspection / Test Method - Visual Inspection
label | Record of conformity - ITP Signed
label | WP
label | Responsibility - Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 2.22 - Step Irons & Ladders
label | Frequency - Each Pit
label | Acceptance Criteria - Drainage pits greater than 1.0 m deep shall be fitted with step irons or ladders in accordance with AS 1657 and this Section.
label | Reference Documents - VicRoads Standard Section 705.12
label | Inspection / Test Method - Visual Inspection
label | Record of conformity - ITP Signed
label | WP
label | Responsibility - Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 2.23 - Construction Tolerances
label | Frequency - Each Lot
label | Acceptance Criteria - The tolerances listed in Clause 610.47 are the allowable deviations of the finished product from the dimensions shown on the drawings. These tolerances will be a basis for acceptance of the work.
label | Reference Documents - VicRoads Standard Section 705.19
label | Inspection / Test Method - Visual Inspection
label | Record of conformity - ITP Signed
label | WP
label | Responsibility - Site Engineer / Site Foreman
date | Date Completed:
section | 3 - Testing & Completion
checkpoint | 3.1 - Compaction and moisture content of backfill & bedding material
label | Frequency - Each Lot
label | Acceptance Criteria - The Contractor shall test the bedding and backfill material at a frequency as shown in Table 701.291 to ensure that all materials comply with the specified requirements.
label | Reference Documents - VicRoads Standard Section Table 701.291
label | Inspection / Test Method - Verify
label | Record of conformity - Test Reports
label | TP
label | Responsibility - Site Engineer
date | Date Completed:
checkpoint | 3.2 - CCTV inspection
label | Frequency - Each Lot
label | Acceptance Criteria - Unless approved otherwise by the Superintendent, all drainage lines constructed beneath pavements shall be inspected, after completion of earthworks to subgrade level and prior to construction of pavement layers, by an independent testing organisation using closed circuit television (CCTV). Reporting of the CCTV inspections shall be in accordance with WSA 05 2013 – Conduit Inspection Reporting Code of Australia, published by Water Services Association of Australia.
label | Reference Documents - VicRoads Standard Section 701.3
label | Inspection / Test Method - Visual inspection
label | Record of conformity - CCTV Report
label | HP
label | Responsibility - Site Engineer/ Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.3 - Repairs
label | Frequency - Each Lot
label | Acceptance Criteria - No repairs shall be undertaken without the Superintendent’s approval of the repair materials and procedures.
label | Reference Documents - VicRoads Standard Section 701.31
label | Inspection / Test Method - Verify
label | Record of conformity - ITP Signed
label | IP
label | Responsibility - Site Engineer
date | Date Completed:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | Print Name:
text | Position:
date | Work Completed On:
date | Date:
checklist | ITP-003a - Sub-Base Construction Wombat Crossing - Red Boundary | itp |  |  |  |  | ITP-003a - Sub-Base Construction Wombat Crossing - Red Boundary
section | 1 - Preliminary Works
checkpoint | 1.1 - Check for correct documentation
label | Frequency - Prior to commencing any activity
label | Acceptance Criteria - Ensure that the most recent copy of the design drawings are used and have been Issued for Construction (IFC).
label | Reference Documents - Drawings and drawing registers
label | Inspection / Test Method - Visual inspection
label | Record of conformity - This ITP signed
label | WP
label | Responsibility - Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 1.2 - Material Mix Design
label | Frequency - Prior to commencing any activity
label | Acceptance Criteria - Material proposed for import as sub-base material meets the requirements of VR Section 812. Obtain material compliance data from the supplier.
label | Reference Documents - Cl 812.04 RC 500.02
label | Inspection / Test Method - Document Review
label | Record of conformity - Mix Design VicRoads Approval
label | HP*
label | Responsibility - Site Engineer
date | Date Completed:
checkpoint | 1.3 - Implementation of all measures and controls
label | Frequency - Prior to commencing any activity
label | Acceptance Criteria - All necessary measures and controls are being implemented, that is: SMP, PMP, EMP, QMP, TMP and SEQ documentation.
label | Reference Documents - SMP, PMP, EMP, QMP, TMP and SEQ documentation.
label | Inspection / Test Method - Visual Inspection
label | Record of conformity - This ITP signed
label | HP*
label | Responsibility - Site Engineer / Site Foreman
date | Date Completed:
section | 2 - Construction Works
checkpoint | 2.1 - Transverse Joints
label | Frequency - Check prior to placing material
label | Acceptance Criteria - Material should be spread to minimize number of joints. Transverse joints shall be offset from one layer to next by not less than 2 metres.
label | Reference Documents - Cl.304.08 (a), Cl.304.08 (c)
label | Inspection / Test Method - Visual Inspection
label | Record of conformity - This ITP signed off
label | IP
label | Responsibility - Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 2.2 - Longitudinal Joints
label | Frequency - Check prior to placing material
label | Acceptance Criteria - Material should be spread to minimise number of joints. Longitudinal joints offset from one layer to next by not less than 150mm Longitudinal joints to be located within 300mm from planned traffic lane lines or within 300 mm of the centre of a traffic lane.
label | Reference Documents - Cl.304.07 (a), Cl.304.08 (d), Cl.304.08 (e)
label | Inspection / Test Method - Visual Inspection
label | Record of conformity - This ITP signed off
label | IP
label | Responsibility - Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 2.3 - Lot Size
label | Frequency - Check prior to placing material
label | Acceptance Criteria - A single lot shall be considered a single layer of 4000m2 or one days production in a single layer, whichever is lesser.
label | Reference Documents - Cl.304.09 (b)(ii) Table 304.121
label | Inspection / Test Method - Site Inspection
label | Record of conformity - Signed ITP
label | IP
label | Responsibility - Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 2.4 - Layer Thickness
label | Frequency - Each Lot
label | Acceptance Criteria - Sub-base shall be constructed to a maximum compacted thickness of 200mm and minimum thickness of 4 times the nominal size of the material.
label | Reference Documents - Cl 304.07b
label | Inspection / Test Method - Site Inspection
label | Record of conformity - Signed ITP
label | IP
label | Responsibility - Site Engineer
date | Date Completed:
checkpoint | 2.5 - Proof Rolling
label | Frequency - Proof Roll each layer
label | Acceptance Criteria - No visible deformation or springing in presence of Superintendent's Rep.( Cl 173) Plant to comply with requirements of Cl 173.03.
label | Static > 12T
label | ○ Pneumatic > 20TNo visible deformation or springing in presence of Superintendent's Rep.( Cl 173) Plant to comply with requirements of Cl 173.03.
label | Static > 12T
label | ○ Pneumatic > 20T
label | Reference Documents - 173.03
label | Inspection / Test Method - Visual inspection
label | Record of conformity - This ITP signed off
label | HP/ WP
label | Responsibility - Site Engineer / Site Foreman / Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 3 - Testing Requirements
checkpoint | 3.1 - Determine Testing Scale & Initial testing frequency
label | Frequency - Prior to Testing
label | Acceptance Criteria - Initially test every lot until 3 consecutive lots of like material and/or work have achieved the standards specified in Clauses 304.09. and 304.12. If no failures, Reduced Frequency applies as specified in Table 304.121.
label | Reference Documents - Cl.304.09, Cl.304.12, Table 304.121
label | Inspection / Test Method - Document Review/ Site Inspection
label | Record of conformity - Signed ITP
label | AP
label | Responsibility - Project Engineer
date | Date Completed:
checkpoint | 3.2 - Compaction Testing
label | Frequency - Every Lot, Every second lot (reduced frequency)
label | Acceptance Criteria - Modified Maximum Density Ratio of not less than 97% Class 3 FCR for pavement under wombat crossing as per Contract Drawings sheet 6 of 25
label | Reference Documents - Contract Drawings (sheet 06 of 25)
label | Inspection / Test Method - Test point
label | Record of conformity - This ITP signed off; Test reports
label | TP
label | Responsibility - Site Engineer
date | Date Completed:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | Print Name:
text | Position:
date | Work Completed On:
date | Date:
checklist | ITP-003b - Sub-Base Construction Deep Lift Asphalt - Red Boundary | itp |  |  |  |  | ITP-003b - Sub-Base Construction Deep Lift Asphalt - Red Boundary
section | 1 - Preliminary Works
checkpoint | 1.1 - Check for correct documentation
label | Frequency - Prior to commencing any activity
label | Acceptance Criteria - Ensure that the most recent copy of the design drawings are used and have been Issued for Construction (IFC).
label | Reference Documents - Drawings and drawing registers
label | Inspection / Test Method - Visual inspection
label | Record of conformity - This ITP signed
label | WP
label | Responsibility - Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 1.2 - Material Mix Design
label | Frequency - Prior to commencing any activity
label | Acceptance Criteria - Material proposed for import as sub-base material meets the requirements of VR Section 812. Obtain material compliance data from the supplier.
label | Reference Documents - Cl 812.04, RC 500.02
label | Inspection / Test Method - Document Review
label | Record of conformity - Mix Design VicRoads Approval
label | HP*
label | Responsibility - Site Engineer
date | Date Completed:
checkpoint | 1.3 - Implementation of all measures and controls
label | Frequency - Prior to commencing any activity
label | Acceptance Criteria - All necessary measures and controls are being implemented, that is: SMP, PMP, EMP, QMP, TMP and SEQ documentation.
label | Reference Documents - SMP, PMP, EMP, QMP, TMP and SEQ documentation.
label | Inspection / Test Method - Visual Inspection
label | Record of conformity - This ITP signed
label | HP*
label | Responsibility - Site Engineer / Site Foreman
date | Date Completed:
section | 2 - Construction Works
checkpoint | 2.1 - Transverse Joints
label | Frequency - Check prior to placing material
label | Acceptance Criteria - Material should be spread to minimize number of joints. Transverse joints shall be offset from one layer to next by not less than 2 metres.
label | Reference Documents - Cl.304.08 (a), Cl.304.08 (c)
label | Inspection / Test Method - Visual Inspection
label | Record of conformity - This ITP signed off
label | IP
label | Responsibility - Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 2.2 - Longitudinal Joints
label | Frequency - Check prior to placing material
label | Acceptance Criteria - Material should be spread to minimise number of joints. Longitudinal joints offset from one layer to next by not less than 150mm Longitudinal joints to be located within 300mm from planned traffic lane lines or within 300 mm of the centre of a traffic lane.
label | Reference Documents - Cl.304.07 (a), Cl.304.08 (d), Cl.304.08 (e)
label | Inspection / Test Method - Visual Inspection
label | Record of conformity - This ITP signed off
label | IP
label | Responsibility - Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 2.3 - Lot Size
label | Frequency - Check prior to placing material
label | Acceptance Criteria - A single lot shall be considered a single layer of 4000m2 or one days production in a single layer, whichever is lesser.
label | Reference Documents - . Cl.304.09 (b)(ii) Table 304.121
label | Inspection / Test Method - Site Inspection
label | Record of conformity - Signed ITP
label | IP
label | Responsibility - Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 2.4 - Layer Thickness
label | Frequency - Each Lot
label | Acceptance Criteria - Sub-base shall be constructed to a maximum compacted thickness of 200mm and minimum thickness of 4 times the nominal size of the material.
label | Reference Documents - Cl 304.07b
label | Inspection / Test Method - Site Inspection
label | Record of conformity - Signed ITP
label | Signed ITP
label | Responsibility - Site Engineer
date | Date Completed:
checkpoint | 2.5 - Proof Rolling
label | Frequency - Proof Roll each layer
label | Acceptance Criteria - No visible deformation or springing in presence of Superintendent's Rep.( Cl 173) Plant to comply with requirements of Cl 173.03.
label | ○ Static > 12T
label | ○ Pneumatic > 20T
label | Reference Documents - 173.03
label | Inspection / Test Method - Visual inspection
label | Record of conformity - This ITP signed off
label | HP/ WP
label | Responsibility - Site Engineer / Site Foreman / Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 3 - Testing Requirements
checkpoint | 3.1 - Determine Testing Scale & Initial testing frequency
label | Frequency - Prior to Testing
label | Acceptance Criteria - Initially test every lot until 3 consecutive lots of like material and/or work have achieved the standards specified in Clauses 304.09. and 304.12. If no failures, Reduced Frequency applies as specified in Table 304.121.
label | Reference Documents - Cl.304.09, Cl.304.12, Table 304.121
label | Inspection / Test Method - Document Review/ Site Inspection
label | Record of conformity - Signed ITP
label | AP
label | Responsibility - Project Engineer
date | Date Completed:
checkpoint | 3.2 - Compaction Testing
label | Frequency - Every Lot, Every second lot (reduced frequency)
label | Acceptance Criteria - Standard Dry Density (SDD) of not less than 98% for existing material to be stabilised with 3% lime & 3% sand, Minimum Density Ratio of 96% of Class 2 FCR as per Contract Drawings sheet 6 of 25
label | Reference Documents - Contract Drawings (sheet 06 of 25)
label | Inspection / Test Method - Test point
label | Record of conformity - This ITP signed off; Test reports
label | TP
label | Responsibility - Site Engineer
date | Date Completed:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | Print Name:
text | Position:
date | Work Completed On:
date | Date:
checklist | ITP-003c - Sub-Base Construction Footpath - Red Boundary | itp |  |  |  |  | ITP-003c - Sub-Base Construction Footpath - Red Boundary
section | 1 - Preliminary Works
checkpoint | 1.1 - Check for correct documentation
label | Frequency - Prior to commencing any activity
label | Acceptance Criteria - Ensure that the most recent copy of the design drawings are used and have been Issued for Construction (IFC).
label | Reference Documents - Drawings and drawing registers
label | Inspection / Test Method - Visual inspection
label | Record of conformity - This ITP signed
label | WP
label | Responsibility - Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 1.2 - Material Mix Design
label | Frequency - Prior to commencing any activity
label | Acceptance Criteria - Material proposed for import as sub-base material meets the requirements of VR Section 812. Obtain material compliance data from the supplier.
label | Reference Documents - Cl 812.04 RC 500.02
label | Inspection / Test Method - Document Review
label | Record of conformity - Mix Design VicRoads Approval
label | HP*
label | Responsibility - Site Engineer
date | Date Completed:
checkpoint | 1.3 - Implementation of all measures and controls
label | Frequency - Prior to commencing any activity
label | Acceptance Criteria - All necessary measures and controls are being implemented, that is: SMP, PMP, EMP, QMP, TMP and SEQ documentation.
label | Reference Documents - SMP, PMP, EMP, QMP, TMP and SEQ documentation.
label | Inspection / Test Method - Visual Inspection
label | Record of conformity - This ITP signed
label | HP*
label | Responsibility - Site Engineer / Site Foreman
date | Date Completed:
section | 2 - Construction Works
checkpoint | 2.1 - Transverse Joints
label | Frequency - Check prior to placing material
label | Acceptance Criteria - Material should be spread to minimize number of joints. Transverse joints shall be offset from one layer to next by not less than 2 metres.
label | Reference Documents - Cl.304.08 (a), Cl.304.08 (c)
label | Inspection / Test Method - Visual Inspection
label | Record of conformity - This ITP signed off
label | IP
label | Responsibility - Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 2.2 - Longitudinal Joints
label | Frequency - Check prior to placing material
label | Acceptance Criteria - Material should be spread to minimise number of joints. Longitudinal joints offset from one layer to next by not less than 150mm Longitudinal joints to be located within 300mm from planned traffic lane lines or within 300 mm of the centre of a traffic lane.
label | Reference Documents - Cl.304.07 (a), Cl.304.08 (d), Cl.304.08 (e)
label | Inspection / Test Method - Visual Inspection
label | Record of conformity - This ITP signed off
label | IP
label | Responsibility - Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 2.3 - Lot Size
label | Frequency - Check prior to placing material
label | Acceptance Criteria - A single lot shall be considered a single layer of 4000m2 or one days production in a single layer, whichever is lesser.
label | Reference Documents - Cl.304.09 (b)(ii), Table 304.121
label | Inspection / Test Method - Site Inspection
label | Record of conformity - Signed ITP
label | IP
label | Responsibility - Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 2.4 - Layer Thickness
label | Frequency - Each Lot
label | Acceptance Criteria - Sub-base shall be constructed to a maximum compacted thickness of 200mm and minimum thickness of 4 times the nominal size of the material.
label | Reference Documents - Cl 304.07b
label | Inspection / Test Method - Site Inspection
label | Record of conformity - Signed ITP
label | IP
label | Responsibility - Site Engineer
date | Date Completed:
checkpoint | 2.5 - Proof Rolling
label | Frequency - Proof Roll each layer
label | Acceptance Criteria - No visible deformation or springing in presence of Superintendent's Rep.( Cl 173) Plant to comply with requirements of Cl 173.03.
label | ○ Static > 12T
label | ○ Pneumatic > 20T
label | Reference Documents - 173.03
label | Inspection / Test Method - Visual inspection
label | Record of conformity - This ITP signed off
label | HP/ WP
label | Responsibility - Site Engineer / Site Foreman / Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 3 - Testing Requirements
checkpoint | 3.1 - Determine Testing Scale & Initial testing frequency
label | Frequency - Prior to Testing
label | Acceptance Criteria - Initially test every lot until 3 consecutive lots of like material and/or work have achieved the standards specified in Clauses 304.09. and 304.12. If no failures, Reduced Frequency applies as specified in Table 304.121.
label | Reference Documents - Cl.304.09, Cl.304.12, Table 304.121
label | Inspection / Test Method - Document Review/ Site Inspection
label | Record of conformity - Signed ITP
label | AP
label | Responsibility - Project Engineer
date | Date Completed:
checkpoint | 3.2 - Compaction Testing
label | Frequency - Every Lot, Every second lot (reduced frequency)
label | Acceptance Criteria - Modified Maximum Dry Density of not less than 97% Class 3 FCR, MMDD of not less than 98% fir Class 2 FCR as per Contract Drawings sheet 6 of 25
label | Reference Documents - Contract Drawings (sheet 06 of 25)
label | Inspection / Test Method - Test point
label | Record of conformity - This ITP signed off; Test reports
label | TP
label | Responsibility - Site Engineer
date | Date Completed:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | Print Name:
text | Position:
date | Work Completed On:
date | Date:
checklist | ITP-004 - Kerb and Channel Red Boundary | itp |  |  |  |  | ITP-004 - Kerb and Channel Red Boundary
section | 1 - Preliminary Works
checkpoint | 1.1 - Check for correct documentation
label | Frequency - Prior to commencing any activity
label | Acceptance Criteria - Ensure that all employees and subcontractors are:
label | – using the correct and complete set of drawings
label | – all drawings are the latest revision
label | Reference Documents - Drawings and drawing registers
label | Inspection / Test Method - Visual inspection
label | Record of conformity - ITP Signed
label | HP*
label | Responsibility - Site Engineer/ Site Foreman
date | Date Completed:
checkpoint | 1.2 - Implementation of all measures and controls
label | Frequency - Prior to commencing any activity
label | Acceptance Criteria - All necessary measures and controls are being implemented, that is: SMP, PMP, EMP, QMP, TMP and SEQ documentation.
label | Reference Documents - SMP, PMP, EMP, QMP, TMP and SEQ documentation.
label | Inspection / Test Method - Visual inspection
label | Record of conformity - ITP Signed
label | IP
label | Responsibility - Site Engineer/ Site Foreman
date | Date Completed:
checkpoint | 1.3 - Mix Design
label | Frequency - Prior to commencing any activity
label | Acceptance Criteria - Approved VR mix design to be used. Details to be sent to the superintendent for approval prior to commencing works.
label | Reference Documents - AS 1379, Cl 703.07, 703.05, 703.23
label | Inspection / Test Method - Verify
label | Record of conformity - ITP Signed, Mix design approval
label | HP*/ WP
label | Responsibility - Site Engineer/ Superintendent
date | Date Completed:
section | 2 - Construction Works
checkpoint | 2.1 - Setting Out
label | Frequency - Prior to start
label | Acceptance Criteria - Set out work in accordance with drawings. The superintendent will review and confirm set out. The alignment and survey/level pegs will be indicated to the Contractor on the Site by the Superintendent prior to the commencement of work. No survey/level pegs to be removed by any persons until completion of works.
label | Reference Documents - Cl 703.17
label | Inspection / Test Method - Verify
label | Record of conformity - ITP Signed
label | HP
label | Responsibility - Site Engineer/ Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 - Temporary Drainage Provisions
label | Frequency - If Required
label | Acceptance Criteria - If obstructing waterways, culverts or channels, temporary diversion of discharge of drainage and stormwater to be in place.
label | Reference Documents - Cl 703.18
label | Inspection / Test Method - Visual inspection
label | Record of conformity - ITP Signed
label | WP
label | Responsibility - Site Engineer/ Site Foreman
date | Date Completed:
checkpoint | 2.3 - Bedding
label | Frequency - Each lot
label | Acceptance Criteria - All bedding material shall conform with the requirements of sections 812 or 820 for crushed rock and crushed concrete respectively. Unless otherwise stated, 20mm Class 3 or 4 bedding shall be used and compacted to a thickness of not less than 100mm. Bedding shall be trimmed to appropriate levels, moistened as necessary, and be firmly compacted.
label | Reference Documents - Cl 703.21
label | Inspection / Test Method - Visual inspection
label | Record of conformity - ITP Signed
label | WP
label | Responsibility - Site Engineer/ Superintendent
date | Date Completed:
checkpoint | 2.4 - Pre-concrete check
label | Frequency - Each lot
label | Acceptance Criteria - Bedding shall be moist but shall have no free water on the surface. Concrete shall not be placed when the air temperature measured at the point of placement is >35°C or <5°C. Temperature of concrete, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C. Formwork - Prior to placing concrete in an earth excavation, formwork shall be erected so that fresh concrete is not placed directly against the sides of the excavation. Concrete extrusion machines have minimum cement content of 320kg/m3.
label | Reference Documents - Cl 703.08, 610.17(a)(b)(c), 703.12
label | Inspection / Test Method - Verify
label | Record of conformity - ITP Signed
textbox | Ambient Temperature |  |  | °C
textbox | Concrete Temperature |  |  | °C
label | HP*/ WP
label | Responsibility - Site Engineer/ Superintendent
date | Date Completed:
checkpoint | 2.5 - Kerb Concrete Mixture/Strength
label | Frequency - Each Lot
label | Acceptance Criteria - Traffic Routes – a minimum of, or equivalent to, 320 kg of cementitious material or geopolymer binder per cubic metre of concrete
label | ○ Local Streets – a minimum of, or equivalent to, 280 kg of cementitious material or geopolymer binder per cubic metre of concrete
label | Reference Documents - Cl 703.05(b)
date | Date Completed:
checkpoint | 2.5 - Concrete Placement
label | Frequency - Each lot
label | Acceptance Criteria - Concrete is to be fed to extrusion machine at a uniform rate. Concrete is to be satisfactorily compacted so that finished surfaces are free from surface pitting larger than 5mm diameter, honey combing or faulty patches
label | Reference Documents - Cl 703.23
label | Inspection / Test Method - Site Inspection
label | Record of conformity - ITP Signed
label | IP
label | Responsibility - Site Engineer
date | Date Completed:
checkpoint | 2.6 - Finish Surfaces
label | Frequency - Each Lot
label | Acceptance Criteria - Edgings: rendered to a thickness not exceeding 3mm and trowel finished. Concrete to have a neat appearance and uniform colour.
label | Reference Documents - Cl 703.25
label | Inspection / Test Method - Visual inspection
label | Record of conformity - ITP Signed
label | IP
label | Responsibility - Site Engineer/ Site Foreman
date | Date Completed:
checkpoint | 2.7 - Tolerances
label | Frequency - Each Lot
label | Acceptance Criteria - Match existing surfaces to within 5mm from dimensions shown on drawings. Section dimensions to be within 5mm and 15mm for width, for dimensions less than 25mm tolerance to be ± 3. Kerb and channel shall be constructed to the level of the adjoining pavement with a tolerance of 0 to +10 mm. Except on curves or shaped areas, the deviation of the finished work from a 3 m straightedge shall not exceed 5 mm at any point.
label | Reference Documents - Cl 703.15
label | Inspection / Test Method - Verify
label | Record of conformity - ITP Signed
label | SCP
label | Responsibility - Site Engineer/ Surveyor
date | Date Completed:
checkpoint | 2.8 - Joints
label | Frequency - Each joint
label | Acceptance Criteria - Transverse joints constructed at intervals not exceeding 2.5m. Groove cut 20mm deep and > 5mm wide on exposed surfaces, with vertical cut made through the base of the groove (depth >50mm from surface of section). Prevent bonding between surfacing and edging either paint with bitumen or use a strip of bitumen
label | Reference Documents - Cl 703.26
label | Inspection / Test Method - Verify
label | Record of conformity - ITP Signed
label | IP
label | Responsibility - Site Engineer/ Site Foreman
date | Date Completed:
checkpoint | 2.9 - Curing
label | Frequency - Each Lot
label | Acceptance Criteria - The curing of exposed concrete surfaces shall commence immediately after finishing operations are progressively completed and shall continue uninterrupted for a period of not less than 7 days after placing the concrete, with the exception of concrete edgings which shall be cured for a period of not less than three days after placing the concrete. Concrete will be cured by method of wet hessian.
label | Reference Documents - Cl 703.1
label | Inspection / Test Method - Verify
label | Record of conformity - ITP Signed
label | IP
label | Responsibility - Site Engineer/ Site Foreman
date | Date Completed:
checkpoint | 2.10 - Backfilling
label | Frequency - Each Lot
label | Acceptance Criteria - Not earlier than 3 days after casting. Topsoil material free from perishable matter, lumps or balls of clay. Topsoil compacted behind the edging to a level of the top of the edging and to a width not less than 300mm unless otherwise specified. Layers shall not exceed 150mm compacted depth.
label | Reference Documents - Cl 703.29
label | Inspection / Test Method - Verify
label | Record of conformity - ITP Signed
label | IP
label | Responsibility - Site Engineer/ Site Foreman
date | Date Completed:
checkpoint | 2.11 - Cracking of Concrete
label | Frequency - Following Completion
label | Acceptance Criteria - The concrete shall have no surface cracks at any stage after construction of width greater than 0.2 mm. Where such cracks exist, they shall be identified as a non-conformance. Cracked sections of concrete shall be either removed and replaced, or repaired in accordance with Section 687 – Repair of Concrete Cracks, as directed by the Superintendent. For damaged kerb and channel and edgings, a length of at least 1 m shall be removed and the replacement section shall be:
label | (a) constructed on compacted bedding;
label | (b) dowelled into the adjoining sections with 12 mm diameter hot dip galvanised dowels embedded at least 100 mm each side of the joint; and
label | (c) shaped and finished with curved trowels to match the profile and surface finish of adjoining sections.
label | Reference Documents - Cl 703.30 Section 687
label | Inspection / Test Method - Verify
label | Record of conformity - ITP Signed
label | IP
label | Responsibility - Site Engineer
date | Date Completed:
section | 3 - Completion
checkpoint | 3.1 - Survey data captured for as-built purposes
label | Frequency - Completion of each lot
label | Acceptance Criteria - Survey to ensure and validate that all works meet level and location requirements. Review of existing survey control marks and any additional control marks providing verification of conformity of as constructed features with design. As built survey recorded to confirm installation within tolerances in the latest IFC drawings.
label | Reference Documents - IFC Drawings / survey records
label | Inspection / Test Method - Document review
label | Record of conformity - As-built survey records
label | SCP
label | Responsibility - Project Engineer/ Surveyor
date | Date Completed:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | Print Name:
text | Position:
date | Work Completed On:
date | Date:
checklist | ITP-005 - General Concrete Paving - Red Boundary | itp |  |  |  |  | ITP-005 - General Concrete Paving - Red Boundary
section | 1 - Preliminary Works
checkpoint | 1.1 - Check for correct documentation
label | Frequency - Prior to commencing any activity
label | Acceptance Criteria - Ensure that all employees and subcontractors are:
label | – using the correct and complete set of drawings
label | – all drawings are the latest revision
label | Reference Documents - Drawings and drawing registers
label | Inspection / Test Method - Visual inspection
label | Record of conformity - ITP Signed
label | HP*
label | Responsibility - Site Engineer/ Site Foreman
date | Date Completed:
checkpoint | 1.2 - Implementation of all measures and controls
label | Frequency - Prior to commencing any activity
label | Acceptance Criteria - All necessary measures and controls are being implemented, that is: SMP, PMP, EMP, QMP, TMP and SEQ documentation.
label | Reference Documents - SMP, PMP, EMP, QMP, TMP and SEQ documentation.
label | Inspection / Test Method - Visual inspection
label | Record of conformity - ITP Signed
label | IP
label | Responsibility - Site Engineer/ Site Foreman
date | Date Completed:
checkpoint | 1.3 - Survey and Set Out
label | Frequency - Prior to commencing any activity
label | Acceptance Criteria - Current design model available for machine control. Clearly mark limit of works, chainage, offsets, cut/fill level etc. (if required) Design drawings must be IFC status
label | Reference Documents - IFC Drawings
label | Inspection / Test Method - Verify
label | Record of conformity - Site Inspection
label | HP*/ WP
label | Responsibility - Site Engineer/ Superintendent
date | Date Completed:
section | 2 - Construction Works
checkpoint | 2.1 - Setting Out
label | Frequency - Prior to start
label | Acceptance Criteria - Set out work in accordance with drawings. The superintendent will review and confirm set out. The alignment and survey/level pegs will be indicated to the Contractor on the Site by the Superintendent prior to the commencement of work. No survey/level pegs to be removed by any persons until completion of works.
label | Reference Documents - Cl 703.17
label | Inspection / Test Method - Verify
label | Record of conformity - ITP Signed
label | HP
label | Responsibility - Site Engineer/ Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 - Excavation and foundation
label | Frequency - Each lot as required
label | Acceptance Criteria - Box out to a sufficient depth to allow for the required compacted thickness of bedding material under the full width of concrete paving. Where it is necessary to excavate existing pavement, the excavation shall not extend more than 150 mm from the edge of the adjacent face. Foundation true to grade and cross section as shown on the drawings by filling and excavating as necessary.
label | Reference Documents - Cl 703.20, Cl703.21
label | Inspection / Test Method - Visual inspection
label | Record of conformity - ITP Signed
label | WP
label | Responsibility - Site Engineer/ Site Foreman
date | Date Completed:
checkpoint | 2.3 - Bedding materials and compaction
label | Frequency - Each lot, Prior to concrete placement
label | Acceptance Criteria - Bedding material shall be compacted size 20mm Class 3/4 Crushed Rock or Class 3/Class 4 crushed concrete. Immediately before concrete is placed, bedding shall be moist but with no free water on the surface. Comply to Table 820.041, Table 820.071.
label | Reference Documents - Cl 703.21, Table 820.041, Table 820.071 IFC Drawings
label | Inspection / Test Method - Visual inspection
label | Record of conformity - ITP Signed
label | WP
label | Responsibility - Site Engineer/ Superintendent
date | Date Completed:
checkpoint | 2.4 - Bedding depths (compacted)
label | Frequency - Each lot
label | Acceptance Criteria - 1. Edgings:
label | ○ When constructed over pavement layers, bedding shall be provided between the pavement layer and the underside of the edging, or the edging thickened to match the pavement layer.
label | ○ When not constructed over pavement layers, bedding ≥ 100 mm compacted thickness.
label | 2. Shared use paths:
label | ○ bedding ≥ 150 mm compacted thickness.
label | 3. Footpaths & Surfacings:
label | ○ bedding ≥ 100 mm compacted thickness
label | Reference Documents - Cl 703.21 (a), Cl703.21(b), Cl703.21(c) IFC drawings
label | Inspection / Test Method - Visual inspection
label | Record of conformity - ITP Signed
label | HP*/ WP
label | Responsibility - Site Engineer/ Superintendent
date | Date Completed:
checkpoint | 2.5 - Ambient weather for concreting
label | Frequency - Each Lot
label | Acceptance Criteria - Concreting operations shall comply with the requirements of Clauses 610.17(a), 610.17(b), 610.17(c) and 610.17(d) for Restrictions and treatments to be applied for concreting in hot, cold and wet weather. The temperature of concrete, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C. Ambient temperature not to be less than 5°C and no more than 35°C.
label | Reference Documents - Cl 703.013, AS/NZS 4671, AS/NZS 4680
label | Inspection / Test Method - All measures in accordance with relevant documentation
label | Record of conformity - Verify
label | WP
label | Responsibility - Site Engineer
date | Date Completed:
checkpoint | 2.6 - Formwork
label | Frequency - Each Lot
label | Acceptance Criteria - Materials, design, construction and stripping of formwork shall comply with the relevant requirements of AS 3610. Joints in formwork shall be constructed such that loss of mortar is prevented. Formwork shall not be stripped until the minimum times specified in AS 3610 Table 5.4.1 have elapsed from the time of completion of the placing of concrete. The minimum time shall also not be less than:
label | (a) 2 days for vertical formwork on external surfaces; and
label | (b) 1 day for vertical forms on permanently hidden surfaces.
label | Reference Documents - Cl 703.12 AS3610
label | Inspection / Test Method - Visual inspection
label | Record of conformity - ITP Signed
label | WP
label | Responsibility - Site Engineer/ Site Foreman
date | Date Completed:
checkpoint | 2.7 - Concrete Placement and Compaction
label | Frequency - Each Lot
label | Acceptance Criteria - Concrete strength to comply with detail on IFC drawings and AS 1379. Concrete shall be thoroughly compacted by means of continuous tamping and internal vibration and shall be worked around any embedment’s and into corners of formwork or excavations to produce a dense concrete free from voids. Workable concrete mixes are exempt from vibration requirement. Concrete testing frequency in accordance with 610 requirements.
label | Reference Documents - IFC drawings Cl 703.01, Cl 703.08, Cl 610.16, AS 1379
label | Inspection / Test Method - Visual inspection
label | Record of conformity - ITP Signed
label | WP
label | Responsibility - Site Engineer/ Site Foreman
date | Date Completed:
checkpoint | 2.8 - Surface Finish
label | Frequency - Each Lot
label | Acceptance Criteria - Exposed surfaces shall be treated as follows:
label | a) Edgings
label | ○ All edgings rendered to a thickness ≤ 3 mm, within 30 minutes of placing or extruding concrete. Mortar shall consist of two parts of fine aggregate, one part of cement, and sufficient water to produce a mix of suitable consistency.
label | (b) Footpaths, other Surfacings and Shared Use Paths
label | ○ Concrete compacted with internal vibration and worked until all the coarse aggregate is below the surface and the mortar comes to the top, struck off and finished to grade and cross section with a wooden float to produce a lightly textured non-skid surface.
label | ○ All edges sharp and clean, and bullnoses regular and of uniform radius. All discoloured concrete shall be cleaned or replaced by the Contractor.
label | ○ Permanently hidden concrete surfaces have a Class 4 surface finish.
label | ○ All other concrete elements shall have a Class 3 surface finish for external surfaces and a Class 4 surface finish for permanently hidden surfaces.
label | Reference Documents - Cl 703.25
label | Inspection / Test Method - Visual inspection
label | Record of conformity - ITP Signed
label | WP
label | Responsibility - Site Engineer/ Site Foreman
date | Date Completed:
checkpoint | 2.9 - Joints
label | Frequency - Each Lot
label | Acceptance Criteria - Transverse joints constructed at right angles to the back of edgings and the edge of footpaths and shared use paths. Joints in footpaths and shared use paths shall align with joints in adjacent edgings.
label | a) Edgings
label | i) Traverse Joints – constructed at regular intervals ≤ 2.5m. Templates for edging using fixed forms shall be removed as soon as practical after finishing work. Resultant slot in edging shall be tooled to a depth of 20mm, and produce a groove ≥ 5 mm wide, following which a vertical cut shall be made through the base of the groove to a depth ≥ 50 mm from the surface.
label | ii) Expansion Joints – placed at junctions with bridges, shall be 15 mm wide and filled with cork/bituminous impregnated particle board strip extending for the full width and depth of edging. Fill placed in position before concrete and held during placing of concrete.
label | b) Footpaths
label | i) Expansion Joints
label | ○ Expansion joints placed at intervals ≤ 10 m. Expansion joint shall be 15 mm wide, filled with cork/bituminous impregnated particle board strip extending for full width and depth of paving. Filler shall be placed before concrete is placed and held in position during concreting.
label | ii) Control Joints
label | ○ Control joints at least 25% of paving thickness deep, 5 mm wide at 2.5 m intervals within 4 hours of placing concrete when air temperature is between 20 degrees and 35 degrees and within 24 hours when air temperature is < 20 degrees.
label | c) Between concrete paving and shared use path
label | ○ Except on narrow medians (< 2.0 m wide) surfaced full width, bonding between the concrete paving or shared use path and the edging prevented by painting the back of the edging with bitumen, or by a bituminous felt material between edging and concrete paving/shared use path.
label | Reference Documents - Cl 703.26 (a), Cl 703.26 (b), Cl 703.26 (c)
label | Inspection / Test Method - Visual inspection
label | Record of conformity - ITP Signed
label | WP
label | Responsibility - Site Engineer/ Site Foreman
date | Date Completed:
checkpoint | 2.10 - Curing
label | Frequency - Each Lot
label | Acceptance Criteria - Match existing fixtures to within 5mm (pit covers, etc). Departure of line and level to design not to exceed 10mm at any point. Rate of change of deviation shall not exceed 10mm in 10m. For curves or shaped areas, the deviation of the finished work shall not exceed 5mm from a 3m straightedge at any point. Section dimensions shall not deviate by more than 5mm except that overall width shall not exceed by more than 15mm. For dimensions less than 25mm the tolerance shall be +/- 3mm. Where median surfacings are to be constructed between edge sections of the same level, paving shall be crowned to produce a crossfall between 1% and 3% towards the edges
label | Reference Documents - Cl 703.10
label | Inspection / Test Method - Verify
label | Record of conformity - ITP Signed
label | IP
label | Responsibility - Site Engineer/ Site Foreman
date | Date Completed:
checkpoint | 2.11 - Tolerances online, level and shape
label | Frequency - Each Lot
label | Acceptance Criteria - Match existing fixtures to within 5mm (pit covers, etc). Departure of line and level to design not to exceed 10mm at any point. Rate of change of deviation shall not exceed 10mm in 10m. For curves or shaped areas, the deviation of the finished work shall not exceed 5mm from a 3m straightedge at any point. Section dimensions shall not deviate by more than 5mm except that overall width shall not exceed by more than 15mm. For dimensions less than 25mm the tolerance shall be +/- 3mm. Where median surfacings are to be constructed between edge sections of the same level, paving shall be crowned to produce a crossfall between 1% and 3% towards the edges.
label | Reference Documents - Cl 703.15 (a), Cl 703.15 (b), Cl703.15 (c)
label | Inspection / Test Method - Visual inspection
label | Record of conformity - ITP Signed
label | IP
label | Responsibility - Site Engineer
date | Date Completed:
checkpoint | 2.12 - Concrete repairs
label | Frequency - Each Lot
label | Acceptance Criteria - Any concrete repairs shall be carried out using a method and materials accepted by the Superintendent.
label | Reference Documents - CL 703.08
label | Inspection / Test Method - Visual inspection
label | Record of conformity - ITP Signed
label | WP
label | Responsibility - Site Engineer/ Site Foreman
date | Date Completed:
section | 3 - Completion
checkpoint | 3.1 - Verification and Lot records complete
label | Frequency - Completion of each lot
label | Acceptance Criteria - Completed work checklists, inspection and test results and contractor conformance records progressively and permanently saved and stored as soon as possible after they are received. Completed lot records are transferred to the Quality Team for final record verification prior to being closed
label | Reference Documents - Test Certificates, QA Plan
label | Inspection / Test Method - Document review
label | Record of conformity - ITP Signed
label | TP
label | Responsibility - Project Engineer/ Site Engineer
date | Date Completed:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | Print Name:
text | Position:
date | Work Completed On:
date | Date:
checklist | ITP-006 - Hot Mix Asphalt | itp |  |  |  |  | ITP-006 - Hot Mix Asphalt
section | 1 - Construction Works
checkpoint | 1.1 - Submission of Mix Design (Type Asphalt, mm Nominal Size)
label | Frequency - Prior to commencing paving
label | Acceptance Criteria - Ensure this mix design has been registered and is reviewed by Superintendent prior to laying mix.
label | Reference Documents - VicRoads Spec. Cl.407.06
label | Inspection / Test Method - Correspondence of receipt of mix design
label | Record of conformity - VR approval, Completed ITP
label | HP
label | Responsibility - Site Engineer/ Asphalt Supervisor / Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.2 - Implementation of all measures and controls
label | Frequency - Prior to commencing any activity
label | Acceptance Criteria - All necessary measures and controls are being implemented, that is: SMP, PMP, EMP, QMP, TMP and SEQ documentation.
label | Reference Documents - SMP, PMP, EMP, QMP, TMP and SEQ documentation.
label | Inspection / Test Method - Visual Inspection
label | Record of conformity - This ITP signed off
label | HP*
label | Responsibility - Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 1.3 - Site Inspection and Base Condition
label | Frequency - Prior to commencing paving
label | Acceptance Criteria - Surface on which asphalt is to be placed is essentially dry and free from puddles and defects (holes, cracks, unstable material and edge irregularities) and loose materials. Material and compaction test certificates conform for pavement
label | Reference Documents - 407.14, AS2150 10.1, AS2150 10.3
label | Inspection / Test Method - Visual Inspection
label | Record of conformity - ITP Signed, Test Certificates, Base Course Checklist
label | HP
label | Responsibility - Site Engineer/ Asphalt Supervisor
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.4 - Dryback
label | Frequency - Prior to commencing paving
label | Acceptance Criteria - Scale B Pavement Dryback and Embedment
label | – 6 randomly selected test sites per lot required
label | – If Mean Moisture Ratio is < 60% & Maximum of any result is < 70% then Ball Penetration not required
label | – If Mean Moisture Ratio is < 65% & Maximum of any result is < 70% then Ball Penetration Maximum individual result is 3mm
label | – Testing schedule in accordance with 310.03 (c)
label | Reference Documents - 310.03(a), 310.03(b) Table 310.031, 310.03(c) Table 310.032
label | Inspection / Test Method - Verify
label | Record of conformity - ITP Signed off
label | TP
label | Responsibility - Site/Project Engineer/ Supervisor
date | Date Completed:
checkpoint | 1.5 - Ambient Conditions for Placing
label | Frequency - Prior to commencing paving
label | Acceptance Criteria - The majority of the surface area to be paved has a temperature greater than or equal to the following: Wearing Courses: 10°C for conventional binders or 15°C for PMBs
label | Reference Documents - 407.17(a)
label | Inspection / Test Method - Verify
label | Record of conformity - Thermometer
label | IP
label | Responsibility - Site Engineer/ Asphalt Supervisor
date | Date Completed:
checkpoint | 1.6 - Planning of Joints
label | Frequency - Prior to commencing paving
label | Acceptance Criteria - Runs to be marked to ensure placement of joints satisfy the following unless otherwise approved by the Client:
label | ○ Transverse Joints Offset from layer to layer by at least 2m
label | ○ Longitudinal Joints Offset from layer to layer by at least
label | ○ 150mm and be within 300mm of the lane line or centre of lane. Wearing course shall be on lane lines.
label | Reference Documents - 407.21 IFC Drawings
label | Inspection / Test Method - Measure and mark out runs by tape measure or survey
label | Record of conformity - Paving Plan
label | WP
label | Responsibility - Project Engineer/ Asphalt Supervisor
date | Date Completed:
checkpoint | 1.7 - Longitudinal Joints with existing Pavement
label | Frequency - Prior to commencing paving
label | Acceptance Criteria - Where new pavement abuts an existing pavement, the existing pavement shall be removed in steps to achieve an offset from layer to layer of not less than 150mm. Depth of step to be cut to the full depth of each indiviual layer.
label | Reference Documents - 407.21 (c)
label | Inspection / Test Method - Visual Inspection
label | Record of conformity - ITP Signed
label | WP
label | Responsibility - Project Engineer/ Asphalt Supervisor
date | Date Completed:
section | 2 - Asphalt Placement works
checkpoint | 2.1 - Frequency of Inspection and Testing at the Mixing Plant
label | Frequency - As per Table 407.151
label | Acceptance Criteria - The frequency shall not be less than that shown in Table 407.111, except that the Superintendent may agree to a lower frequency where the Contractor has implemented a system of statistical process control and can demonstrate that such lower frequency is adequate to assure the quality of the product.
label | Reference Documents - 407.151
label | Inspection / Test Method - Test Inspection
label | Record of conformity - ITP Signed
label | TP
label | Responsibility - Project Engineer/ Asphalt Supervisor
date | Date Completed:
checkpoint | 2.2 - Tack Coat
label | Frequency - Prior to commencing paving
label | Acceptance Criteria - As per VicRoads Section 407.15, a tack coat shall be applied to cleaned/existing asphalt or a sealed surface on which fresh asphalt is to be placed unless the unsealed surface has been primed. Tack coat is not required on primed surfaces, on clean, freshly placed asphalt or when the layer to be placed exceeds 50mm. Tack coat to be sprayed on existing asphalt joints. Tack coat must be allowed to turn from brown to black before paving. If required, tack coat to be sprayed in a uniform film over the surface to be paved at a rate of 0.15-0.30 L/m2 of residual binder (60% bitumen )or 0.30 to 0.60 litres/m2 (30% bitumen content). This rate is to be doubled on joints and chases.
label | Reference Documents - 407.19 AS2150 11
label | Inspection / Test Method - Visual Inspection
label | Record of conformity - Spray area
label | WP
label | Responsibility - Site Engineer/ Asphalt Supervisor
date | Date Completed:
checkpoint | 2.3 - Commencement of Placing
label | Frequency - Prior to commencing Paving
label | Acceptance Criteria - The placement of asphalt on the sub-base or granular base for a new pavement or for an overlay of an existing bituminous surfaced pavement shall not commence until the consent to proceed is obtained from the Client.
label | Reference Documents - 407.23
label | Inspection / Test Method - Visual Inspection
label | Record of conformity - ITP Signed
label | HP
label | Responsibility - Site Engineer/ Asphalt Supervisor / Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.4 - Mix Design Confirmation
label | Frequency - Each lot
label | Acceptance Criteria - Check correct mix design as per pavement design has been delivered prior to laying mix.
label | Reference Documents - VicRoads Spec. Cl.407.09
label | Inspection / Test Method - Visual Inspection & Delivery Docket
label | Record of conformity - Delivery docket, Completed ITP
label | HP*
label | Responsibility - Site Engineer/ Asphalt Supervisor
date | Date Completed:
checkpoint | 2.5 - Delivery of Mix
label | Frequency - Each load
label | Acceptance Criteria - Asphalt is not segregated, binder is not separated or does not contain uncoated particles and the temperature from mixing plant is not more than 175°C.
label | Reference Documents - 407.11
label | Inspection / Test Method - Visual Inspection
label | Record of conformity - Delivery Docket
label | WP
label | Responsibility - Site Engineer/ Asphalt Supervisor
date | Date Completed:
checkpoint | 2.6 - Traceability
label | Frequency - Each lot
label | Acceptance Criteria - Ability to locate asphalt test results placed in three dimensions i.e. start/end chainage, offset/lane and layer
label | Reference Documents - Fulton Hogan Quality Plan
label | Inspection / Test Method - Verify
label | Record of conformity - Daily Lot Record
label | IP
label | Responsibility - Site Engineer/ Asphalt Supervisor
date | Date Completed:
checkpoint | 2.7 - Layer Thickness and Level Control
label | Frequency - Regularly during paving
label | Acceptance Criteria - Thickness of asphalt layer conforms to asphalt thickness on drawings or specifications
label | Reference Documents - IFC Drawings
label | Inspection / Test Method - Verify
label | Record of conformity - Dips using ruler or dip stick
label | WP
label | Responsibility - Site Engineer/ Asphalt Supervisor
date | Date Completed:
checkpoint | 2.8 - Paver Stoppages
label | Frequency - If paver stops
label | Acceptance Criteria - A transverse joint shall be constructed if the asphalt in front of the screed cools to below 120°C
label | Reference Documents - 407.25 (c)
label | Inspection / Test Method - Verify
label | Record of conformity - Thermometer
label | WP
label | Responsibility - Site Engineer/ Asphalt Supervisor
date | Date Completed:
checkpoint | 2.9 - Surface Finish of Wearing Course
label | Frequency - During paving and after final roll
label | Acceptance Criteria - The finished surface of asphalt wearing course shall be of uniform appearance, free of dragged areas, cracks, open textured patches and roller marks
label | Reference Documents - 407.29 (a)(i)
label | Inspection / Test Method - Visual Inspection
label | Record of conformity - ITP Signed
label | WP
label | Responsibility - Site Engineer/ Asphalt Supervisor
date | Date Completed:
checkpoint | 2.10 - Kerb and Channel
label | Frequency - During paving and after final roll
label | Acceptance Criteria - The edge of the wearing course shall be either flush with or not more than 5 mm above the lip of the channel unless otherwise specified
label | Reference Documents - 407.29 (a)(ii)
label | Inspection / Test Method - Visual Inspection
label | Record of conformity - ITP Signed
label | WP
label | Responsibility - Site Engineer/ Asphalt Supervisor
date | Date Completed:
checkpoint | 2.11 - Alignment of layers not placed against concrete edge
label | Frequency - During paving and at completion of work
label | Acceptance Criteria - The edge of asphalt layers shall not be more than 50mm inside nor more than 100mm outside, the designed offset from centreline or design line. The rate of change of offset of the edge of layer shall not be greater than 25mm in 10m
label | Reference Documents - 407.29 (a)(iv) Drawings
label | Inspection / Test Method - Visual Inspection
label | Record of conformity - ITP Signed
label | IP
label | Responsibility - Site Engineer/ Asphalt Supervisor
date | Date Completed:
checkpoint | 2.12 - Width of layers not placed against concrete edge
label | Frequency - During paving and at completion of work
label | Acceptance Criteria - The width of asphalt layers shall not be less than the design or specified width of layer by more than 50mm or greater than the design or specified width by more than 100mm. The average width over any 300m shall not be less than the design or specified width
label | Reference Documents - 407.29 (a)(v)
label | Inspection / Test Method - Visual Inspection
label | Record of conformity - ITP Signed
label | IP
label | Responsibility - Site Engineer/ Asphalt Supervisor
date | Date Completed:
section | 3 - Testing
checkpoint | 3.1 - Compaction
label | Frequency - Per Lot
label | Acceptance Criteria - For layers <50mm, if characteristic density ratio is:
label | ○ 94.0% or greater Accept lot
label | ○ 91.0% to 93.9% Lot may be accepted at reduced rate
label | Reference Documents - Table 407.271
label | Inspection / Test Method - Verify
label | Record of conformity - Test Report
label | TP
label | Responsibility - Site Engineer/ Lab Technician
date | Date Completed:
checkpoint | 3.2 - Level Conformance
label | Frequency - Per 4,000m2 at completion of work
label | Acceptance Criteria - Scale B
label | Individual departures from design not to exceed ±8mm with a standard deviation of no greater than 10mm. Minimum number of measurements per lot is 40.
label | (ii) Kerb and Channel
label | ○ Refer to Item 2.10 of this ITP
label | Reference Documents - Table 407.293, Table 407.292
label | Inspection / Test Method - Survey by VicRoads Section 173
label | Record of conformity - Survey Conformance
label | SCP
label | Responsibility - Site Engineer/ Surveyor
date | Date Completed:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | Print Name:
text | Position:
date | Work Completed On:
date | Date:
checklist | ITP-007 - Pavement Markings | itp |  |  |  |  | ITP-007 - Pavement Markings
section | 1 - General
checkpoint | 1.1 - Check for correct documentation
label | Frequency - Prior to commencing any activity
label | Acceptance Criteria - Ensure that all employees and subcontractors are:
label | – using the correct and complete set of drawings
label | – all drawings are the latest revision
label | Reference Documents - Drawings and drawing registers
label | Inspection / Test Method - Visual inspection
label | Record of conformity - This ITP signed
label | HP*
label | Responsibility - Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 1.2 - Line marking conformance
label | Frequency - Prior to commencing any activity
label | Acceptance Criteria - Materials to be used must conform with the specification
label | Reference Documents - Cl 721.A05 IFC Drawing
label | Inspection / Test Method - Record Review
label | Record of conformity - This ITP signed
label | IP
label | Responsibility - Contractor Representative
date | Date Completed:
checkpoint | 1.3 - Site Preparation
label | Frequency - Prior to commencing any activity
label | Acceptance Criteria - Removal of any existing unsound, obsolete or redundant pavement markings
label | Reference Documents - Cl 721.A06
label | Inspection / Test Method - Visual inspection
label | Record of conformity - This ITP signed
label | IP
label | Responsibility - Contractor Representative
date | Date Completed:
checkpoint | 1.4 - Set-out of Pavement Markings
label | Frequency - Prior to commencing any activity
label | Acceptance Criteria - Pavement markings to set-out in accordance with IFC Drawings
label | Reference Documents - Cl 721.A09
label | Inspection / Test Method - Visual inspection
label | Record of conformity - This ITP signed
label | IP
label | Responsibility - Contractor Representative
date | Date Completed:
section | 2 - Pavement Markings
checkpoint | 2.1 - Acceptance of Work
label | Frequency - Each Lot as required
label | Acceptance Criteria - Where removal of unsuitable pavement marking is required, the method of removal shall be subject to the approval of the Superintendent before removal works commence.
label | Reference Documents - 721.A12
label | Inspection / Test Method - Visual Inspection
label | Record of conformity - This ITP signed
label | HP
label | Responsibility - Site Engineer / Site Foreman / Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 - Position of Markings
label | Frequency - Each Lot as required
label | Acceptance Criteria - All markings are to be set out in accordance with the dimensions and spacings as required by the appropriate standard in Clause 721.A03. Painting/application of material shall not commence until the Superintendent has inspected the set out and given consent to proceed, unless an exemption has been granted in writing by the Superintendent.
label | Reference Documents - 721.B05
label | Inspection / Test Method - Visual Inspection
label | Record of conformity - This ITP Signed
label | HP
label | Responsibility - Site Engineer / Site Foreman / Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 - Installation of Linemarking
label | Frequency - During Construction
label | Acceptance Criteria - Line marking installed as per the IFC drawings
label | Reference Documents - IFC Drawings
label | Inspection / Test Method - Visual inspection
label | Record of conformity - This ITP Signed
label | IP*
label | Responsibility - Site Engineer / Site Foreman
date | Date Completed:
section | 3 - Sign Installation
checkpoint | 3.1 - Completion Inspection
label | Frequency - Each Lot as required
label | Acceptance Criteria - Completed marking shall be uniform in appearance, texture, width and thickness and the surface shall be free from blister, air bubbles, tears, lumps, overlaps, unbeaded areas, tyre marks or other defects. Edges and cuts-offs shall be neat and sharp , and there shall be no visible run-off, overspray, dribbles, splash or spillage on to the surrounding area, or on to parked or passing vehicles.
label | Inspection / Test Method - Visual inspection
label | Record of conformity - This ITP Signed
label | WP
label | Responsibility - Site Engineer / Site Foreman / Superintendent
date | Date Completed:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | Print Name:
text | Position:
date | Work Completed On:
date | Date:
checklist | ITP-008 - Landscaping - Irrigation | itp |  |  |  |  | ITP-008 - Landscaping - Irrigation
section | 1 - Preliminary Works
checkpoint | 1.1 - Pre-commencement meeting
label | Frequency - Prior to commencing any activity
label | Acceptance Criteria - Hold a pre-commencement meeting with council's representative prior to commencing any landscaping activities
label | Reference Documents - IFC Drawings / Landscape Plan
label | Inspection / Test Method - Verify
label | Record of conformity - ITP Signed
label | HP
label | Responsibility - superintendent/ Site Engineer
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.2 - Check for correct documentation
label | Frequency - Prior to commencing any activity
label | Acceptance Criteria - Ensure that all employees and subcontractors are:
label | – using the correct and complete set of drawings
label | – all drawings are the latest revision
label | Reference Documents - Drawings and drawing registers
label | Inspection / Test Method - Visual inspection
label | Record of conformity - ITP Signed
label | HP*
label | Responsibility - Site Engineer /Site Foreman
date | Date Completed:
checkpoint | 1.3 - Implementation of all measures and controls
label | Frequency - Prior to commencing any activity
label | Acceptance Criteria - All necessary measures and controls are being implemented, that is: SMP, PMP, EMP, QMP, TMP and SEQ documentation.
label | Reference Documents - SMP, PMP, EMP, QMP, TMP and SEQ documentation.
label | Inspection / Test Method - Visual inspection
label | Record of conformity - ITP Signed
label | IP
label | Responsibility - Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 1.4 - Irrigation System
label | Frequency - Prior to commencing any activity
label | Acceptance Criteria - The contractor shall get the design approval from City of Ballarat on the irrigation system prior to commencing the activity
label | Reference Documents - Landscape Specification Cl 7.1
label | Inspection / Test Method - Verify
label | Record of conformity - ITP Signed
label | HP
label | Responsibility - Superintendent/ Site Engineer
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 2 - Construction Works
checkpoint | 2.1 - Setting Out
label | Frequency - Prior to start
label | Acceptance Criteria - Set out work in accordance with drawings. The superintendent will review and confirm set out. The alignment and survey/level pegs will be indicated to the Contractor on the Site by the Superintendent prior to the commencement of work. No survey/level pegs to be removed by any persons until completion of works.
label | Reference Documents - Cl 703.17
label | Inspection / Test Method - Verify
label | Record of conformity - ITP Signed
label | HP
label | Responsibility - Site Engineer/ Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 - Stripping of Topsoil
label | Frequency - As required
label | Acceptance Criteria - Topsoil shall be stripped for the full width of the formation:
label | (a) defined by the line through batter points extended to include any rounding and any surface and catch drains;
label | (b) by a means which avoids contamination with subsoil and does not increase the extent of unstable areas; and
label | (c) placed in stockpile or prepared areas.
label | ○ Unless there is an excess of topsoil to be removed from site, topsoil shall not be removed from the site.
label | ○ The Contractor shall treat and manage site topsoil before stripping, and after spreading, to remove and/or minimise the spread of weeds and other pathogens and pest organisms throughout the site.
label | ○ Stockpiles shall be maintained in a neat, well shaped state capable of shedding water. Topsoil shall be re spread as soon as practicable.
label | ○ Stripped surfaces shall be graded to an even self draining surface.
label | Reference Documents - Cl 204.05
label | Inspection / Test Method - Visual inspection
label | Record of conformity - ITP Signed
label | IP
label | Responsibility - Site Engineer/ Site Foreman
date | Date Completed:
checkpoint | 2.3 - Topsoiling
label | Frequency - As Required
label | Acceptance Criteria - Topsoiling shall not be placed over cut and fill areas until the Contractor has verified that such areas comply with the requirements in Clause 204.03. All unpaved cut and fill areas within the limits of the batters, including batter roundings but excluding cut batters steeper than 1.5 to 1 (horizontal to vertical), and any other area disturbed by the Contractor's operations, shall be topsoiled to the following thicknesses measured normal to the slope:
label | (a) batters with slopes of 2 to 1 (horizontal to vertical) or steeper 50 mm minimum
label | (b) tree and shrub plantation bed areas other than (a) above - 100 mm minimum
label | (c) verges: In areas without kerb and channel or concrete edging strips the depth of topsoil shall vary uniformly from 50 mm deep at the outside edge of verge to 20 mm deep within 100 mm of the edge of seal or asphalt surface treatment
label | (d) all other areas 75 mm minimum.
label | ○ Topsoil shall be placed and levelled but not compacted except for verge areas, which shall be compacted. Topsoil on batters shall be placed so as to prevent rilling.
label | ○ The surface level of topsoil shall match the finished surface level, or level of back of kerb or concrete edging, as appropriate.
label | Reference Documents - 204.17
label | Inspection / Test Method - Inspect
label | Record of conformity - This ITP Signed
label | IP
label | Responsibility - Site Foreman
date | Date Completed:
checkpoint | 2.4 - Tree Clearing
label | Frequency - As Required
label | Acceptance Criteria - The Contractor shall seek the Superintendent's approval prior to the removal of any tree. An inspection of the tree by the Superintendent or the Superintendent's environmental representative, along with the City of Ballarat is required.
label | Reference Documents - Cl 200.1
label | Inspection / Test Method - Verify
label | Record of conformity - This ITP Signed
label | HP*
label | Responsibility - Site Foreman / Site Engineer
date | Date Completed:
checkpoint | 2.5 - Hard infrastructure preparation
label | Frequency - Each Lot
label | Acceptance Criteria - Footings excavation – Site excavation shall be excavation within the limits. The Contractor shall conduct its operations such that the area outside the limits of the excavation is not unduly disturbed. The Contractor shall not commence placing any fill on the prepared areas until the area has been reviewed by the Superintendent. Reinforcement for pavement/footing – All steel reinforcement shall be securely held during placing and compacting of the concrete.
label | Reference Documents - Cl 204.06 (d), Cl 204.10 (b), CL610.26 (a)
label | Inspection / Test Method - Site Inspection
label | Record of conformity - This ITP Signed
label | HP
label | Responsibility - Superintendent/ Site Engineer
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.5 - Soil Preparation
label | Frequency - Each Lot
label | Acceptance Criteria - All the necessary soil/garden bed preparation shall be approved by the superintendent prior to planting. The planting soil should be prepared in accordance with the Tree Planting Detail and the landscape specification plan.
label | Reference Documents - Landscape Specification Cl 10.1 (iii)
label | Inspection / Test Method - Site Inspection
label | Record of conformity - ITP Signed
label | HP
label | Responsibility - Superintendent/ Site Engineer
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.6 - Plant Stock
label | Frequency - Each Lot
label | Acceptance Criteria - All of the trees and garden bed plants shall be inspected and approved by the council representative prior to plantation.At the nursery ensure that individual trees and batches are clearly labelled with the species name and cultivar / variety / provenance where appropriate. Hardwood stakes, as per details are to be installed immediately after planting. Stakes are to be driven 600mm into the ground or deep enough to ensure that the stake will remain stable and vertical.
label | Reference Documents - Landscape Specification Cl 10.1 (vi)
label | Inspection / Test Method - Visual inspection
label | Record of conformity - ITP Signed
label | HP
label | Responsibility - Superintendent/ Site Engineer
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.7 - Mulching
label | Frequency - Each Lot
label | Acceptance Criteria - After topsoil placement and planting-out of the plant material in all garden beds, supply and spread mulch to an average compacted depth of 75mm. The mulch shall be free from soil clods, rocks and all other non-organic matter.
label | Reference Documents - Landscape Specification Cl 10.1 (vii)
label | Inspection / Test Method - Visual inspection
label | Record of conformity - ITP Signed
label | HP
label | Responsibility - Superintendent/ Site Engineer
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.8 - Furniture
label | Frequency - Each Lot
label | Acceptance Criteria - All the furnitures is to be installed in accordance with the manufacturer's specification
label | Reference Documents - Landscape Specification Cl 9.0
label | Inspection / Test Method - Visual inspection
label | Record of conformity - ITP Signed
label | IP
label | Responsibility - Site Engineer/Site Foreman
date | Date Completed:
section | 3 - Completion
checkpoint | 3.1 - Practical Completion
label | Frequency - Completion of each lot
label | Acceptance Criteria - Survey to ensure and validate that all works meet level and location requirements. Review of existing survey control marks and any additional control marks providing verification of conformity of as constructed features with design. As built survey recorded to confirm installation within tolerances in the latest IFC drawings.
label | Reference Documents - IFC Drawings / survey records
label | Inspection / Test Method - Document review
label | Record of conformity - As-built survey records
label | SCP
label | Responsibility - Project Engineer/ Surveyor
date | Date Completed:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | Print Name:
text | Position:
date | Work Completed On:
date | Date: