## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-002 - Stormwater Drainage Red Boundary Rev. 3 | itp |  |  |  |  | ITP-002 - Stormwater Drainage Red Boundary Rev. 3
section | 1 - Preliminary Works
checkpoint | 1.1 - Check for correct documentation
label | Frequency - Prior to commencing any activity
label | Acceptance Criteria - Ensure that all employees and subcontractors are using the correct and complete set of IFC Drawings.
label | Reference Documents - IFC Drawings
label | Inspection / Test Method - Visual inspection
label | Record of conformity - ITP Signed
label | IHP
label | Responsibility - Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 1.2 - Implementation of all measures and controls
label | Frequency - Prior to commencing any activity
label | Acceptance Criteria - Ensure all relevant project documentation has been submitted and approved by Superintendent including SMP, PMP, EMP, QMP, TMP and SEQ documentation.
label | Reference Documents - SMP, PMP, EMP, QMP, TMP & SEQ
label | Inspection / Test Method - Visual Inspection
label | Record of conformity - ITP Signed
label | HP
label | Responsibility - Site Engineer/ Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.3 - Purchase and delivery of pre-cast drainage components
label | Frequency - Each Delivery
label | Acceptance Criteria - Precast materials to be used for construction have been inspected and are free from defects or damage.
label | Reference Documents - VicRoads Standard Section 701.05
label | Inspection / Test Method - Visual Inspection
label | Record of conformity - ITP Signed
label | WP
label | Responsibility - Site Engineer
date | Date Completed:
checkpoint | 1.5 - Backfill material Classification
label | Frequency - Prior to start
label | Acceptance Criteria - Approved compacted backfill within bedding zone to be 20mm Class 3 Fine Crushed Rock as nominated on the IFC Design Drawings
label | Reference Documents - Dwg No. 982RD-06 Sheet 6 Note 1
label | Inspection / Test Method - Verify
label | Record of conformity - Test Reports from supplier
label | TP
label | Responsibility - Site Engineer
date | Date Completed:
checkpoint | 1.6 - Mortar material classification
label | Frequency - Prior to start
label | Acceptance Criteria - Mortar used in the laying of box culvert sections or as jointing for pipes shall comply with the requirements of clause 610.32.
label | Reference Documents - VicRoads Standard Section 701.09 (e)
label | Inspection / Test Method - Verify
label | Record of conformity - Test Reports from supplier
label | TP
label | Responsibility - Site Engineer
date | Date Completed:
section | 2 - Construction Works
checkpoint | 2.1 - Excavation Permit
label | Frequency - Each lot
label | Acceptance Criteria - An excavation permit must be issued prior to any excavation commencing. Plant and equipment shall be appropriate for the task. Excavation operations shall not disturb areas outside the limit of excavation.
label | Reference Documents - Excavation permit
label | Inspection / Test Method - Verify
label | Record of conformity - ITP Signed
label | IHP
label | Responsibility - Site Engineer
date | Date Completed:
checkpoint | 2.12 - Conformity with Drawings
label | Frequency - Prior to Excavation
label | Acceptance Criteria - Prior to commencement of excavation for the pits and drainage lines the Contractor shall conﬁrm the position of all drainage components with the Superintendent. Unless specified otherwise the tolerance on location of pipes compared to the design or a change to the design notified in accordance with this clause shall be:
label | (a) offset of entry pits required to match lines of kerbs or barriers ±20 mm
label | (b) plan location of pits other than offsets to kerb lines or barriers ±100 mm
label | (c) invert level of pipes at pits ±50 mm
label | (d) departure from design grade of pipe runs ±10 mm in 10 m provided minimum grade is not less than 1:250
label | Reference Documents - VicRoads Standard Section 701.09
label | Inspection / Test Method - Visual Inspection
label | Record of conformity - ITP Signed
label | HP
label | Responsibility - Site Engineer/ Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.13 - Excavation
label | Frequency - Each Trench
label | Acceptance Criteria - For pipe culverts, the width of trench at and below the level of the top of the pipe shall be such that the horizontal clearance from the outside of the pipe to the wall of the trench is within the limits Min 300mm and Max. 600mm.
label | Reference Documents - VicRoads Standard Section Table 701.151 Dwg No. 982RD-06 Sheet 6
label | Inspection / Test Method - Visual Inspection
label | Record of conformity - ITP Signed
label | HP
label | Responsibility - Site Engineer/ Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.14 - Compact base of trench
label | Frequency - Each Trench
label | Acceptance Criteria - The base of the trench shall be compacted to refusal using mechanical plant.
label | Reference Documents - VicRoads Standard Section 701.15
label | Inspection / Test Method - Visual Inspection
label | Record of conformity - ITP Signed
label | WP
label | Responsibility - Site Engineer
date | Date Completed:
checkpoint | 2.15 - Placement of Bedding Material
label | Frequency - Each Trench
label | Acceptance Criteria - Bedding material shall be compacted to no less than the below thickness:
label | – 100mm where D < 1500mm
label | – 150mm where D > 1500mm
label | ○ where D is the nominal pipe diameter or culvert width.
label | Reference Documents - Dwg No. 982RD-06 Sheet 6
label | Inspection / Test Method - Visual Inspection
label | Record of conformity - ITP Signed
label | WP
label | Responsibility - Site Engineer
date | Date Completed:
checkpoint | 2.16 - Laying of Pipes
label | Frequency - Each Line
label | Acceptance Criteria - Laying of pipes shall not commence until the Contractor has verified that pipe bedding complies with the lines and levels of the design drawings and that pipes are not damaged and comply with the requirements of clause 701.04 and Clause 701.05 respectively.
label | Reference Documents - VicRoads Standard Section 701.17
label | Inspection / Test Method - Visual Inspection
label | Record of conformity - ITP Signed
label | IHP
label | Responsibility - Site Engineer
date | Date Completed:
checkpoint | 2.17 - Jointing Pipe Sections
label | Frequency - Each Line
label | Acceptance Criteria - Join pipes with rubber rings in accordance with manufacturer's instructions, check that the rings are clean and undisturbed. Any disturbed rings are to be cleaned and reassembled
label | Reference Documents - VicRoads Standard Section 701.18
label | Inspection / Test Method - Visual Inspection
label | Record of conformity - ITP Signed
label | WP
label | Responsibility - Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 2.18 - Jointing to Pits
label | Frequency - Each Pit
label | Acceptance Criteria - The joints between various components such as drainage pits, access chambers and pipes shall be made watertight using a cementitious mortar in accordance with the requirements of clause 610.33.
label | Reference Documents - VicRoads Standard Section 705.15
label | Inspection / Test Method - Visual Inspection
label | Record of conformity - ITP Signed
label | WP
label | Responsibility - Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 2.19 - Place & compact backfill material over pipes
label | Frequency - Each Lot
label | Acceptance Criteria - Unless the pipe is installed through an existing paved area, selected and ordinary backﬁll shall be placed as follows under, around, and above the culvert after the sections are bedded and compacted as speciﬁed in Clause 701.15.
label | (i) Culvert Under Area not to be Paved
label | ○ The trench shall be backﬁlled with selected backﬁll material to a level 0.3 m above the top of the culvert and with ordinary backﬁll material above that level.
label | (ii) Culvert under area not to be paved
label | ○ The trench shall be backfilled with selected backfill material to a level 0.3 m above the top of the culvert and with ordinary backfill material above that level.
label | Reference Documents - VicRoads Standard Section 701.19 Dwg No. 982RD-06 Sheet 6
label | Inspection / Test Method - Visual Inspection
label | Record of conformity - ITP Signed
label | IHP
label | Responsibility - Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 2.20 - Place & compact backfill material around pits
label | Frequency - Each Pit
label | Acceptance Criteria - Backfilling around drainage pits shall be placed in layers not exceeding 300 mm loose thickness and compacted to refusal using handheld mechanical equipment
label | Reference Documents - VicRoads Standard Section 705.18
label | Inspection / Test Method - Visual Inspection
label | Record of conformity - ITP Signed
label | WP
label | Responsibility - Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 2.21 - Backfilling with cement stabilised sand
label | Frequency - Each Trench
label | Acceptance Criteria - Where approval is given from superintendent, culverts in trenches may be backfilled to half the pipe diameter or box culvert height with 3% stabilised sand with a water content sufficient to ensure penetration beneath the pipe or box culvert invert without leaving free surface water.
label | Reference Documents - VicRoads Standard Section 701.19 (c)
label | Inspection / Test Method - Visual Inspection
label | Record of conformity - ITP Signed
label | WP
label | Responsibility - Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 2.22 - Step Irons & Ladders
label | Frequency - Each Pit
label | Acceptance Criteria - Drainage pits greater than 1.0 m deep shall be fitted with step irons or ladders in accordance with AS 1657 and this Section.
label | Reference Documents - VicRoads Standard Section 705.12
label | Inspection / Test Method - Visual Inspection
label | Record of conformity - ITP Signed
label | WP
label | Responsibility - Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 2.23 - Construction Tolerances
label | Frequency - Each Lot
label | Acceptance Criteria - The tolerances listed in Clause 610.47 are the allowable deviations of the finished product from the dimensions shown on the drawings. These tolerances will be a basis for acceptance of the work.
label | Reference Documents - VicRoads Standard Section 705.19
label | Inspection / Test Method - Visual Inspection
label | Record of conformity - ITP Signed
label | WP
label | Responsibility - Site Engineer / Site Foreman
date | Date Completed:
section | 3 - Testing & Completion
checkpoint | 3.1 - Compaction and moisture content of backfill & bedding material
label | Frequency - Each Lot
label | Acceptance Criteria - The Contractor shall test the bedding and backfill material at a frequency as shown in Table 701.291 to ensure that all materials comply with the specified requirements.
label | Reference Documents - VicRoads Standard Section Table 701.291
label | Inspection / Test Method - Verify
label | Record of conformity - Test Reports
label | TP
label | Responsibility - Site Engineer
date | Date Completed:
checkpoint | 3.2 - CCTV inspection
label | Frequency - Each Lot
label | Acceptance Criteria - Unless approved otherwise by the Superintendent, all drainage lines constructed beneath pavements shall be inspected, after completion of earthworks to subgrade level and prior to construction of pavement layers, by an independent testing organisation using closed circuit television (CCTV). Reporting of the CCTV inspections shall be in accordance with WSA 05 2013 – Conduit Inspection Reporting Code of Australia, published by Water Services Association of Australia.
label | Reference Documents - VicRoads Standard Section 701.3
label | Inspection / Test Method - Visual inspection
label | Record of conformity - CCTV Report
label | HP
label | Responsibility - Site Engineer/ Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.3 - Repairs
label | Frequency - Each Lot
label | Acceptance Criteria - No repairs shall be undertaken without the Superintendent’s approval of the repair materials and procedures.
label | Reference Documents - VicRoads Standard Section 701.31
label | Inspection / Test Method - Verify
label | Record of conformity - ITP Signed
label | IP
label | Responsibility - Site Engineer
date | Date Completed:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | Print Name:
text | Position:
date | Work Completed On:
date | Date: