## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-003b - Sub-Base Construction Deep Lift Asphalt - Red Boundary | itp |  |  |  |  | ITP-003b - Sub-Base Construction Deep Lift Asphalt - Red Boundary
section | 1 - Preliminary Works
checkpoint | 1.1 - Check for correct documentation
label | Frequency - Prior to commencing any activity
label | Acceptance Criteria - Ensure that the most recent copy of the design drawings are used and have been Issued for Construction (IFC).
label | Reference Documents - Drawings and drawing registers
label | Inspection / Test Method - Visual inspection
label | Record of conformity - This ITP signed
label | WP
label | Responsibility - Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 1.2 - Material Mix Design
label | Frequency - Prior to commencing any activity
label | Acceptance Criteria - Material proposed for import as sub-base material meets the requirements of VR Section 812. Obtain material compliance data from the supplier.
label | Reference Documents - Cl 812.04, RC 500.02
label | Inspection / Test Method - Document Review
label | Record of conformity - Mix Design VicRoads Approval
label | HP*
label | Responsibility - Site Engineer
date | Date Completed:
checkpoint | 1.3 - Implementation of all measures and controls
label | Frequency - Prior to commencing any activity
label | Acceptance Criteria - All necessary measures and controls are being implemented, that is: SMP, PMP, EMP, QMP, TMP and SEQ documentation.
label | Reference Documents - SMP, PMP, EMP, QMP, TMP and SEQ documentation.
label | Inspection / Test Method - Visual Inspection
label | Record of conformity - This ITP signed
label | HP*
label | Responsibility - Site Engineer / Site Foreman
date | Date Completed:
section | 2 - Construction Works
checkpoint | 2.1 - Transverse Joints
label | Frequency - Check prior to placing material
label | Acceptance Criteria - Material should be spread to minimize number of joints. Transverse joints shall be offset from one layer to next by not less than 2 metres.
label | Reference Documents - Cl.304.08 (a), Cl.304.08 (c)
label | Inspection / Test Method - Visual Inspection
label | Record of conformity - This ITP signed off
label | IP
label | Responsibility - Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 2.2 - Longitudinal Joints
label | Frequency - Check prior to placing material
label | Acceptance Criteria - Material should be spread to minimise number of joints. Longitudinal joints offset from one layer to next by not less than 150mm Longitudinal joints to be located within 300mm from planned traffic lane lines or within 300 mm of the centre of a traffic lane.
label | Reference Documents - Cl.304.07 (a), Cl.304.08 (d), Cl.304.08 (e)
label | Inspection / Test Method - Visual Inspection
label | Record of conformity - This ITP signed off
label | IP
label | Responsibility - Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 2.3 - Lot Size
label | Frequency - Check prior to placing material
label | Acceptance Criteria - A single lot shall be considered a single layer of 4000m2 or one days production in a single layer, whichever is lesser.
label | Reference Documents - . Cl.304.09 (b)(ii) Table 304.121
label | Inspection / Test Method - Site Inspection
label | Record of conformity - Signed ITP
label | IP
label | Responsibility - Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 2.4 - Layer Thickness
label | Frequency - Each Lot
label | Acceptance Criteria - Sub-base shall be constructed to a maximum compacted thickness of 200mm and minimum thickness of 4 times the nominal size of the material.
label | Reference Documents - Cl 304.07b
label | Inspection / Test Method - Site Inspection
label | Record of conformity - Signed ITP
label | Signed ITP
label | Responsibility - Site Engineer
date | Date Completed:
checkpoint | 2.5 - Proof Rolling
label | Frequency - Proof Roll each layer
label | Acceptance Criteria - No visible deformation or springing in presence of Superintendent's Rep.( Cl 173) Plant to comply with requirements of Cl 173.03.
label | ○ Static > 12T
label | ○ Pneumatic > 20T
label | Reference Documents - 173.03
label | Inspection / Test Method - Visual inspection
label | Record of conformity - This ITP signed off
label | HP/ WP
label | Responsibility - Site Engineer / Site Foreman / Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 3 - Testing Requirements
checkpoint | 3.1 - Determine Testing Scale & Initial testing frequency
label | Frequency - Prior to Testing
label | Acceptance Criteria - Initially test every lot until 3 consecutive lots of like material and/or work have achieved the standards specified in Clauses 304.09. and 304.12. If no failures, Reduced Frequency applies as specified in Table 304.121.
label | Reference Documents - Cl.304.09, Cl.304.12, Table 304.121
label | Inspection / Test Method - Document Review/ Site Inspection
label | Record of conformity - Signed ITP
label | AP
label | Responsibility - Project Engineer
date | Date Completed:
checkpoint | 3.2 - Compaction Testing
label | Frequency - Every Lot, Every second lot (reduced frequency)
label | Acceptance Criteria - Standard Dry Density (SDD) of not less than 98% for existing material to be stabilised with 3% lime & 3% sand, Minimum Density Ratio of 96% of Class 2 FCR as per Contract Drawings sheet 6 of 25
label | Reference Documents - Contract Drawings (sheet 06 of 25)
label | Inspection / Test Method - Test point
label | Record of conformity - This ITP signed off; Test reports
label | TP
label | Responsibility - Site Engineer
date | Date Completed:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | Print Name:
text | Position:
date | Work Completed On:
date | Date: