## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-004 - Kerb and Channel Red Boundary | itp |  |  |  |  | ITP-004 - Kerb and Channel Red Boundary
section | 1 - Preliminary Works
checkpoint | 1.1 - Check for correct documentation
label | Frequency - Prior to commencing any activity
label | Acceptance Criteria - Ensure that all employees and subcontractors are:
label | – using the correct and complete set of drawings
label | – all drawings are the latest revision
label | Reference Documents - Drawings and drawing registers
label | Inspection / Test Method - Visual inspection
label | Record of conformity - ITP Signed
label | HP*
label | Responsibility - Site Engineer/ Site Foreman
date | Date Completed:
checkpoint | 1.2 - Implementation of all measures and controls
label | Frequency - Prior to commencing any activity
label | Acceptance Criteria - All necessary measures and controls are being implemented, that is: SMP, PMP, EMP, QMP, TMP and SEQ documentation.
label | Reference Documents - SMP, PMP, EMP, QMP, TMP and SEQ documentation.
label | Inspection / Test Method - Visual inspection
label | Record of conformity - ITP Signed
label | IP
label | Responsibility - Site Engineer/ Site Foreman
date | Date Completed:
checkpoint | 1.3 - Mix Design
label | Frequency - Prior to commencing any activity
label | Acceptance Criteria - Approved VR mix design to be used. Details to be sent to the superintendent for approval prior to commencing works.
label | Reference Documents - AS 1379, Cl 703.07, 703.05, 703.23
label | Inspection / Test Method - Verify
label | Record of conformity - ITP Signed, Mix design approval
label | HP*/ WP
label | Responsibility - Site Engineer/ Superintendent
date | Date Completed:
section | 2 - Construction Works
checkpoint | 2.1 - Setting Out
label | Frequency - Prior to start
label | Acceptance Criteria - Set out work in accordance with drawings. The superintendent will review and confirm set out. The alignment and survey/level pegs will be indicated to the Contractor on the Site by the Superintendent prior to the commencement of work. No survey/level pegs to be removed by any persons until completion of works.
label | Reference Documents - Cl 703.17
label | Inspection / Test Method - Verify
label | Record of conformity - ITP Signed
label | HP
label | Responsibility - Site Engineer/ Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 - Temporary Drainage Provisions
label | Frequency - If Required
label | Acceptance Criteria - If obstructing waterways, culverts or channels, temporary diversion of discharge of drainage and stormwater to be in place.
label | Reference Documents - Cl 703.18
label | Inspection / Test Method - Visual inspection
label | Record of conformity - ITP Signed
label | WP
label | Responsibility - Site Engineer/ Site Foreman
date | Date Completed:
checkpoint | 2.3 - Bedding
label | Frequency - Each lot
label | Acceptance Criteria - All bedding material shall conform with the requirements of sections 812 or 820 for crushed rock and crushed concrete respectively. Unless otherwise stated, 20mm Class 3 or 4 bedding shall be used and compacted to a thickness of not less than 100mm. Bedding shall be trimmed to appropriate levels, moistened as necessary, and be firmly compacted.
label | Reference Documents - Cl 703.21
label | Inspection / Test Method - Visual inspection
label | Record of conformity - ITP Signed
label | WP
label | Responsibility - Site Engineer/ Superintendent
date | Date Completed:
checkpoint | 2.4 - Pre-concrete check
label | Frequency - Each lot
label | Acceptance Criteria - Bedding shall be moist but shall have no free water on the surface. Concrete shall not be placed when the air temperature measured at the point of placement is >35°C or <5°C. Temperature of concrete, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C. Formwork - Prior to placing concrete in an earth excavation, formwork shall be erected so that fresh concrete is not placed directly against the sides of the excavation. Concrete extrusion machines have minimum cement content of 320kg/m3.
label | Reference Documents - Cl 703.08, 610.17(a)(b)(c), 703.12
label | Inspection / Test Method - Verify
label | Record of conformity - ITP Signed
textbox | Ambient Temperature |  |  | °C
textbox | Concrete Temperature |  |  | °C
label | HP*/ WP
label | Responsibility - Site Engineer/ Superintendent
date | Date Completed:
checkpoint | 2.5 - Kerb Concrete Mixture/Strength
label | Frequency - Each Lot
label | Acceptance Criteria - Traffic Routes – a minimum of, or equivalent to, 320 kg of cementitious material or geopolymer binder per cubic metre of concrete
label | ○ Local Streets – a minimum of, or equivalent to, 280 kg of cementitious material or geopolymer binder per cubic metre of concrete
label | Reference Documents - Cl 703.05(b)
date | Date Completed:
checkpoint | 2.5 - Concrete Placement
label | Frequency - Each lot
label | Acceptance Criteria - Concrete is to be fed to extrusion machine at a uniform rate. Concrete is to be satisfactorily compacted so that finished surfaces are free from surface pitting larger than 5mm diameter, honey combing or faulty patches
label | Reference Documents - Cl 703.23
label | Inspection / Test Method - Site Inspection
label | Record of conformity - ITP Signed
label | IP
label | Responsibility - Site Engineer
date | Date Completed:
checkpoint | 2.6 - Finish Surfaces
label | Frequency - Each Lot
label | Acceptance Criteria - Edgings: rendered to a thickness not exceeding 3mm and trowel finished. Concrete to have a neat appearance and uniform colour.
label | Reference Documents - Cl 703.25
label | Inspection / Test Method - Visual inspection
label | Record of conformity - ITP Signed
label | IP
label | Responsibility - Site Engineer/ Site Foreman
date | Date Completed:
checkpoint | 2.7 - Tolerances
label | Frequency - Each Lot
label | Acceptance Criteria - Match existing surfaces to within 5mm from dimensions shown on drawings. Section dimensions to be within 5mm and 15mm for width, for dimensions less than 25mm tolerance to be ± 3. Kerb and channel shall be constructed to the level of the adjoining pavement with a tolerance of 0 to +10 mm. Except on curves or shaped areas, the deviation of the finished work from a 3 m straightedge shall not exceed 5 mm at any point.
label | Reference Documents - Cl 703.15
label | Inspection / Test Method - Verify
label | Record of conformity - ITP Signed
label | SCP
label | Responsibility - Site Engineer/ Surveyor
date | Date Completed:
checkpoint | 2.8 - Joints
label | Frequency - Each joint
label | Acceptance Criteria - Transverse joints constructed at intervals not exceeding 2.5m. Groove cut 20mm deep and > 5mm wide on exposed surfaces, with vertical cut made through the base of the groove (depth >50mm from surface of section). Prevent bonding between surfacing and edging either paint with bitumen or use a strip of bitumen
label | Reference Documents - Cl 703.26
label | Inspection / Test Method - Verify
label | Record of conformity - ITP Signed
label | IP
label | Responsibility - Site Engineer/ Site Foreman
date | Date Completed:
checkpoint | 2.9 - Curing
label | Frequency - Each Lot
label | Acceptance Criteria - The curing of exposed concrete surfaces shall commence immediately after finishing operations are progressively completed and shall continue uninterrupted for a period of not less than 7 days after placing the concrete, with the exception of concrete edgings which shall be cured for a period of not less than three days after placing the concrete. Concrete will be cured by method of wet hessian.
label | Reference Documents - Cl 703.1
label | Inspection / Test Method - Verify
label | Record of conformity - ITP Signed
label | IP
label | Responsibility - Site Engineer/ Site Foreman
date | Date Completed:
checkpoint | 2.10 - Backfilling
label | Frequency - Each Lot
label | Acceptance Criteria - Not earlier than 3 days after casting. Topsoil material free from perishable matter, lumps or balls of clay. Topsoil compacted behind the edging to a level of the top of the edging and to a width not less than 300mm unless otherwise specified. Layers shall not exceed 150mm compacted depth.
label | Reference Documents - Cl 703.29
label | Inspection / Test Method - Verify
label | Record of conformity - ITP Signed
label | IP
label | Responsibility - Site Engineer/ Site Foreman
date | Date Completed:
checkpoint | 2.11 - Cracking of Concrete
label | Frequency - Following Completion
label | Acceptance Criteria - The concrete shall have no surface cracks at any stage after construction of width greater than 0.2 mm. Where such cracks exist, they shall be identified as a non-conformance. Cracked sections of concrete shall be either removed and replaced, or repaired in accordance with Section 687 – Repair of Concrete Cracks, as directed by the Superintendent. For damaged kerb and channel and edgings, a length of at least 1 m shall be removed and the replacement section shall be:
label | (a) constructed on compacted bedding;
label | (b) dowelled into the adjoining sections with 12 mm diameter hot dip galvanised dowels embedded at least 100 mm each side of the joint; and
label | (c) shaped and finished with curved trowels to match the profile and surface finish of adjoining sections.
label | Reference Documents - Cl 703.30 Section 687
label | Inspection / Test Method - Verify
label | Record of conformity - ITP Signed
label | IP
label | Responsibility - Site Engineer
date | Date Completed:
section | 3 - Completion
checkpoint | 3.1 - Survey data captured for as-built purposes
label | Frequency - Completion of each lot
label | Acceptance Criteria - Survey to ensure and validate that all works meet level and location requirements. Review of existing survey control marks and any additional control marks providing verification of conformity of as constructed features with design. As built survey recorded to confirm installation within tolerances in the latest IFC drawings.
label | Reference Documents - IFC Drawings / survey records
label | Inspection / Test Method - Document review
label | Record of conformity - As-built survey records
label | SCP
label | Responsibility - Project Engineer/ Surveyor
date | Date Completed:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | Print Name:
text | Position:
date | Work Completed On:
date | Date: