## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-005 - General Concrete Paving - Red Boundary | itp |  |  |  |  | ITP-005 - General Concrete Paving - Red Boundary
section | 1 - Preliminary Works
checkpoint | 1.1 - Check for correct documentation
label | Frequency - Prior to commencing any activity
label | Acceptance Criteria - Ensure that all employees and subcontractors are:
label | – using the correct and complete set of drawings
label | – all drawings are the latest revision
label | Reference Documents - Drawings and drawing registers
label | Inspection / Test Method - Visual inspection
label | Record of conformity - ITP Signed
label | HP*
label | Responsibility - Site Engineer/ Site Foreman
date | Date Completed:
checkpoint | 1.2 - Implementation of all measures and controls
label | Frequency - Prior to commencing any activity
label | Acceptance Criteria - All necessary measures and controls are being implemented, that is: SMP, PMP, EMP, QMP, TMP and SEQ documentation.
label | Reference Documents - SMP, PMP, EMP, QMP, TMP and SEQ documentation.
label | Inspection / Test Method - Visual inspection
label | Record of conformity - ITP Signed
label | IP
label | Responsibility - Site Engineer/ Site Foreman
date | Date Completed:
checkpoint | 1.3 - Survey and Set Out
label | Frequency - Prior to commencing any activity
label | Acceptance Criteria - Current design model available for machine control. Clearly mark limit of works, chainage, offsets, cut/fill level etc. (if required) Design drawings must be IFC status
label | Reference Documents - IFC Drawings
label | Inspection / Test Method - Verify
label | Record of conformity - Site Inspection
label | HP*/ WP
label | Responsibility - Site Engineer/ Superintendent
date | Date Completed:
section | 2 - Construction Works
checkpoint | 2.1 - Setting Out
label | Frequency - Prior to start
label | Acceptance Criteria - Set out work in accordance with drawings. The superintendent will review and confirm set out. The alignment and survey/level pegs will be indicated to the Contractor on the Site by the Superintendent prior to the commencement of work. No survey/level pegs to be removed by any persons until completion of works.
label | Reference Documents - Cl 703.17
label | Inspection / Test Method - Verify
label | Record of conformity - ITP Signed
label | HP
label | Responsibility - Site Engineer/ Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 - Excavation and foundation
label | Frequency - Each lot as required
label | Acceptance Criteria - Box out to a sufficient depth to allow for the required compacted thickness of bedding material under the full width of concrete paving. Where it is necessary to excavate existing pavement, the excavation shall not extend more than 150 mm from the edge of the adjacent face. Foundation true to grade and cross section as shown on the drawings by filling and excavating as necessary.
label | Reference Documents - Cl 703.20, Cl703.21
label | Inspection / Test Method - Visual inspection
label | Record of conformity - ITP Signed
label | WP
label | Responsibility - Site Engineer/ Site Foreman
date | Date Completed:
checkpoint | 2.3 - Bedding materials and compaction
label | Frequency - Each lot, Prior to concrete placement
label | Acceptance Criteria - Bedding material shall be compacted size 20mm Class 3/4 Crushed Rock or Class 3/Class 4 crushed concrete. Immediately before concrete is placed, bedding shall be moist but with no free water on the surface. Comply to Table 820.041, Table 820.071.
label | Reference Documents - Cl 703.21, Table 820.041, Table 820.071 IFC Drawings
label | Inspection / Test Method - Visual inspection
label | Record of conformity - ITP Signed
label | WP
label | Responsibility - Site Engineer/ Superintendent
date | Date Completed:
checkpoint | 2.4 - Bedding depths (compacted)
label | Frequency - Each lot
label | Acceptance Criteria - 1. Edgings:
label | ○ When constructed over pavement layers, bedding shall be provided between the pavement layer and the underside of the edging, or the edging thickened to match the pavement layer.
label | ○ When not constructed over pavement layers, bedding ≥ 100 mm compacted thickness.
label | 2. Shared use paths:
label | ○ bedding ≥ 150 mm compacted thickness.
label | 3. Footpaths & Surfacings:
label | ○ bedding ≥ 100 mm compacted thickness
label | Reference Documents - Cl 703.21 (a), Cl703.21(b), Cl703.21(c) IFC drawings
label | Inspection / Test Method - Visual inspection
label | Record of conformity - ITP Signed
label | HP*/ WP
label | Responsibility - Site Engineer/ Superintendent
date | Date Completed:
checkpoint | 2.5 - Ambient weather for concreting
label | Frequency - Each Lot
label | Acceptance Criteria - Concreting operations shall comply with the requirements of Clauses 610.17(a), 610.17(b), 610.17(c) and 610.17(d) for Restrictions and treatments to be applied for concreting in hot, cold and wet weather. The temperature of concrete, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C. Ambient temperature not to be less than 5°C and no more than 35°C.
label | Reference Documents - Cl 703.013, AS/NZS 4671, AS/NZS 4680
label | Inspection / Test Method - All measures in accordance with relevant documentation
label | Record of conformity - Verify
label | WP
label | Responsibility - Site Engineer
date | Date Completed:
checkpoint | 2.6 - Formwork
label | Frequency - Each Lot
label | Acceptance Criteria - Materials, design, construction and stripping of formwork shall comply with the relevant requirements of AS 3610. Joints in formwork shall be constructed such that loss of mortar is prevented. Formwork shall not be stripped until the minimum times specified in AS 3610 Table 5.4.1 have elapsed from the time of completion of the placing of concrete. The minimum time shall also not be less than:
label | (a) 2 days for vertical formwork on external surfaces; and
label | (b) 1 day for vertical forms on permanently hidden surfaces.
label | Reference Documents - Cl 703.12 AS3610
label | Inspection / Test Method - Visual inspection
label | Record of conformity - ITP Signed
label | WP
label | Responsibility - Site Engineer/ Site Foreman
date | Date Completed:
checkpoint | 2.7 - Concrete Placement and Compaction
label | Frequency - Each Lot
label | Acceptance Criteria - Concrete strength to comply with detail on IFC drawings and AS 1379. Concrete shall be thoroughly compacted by means of continuous tamping and internal vibration and shall be worked around any embedment’s and into corners of formwork or excavations to produce a dense concrete free from voids. Workable concrete mixes are exempt from vibration requirement. Concrete testing frequency in accordance with 610 requirements.
label | Reference Documents - IFC drawings Cl 703.01, Cl 703.08, Cl 610.16, AS 1379
label | Inspection / Test Method - Visual inspection
label | Record of conformity - ITP Signed
label | WP
label | Responsibility - Site Engineer/ Site Foreman
date | Date Completed:
checkpoint | 2.8 - Surface Finish
label | Frequency - Each Lot
label | Acceptance Criteria - Exposed surfaces shall be treated as follows:
label | a) Edgings
label | ○ All edgings rendered to a thickness ≤ 3 mm, within 30 minutes of placing or extruding concrete. Mortar shall consist of two parts of fine aggregate, one part of cement, and sufficient water to produce a mix of suitable consistency.
label | (b) Footpaths, other Surfacings and Shared Use Paths
label | ○ Concrete compacted with internal vibration and worked until all the coarse aggregate is below the surface and the mortar comes to the top, struck off and finished to grade and cross section with a wooden float to produce a lightly textured non-skid surface.
label | ○ All edges sharp and clean, and bullnoses regular and of uniform radius. All discoloured concrete shall be cleaned or replaced by the Contractor.
label | ○ Permanently hidden concrete surfaces have a Class 4 surface finish.
label | ○ All other concrete elements shall have a Class 3 surface finish for external surfaces and a Class 4 surface finish for permanently hidden surfaces.
label | Reference Documents - Cl 703.25
label | Inspection / Test Method - Visual inspection
label | Record of conformity - ITP Signed
label | WP
label | Responsibility - Site Engineer/ Site Foreman
date | Date Completed:
checkpoint | 2.9 - Joints
label | Frequency - Each Lot
label | Acceptance Criteria - Transverse joints constructed at right angles to the back of edgings and the edge of footpaths and shared use paths. Joints in footpaths and shared use paths shall align with joints in adjacent edgings.
label | a) Edgings
label | i) Traverse Joints – constructed at regular intervals ≤ 2.5m. Templates for edging using fixed forms shall be removed as soon as practical after finishing work. Resultant slot in edging shall be tooled to a depth of 20mm, and produce a groove ≥ 5 mm wide, following which a vertical cut shall be made through the base of the groove to a depth ≥ 50 mm from the surface.
label | ii) Expansion Joints – placed at junctions with bridges, shall be 15 mm wide and filled with cork/bituminous impregnated particle board strip extending for the full width and depth of edging. Fill placed in position before concrete and held during placing of concrete.
label | b) Footpaths
label | i) Expansion Joints
label | ○ Expansion joints placed at intervals ≤ 10 m. Expansion joint shall be 15 mm wide, filled with cork/bituminous impregnated particle board strip extending for full width and depth of paving. Filler shall be placed before concrete is placed and held in position during concreting.
label | ii) Control Joints
label | ○ Control joints at least 25% of paving thickness deep, 5 mm wide at 2.5 m intervals within 4 hours of placing concrete when air temperature is between 20 degrees and 35 degrees and within 24 hours when air temperature is < 20 degrees.
label | c) Between concrete paving and shared use path
label | ○ Except on narrow medians (< 2.0 m wide) surfaced full width, bonding between the concrete paving or shared use path and the edging prevented by painting the back of the edging with bitumen, or by a bituminous felt material between edging and concrete paving/shared use path.
label | Reference Documents - Cl 703.26 (a), Cl 703.26 (b), Cl 703.26 (c)
label | Inspection / Test Method - Visual inspection
label | Record of conformity - ITP Signed
label | WP
label | Responsibility - Site Engineer/ Site Foreman
date | Date Completed:
checkpoint | 2.10 - Curing
label | Frequency - Each Lot
label | Acceptance Criteria - Match existing fixtures to within 5mm (pit covers, etc). Departure of line and level to design not to exceed 10mm at any point. Rate of change of deviation shall not exceed 10mm in 10m. For curves or shaped areas, the deviation of the finished work shall not exceed 5mm from a 3m straightedge at any point. Section dimensions shall not deviate by more than 5mm except that overall width shall not exceed by more than 15mm. For dimensions less than 25mm the tolerance shall be +/- 3mm. Where median surfacings are to be constructed between edge sections of the same level, paving shall be crowned to produce a crossfall between 1% and 3% towards the edges
label | Reference Documents - Cl 703.10
label | Inspection / Test Method - Verify
label | Record of conformity - ITP Signed
label | IP
label | Responsibility - Site Engineer/ Site Foreman
date | Date Completed:
checkpoint | 2.11 - Tolerances online, level and shape
label | Frequency - Each Lot
label | Acceptance Criteria - Match existing fixtures to within 5mm (pit covers, etc). Departure of line and level to design not to exceed 10mm at any point. Rate of change of deviation shall not exceed 10mm in 10m. For curves or shaped areas, the deviation of the finished work shall not exceed 5mm from a 3m straightedge at any point. Section dimensions shall not deviate by more than 5mm except that overall width shall not exceed by more than 15mm. For dimensions less than 25mm the tolerance shall be +/- 3mm. Where median surfacings are to be constructed between edge sections of the same level, paving shall be crowned to produce a crossfall between 1% and 3% towards the edges.
label | Reference Documents - Cl 703.15 (a), Cl 703.15 (b), Cl703.15 (c)
label | Inspection / Test Method - Visual inspection
label | Record of conformity - ITP Signed
label | IP
label | Responsibility - Site Engineer
date | Date Completed:
checkpoint | 2.12 - Concrete repairs
label | Frequency - Each Lot
label | Acceptance Criteria - Any concrete repairs shall be carried out using a method and materials accepted by the Superintendent.
label | Reference Documents - CL 703.08
label | Inspection / Test Method - Visual inspection
label | Record of conformity - ITP Signed
label | WP
label | Responsibility - Site Engineer/ Site Foreman
date | Date Completed:
section | 3 - Completion
checkpoint | 3.1 - Verification and Lot records complete
label | Frequency - Completion of each lot
label | Acceptance Criteria - Completed work checklists, inspection and test results and contractor conformance records progressively and permanently saved and stored as soon as possible after they are received. Completed lot records are transferred to the Quality Team for final record verification prior to being closed
label | Reference Documents - Test Certificates, QA Plan
label | Inspection / Test Method - Document review
label | Record of conformity - ITP Signed
label | TP
label | Responsibility - Project Engineer/ Site Engineer
date | Date Completed:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | Print Name:
text | Position:
date | Work Completed On:
date | Date: