## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-007 - Pavement Markings | itp |  |  |  |  | ITP-007 - Pavement Markings
section | 1 - General
checkpoint | 1.1 - Check for correct documentation
label | Frequency - Prior to commencing any activity
label | Acceptance Criteria - Ensure that all employees and subcontractors are:
label | – using the correct and complete set of drawings
label | – all drawings are the latest revision
label | Reference Documents - Drawings and drawing registers
label | Inspection / Test Method - Visual inspection
label | Record of conformity - This ITP signed
label | HP*
label | Responsibility - Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 1.2 - Line marking conformance
label | Frequency - Prior to commencing any activity
label | Acceptance Criteria - Materials to be used must conform with the specification
label | Reference Documents - Cl 721.A05 IFC Drawing
label | Inspection / Test Method - Record Review
label | Record of conformity - This ITP signed
label | IP
label | Responsibility - Contractor Representative
date | Date Completed:
checkpoint | 1.3 - Site Preparation
label | Frequency - Prior to commencing any activity
label | Acceptance Criteria - Removal of any existing unsound, obsolete or redundant pavement markings
label | Reference Documents - Cl 721.A06
label | Inspection / Test Method - Visual inspection
label | Record of conformity - This ITP signed
label | IP
label | Responsibility - Contractor Representative
date | Date Completed:
checkpoint | 1.4 - Set-out of Pavement Markings
label | Frequency - Prior to commencing any activity
label | Acceptance Criteria - Pavement markings to set-out in accordance with IFC Drawings
label | Reference Documents - Cl 721.A09
label | Inspection / Test Method - Visual inspection
label | Record of conformity - This ITP signed
label | IP
label | Responsibility - Contractor Representative
date | Date Completed:
section | 2 - Pavement Markings
checkpoint | 2.1 - Acceptance of Work
label | Frequency - Each Lot as required
label | Acceptance Criteria - Where removal of unsuitable pavement marking is required, the method of removal shall be subject to the approval of the Superintendent before removal works commence.
label | Reference Documents - 721.A12
label | Inspection / Test Method - Visual Inspection
label | Record of conformity - This ITP signed
label | HP
label | Responsibility - Site Engineer / Site Foreman / Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 - Position of Markings
label | Frequency - Each Lot as required
label | Acceptance Criteria - All markings are to be set out in accordance with the dimensions and spacings as required by the appropriate standard in Clause 721.A03. Painting/application of material shall not commence until the Superintendent has inspected the set out and given consent to proceed, unless an exemption has been granted in writing by the Superintendent.
label | Reference Documents - 721.B05
label | Inspection / Test Method - Visual Inspection
label | Record of conformity - This ITP Signed
label | HP
label | Responsibility - Site Engineer / Site Foreman / Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 - Installation of Linemarking
label | Frequency - During Construction
label | Acceptance Criteria - Line marking installed as per the IFC drawings
label | Reference Documents - IFC Drawings
label | Inspection / Test Method - Visual inspection
label | Record of conformity - This ITP Signed
label | IP*
label | Responsibility - Site Engineer / Site Foreman
date | Date Completed:
section | 3 - Sign Installation
checkpoint | 3.1 - Completion Inspection
label | Frequency - Each Lot as required
label | Acceptance Criteria - Completed marking shall be uniform in appearance, texture, width and thickness and the surface shall be free from blister, air bubbles, tears, lumps, overlaps, unbeaded areas, tyre marks or other defects. Edges and cuts-offs shall be neat and sharp , and there shall be no visible run-off, overspray, dribbles, splash or spillage on to the surrounding area, or on to parked or passing vehicles.
label | Inspection / Test Method - Visual inspection
label | Record of conformity - This ITP Signed
label | WP
label | Responsibility - Site Engineer / Site Foreman / Superintendent
date | Date Completed:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | Print Name:
text | Position:
date | Work Completed On:
date | Date: