## Folder Structure
Level No. | Room type | Check list
53 | Bathroom 01 | Bathroom checklist
| Master Ensuite | Bathroom 1 Checklist
| Laundry | Laundry Checklist
54 | Master Ensuite | Master Ensuite Checklist
| Ensuite 1 | Ensuite 1 Checklist
| Ensuite 2 | Ensuite 1 Checklist
| Ensuite 3 | Bathroom checklist
| Laundry | Laundry Checklist
| Powder room | Laundry Checklist
| Common area | ST07 Terra Vein installation Checklist

## Checklist
Checklist | Bathroom Checklist
Section | Substrate inspection
checkpoint | All prior works done
Wall square and plumb
Section | Soundproofing
checkpoint | Primer Applied
Soundproofing DS70
Ardex X18 soundproofing adhesive
Ardex K65 FLC over UFH
Section | Waterproofing
checkpoint | Ardex Multiprime Peimer to all relevant substrate
Apply Ardex STB & STA tape to all change plane, penetration, and floor waste area
Apply WPM 002 waterproofing (2 cost)
Water test complete
Section | Tiling
checkpoint | Setting out tiles according to construction drawing / Site confirmation
Primer applied prior to tiling
Full coverage of tiles with adhesive
Tile lippiness checked and to acceptable standard
Finishing trims & transition bars edge alignment
Section | Grout and silicone
checkpoint | Adhesive fully cured and clean properly
Grout work properly into all joint
Silicone applied to a acceptable finish
Section | Completion
checkpoint | Photo taken of completed area
Checklist | Master Ensuite Checklist
Section | Substrate inspection
checkpoint | All prior works done
Wall square and plumb
Section | Soundproofing
checkpoint | Primer Applied
Soundproofing DS70
Ardex X18 soundproofing adhesive
Ardex K65 FLC over UFH
Section | Waterproofing
checkpoint | Ardex Multiprime Peimer to all relevant substrate
Apply Ardex STB & STA tape to all change plane, penetration, and floor waste area
Apply WPM 002 waterproofing (2 cost)
Water test complete
Section | Tiling (bathroom floor)
checkpoint | Setting out tiles according to construction drawing / Site confirmation
Primer applied prior to tiling
Full coverage of tiles with adhesive
Tile lippiness checked and to acceptable standard
Finishing trims & transition bars edge alignment
Section | Tiling (shower floor & wall)
checkpoint | Setting out tiles according to construction drawing / Site confirmation
Section | Sealer
checkpoint | Sealer applied
Section | Grout and silicone
checkpoint | Adhesive fully cured and clean properly
Grout work properly into all joint
Silicone applied to a acceptable finish
Section | Completion
checkpoint | Photo taken of completed area
Checklist | Laundry Checklist
Section | Substrate inspection
checkpoint | All prior works done
Section | Soundproofing
checkpoint | Primer Applied
Soundproofing DS70
Ardex X18 soundproofing adhesive
Section | Waterproofing
checkpoint | Ardex Multiprime Peimer to all relevant substrate
Apply Ardex STB & STA tape to all change plane, penetration, and floor waste area
Apply WPM 002 waterproofing (2 cost)
Section | Tiling
checkpoint | Setting out tiles according to construction drawing / Site confirmation
Section | Sealer
checkpoint | Sealer applied
Section | Completion
checkpoint | Photo taken of completed area
Checklist | ST07 Terra Vein installation Checklist
Section | Substrate inspection
checkpoint | All prior works done
Section | Soundproofing
checkpoint | Primer Applied
Soundproofing DS70
Ardex X18 soundproofing adhesive
Section | Tiling
checkpoint | Setting out tiles according to construction drawing / Site confirmation
Section | Sealer
checkpoint | Sealer applied
Section | Completion
checkpoint | Photo taken of completed area
Checklist | Bathroom 1 Checklist
Section | Substrate inspection
checkpoint | All prior works done
Wall square and plumb
Section | Soundproofing
checkpoint | Primer Applied
Soundproofing DS70
Ardex X18 soundproofing adhesive
Ardex K65 FLC over UFH
Section | Waterproofing
checkpoint | Ardex Multiprime Peimer to all relevant substrate
Apply Ardex STB & STA tape to all change plane, penetration, and floor waste area
Apply WPM 002 waterproofing (2 cost)
Water test complete
Section | Tiling (Mosic)
checkpoint | Setting out tiles according to construction drawing / Site confirmation
Primer applied prior to tiling
Full coverage of tiles with adhesive
Tile lippiness checked and to acceptable standard
Finishing trims & transition bars edge alignment
Section | Grout and silicone
checkpoint | Adhesive fully cured and clean properly
Grout work properly into all joint
Silicone applied to a acceptable finish
Section | Completion
checkpoint | Photo taken of completed area
Checklist | Ensuite 1 Checklist
Section | Substrate inspection
checkpoint | All prior works done
Wall square and plumb
Section | Soundproofing
checkpoint | Primer Applied
Soundproofing DS70
Ardex X18 soundproofing adhesive
Ardex K65 FLC over UFH
Section | Waterproofing
checkpoint | Ardex Multiprime Peimer to all relevant substrate
Apply Ardex STB & STA tape to all change plane, penetration, and floor waste area
Apply WPM 002 waterproofing (2 cost)
Water test complete
Section | Tiling (floor tiling)
checkpoint | Setting out tiles according to construction drawing / Site confirmation
Sealer applied
Section | Tiling (bathroom & shower wall)
checkpoint | Setting out tiles according to construction drawing / Site confirmation
Primer applied prior to tiling
Full coverage of tiles with adhesive
Tile lippiness checked and to acceptable standard
Section | Grout and silicone
checkpoint | Adhesive fully cured and clean properly
Grout work properly into all joint
Silicone applied to a acceptable finish
Section | Completion
checkpoint | Photo taken of completed area