## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned | be5347d3-1444-43f3-ad41-a3ba8da43ef9 |  | checklist | Structural Curtain Walls |  |  |  |  | Yes | Structural Curtain Walls | 05de0331-61e7-4cdf-915b-f5f7c2ecea1f
checkpoint-group | c854b804-0b03-41e6-96de-f5d1c6c2963e |  | section | Curtain Wall External Checklist
checkpoint-status | 77f6dc80-83f8-4d13-b7fe-14183a587864 |  | checkpoint | Setout / grids/ datum lines (refer to Survey mark/Setting out) MUST ATTACHED SURVEY DRAWING SHOWING LEVELS AND SLAB EDGES
checkpoint-status | e71f1bea-05ec-4fb3-816f-7b354fb40f77 |  | checkpoint | Opening acceptance as per drawings MUST ADD SURVEY DRAWING
checkpoint-status | 0cbc2bbd-839e-422b-99ef-a54967fb4ad4 |  | checkpoint | Secondary Bracket Installed, Bolt torque Mark with paint marker when toqued(refer to SD)PHOTO REQUIRED
checkpoint-status | 02a7b9b6-e28f-4090-bb57-83c12af2cae5 |  | checkpoint | Waterproofing ( Check that water proofing is over area where airseal is going to be) PHOTO REQUIRED
checkpoint-status | d11fc2d3-e9be-482a-b8e7-93634b5df0c0 |  | checkpoint | Install subsill /Jamb/ Deadload blocks/ splicers / soakers
checkpoint-status | c256b6bb-6fe1-4a47-ba72-03556c43e4d0 |  | checkpoint | Splices,Top Angle fitted & soakers sealed - PHOTO REQUIRED
checkpoint-status | dcda04d4-22cd-4aef-91e5-66f3c52359f5 |  | checkpoint | All Fixings over sealed PHOTO REQUIRED
checkpoint-status | 6abdb546-2ed0-440e-80f1-774d4709c580 |  | checkpoint | Ensure no packers visable out of line where airseal is to be installed.
checkpoint-status | f42d975a-3b03-4de1-8f27-b8cee5ca67c0 |  | checkpoint | Install backer rod - PHOTO REQUIRED
checkpoint-status | da5ce578-b97e-40f1-bdca-5431e478c7a4 |  | checkpoint | Complete airseal within application time allowed - PHOTO REQUIRED
checkpoint-status | 99e497b4-1b62-43fc-8273-6b16e8319a86 |  | checkpoint | Install panels as per drawings
checkpoint-status | 841aa54f-2775-46b3-818f-2710e6ee65fc |  | checkpoint | Install glazing rubber with correct orientation/ no breaks and full height between panel and frame PHOTO'S REQUIRED
checkpoint-status | 39d549ac-6358-4858-8c98-d8bd5d8314ee |  | checkpoint | External flashings / weather seals installed and SEALED if drawing indicates - PHOTO REQUIRED
checkpoint-group | 7e36450f-e266-4c8b-bd6c-32b87ea1650e |  | section | Curtain Wall Internal Checklist
checkpoint-status | c667ef77-b768-4108-a703-1bc2e02cb818 |  | checkpoint | Airseal and internal flashings
checkpoint-status | fb57ead4-f915-498f-bf41-5125fc6575df |  | checkpoint | Ensure no packers visable out of line where airseal is to be installed.
checkpoint-status | b631bbeb-8d63-4a50-ab98-147972f2e036 |  | checkpoint | Panel locked off position as per module PHOTO REQUIRED
checkpoint-status | 45c21211-59f6-4a9d-97b6-1ee9f03c252f |  | checkpoint | Crusifix sealing done on panel to panel cross joints? PHOTO REQUIRED
checkpoint-group | 47fcd9f1-d7b1-4fbe-b9ae-a69ba6cddd12 |  | section | Internal fire seal and trunking
checkpoint-status | e94dd8ab-d9ca-4643-8938-756d79ded382 |  | checkpoint | Galv. Z support clips installed
checkpoint-status | 53202bd8-1fe4-4919-9e72-17cedf7c601a |  | checkpoint | fire insulation installed - PHOTO REQUIRED
checkpoint-status | 70b4842c-23b3-4712-8dc4-df117f53bf6b |  | checkpoint | Trims and closers (smoke seal) - PHOTO REQUIRED
checkpoint-status | e8d41de3-af6a-4502-8af9-1eb0ec3c70fd |  | checkpoint | Sill Trunking Installed - PHOTO REQUIRED
checkpoint-status | 391b6677-b339-4c27-8600-3c3a42e6f1fd |  | checkpoint | Vertical Trunking Installed - PHOTO REQUIRED
checkpoint-group | 93a0c5b4-ec9b-4c65-81e9-bd0a6fa1dbfa |  | section | Fins
checkpoint-status | d85c6f4d-7547-4a3a-b8bf-c0820e738714 |  | checkpoint | Horizontal & Vertical Fins Installed
checkpoint-status | 25b66c9f-5909-43fc-bff8-e06271b373fd |  | checkpoint | Fin bolts tight and locked off as per drawings
checkpoint-group | ba9eecbd-0211-40f8-85fb-b23203060371 |  | section | Glass
checkpoint-status | fa07d144-26a2-43ff-9f08-0ff45dc117d3 |  | checkpoint | Glass installed and no damaged glass
checkpoint-group | f35f3325-dbc0-45ff-ab37-219e4c56d671 |  | section | Wight Aluminium sign off
checkpoint-status | 3dfe5410-90de-4160-a628-28c9c1fea830 |  | checkpoint | Trade clean / protected
checkpoint-status | ad112a9b-9418-4621-916b-c3371c2b43df |  | checkpoint | All elements completed correctly as per specification, reviewed and approved
holdpoint | 30b1dc39-b600-401d-92e7-dfc6fe302d0f |  | signoff | Raise Remedial / Request Signoff
checklist-sectioned | 71431aa3-b656-4bf4-9853-ef958caf5df7 |  | checklist | Shopfront Frame Installation |  |  |  |  | Yes | Shopfront Frame Installation | 48c4b3fd-e2c5-4f2b-8e08-4806b037ddd5
checkpoint-group | f6daee50-838d-4b30-a1cc-ba718a8036a1 |  | section | Joinery Install
checkpoint-status | a708d528-c451-4f43-84a2-d8e1c170eca0 |  | checkpoint | Opening and Sill Acceptable, All elements approved as per drawings
checkpoint-status | 98b87c6f-2b72-476d-8962-99df281453ea |  | checkpoint | Check S/S flashing RL and size
checkpoint-status | 35127364-76fa-4445-879a-1529bc60b64f |  | checkpoint | Check the dimentions & Level (ADD survey drawings in here if not as per drawings)
checkpoint-status | d0d5c1b1-7481-476d-88e4-b310f71d1aef |  | checkpoint | Check rebate is correct as per drawings PHOTO REQUIRED
text | 20f82cf6-a7c7-5b6c-993c-a1fe9f66ea30 |  | textbox
checkpoint-status | 6ffb95a0-fdc2-45ea-a990-e16536cd18a0 |  | checkpoint | Waterproofing ( Check that water proofing is over area where airseal is going to be) PHOTO REQUIRED
checkpoint-status | 2ecac4cc-c6f6-4171-9498-79fd55912217 |  | checkpoint | Check the joinery if there is any damage
checkpoint-status | 6fefd3d5-27ce-48b0-af50-f03a969d0d1a |  | checkpoint | Install the frame perimeter into the position with approved fixing
checkpoint-status | 140f7c53-1d71-407a-ac67-974481a3cdab |  | checkpoint | Install subsill / Deadload blocks/ splicers / soakers
checkpoint-status | a7781e52-831c-4ce2-b14f-7b2f42165c61 |  | checkpoint | Seal anchor bolt to S/S flashing. PHOTO REQUIRED
checkpoint-status | c405ce8b-1b51-42e7-a3a8-40acf7a9cbdb |  | checkpoint | Splices,Top Angle fitted & soakers sealed - PHOTO REQUIRED
checkpoint-status | 37693516-19d0-4c4b-9413-90c2b1807f76 |  | checkpoint | All fixings oversealed on frame and no tooling damage on frame PHOTO REQUIRED
checkpoint-status | 4be493f9-e869-4603-9b22-914d2458bd28 |  | checkpoint | Ensure no packers visable out of line where airseal is to be installed.
checkpoint-status | fe34ac7e-6254-4e6e-bd19-9aa6ae082de6 |  | checkpoint | Application of the Airseal Sealant w/ PE rod complete PHOTO'S REQUIRED
text | c614eb9c-8bb3-5c8b-a6c9-fca0bb6d15b3 |  | textbox
checkpoint-status | 34c117b1-16fe-4d90-b00b-335b28f5a506 |  | checkpoint | Install frames
checkpoint-status | 5bff07d8-c00f-4501-a3b9-6b4f6580f281 |  | checkpoint | Glazing rubber installed around frame and Unit. PHOTO REQUIRED
checkpoint-status | 7dcb56e2-084b-4142-8333-e044845937ab |  | checkpoint | Install fixings to fixoff frames as per drawings PHOTO REQUIRED
checkpoint-status | 384b1443-08cf-4d21-8f75-7ba98233576c |  | checkpoint | flashings installed and sealed as per drawings PHOTO REQUIRED
checkpoint-group | ad67b0e7-bbdd-441e-8b54-211861ef0ffa |  | section | Manual Doors
checkpoint-status | 2590a8ad-9723-4690-b1f9-9622a24e7349 |  | checkpoint | Install the door into the position also the thresholds
checkpoint-status | c052fc2c-5d4c-427e-b905-33a0e624e32a |  | checkpoint | All Door seals installed and complete
checkpoint-status | ab91bf51-2db5-4c8e-a846-18e53a47eb1e |  | checkpoint | All Harware installed and in working order
checkpoint-group | 1839820e-e8e1-492b-8946-034540560a8d |  | section | Glass
checkpoint-status | 5333337a-f5d1-4360-bf05-2f3a2e8b4be0 |  | checkpoint | Glass installed and no damaged glass
checkpoint-group | 7f3b27f0-3cdb-4d51-a59e-55d86728432b |  | section | Wight Aluminium sign off
checkpoint-status | 9f679bc1-4a48-4f20-aaf2-d844959b9dc4 |  | checkpoint | All elements completed correctly as per specification, reviewed and approved
holdpoint | 9dd7f614-db91-4043-afbf-f2fe32df415d |  | signoff | Raise Remedial / Request Signoff