## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | ITC-001 DUCT ROUGH IN |  |  |  |  | Yes | ITC-001 DUCT ROUGH IN | 4bb1a862-d164-44d4-a4bc-5fae22c794a8
checkpoint-status |  |  | checkpoint | Installed to Entire standard (ENT-STD-3.1) and to latest drawings
checkpoint-status |  |  | checkpoint | Cleats installed
checkpoint-status |  |  | checkpoint | Insulated as required
checkpoint-status |  |  | checkpoint | No visible damage
checkpoint-status |  |  | checkpoint | Flex Supported to Entire standard (ENT-STD-1.1)
checkpoint-status |  |  | checkpoint | Seismic restraints installed as per Seismic design
checkpoint-status |  |  | checkpoint | Kitchen Exhaust duct installed and sealed correctly
checkpoint-status |  |  | checkpoint | Fan Coil Units installed as per the latest drawing
checkpoint-status |  |  | checkpoint | Split Units Indoor Unit installed as per the latest drawing
checklist-flat |  |  | checklist | ITC-002 PIPE ROUGH IN |  |  |  |  | Yes | ITC-002 PIPE ROUGH IN | a39e6c3d-6808-4c67-8b2a-48c1bf5158de
checkpoint-status |  |  | checkpoint | Pipes installed to Entire standards and latest drawings
checkpoint-status |  |  | checkpoint | Hydrostatically tested as per (ITC-010 & ITC-011)
checkpoint-status |  |  | checkpoint | Pipes insulated as required
checkpoint-status |  |  | checkpoint | Vibration isolation hangers installed where required as per the design (Level 4 plant room)
checkpoint-status |  |  | checkpoint | Seismic restraints installed as per Seismic design
checkpoint-status |  |  | checkpoint | Drains installed to standard & on correct grade
checkpoint-status |  |  | checkpoint | Refrigeration pressure test as per (ITC-013)
checklist-sectioned |  |  | checklist | ITC-004 Penetration Treatment (sign off by relevant sub contractor) |  |  |  |  | Yes | ITC-004 Penetration Treatment (sign off by relevant sub contractor) | a8da3a94-4fd2-4e51-9d0b-eae640b5ba28
checkpoint-group |  |  | section | Penetrations
checkpoint-status |  |  | checkpoint | Acoustic penetrations correctly sealed
checkpoint-status |  |  | checkpoint | Fire Penetrations correctly sealed
checkpoint-status |  |  | checkpoint | Photos and documentation captured by contractor
checkpoint-status |  |  | checkpoint | Penetrations labeled as required
checklist-sectioned |  |  | checklist | ITC-006 Subcontractor Rough In (sign off by relevant contractor) |  |  |  |  | Yes | ITC-006 Subcontractor Rough In (sign off by relevant contractor) | c21254dc-b709-46b9-b678-684c76f642ae
checkpoint-group |  |  | section | Mechanical Electrical
checkpoint-status |  |  | checkpoint | Mech elec wires installed as per design
checkpoint-status |  |  | checkpoint | MSSB Installed as per design
checkpoint-status |  |  | checkpoint | Wall and or Ceiling rough in complete (If required) ready for closing up by ceiling/wall contractor
checkpoint-group |  |  | section | Controls
checkpoint-status |  |  | checkpoint | Control wire installed as per design
checkpoint-status |  |  | checkpoint | Control Panel Installed as per design
checkpoint-status |  |  | checkpoint | Wall and or Ceiling rough in complete (If required) ready for closing up by ceiling/wall contractor
checkpoint-status |  |  | checkpoint | Devices fit off as required
checkpoint-group |  |  | section | Insulation
checkpoint-status |  |  | checkpoint | Pipe Insulation installed as required
checkpoint-status |  |  | checkpoint | Pipe Cladding Installed as required
checklist-sectioned |  |  | checklist | ITC-07 Fire/smoke damper checklist |  |  |  |  | Yes | ITC-07 Fire/smoke damper checklist | e59f3cc6-43be-4b7b-bfba-ddb049b55cdd
checkpoint-group |  |  | section | Fire/smoke dampers
checkpoint-status |  |  | checkpoint | Access panel in duct / ceiling for damper access, installed
checkpoint-status |  |  | checkpoint | Fire/Smoke dampers labelled
checkpoint-status |  |  | checkpoint | Installed to manufacturers requirements
checklist-sectioned |  |  | checklist | ITC-003 Floor Fit Off |  |  |  |  | Yes | ITC-003 Floor Fit Off | fb607169-562d-4b2b-bbd4-1a947ad7d029
checkpoint-group |  |  | section | Grilles
checkpoint-status |  |  | checkpoint | Installed to latest drawing
checkpoint-status |  |  | checkpoint | Balancing dampers open
checkpoint-status |  |  | checkpoint | No visible damage
checkpoint-group |  |  | section | Filters
checkpoint-status |  |  | checkpoint | Installed to latest drawing
checkpoint-status |  |  | checkpoint | Accessible
checkpoint-group |  |  | section | Equipment
checkpoint-status |  |  | checkpoint | Access panels in correct location
checkpoint-status |  |  | checkpoint | Equipment clearly labelled
checklist-sectioned |  |  | checklist | ITC-005 Equipment Installation Level 4 Plant Room |  |  |  |  | Yes | ITC-005 Equipment Installation Level 4 Plant Room | fdffb885-fcc3-4001-abff-c1a6a384f426
checkpoint-group |  |  | section | Fans
checkpoint-status |  |  | checkpoint | Installed to latest drawing in the correct positions and egress access clearances checked
checkpoint-status |  |  | checkpoint | Vibration isolations installed
checkpoint-status |  |  | checkpoint | Seismic restraints Installed as per Seismic design
checkpoint-status |  |  | checkpoint | Labelled
checkpoint-group |  |  | section | Energy Recovery Systems
checkpoint-status |  |  | checkpoint | Installed to latest drawing in the correct positions and egress access clearances checked
checkpoint-status |  |  | checkpoint | Vibration isolations installed
checkpoint-status |  |  | checkpoint | Seismic restraints Installed as per Seismic design
checkpoint-status |  |  | checkpoint | Unit clearly labelled
checkpoint-group |  |  | section | DX Split Systems Condensing Units
checkpoint-status |  |  | checkpoint | Installed to latest drawing in the correct positions and egress access clearances checked
checkpoint-status |  |  | checkpoint | Vibration isolations installed
checkpoint-status |  |  | checkpoint | Seismic restraints Installed as per Seismic design
checkpoint-status |  |  | checkpoint | Units clearly labelled
checkpoint-group |  |  | section | Chillers
checkpoint-status |  |  | checkpoint | Installed to latest drawing in the correct positions and egress access clearances checked
checkpoint-status |  |  | checkpoint | Vibration isolations installed
checkpoint-status |  |  | checkpoint | Seismic restraints Installed as per Seismic design
checkpoint-status |  |  | checkpoint | Units clearly labelled
checkpoint-group |  |  | section | Pumps
checkpoint-status |  |  | checkpoint | Installed to latest drawing in the correct positions and egress access clearances checked
checkpoint-status |  |  | checkpoint | Vibration isolations installed
checkpoint-status |  |  | checkpoint | Seismic restraints Installed as per Seismic design
checkpoint-status |  |  | checkpoint | Units clearly labelled
checkpoint-group |  |  | section | Buffer Tanks
checkpoint-status |  |  | checkpoint | Installed to latest drawing in the correct positions and egress access clearances checked
checkpoint-status |  |  | checkpoint | Seismic restraints Installed as per Seismic design
checkpoint-status |  |  | checkpoint | Units clearly labelled
checkpoint-group |  |  | section | Expansion and Auto Fill Systems
checkpoint-status |  |  | checkpoint | Installed to latest drawing
checkpoint-status |  |  | checkpoint | Units clearly labelled