## Sheet1
ConQA Team Notes:
Document Title: |  | ITP-088-STR-SSB-CFA Piling
ITP Description: |  | CFA Piling
Discipline (e.g. CIV/STR/RAIL: |  | 088-STR-SSB
Revision Number: |  | 0
Revision Date: |  | 2023-10-06
ITP created by: |  | Victor Mira
ITP approved for use by: |  | Victor Mira
Special Notes to ConQA Team : |  | ITP to be visible for SSB
Inspection & Test Plan - CFA Piling
|  |  | Document No.: | [5 empty] | Revision: | 0
[9 empty] | Date: | 2023-10-06
Legend: HP: Hold Point, HP* Internal Hold Point, WP: Witness Point, IP: Inspection Point, SP: Surveillance Point
Item | Task/Activity Description | Reference | Acceptance Criteria | Inspection / Test |  |  | Responsibility | Verifying Documents | Date Completed | Sign-off
|  |  |  | Method | Frequency | Category
1 | Referenced Documentation
1.1 | Non Dependent | VicRoads Section 607 March 2015 | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
1.2 | Non Dependent | VicRoads Section 610 June 2019 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
1.3 | Non Dependent | VicRoads Section 611 November 2018 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
1.4 | Non Dependent | AS2159-2009 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
1.5 | Non Dependent | AS3810.1-2015 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
1.6 | Non Dependent | AS5100.3-2017 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
2 | Preliminaries - Materials
2.1 | Concrete Mix | 610.07 Table 610.071 | Concrete Mix is Registered with VicRoads. Concrete mix meets strength, grade, and maximum aggregate size as detailed on drawings. Enter: Teambinder Material Approval number [free text box] | Document Review | Once, for each mix design, 4 weeks prior to placement of concrete | HP | Nominated Authority | ConQA Hold Point Release
2.2 | ACRS Certification (for Reinforcement) | 611.05 (a) | Current ACRS certification for materials and for bar processing. Note: ACRS certificate may cover both aspects or be for each separate portion (e.g 1 for the material supplier and another for the bar processor (bending, cropping and delivery) Enter: Teambinder Material Approval number [free text box] | Document Review | Once for each supplier, 14 days of award of contract | HP | Nominated Authority | This ITP
2.3 | Bar Chairs/Aspros Certification | 610.26 (a) | Wheels, and spacers require bi-annual testing to demonstrate suitability to prevent excessive deformation under loads. Enter: Teambinder Material Approval number [free text box] | Document Review | Once for each supplier, 14 days prior to placement of reinforcement | HP | Nominated Authority | This ITP
3 | Preliminaries - Procedures & Documentation
3.1 | Working Platform certification | Piling platform design | Satisfies minimum plant bearing pressures requirement. ATTACH: Piiling Platform Certificate | Document Review | Prior to works commencing & after rain event which there is >10mm in a 24hr period. | HP | Piling Contractor/Geotechnical Engineer/Fulton Hogan Engineer | This ITP Platform Certification
3.2 | Concrete CFA Pile Design | 607.01 IFC Drawings | Concrete CFA piles shall not be used in foundations for bridges and other structures on or over roads without the approval of the Superintendent. Enter: Teambinder Approval number [free text box] | Document Review | Where applicable, once, 4 weeks prior to the commencement of piling | HP | Nominated Authority | This ITP
3.3 | Piling Operations Work Procedure | 606.03 (a) | Piling operations work procedure to be submitted for review to the Nominated Authority. Enter: Teambinder Approval number [free text box] | Document Review | Once, 4 weeks prior to the commencement of piling | HP | Nominated Authority | ConQA Hold Point Release
3.4 | Casting Under Water Procedure | 607.04 | Where applicable, casting under water procedure using a temporary steel casing to be submitted for review to the Nominated Authority. Enter: Teambinder Approval number [free text box] Note: Piling Operations Work Procedure may cover this requirement - if so, use the same Teambinder Approval Number if this is the case. | Document Review | Where applicable, once, prior to placement of concrete | HP | Nominated Authority | This ITP
3.5 | Dynamic Pile Testing Procedure | 607.07 | Details of the proposed pile driving rig, hammer size and drop heights to be submitted for review to the Nominated Authority. Enter: Teambinder Approval number [free text box] | Document Review | Once, prior to testing | HP | Nominated Authority | This ITP
3.6 | Pre-qualified Pile Testing Consultant | 607.07 | All testing shall be undertaken by a Vicroads pre-qualified consultant who is independent of the piling contractor. Details of the consultant to be submitted for review to the Nominated Authority. Enter: Teambinder Approval number [free text box] | Document Review | Once, 2 weeks prior to testing | HP | Nominated Authority | ConQA Hold Point Release
3.7 | Reinforcement Welding Specifications & Qualifications | 611.13 (a) AS/NZS1554.3, Clauses 3.3.2 & 3.3.3 611.14 (b) | Where applicable, welded splices shall not commence until the welding specification & qualifications (including macro inspection) have been submitted for review to the Nominated Authority. Enter: Teambinder Approval number [free text box] | Document Review | Where applicable, once, prior to welding | HP | Nominated Authority | ConQA Hold Point Release
4 | Pre-construction Activities
4.1 | IFC Drawings | MRPA Quality Management Plan | Check the revision of the IFC drawings are current as per the drawing register (on Teambinder) | Document Review | Prior to starting Works and at regular intervals | HP* | All | This ITP
4.2 | Survey Set-out | IFC Drawings 607.06 (a ) | Survey activities undertaken to ensure and validate that all Works meet location requirements of ±75mm. Attach: Lot Map, Marked drawing to indicate the location of piles in the Lot | Measure Visual | Each pile | IP | Surveyor SE/PE/SPE | This ITP
4.3 | Protection of Adjacent Piles | 607.05 | Pile construction shall not result in damage to adjacent newly cast piles due to ground vibration. Pile excavation shall not commence within 2 metres or three pile diameters (whichever is the greater) of a newly cast pile until the concrete in the newly cast pile has attained a strength of 15 MPa | Measure Visual | Each pile | HP* | SPE/PE | This ITP
5 | Construction Activities
5.1 | Reinforcement - Inspection | IFC Drawings 611.06 611.09 611.10 611.11 611.12 | The correct reinforcement grade, quantity, size, orientation, location and spacing as shown on the structural drawings. Projecting reinforcement is the correct length and location. Splice lengths achieve the minimum length and are in contact for this length. The reinforcement surface condition is free from dirt, debris and damage. Bar chairs or wheels used at no greater than 2m centres so that the minimum cover as shown on the structural drawings all around and has been achieved (including tie wire locations). The resulting reinforcement cage securely held with sufficient ties (or tacks) to limit displacement or deformation during handling. | Measure Visual | Each pile | IP | Foreman SE/PE/SPE | This ITP
5.2 | Reinforcement - Electrical Continuity | IFC Drawings 610.29 (d) 610.43 | Pile reinforcement cage to be made electrically continuous by: i. tack welding 4 no. min. longitudinal bars to all intersections of the helix at 2.0m centres max. (at every intersection is preferable) ii. tack welding the selected longitudinal bars at all splices (2 tacks minimum per bar) iii. tack welding or fastening the grounding clamps to the longitudinal reinforcement Evidence that the resistance across the cage has a maximum value of 0.01Ω / 10,000µΩ is required. Photograph or attach: Ohmmeter reading across the splice or end to end of the reinforcement cage | Measure Visual | Where applicable, each pile | IP | Earthing Engineer SE/PE/SPE | This ITP
5.3 | Augering Operations | IFC Drawings 607.04 | Augering performed to the required diameter and depths shown on the IFC Drawings under the instruction of an experienced geotechnical engineer. The augering shall be in once continuous operation with boring rate, penetration rate and torque monitored and recorded through-out the entire process. Where piles are founded on rock, they shall extend into the rock at a depth shown on the IFC Drawings. | Measure Visual | Each pile | IP | Surveyor SE/PE/SPE | This ITP
5.4 | Inspection of Excavated Material | 607.04 | Excavated material to be inspected by the geotechnical engineer to confirm that the geotechnical strength of the materials in the pile wall base have satisfied the design assumptions. Attach: Geotechnical Field Sheet or Report | Measure Visual | Each pile | HP | Geotechnical Engineer | ConQA Hold Point Release
5.5 | Increase in Depth Beyond Design | 607.04 (a - d) Piling Operations Work Procedure | Where increasing the pile depth beyond the levels shown on the IFC Drawings is necessary, follow the approved work procedure and obtain confirmation from the geotechnical engineer that the newly bored depth has achieved the required design capacity. A full account of the changes shall be submitted for approval to the Nominated Authority: Attach: Geotechnical Engineer's Acceptance of the New Pile Depth | Measure Document Review | Where applicable | HP | Geotechnical Engineer | ConQA Hold Point Release
5.6 | Weather Conditions & Evaporation Limits | Hot and/or Cold Weather Concreting Procedure 610.17 610.17 (a) & (e) Table 610.171 | All freshly finished concrete surfaces shall be protected where required from the sun, wind or rain, until curing is implemented. The temperature of concrete, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C. The air temperature, relative humidity, concrete temperature and wind velocity are measured to determine the evaporation rate of water from the concrete. Record: Required information on the Concrete Pour Record. | Measure Visual | Each pile | IP | Foreman SE/PE/SPE | This ITP
5.7 | Concrete Testing - Sampling Frequency | Site Sampling & Testing Procedure 610.16 (b) Table 610.161 | Concrete cast in one continuous operation to be tested at a frequency as shown below: 0m³ to 10m³ = 1 sample 10m³ to 25m³ = 2 samples 25m³ to 50m³ = 3 samples 50m³ to 100m³ = 4 samples + 2 no. VPV cylinders. For each additional 50m³ and additional sample shall be taken. where the time interval between the end of discharge of one truckload of concrete and the beginning of discharge of the next truckload exceeds 45 minutes, the minimum number of test samples shall be one (1) per truckload of concrete Each sample shall consist of 1 no. slump or spread test and 3 no. compressive strength cylinders minimum. Compressive strength cylinders = 1 no. 7 day strength, 2 no. 28 day strength. Note: Additional cylinders may be required for other purposes such as early strength determination of adjacent piles. Record: Required information on the Concrete Pour Record. | Test | Each pile | IP | Concrete Tester Foreman SE/PE/SPE | This ITP
5.8 | Concrete Testing - Spread, Passability & Viscosity | 610.13 (b) | Spread range = 550mm to 750mm T500 = 2 seconds to 5 seconds (to reach a spread of 500mm) Passability = ≤10mm (aggregate height differential) Record: Required information on the Concrete Pour Record. | Test | Each sample of Self-compacting Concrete | IP | Concrete Tester | This ITP
5.9 | Concrete Testing - Compressive Strength Cylinders | Site Sampling & Testing Procedure 610.16 | Correct quantity of cylinders manufactured per sample. Record: Required information on the Concrete Pour Record. | Test | Each sample | IP | Concrete Tester | This ITP
5.10 | Concrete Placement & Compaction | Piling Operations Work Procedure 610.18 (a) & (b) 610.18 (d) (i) 607.04 | All concrete batches are traceable. The concrete delivery hose shall be primed, pressurised before the toe of the auger is extracted. The concrete flow, positive pressure and over-supply rate shall follow the approved Piling operations work procedure, be continuous and monitored through-out the concrete pumping process to ensure that the excavation is completely filled, leaving no voids or inclusions. Pile height is to be constructed to ground level or a 300mm above the cut-off level to allow for breaking back of sound concrete. Concrete shall not be dropped freely from a height exceeding two metres Record: Required information on the Concrete Pour Record. Attach: Concrete Pour Record Attach: Concrete Dockets | Visual | Each load | SP | Foreman SE/PE/SPE
5.11 | Reinforcement - Placement | IFC Drawings 607.04 | The cage to descend into the plastic concrete under its self-weight - care to be taken to centralise the cage so that there is no dislodgement of excavated material contaminating the concrete. Note: Vibration of the cage shall only be performed under approval from the Nominated Authority along with evidence that the vibration does not segregate the placed concrete. If the cage cannot be positioned into its final level, the pile shall be rejected. | Measure Visual | Each pile | IP | Foreman SE/PE/SPE | This ITP
5.12 | Cast-in Items | IFC Drawings 610.46 (a), Table 610.462 (November 2018) 610.47 (a) Table 610.472 (March/June 2019) AS3810.1 Table 3.3.6.2 | All cast-in items are the correct type, grade, quantity, size, orientation and location as shown on the structural drawings and are securely fastened during the hardening of the concrete to prevent dislodgement. Any exposed threads, conduits, ducts or voids shall be protected by suitable means to prevent concrete or grout ingress. Tack welding of any cast-in items shall be performed by someone pre-qualified to do so. Grout tubes shall be fastened at regular intervals to prevent kinking. Placement tolerances to comply with the IFC drawings, if not specified, use the following: i. Bolts, ferrules, projecting bars & couplers = ±3mm ii. Running dimensions of a group of the above = ±6mm iii. Ducts and conduit location = ±12mm iv. Diameter of ducts and conduits = ±3mm | Measure Visual | Where applicable, each pile | IP | Foreman SE/PE/SPE | This ITP
6 | Post-construction Activities
6.1 | Pile Trimming | IFC Drawings AS2159 Clause 7.2.2 - 3 607.04 | Piles shall not be broken back until a minimum of 24 hours after completion of the placement of concrete. Care shall be taken to ensure that the full cross-sectional area of the pile is at the required RL without any cracking or damage. Any weak or damaged concrete shall be removed back to sound concrete. | Measure Visual | Where applicable, each pile | IP | SE/PE/SPE | This ITP
6.2 | Compressive Strength Test Results | IFC Drawings Table 610.05.051 610.16 (g) | 7 day compressive strength to comply with table 610.051 for early indication that the strength is tracking correctly. 28 day compressive strength (average of the 2 no. cylinders) per sample comply with the design strength. Note: 1 of the 2 no. 28 day cylinders per sample may be as low as 90% of the required strength, so long as the average meets the required strength. Attach: Compressive Strength Test Results | Document Review | Each cylinder | IP | SE/PE/SPE | This ITP
6.3 | Pile Integrity Testing | 607.07 AS2159 Clause 8.8 | Pile integrity testing shall be conducted after the concrete strength has reached 25MPa but not less than 7 days from casting. Cross-sectional area = ≥90% Attach: Pile Integrity Test Report | Document Review | Each pile | IP | Testing Consultant SE/PE/SPE | This ITP
6.4 | Dynamic Pile Testing | 607.07 (b) AS2159 Clause 8.7 | Dynamic pile testing shall be conducted after the concrete strength has reached the 28 day compressive strength. Measured Ultimate capacity = ≥ values on IFC drawings Attach: Dynamic Pile Test Report | Document Review | Where applicable, 1 test per pile cap / abutment, where pile toe RL varies >2m from the test pile. | IP | Testing Consultant SE/PE/SPE | This ITP
6.5 | As-built Survey | IFC Drawings 607.06 (a & b) AS2159 Clause 7.2.2 | The following tolerances apply to piles: i. Centre of pile head plan location = ±75mm ii. Variance from vertical or rake = 1:50 iii. Irregularities in straightness = 1:100 iv. RL = ±25mm Attach: Survey As-builts / Survey Report | Document Review | Each pile | IP | Surveyor SE/PE/SPE | This ITP
6.6 | Non-conformance Report (NCR) Closure | MRPA Quality Management Plan | Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed. | Document Review | Once, prior to closure of this lot / element / Work area | HP* | SE/PE/SPE | This ITP
Final Inspection
On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
Print Name: Position: Signature: Date: / /