## Structure
Id | Tier 1 | Tier 2 | Tier 3 | Tier 4 | Tier 5 | Tier 6 | Checklist Template
fo:f004b7af-b1f6-402b-b894-96090918b038 | A1401 Eva Copper Bulk Earthworks
cl:1ad3dc41-7de9-484f-b0ff-7327d7431f2f | A1401 Eva Copper Bulk Earthworks | ITP-000 Pre-construction - Construction Management Plan |  |  |  |  | ITP-000 Pre-construction - CMP
fo:35901629-9ffc-4446-9a45-96515d31a715 | A1401 Eva Copper Bulk Earthworks | ITP-000 Pre-construction - Construction Management Plan AWP1B
fo:7d85d0ae-3cbf-4d88-9de4-3418d4d2937e | Main Access Road (MAR)
cl:3e96928c-d37e-4e84-bb43-759794579864 | Main Access Road (MAR) | MAR-Pre Construction (ITP-000) |  |  |  |  | ITP-000 Pre-construction
fo:d85b44c5-371c-4a09-9847-803f5a1cff4b | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001)
cl:601429a2-74bf-453d-a25e-49aedf0e3811 | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | MAR_C&G |  |  |  | ITP-001 Clear & Grub
cl:b1e3edb5-2407-40c6-b3ea-2e777d5dfc1f | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-003 CH1190 to CH1690 |  |  |  | ITP-001 Clear & Grub
cl:b406a2c5-97ef-41e2-9979-075f7c835861 | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-004 |  |  |  | ITP-001 Clear & Grub
cl:f1e4f780-fc73-44c7-ae56-24c8a8f51645 | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-005 |  |  |  | ITP-001 Clear & Grub
cl:3721ff4f-dbd9-4750-bcc4-9b5b2922141c | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-006 |  |  |  | ITP-001 Clear & Grub
cl:42eb673b-7480-418c-9ff4-deae157d50bf | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-007 |  |  |  | ITP-001 Clear & Grub
cl:e33db8cf-01ab-4374-ac31-dc1e054bc56e | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-008 |  |  |  | ITP-001 Clear & Grub
cl:4f77e1ab-6019-4331-8b69-828314b7b4e9 | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-009 |  |  |  | ITP-001 Clear & Grub
cl:fab03817-8be3-4a5b-bb6e-7b609a819c21 | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-010 |  |  |  | ITP-001 Clear & Grub
cl:1674f482-e023-4aad-a33a-5e7a7c690be6 | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-011 |  |  |  | ITP-001 Clear & Grub
cl:0c070f07-ec98-4b78-97f1-d77ed3524865 | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-012 |  |  |  | ITP-001 Clear & Grub
cl:cd9dfc60-45c5-4236-8353-d2b31a85ac10 | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-013 |  |  |  | ITP-001 Clear & Grub
cl:0effada5-ca7a-4b98-a8c6-6a9c073614b4 | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-014 |  |  |  | ITP-001 Clear & Grub
cl:85d28f37-2ea1-4ea6-b9a0-7d7e71e0a0cf | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-015 |  |  |  | ITP-001 Clear & Grub
cl:a72b0ea7-6afe-4cc0-b964-01304723282a | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-016 |  |  |  | ITP-001 Clear & Grub
cl:051c9f1d-d8c1-464a-bda4-bb415b94b705 | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-017 |  |  |  | ITP-001 Clear & Grub
cl:d1b56c72-d57c-4afd-b716-5641d17210b7 | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-018 |  |  |  | ITP-001 Clear & Grub
fo:57e77821-f560-47f8-8240-56505ee41058 | Main Access Road (MAR) | ITP-002 Topsoil Stripping
cl:dde51873-c2b5-4bea-b167-82115f1a2514 | Main Access Road (MAR) | ITP-002 Topsoil Stripping | MAR_Topsoil Strip |  |  |  | ITP-002 Topsoil Stripping
cl:8317e097-e36c-4786-909c-0676614fd2f0 | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-002 |  |  |  | ITP-002 Topsoil Stripping
cl:2bda6402-ac23-4e73-be43-03c89c1031bc | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-003 |  |  |  | ITP-002 Topsoil Stripping
cl:4f8d8ae6-4e61-4fe7-85fd-c923ce0a90b4 | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-004 |  |  |  | ITP-002 Topsoil Stripping
cl:bde07827-3e74-4f9c-ac80-4be5ff966004 | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-005 |  |  |  | ITP-002 Topsoil Stripping
cl:098b6870-213c-4c04-b4b8-a728d554843f | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-006 |  |  |  | ITP-002 Topsoil Stripping
cl:cd3ee4c6-dc94-48db-95dd-856df713ad3b | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-007 |  |  |  | ITP-002 Topsoil Stripping
cl:890586ba-3090-4dbf-9301-4c42131e6071 | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-008 |  |  |  | ITP-002 Topsoil Stripping
cl:8d598f4d-ceaa-45b0-8440-e65f16dd4594 | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-009 |  |  |  | ITP-002 Topsoil Stripping
cl:5e887b02-4eff-475f-88ec-1338b04019ac | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-010 |  |  |  | ITP-002 Topsoil Stripping
cl:e7d0f507-3ba6-4741-888e-5b243a81ba4a | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-011 |  |  |  | ITP-002 Topsoil Stripping
cl:498fa056-53e6-4adf-836a-db22afe3c868 | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-012 |  |  |  | ITP-002 Topsoil Stripping
cl:22b7127d-bfb7-4635-a01d-3fdec26b5a48 | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-013 |  |  |  | ITP-002 Topsoil Stripping
cl:c05fcc86-fd09-437f-b001-613dac76b03b | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-014 |  |  |  | ITP-002 Topsoil Stripping
cl:a48b81b5-f8da-4249-a9ba-d92a49debb55 | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-015 |  |  |  | ITP-002 Topsoil Stripping
cl:6f3bc2e6-9027-42ca-b7d0-ad548a1c31db | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-016 |  |  |  | ITP-002 Topsoil Stripping
cl:32331128-a4ca-4fcd-ad45-79bcd149cee1 | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-017 |  |  |  | ITP-002 Topsoil Stripping
fo:24f6d677-01bc-417a-999b-bf709c6e8293 | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation
cl:5faede6d-452d-473d-9d83-053657020978 | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-001 CH192 to CH265 |  |  |  | ITP-003 Subgrade/Foundation Preparation
cl:dd921dce-64f6-4358-8403-c80cd07d931b | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-002 |  |  |  | ITP-003 Subgrade/Foundation Preparation
cl:dfd435c3-f0c0-4b2f-b551-fc40fbf36967 | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-003 |  |  |  | ITP-003 Subgrade/Foundation Preparation
cl:daf905da-f777-4c54-a111-92e86f98d02b | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-004 CH732 to CH1050 |  |  |  | ITP-003 Subgrade/Foundation Preparation
cl:8c4c1f20-301a-4faa-82ae-3a21fb30320b | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-005 |  |  |  | ITP-003 Subgrade/Foundation Preparation
cl:8a8758d6-38e3-445b-b0be-0ebd2130b1a2 | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-006 |  |  |  | ITP-003 Subgrade/Foundation Preparation
cl:c3a4e319-d9e4-4abf-8ab0-310e329d8dfb | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-007 |  |  |  | ITP-003 Subgrade/Foundation Preparation
cl:e2120dd6-877c-4aca-ab5a-3f38539ba750 | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-008 |  |  |  | ITP-003 Subgrade/Foundation Preparation
cl:9e446b56-5b71-414c-b651-c19177db5219 | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-009 |  |  |  | ITP-003 Subgrade/Foundation Preparation
cl:0c6af84e-b3e2-4e3d-8a46-279a72951b31 | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-010 |  |  |  | ITP-003 Subgrade/Foundation Preparation
cl:16292971-d3e5-4945-b32c-5b65fd414654 | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-011 |  |  |  | ITP-003 Subgrade/Foundation Preparation
cl:e7554a30-6ea5-4fa1-b698-ffcee940ce63 | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-012 |  |  |  | ITP-003 Subgrade/Foundation Preparation
cl:12f8a2b1-6bca-4b5a-97fd-c5bfbfceb333 | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-013 |  |  |  | ITP-003 Subgrade/Foundation Preparation
cl:87ce06d5-dab0-4bd6-a3eb-f91859570e1c | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-014 |  |  |  | ITP-003 Subgrade/Foundation Preparation
cl:87a11975-8cc5-4b0b-bf54-fa5714dfd860 | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-015 |  |  |  | ITP-003 Subgrade/Foundation Preparation
cl:f93d9f8c-c94e-4d09-a0e1-8375e5292ea7 | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-016 |  |  |  | ITP-003 Subgrade/Foundation Preparation
cl:0a32f121-dd2d-4b60-8836-1f780e04db42 | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-017 |  |  |  | ITP-003 Subgrade/Foundation Preparation
fo:a717e159-76f7-4258-86b9-569121b26d83 | Main Access Road (MAR) | ITP-004 RCP Installation
cl:eb4aa3a2-74b6-428c-9b75-1400a2dcc6c5 | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-001 |  |  |  | ITP-004 RCP Installation
cl:72b6fca6-3997-40a7-ad4f-c5f8f57abcac | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-002 |  |  |  | ITP-004 RCP Installation
cl:ef0d1275-885b-4ee9-b427-9f5bbda141ad | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-003 |  |  |  | ITP-004 RCP Installation
cl:a1582baf-1390-4cee-8145-7bd0946116f2 | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-004 |  |  |  | ITP-004 RCP Installation
cl:56672165-5146-4425-9bd6-510c095ba0d3 | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-005_1415 |  |  |  | ITP-004 RCP Installation
cl:e0b7a3cf-bb64-4ec4-8455-5da0e1444bdc | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-006_CH1564 |  |  |  | ITP-004 RCP Installation
cl:54aef0c1-90a6-42ab-b32f-50385b4126e4 | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-007_2355 |  |  |  | ITP-004 RCP Installation
cl:334a960a-bfaf-4175-a384-024b6765292d | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-008_CH2385 |  |  |  | ITP-004 RCP Installation
cl:ef206ea2-e824-42ff-9ec1-9cbca5556483 | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-009_2715 |  |  |  | ITP-004 RCP Installation
cl:d7fe2708-d0db-468e-8422-c639bfc5cca0 | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-010 |  |  |  | ITP-004 RCP Installation
cl:8584bee6-a760-4608-9e42-1727da0b9fed | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-011 |  |  |  | ITP-004 RCP Installation
cl:9dbc8f4c-c2f4-4fe6-9994-249789a85e2f | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-012 |  |  |  | ITP-004 RCP Installation
cl:2717c2dd-f499-4b9b-a7d1-e4e58773c9b5 | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-013 |  |  |  | ITP-004 RCP Installation
cl:3097c0b9-989c-4421-b2eb-94085d48b7d9 | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-014 |  |  |  | ITP-004 RCP Installation
cl:b9f58684-3edb-42e5-8a7d-cc6530eeea36 | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-015 |  |  |  | ITP-004 RCP Installation
cl:74498f1b-f1b4-4d43-a846-ed5ebaf88e1a | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-016 |  |  |  | ITP-004 RCP Installation
cl:0876f56a-2c12-48dc-8a0f-0e0c0dd35b52 | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-017 |  |  |  | ITP-004 RCP Installation
fo:37b7317d-c0d3-43dc-aca5-3d01a63f7871 | Main Access Road (MAR) | ITP-004 RCP Installation | Global RCP
cl:422980e3-ac79-4913-b4ad-54ef63cf0d32 | Main Access Road (MAR) | ITP-004 RCP Installation | Global RCP | ITP-004 RCP Installation-MAR-018 - Global |  |  | ITP-004 RCP Installation
fo:75b4516d-a6b1-44ae-a9a8-5f917a360ae2 | Main Access Road (MAR) | ITP-008 Embankment Construction
cl:677bd369-096a-4938-9fa5-fc2031fac91e | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-001 |  |  |  | ITP-008 Embankment Construction
cl:55dd702f-9ef0-4d44-b31c-11f4a89a057c | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-002 |  |  |  | ITP-008 Embankment Construction
cl:21ed1d63-15df-421c-8ea0-1662ef191936 | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-003 |  |  |  | ITP-008 Embankment Construction
cl:72b1db10-1292-4f46-b3bf-822d4bc53073 | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-004 |  |  |  | ITP-008 Embankment Construction
cl:71558f67-7388-476c-b403-7bdf8ca4578b | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-005 |  |  |  | ITP-008 Embankment Construction
cl:8815128e-ec87-48da-a663-0f168a937a26 | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-006 |  |  |  | ITP-008 Embankment Construction
cl:b5312136-2d65-40fb-a4ea-3adcb065938b | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-007 |  |  |  | ITP-008 Embankment Construction
cl:16667826-9565-4d11-b909-c2201b54448b | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-008 |  |  |  | ITP-008 Embankment Construction
cl:c7b6301c-1383-4a62-b466-ac1369643971 | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-009 |  |  |  | ITP-008 Embankment Construction
cl:48f8a636-f478-4fde-b1b2-bd0342c530df | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-010 |  |  |  | ITP-008 Embankment Construction
cl:1d69aa48-b390-4956-ace2-858e4bcf6c56 | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-011 |  |  |  | ITP-008 Embankment Construction
cl:a8234618-0e56-45ee-8c35-e5aa30bb12cb | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-012 |  |  |  | ITP-008 Embankment Construction
cl:edde45ff-09a9-49cc-b485-0fd70ebadf74 | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-013 |  |  |  | ITP-008 Embankment Construction
cl:c9959181-8906-4731-9758-8476ccbc2ae4 | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-014 |  |  |  | ITP-008 Embankment Construction
cl:1d851afd-6473-4983-86ff-3944ee158b12 | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-015 |  |  |  | ITP-008 Embankment Construction
cl:b88a7678-4b1d-4d3f-b470-553e064a93e4 | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-016 |  |  |  | ITP-008 Embankment Construction
cl:40473b7b-e086-45dd-a85c-dc23e476f2f3 | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-017 |  |  |  | ITP-008 Embankment Construction
fo:1e4854a5-aee2-4d2f-b11f-8d2bc2919597 | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements
cl:3ab8f4bf-0aba-4f15-9b6a-18f0b2f28529 | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-001 |  |  |  | ITP-009 Unbound Gravel Pavements
cl:7d8b619b-e51f-4180-943b-6f39301cd46e | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-002 |  |  |  | ITP-009 Unbound Gravel Pavements
cl:9c2e4830-6b5e-4d6d-9ece-69056bc38f4d | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-003 |  |  |  | ITP-009 Unbound Gravel Pavements
cl:ded39db4-f2a2-4925-b6ab-9cb39d7a8bf4 | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-004 |  |  |  | ITP-009 Unbound Gravel Pavements
cl:5c51972b-e8fc-4c9e-b95a-77776cedcf01 | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-005 |  |  |  | ITP-009 Unbound Gravel Pavements
cl:cd26b24b-154d-4209-bd7f-c15eaa603b5d | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-006 |  |  |  | ITP-009 Unbound Gravel Pavements
cl:d2221e0e-7fec-4435-b9e9-ce8c59a00f43 | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-007 |  |  |  | ITP-009 Unbound Gravel Pavements
cl:8bf7387d-1f7f-49cc-91b0-9d65f23d51ae | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-008 |  |  |  | ITP-009 Unbound Gravel Pavements
cl:4135d0fd-e369-4db5-8b1d-64b555bface3 | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-009 |  |  |  | ITP-009 Unbound Gravel Pavements
cl:cd217768-3a25-4510-9a00-4a324a6b7d53 | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-010 |  |  |  | ITP-009 Unbound Gravel Pavements
cl:60e52ec7-e21f-4914-989d-dab702e49363 | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-011 |  |  |  | ITP-009 Unbound Gravel Pavements
cl:cd8e4393-0349-44c2-b395-3fa06e343cc2 | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-012 |  |  |  | ITP-009 Unbound Gravel Pavements
cl:782443f2-4ab3-4828-bbf1-0077f779e483 | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-013 |  |  |  | ITP-009 Unbound Gravel Pavements
cl:799a734d-2a84-4459-bef2-728a6f1a1fd0 | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-014 |  |  |  | ITP-009 Unbound Gravel Pavements
cl:102244ca-aa1f-4286-9f8d-e192b970b302 | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-015 |  |  |  | ITP-009 Unbound Gravel Pavements
cl:2109d4a3-b736-4722-97b9-3f90f38d7a11 | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-016 |  |  |  | ITP-009 Unbound Gravel Pavements
cl:c791f107-4611-4016-950b-83138e3a4a0e | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-017 |  |  |  | ITP-009 Unbound Gravel Pavements
fo:95a10aa0-b143-41df-94ec-19fd11ecb5a6 | AWP-1A
fo:7d85d0ae-3cbf-4d88-9de4-3418d4d2937e | AWP-1A | Main Access Road (MAR)
cl:3e96928c-d37e-4e84-bb43-759794579864 | AWP-1A | Main Access Road (MAR) | MAR-Pre Construction (ITP-000) |  |  |  | ITP-000 Pre-construction
fo:d85b44c5-371c-4a09-9847-803f5a1cff4b | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001)
cl:601429a2-74bf-453d-a25e-49aedf0e3811 | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | MAR_C&G |  |  | ITP-001 Clear & Grub
cl:b1e3edb5-2407-40c6-b3ea-2e777d5dfc1f | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-003 CH1190 to CH1690 |  |  | ITP-001 Clear & Grub
cl:b406a2c5-97ef-41e2-9979-075f7c835861 | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-004 |  |  | ITP-001 Clear & Grub
cl:f1e4f780-fc73-44c7-ae56-24c8a8f51645 | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-005 |  |  | ITP-001 Clear & Grub
cl:3721ff4f-dbd9-4750-bcc4-9b5b2922141c | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-006 |  |  | ITP-001 Clear & Grub
cl:42eb673b-7480-418c-9ff4-deae157d50bf | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-007 |  |  | ITP-001 Clear & Grub
cl:e33db8cf-01ab-4374-ac31-dc1e054bc56e | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-008 |  |  | ITP-001 Clear & Grub
cl:4f77e1ab-6019-4331-8b69-828314b7b4e9 | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-009 |  |  | ITP-001 Clear & Grub
cl:fab03817-8be3-4a5b-bb6e-7b609a819c21 | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-010 |  |  | ITP-001 Clear & Grub
cl:1674f482-e023-4aad-a33a-5e7a7c690be6 | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-011 |  |  | ITP-001 Clear & Grub
cl:0c070f07-ec98-4b78-97f1-d77ed3524865 | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-012 |  |  | ITP-001 Clear & Grub
cl:cd9dfc60-45c5-4236-8353-d2b31a85ac10 | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-013 |  |  | ITP-001 Clear & Grub
cl:0effada5-ca7a-4b98-a8c6-6a9c073614b4 | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-014 |  |  | ITP-001 Clear & Grub
cl:85d28f37-2ea1-4ea6-b9a0-7d7e71e0a0cf | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-015 |  |  | ITP-001 Clear & Grub
cl:a72b0ea7-6afe-4cc0-b964-01304723282a | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-016 |  |  | ITP-001 Clear & Grub
cl:051c9f1d-d8c1-464a-bda4-bb415b94b705 | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-017 |  |  | ITP-001 Clear & Grub
cl:d1b56c72-d57c-4afd-b716-5641d17210b7 | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-018 |  |  | ITP-001 Clear & Grub
fo:57e77821-f560-47f8-8240-56505ee41058 | AWP-1A | Main Access Road (MAR) | ITP-002 Topsoil Stripping
cl:dde51873-c2b5-4bea-b167-82115f1a2514 | AWP-1A | Main Access Road (MAR) | ITP-002 Topsoil Stripping | MAR_Topsoil Strip |  |  | ITP-002 Topsoil Stripping
cl:8317e097-e36c-4786-909c-0676614fd2f0 | AWP-1A | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-002 |  |  | ITP-002 Topsoil Stripping
cl:2bda6402-ac23-4e73-be43-03c89c1031bc | AWP-1A | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-003 |  |  | ITP-002 Topsoil Stripping
cl:4f8d8ae6-4e61-4fe7-85fd-c923ce0a90b4 | AWP-1A | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-004 |  |  | ITP-002 Topsoil Stripping
cl:bde07827-3e74-4f9c-ac80-4be5ff966004 | AWP-1A | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-005 |  |  | ITP-002 Topsoil Stripping
cl:098b6870-213c-4c04-b4b8-a728d554843f | AWP-1A | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-006 |  |  | ITP-002 Topsoil Stripping
cl:cd3ee4c6-dc94-48db-95dd-856df713ad3b | AWP-1A | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-007 |  |  | ITP-002 Topsoil Stripping
cl:890586ba-3090-4dbf-9301-4c42131e6071 | AWP-1A | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-008 |  |  | ITP-002 Topsoil Stripping
cl:8d598f4d-ceaa-45b0-8440-e65f16dd4594 | AWP-1A | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-009 |  |  | ITP-002 Topsoil Stripping
cl:5e887b02-4eff-475f-88ec-1338b04019ac | AWP-1A | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-010 |  |  | ITP-002 Topsoil Stripping
cl:e7d0f507-3ba6-4741-888e-5b243a81ba4a | AWP-1A | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-011 |  |  | ITP-002 Topsoil Stripping
cl:498fa056-53e6-4adf-836a-db22afe3c868 | AWP-1A | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-012 |  |  | ITP-002 Topsoil Stripping
cl:22b7127d-bfb7-4635-a01d-3fdec26b5a48 | AWP-1A | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-013 |  |  | ITP-002 Topsoil Stripping
cl:c05fcc86-fd09-437f-b001-613dac76b03b | AWP-1A | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-014 |  |  | ITP-002 Topsoil Stripping
cl:a48b81b5-f8da-4249-a9ba-d92a49debb55 | AWP-1A | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-015 |  |  | ITP-002 Topsoil Stripping
cl:6f3bc2e6-9027-42ca-b7d0-ad548a1c31db | AWP-1A | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-016 |  |  | ITP-002 Topsoil Stripping
cl:32331128-a4ca-4fcd-ad45-79bcd149cee1 | AWP-1A | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-017 |  |  | ITP-002 Topsoil Stripping
fo:24f6d677-01bc-417a-999b-bf709c6e8293 | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation
cl:5faede6d-452d-473d-9d83-053657020978 | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-001 CH192 to CH265 |  |  | ITP-003 Subgrade/Foundation Preparation
cl:dd921dce-64f6-4358-8403-c80cd07d931b | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-002 |  |  | ITP-003 Subgrade/Foundation Preparation
cl:dfd435c3-f0c0-4b2f-b551-fc40fbf36967 | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-003 |  |  | ITP-003 Subgrade/Foundation Preparation
cl:daf905da-f777-4c54-a111-92e86f98d02b | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-004 CH732 to CH1050 |  |  | ITP-003 Subgrade/Foundation Preparation
cl:8c4c1f20-301a-4faa-82ae-3a21fb30320b | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-005 |  |  | ITP-003 Subgrade/Foundation Preparation
cl:8a8758d6-38e3-445b-b0be-0ebd2130b1a2 | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-006 |  |  | ITP-003 Subgrade/Foundation Preparation
cl:c3a4e319-d9e4-4abf-8ab0-310e329d8dfb | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-007 |  |  | ITP-003 Subgrade/Foundation Preparation
cl:e2120dd6-877c-4aca-ab5a-3f38539ba750 | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-008 |  |  | ITP-003 Subgrade/Foundation Preparation
cl:9e446b56-5b71-414c-b651-c19177db5219 | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-009 |  |  | ITP-003 Subgrade/Foundation Preparation
cl:0c6af84e-b3e2-4e3d-8a46-279a72951b31 | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-010 |  |  | ITP-003 Subgrade/Foundation Preparation
cl:16292971-d3e5-4945-b32c-5b65fd414654 | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-011 |  |  | ITP-003 Subgrade/Foundation Preparation
cl:e7554a30-6ea5-4fa1-b698-ffcee940ce63 | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-012 |  |  | ITP-003 Subgrade/Foundation Preparation
cl:12f8a2b1-6bca-4b5a-97fd-c5bfbfceb333 | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-013 |  |  | ITP-003 Subgrade/Foundation Preparation
cl:87ce06d5-dab0-4bd6-a3eb-f91859570e1c | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-014 |  |  | ITP-003 Subgrade/Foundation Preparation
cl:87a11975-8cc5-4b0b-bf54-fa5714dfd860 | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-015 |  |  | ITP-003 Subgrade/Foundation Preparation
cl:f93d9f8c-c94e-4d09-a0e1-8375e5292ea7 | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-016 |  |  | ITP-003 Subgrade/Foundation Preparation
cl:0a32f121-dd2d-4b60-8836-1f780e04db42 | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-017 |  |  | ITP-003 Subgrade/Foundation Preparation
fo:a717e159-76f7-4258-86b9-569121b26d83 | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation
cl:eb4aa3a2-74b6-428c-9b75-1400a2dcc6c5 | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-001 |  |  | ITP-004 RCP Installation
cl:72b6fca6-3997-40a7-ad4f-c5f8f57abcac | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-002 |  |  | ITP-004 RCP Installation
cl:ef0d1275-885b-4ee9-b427-9f5bbda141ad | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-003 |  |  | ITP-004 RCP Installation
cl:a1582baf-1390-4cee-8145-7bd0946116f2 | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-004 |  |  | ITP-004 RCP Installation
cl:56672165-5146-4425-9bd6-510c095ba0d3 | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-005_1415 |  |  | ITP-004 RCP Installation
cl:e0b7a3cf-bb64-4ec4-8455-5da0e1444bdc | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-006_CH1564 |  |  | ITP-004 RCP Installation
cl:54aef0c1-90a6-42ab-b32f-50385b4126e4 | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-007_2355 |  |  | ITP-004 RCP Installation
cl:334a960a-bfaf-4175-a384-024b6765292d | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-008_CH2385 |  |  | ITP-004 RCP Installation
cl:ef206ea2-e824-42ff-9ec1-9cbca5556483 | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-009_2715 |  |  | ITP-004 RCP Installation
cl:d7fe2708-d0db-468e-8422-c639bfc5cca0 | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-010 |  |  | ITP-004 RCP Installation
cl:8584bee6-a760-4608-9e42-1727da0b9fed | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-011 |  |  | ITP-004 RCP Installation
cl:9dbc8f4c-c2f4-4fe6-9994-249789a85e2f | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-012 |  |  | ITP-004 RCP Installation
cl:2717c2dd-f499-4b9b-a7d1-e4e58773c9b5 | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-013 |  |  | ITP-004 RCP Installation
cl:3097c0b9-989c-4421-b2eb-94085d48b7d9 | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-014 |  |  | ITP-004 RCP Installation
cl:b9f58684-3edb-42e5-8a7d-cc6530eeea36 | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-015 |  |  | ITP-004 RCP Installation
cl:74498f1b-f1b4-4d43-a846-ed5ebaf88e1a | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-016 |  |  | ITP-004 RCP Installation
cl:0876f56a-2c12-48dc-8a0f-0e0c0dd35b52 | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-017 |  |  | ITP-004 RCP Installation
fo:37b7317d-c0d3-43dc-aca5-3d01a63f7871 | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | Global RCP
cl:422980e3-ac79-4913-b4ad-54ef63cf0d32 | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | Global RCP | ITP-004 RCP Installation-MAR-018 - Global |  | ITP-004 RCP Installation
fo:75b4516d-a6b1-44ae-a9a8-5f917a360ae2 | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction
cl:677bd369-096a-4938-9fa5-fc2031fac91e | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-001 |  |  | ITP-008 Embankment Construction
cl:55dd702f-9ef0-4d44-b31c-11f4a89a057c | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-002 |  |  | ITP-008 Embankment Construction
cl:21ed1d63-15df-421c-8ea0-1662ef191936 | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-003 |  |  | ITP-008 Embankment Construction
cl:72b1db10-1292-4f46-b3bf-822d4bc53073 | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-004 |  |  | ITP-008 Embankment Construction
cl:71558f67-7388-476c-b403-7bdf8ca4578b | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-005 |  |  | ITP-008 Embankment Construction
cl:8815128e-ec87-48da-a663-0f168a937a26 | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-006 |  |  | ITP-008 Embankment Construction
cl:b5312136-2d65-40fb-a4ea-3adcb065938b | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-007 |  |  | ITP-008 Embankment Construction
cl:16667826-9565-4d11-b909-c2201b54448b | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-008 |  |  | ITP-008 Embankment Construction
cl:c7b6301c-1383-4a62-b466-ac1369643971 | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-009 |  |  | ITP-008 Embankment Construction
cl:48f8a636-f478-4fde-b1b2-bd0342c530df | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-010 |  |  | ITP-008 Embankment Construction
cl:1d69aa48-b390-4956-ace2-858e4bcf6c56 | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-011 |  |  | ITP-008 Embankment Construction
cl:a8234618-0e56-45ee-8c35-e5aa30bb12cb | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-012 |  |  | ITP-008 Embankment Construction
cl:edde45ff-09a9-49cc-b485-0fd70ebadf74 | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-013 |  |  | ITP-008 Embankment Construction
cl:c9959181-8906-4731-9758-8476ccbc2ae4 | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-014 |  |  | ITP-008 Embankment Construction
cl:1d851afd-6473-4983-86ff-3944ee158b12 | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-015 |  |  | ITP-008 Embankment Construction
cl:b88a7678-4b1d-4d3f-b470-553e064a93e4 | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-016 |  |  | ITP-008 Embankment Construction
cl:40473b7b-e086-45dd-a85c-dc23e476f2f3 | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-017 |  |  | ITP-008 Embankment Construction
fo:1e4854a5-aee2-4d2f-b11f-8d2bc2919597 | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements
cl:3ab8f4bf-0aba-4f15-9b6a-18f0b2f28529 | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-001 |  |  | ITP-009 Unbound Gravel Pavements
cl:7d8b619b-e51f-4180-943b-6f39301cd46e | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-002 |  |  | ITP-009 Unbound Gravel Pavements
cl:9c2e4830-6b5e-4d6d-9ece-69056bc38f4d | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-003 |  |  | ITP-009 Unbound Gravel Pavements
cl:ded39db4-f2a2-4925-b6ab-9cb39d7a8bf4 | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-004 |  |  | ITP-009 Unbound Gravel Pavements
cl:5c51972b-e8fc-4c9e-b95a-77776cedcf01 | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-005 |  |  | ITP-009 Unbound Gravel Pavements
cl:cd26b24b-154d-4209-bd7f-c15eaa603b5d | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-006 |  |  | ITP-009 Unbound Gravel Pavements
cl:d2221e0e-7fec-4435-b9e9-ce8c59a00f43 | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-007 |  |  | ITP-009 Unbound Gravel Pavements
cl:8bf7387d-1f7f-49cc-91b0-9d65f23d51ae | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-008 |  |  | ITP-009 Unbound Gravel Pavements
cl:4135d0fd-e369-4db5-8b1d-64b555bface3 | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-009 |  |  | ITP-009 Unbound Gravel Pavements
cl:cd217768-3a25-4510-9a00-4a324a6b7d53 | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-010 |  |  | ITP-009 Unbound Gravel Pavements
cl:60e52ec7-e21f-4914-989d-dab702e49363 | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-011 |  |  | ITP-009 Unbound Gravel Pavements
cl:cd8e4393-0349-44c2-b395-3fa06e343cc2 | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-012 |  |  | ITP-009 Unbound Gravel Pavements
cl:782443f2-4ab3-4828-bbf1-0077f779e483 | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-013 |  |  | ITP-009 Unbound Gravel Pavements
cl:799a734d-2a84-4459-bef2-728a6f1a1fd0 | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-014 |  |  | ITP-009 Unbound Gravel Pavements
cl:102244ca-aa1f-4286-9f8d-e192b970b302 | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-015 |  |  | ITP-009 Unbound Gravel Pavements
cl:2109d4a3-b736-4722-97b9-3f90f38d7a11 | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-016 |  |  | ITP-009 Unbound Gravel Pavements
cl:c791f107-4611-4016-950b-83138e3a4a0e | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-017 |  |  | ITP-009 Unbound Gravel Pavements
fo:0c928e20-2a87-4c4d-8bd5-d49fc55285aa | AWP-1A | Village Access Road
cl:ce5f8716-8a08-452a-83f4-ab67299b6b5f | AWP-1A | Village Access Road | ITP-000 Pre-construction-VAR |  |  |  | ITP-000 Pre-construction
fo:fe09df21-500d-45c7-80d6-a23a9f46db7c | AWP-1A | Village Access Road | ITP-001 Clear & Grub
cl:eec82efc-3ac4-44da-a09b-e7aa54d50a73 | AWP-1A | Village Access Road | ITP-001 Clear & Grub | ITP-001 Clear & Grub-VAR-001 |  |  | ITP-001 Clear & Grub
cl:96088604-9e73-4737-92c8-b182ebea7e73 | AWP-1A | Village Access Road | ITP-001 Clear & Grub | ITP-001 Clear & Grub-VAR-002 |  |  | ITP-001 Clear & Grub
fo:1a9212f2-c597-4f0a-86ba-4a534a1f8c54 | AWP-1A | Village Access Road | ITP-002 Topsoil Stripping
cl:2f7f622b-dee3-40fa-b4d4-d11aff2d618f | AWP-1A | Village Access Road | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-VAR-001 |  |  | ITP-002 Topsoil Stripping
cl:b06d0ba7-4979-4431-8a84-397bacc12308 | AWP-1A | Village Access Road | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-VAR-002 |  |  | ITP-002 Topsoil Stripping
fo:af77ee01-10ad-4e1a-a5e7-43cc17662234 | AWP-1A | Village Access Road | ITP-003 Subgrade/Foundation Preparation
cl:2addc368-ad46-4a60-8a50-f442ecc3a00c | AWP-1A | Village Access Road | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-VAR-001 |  |  | ITP-003 Subgrade/Foundation Preparation
cl:8700bf87-789c-42c6-962c-8599ed772427 | AWP-1A | Village Access Road | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-VAR-002 |  |  | ITP-003 Subgrade/Foundation Preparation
fo:48e5770a-2e74-42f4-9e23-6a6b30bc841b | AWP-1A | Village Access Road | ITP-004 RCP Installation
cl:8203d441-4a86-407c-bb91-4c1aab0c5def | AWP-1A | Village Access Road | ITP-004 RCP Installation | ITP-004 RCP Installation-VAR-001 |  |  | ITP-004 RCP Installation
cl:9dd4ae65-c256-4d9b-a28e-98dfe0a92616 | AWP-1A | Village Access Road | ITP-004 RCP Installation | ITP-004 RCP Installation-VAR-002 |  |  | ITP-004 RCP Installation
fo:e9afbb01-b20f-4142-a67b-2e8d849ff4d0 | AWP-1A | Village Access Road | ITP-008 Embankment Construction
cl:d03a27b9-4791-498b-a7b0-88ddcb11e7f0 | AWP-1A | Village Access Road | ITP-008 Embankment Construction | ITP-008 Embankment Construction-VAR-001 |  |  | ITP-008 Embankment Construction
cl:08b4f1e7-d822-4d9f-88b2-748d2d979e83 | AWP-1A | Village Access Road | ITP-008 Embankment Construction | ITP-008 Embankment Construction-VAR-002 |  |  | ITP-008 Embankment Construction
fo:57da40bc-a2a9-417c-a52a-3cdbab9e170a | AWP-1A | Village Access Road | ITP-009 Unbound Gravel Pavements
cl:eaa0e5ad-0014-4d40-91d4-2543189b840d | AWP-1A | Village Access Road | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-VAR-001 |  |  | ITP-009 Unbound Gravel Pavements
cl:12ac3408-6f63-41d1-9325-bd7fd5d5c990 | AWP-1A | Village Access Road | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-VAR-002 |  |  | ITP-009 Unbound Gravel Pavements
fo:1e9e31df-0cd1-41fa-8912-4d769310929a | AWP-1A | Turkeys Nest
cl:863b5df0-70cf-44bb-81d8-1398c8f7ace6 | AWP-1A | Turkeys Nest | ITP-000 Pre-construction-TN |  |  |  | ITP-000 Pre-construction
fo:ed8dee25-253b-45bd-ba2e-9d6c67697794 | AWP-1A | Turkeys Nest | ITP-001 Clear & Grub
cl:9c1e0124-17e1-4f0d-9222-fb83608c0278 | AWP-1A | Turkeys Nest | ITP-001 Clear & Grub | ITP-001 Clear & Grub-TN-001 |  |  | ITP-001 Clear & Grub
fo:3bd7449c-5423-4687-b603-dc9b6257b6dd | AWP-1A | Turkeys Nest | ITP-002 Topsoil Stripping
cl:c785cedb-987d-47ed-a39c-68580156cfef | AWP-1A | Turkeys Nest | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-TN-001 |  |  | ITP-002 Topsoil Stripping
fo:dae28d4b-9193-40fe-ba4a-519d7097ffc8 | AWP-1A | Turkeys Nest | ITP-003 Subgrade/Foundation Preparation
cl:a1d00da8-7c41-42d6-b580-d852ad6f4015 | AWP-1A | Turkeys Nest | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-TN-001 |  |  | ITP-003 Subgrade/Foundation Preparation
fo:272795d0-2a8e-4f8b-b759-4f948b7b3c0b | AWP-1A | Turkeys Nest | ITP-004 RCP Installation
cl:a68f9673-a993-4460-aef7-eb828693691b | AWP-1A | Turkeys Nest | ITP-004 RCP Installation | ITP-004 RCP Installation-TN-001 |  |  | ITP-004 RCP Installation
fo:3f091cbf-098c-4bbc-b39c-1806e4b4bbeb | AWP-1A | Turkeys Nest | ITP-008 Embankment Construction
cl:bf9e7e0d-5416-4121-9d39-cd434327914b | AWP-1A | Turkeys Nest | ITP-008 Embankment Construction | ITP-008 Embankment Construction-TN-001 |  |  | ITP-008 Embankment Construction
fo:7b1697c3-85fc-4743-bd2f-36958dfafb5a | AWP-1A | Turkeys Nest | ITP-009 Unbound Gravel Pavements
cl:4c018e8a-b33e-468b-b03a-7a98da8469f8 | AWP-1A | Turkeys Nest | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-TN-001 |  |  | ITP-009 Unbound Gravel Pavements
fo:02bf0ee6-f108-4dd4-903f-2f8dceb4af8b | AWP-1A | Village Pad
cl:a873b51e-ed65-44d2-a656-be824629281a | AWP-1A | Village Pad | ITP-000 Pre-construction-VP |  |  |  | ITP-000 Pre-construction
fo:6ea5f570-2552-4240-a115-249514b179be | AWP-1A | Village Pad | ITP-001 Clear & Grub
cl:dcd0b356-bcb7-492f-8bd8-1f03b6a49c33 | AWP-1A | Village Pad | ITP-001 Clear & Grub | ITP-001 Clear & Grub-VP-001 |  |  | ITP-001 Clear & Grub
fo:e424628c-5625-479c-91aa-35e78fbb1ccf | AWP-1A | Village Pad | ITP-002 Topsoil Stripping
cl:7b5ca7e4-80a1-4638-8249-e4f8e6871ba4 | AWP-1A | Village Pad | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-VP-001 |  |  | ITP-002 Topsoil Stripping
fo:c4748140-36a1-4596-b785-5fc0d8141231 | AWP-1A | Village Pad | ITP-003 Foundation Preparation-VP
cl:b49cbe14-4567-4781-bde0-d751a945ad52 | AWP-1A | Village Pad | ITP-003 Foundation Preparation-VP | ITP-003 Foundation Preparation-VP002.003.010.011.014.015_FP1 |  |  | ITP-003 Subgrade/Foundation Preparation
cl:190640f7-fe77-42dd-9dcf-f0dc4cc8569f | AWP-1A | Village Pad | ITP-003 Foundation Preparation-VP | ITP-003 Foundation Preparation-VP004.005.006.007.008.017.018_FP2 |  |  | ITP-003 Subgrade/Foundation Preparation
cl:8fe28aa9-4762-4573-ad1f-c93fd32862a6 | AWP-1A | Village Pad | ITP-003 Foundation Preparation-VP | ITP-003 Foundation Preparation-VP001.012.013_FP3 |  |  | ITP-003 Subgrade/Foundation Preparation
fo:80994afa-a53d-40c0-b4f6-d85f75378086 | AWP-1A | Village Pad | ITP-004 RCP Installation
cl:cda7526f-5945-417c-a387-8dae7b459a1f | AWP-1A | Village Pad | ITP-004 RCP Installation | ITP-004 RCP Installation-VP-001 |  |  | ITP-004 RCP Installation
fo:3ac19088-7aa9-4bc4-bcde-240ff7039a7c | AWP-1A | Village Pad | ITP-008 Embankment Construction
cl:b212dd87-d68c-47b0-a5e5-6bdbcc3b5473 | AWP-1A | Village Pad | ITP-008 Embankment Construction | ITP-008 Embankment Construction-VP-001 |  |  | ITP-008 Embankment Construction
fo:dd6db870-7c87-4327-9fd2-9c9309a7e4d0 | AWP-1A | Village Pad | ITP-009 Unbound Gravel Pavements
cl:3fe0627c-caaf-4216-b936-e959750e1735 | AWP-1A | Village Pad | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-VP-001 |  |  | ITP-009 Unbound Gravel Pavements
cl:bcfe35ca-d308-438a-9c66-9112a48dc484 | AWP-1A | Village Pad | ITP-009 Unbound Gravel Pavements | ITP-003 Subgrade/Foundation Preparation-VP-008 - 008/017_FP5,FP7 |  |  | ITP-003 Subgrade/Foundation Preparation
fo:0c928e20-2a87-4c4d-8bd5-d49fc55285aa | Village Access Road
cl:ce5f8716-8a08-452a-83f4-ab67299b6b5f | Village Access Road | ITP-000 Pre-construction-VAR |  |  |  |  | ITP-000 Pre-construction
fo:fe09df21-500d-45c7-80d6-a23a9f46db7c | Village Access Road | ITP-001 Clear & Grub
cl:eec82efc-3ac4-44da-a09b-e7aa54d50a73 | Village Access Road | ITP-001 Clear & Grub | ITP-001 Clear & Grub-VAR-001 |  |  |  | ITP-001 Clear & Grub
cl:96088604-9e73-4737-92c8-b182ebea7e73 | Village Access Road | ITP-001 Clear & Grub | ITP-001 Clear & Grub-VAR-002 |  |  |  | ITP-001 Clear & Grub
fo:1a9212f2-c597-4f0a-86ba-4a534a1f8c54 | Village Access Road | ITP-002 Topsoil Stripping
cl:2f7f622b-dee3-40fa-b4d4-d11aff2d618f | Village Access Road | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-VAR-001 |  |  |  | ITP-002 Topsoil Stripping
cl:b06d0ba7-4979-4431-8a84-397bacc12308 | Village Access Road | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-VAR-002 |  |  |  | ITP-002 Topsoil Stripping
fo:af77ee01-10ad-4e1a-a5e7-43cc17662234 | Village Access Road | ITP-003 Subgrade/Foundation Preparation
cl:2addc368-ad46-4a60-8a50-f442ecc3a00c | Village Access Road | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-VAR-001 |  |  |  | ITP-003 Subgrade/Foundation Preparation
cl:8700bf87-789c-42c6-962c-8599ed772427 | Village Access Road | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-VAR-002 |  |  |  | ITP-003 Subgrade/Foundation Preparation
fo:48e5770a-2e74-42f4-9e23-6a6b30bc841b | Village Access Road | ITP-004 RCP Installation
cl:8203d441-4a86-407c-bb91-4c1aab0c5def | Village Access Road | ITP-004 RCP Installation | ITP-004 RCP Installation-VAR-001 |  |  |  | ITP-004 RCP Installation
cl:9dd4ae65-c256-4d9b-a28e-98dfe0a92616 | Village Access Road | ITP-004 RCP Installation | ITP-004 RCP Installation-VAR-002 |  |  |  | ITP-004 RCP Installation
fo:e9afbb01-b20f-4142-a67b-2e8d849ff4d0 | Village Access Road | ITP-008 Embankment Construction
cl:d03a27b9-4791-498b-a7b0-88ddcb11e7f0 | Village Access Road | ITP-008 Embankment Construction | ITP-008 Embankment Construction-VAR-001 |  |  |  | ITP-008 Embankment Construction
cl:08b4f1e7-d822-4d9f-88b2-748d2d979e83 | Village Access Road | ITP-008 Embankment Construction | ITP-008 Embankment Construction-VAR-002 |  |  |  | ITP-008 Embankment Construction
fo:57da40bc-a2a9-417c-a52a-3cdbab9e170a | Village Access Road | ITP-009 Unbound Gravel Pavements
cl:eaa0e5ad-0014-4d40-91d4-2543189b840d | Village Access Road | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-VAR-001 |  |  |  | ITP-009 Unbound Gravel Pavements
cl:12ac3408-6f63-41d1-9325-bd7fd5d5c990 | Village Access Road | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-VAR-002 |  |  |  | ITP-009 Unbound Gravel Pavements
fo:ad08f53e-1753-4db8-8842-8446e5b8061a | AWP-1B
fo:215ffbc9-6981-478a-9609-8a75952ba833 | AWP-1B | Process Plant
cl:dbbb96c4-cbaf-4489-9dc8-5cca11326792 | AWP-1B | Process Plant | ITP-000 Pre-construction-PP |  |  |  | ITP-000 Pre-construction
fo:cfe91acb-5478-4a53-8569-4515ba9e7906 | AWP-1B | Process Plant | ITP-001 Clear & Grub
cl:9b3084a9-2ff3-4c55-a4cf-1ef6945702b5 | AWP-1B | Process Plant | ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-001 |  |  | ITP-001 Clear & Grub
cl:263d5a5c-0e10-4f86-b4d7-e052179fb61d | AWP-1B | Process Plant | ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-002 |  |  | ITP-001 Clear & Grub
cl:45cb3de9-b82e-4bcd-b795-eb8fc7c59f10 | AWP-1B | Process Plant | ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-003 |  |  | ITP-001 Clear & Grub
cl:4941b796-b809-4e6d-bbb0-cdb857d5144e | AWP-1B | Process Plant | ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-004 |  |  | ITP-001 Clear & Grub
cl:e94c4960-c452-405f-956e-1f03cd758a70 | AWP-1B | Process Plant | ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-005 |  |  | ITP-001 Clear & Grub
cl:79d2a2d6-46cf-4299-9604-afcd416acd33 | AWP-1B | Process Plant | ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-006 |  |  | ITP-001 Clear & Grub
fo:9c5a4a3d-692e-45c6-a307-80c51f137e0d | AWP-1B | Process Plant | ITP-002 Topsoil Stripping
cl:87d789b1-653f-43e1-b6a0-1fc2c40e8973 | AWP-1B | Process Plant | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-PP-001 |  |  | ITP-002 Topsoil Stripping
cl:112ff002-8ffb-443f-b91d-8cda3058e037 | AWP-1B | Process Plant | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-PP-002 |  |  | ITP-002 Topsoil Stripping
cl:d98da602-4a75-4ac3-9326-9818772e906c | AWP-1B | Process Plant | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-PP-003 |  |  | ITP-002 Topsoil Stripping
cl:ab80b72a-3510-4f6a-bca7-c488e1578588 | AWP-1B | Process Plant | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-PP-004 |  |  | ITP-002 Topsoil Stripping
cl:b995c116-cc00-483d-a290-50f2c7deeb2c | AWP-1B | Process Plant | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-PP-005 |  |  | ITP-002 Topsoil Stripping
cl:bce65fde-c703-4ac8-9b3b-17e5b4eeb76a | AWP-1B | Process Plant | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-PP-006 |  |  | ITP-002 Topsoil Stripping
fo:7649e56f-41c2-421b-b180-f2d24991dbd9 | AWP-1B | Process Plant | ITP-003 Subgrade/Foundation Preparation
cl:7d2202b9-930d-41a4-a326-190917c09d4f | AWP-1B | Process Plant | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-PP-001 |  |  | ITP-003 Subgrade/Foundation Preparation
cl:1d16e40f-dbc0-4e18-9127-6c88e225c757 | AWP-1B | Process Plant | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-PP-002 |  |  | ITP-003 Subgrade/Foundation Preparation
cl:8647b7b5-ffd1-4566-8a6d-f4ebbd94e6ac | AWP-1B | Process Plant | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-PP-003 |  |  | ITP-003 Subgrade/Foundation Preparation
cl:559c6287-adee-4dfa-8ec7-b979dad2fb7c | AWP-1B | Process Plant | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-PP-004 |  |  | ITP-003 Subgrade/Foundation Preparation
cl:0065894c-41ff-4c17-8285-413a35f383ae | AWP-1B | Process Plant | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-PP-005 |  |  | ITP-003 Subgrade/Foundation Preparation
cl:cf3526a3-39c6-4ed8-b27a-160122a63181 | AWP-1B | Process Plant | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-PP-006 |  |  | ITP-003 Subgrade/Foundation Preparation
fo:7ecc4b1a-dbc7-4ce6-9686-79ef3bf1ec39 | AWP-1B | Process Plant | ITP-004 RCP Installation
cl:327686f6-4cfc-42c5-bb1a-33d56d1d6b82 | AWP-1B | Process Plant | ITP-004 RCP Installation | ITP-004 RCP Installation-PP-001 |  |  | ITP-004 RCP Installation
cl:78c12252-ccdc-44f0-8ec8-a1e7a7add732 | AWP-1B | Process Plant | ITP-004 RCP Installation | ITP-004 RCP Installation-PP-002 |  |  | ITP-004 RCP Installation
cl:ea5712bd-2726-4f90-aef1-88828567cfab | AWP-1B | Process Plant | ITP-004 RCP Installation | ITP-004 RCP Installation-PP-003 |  |  | ITP-004 RCP Installation
cl:b3da67de-d5f8-4307-9505-6854525fd8b5 | AWP-1B | Process Plant | ITP-004 RCP Installation | ITP-004 RCP Installation-PP-004 |  |  | ITP-004 RCP Installation
cl:716ed9c9-4c7b-482b-a67d-0b6da1f448f3 | AWP-1B | Process Plant | ITP-004 RCP Installation | ITP-004 RCP Installation-PP-005 |  |  | ITP-004 RCP Installation
cl:0ec6dbf8-4c10-4c45-998d-72abcbf29ad6 | AWP-1B | Process Plant | ITP-004 RCP Installation | ITP-004 RCP Installation-PP-006 |  |  | ITP-004 RCP Installation
fo:1dbf4df1-5474-4785-bb68-680b9e26d5f5 | AWP-1B | Process Plant | ITP-008 Embankment Construction
cl:34a0f8ef-207f-4f96-9919-9e5c4749c252 | AWP-1B | Process Plant | ITP-008 Embankment Construction | ITP-008 Embankment Construction-PP-001 |  |  | ITP-008 Embankment Construction
cl:9386c9cd-c572-49f2-b0db-9a4e30c5081e | AWP-1B | Process Plant | ITP-008 Embankment Construction | ITP-008 Embankment Construction-PP-002 |  |  | ITP-008 Embankment Construction
cl:35a4ec69-97d7-430c-90f4-cfab9eeccef8 | AWP-1B | Process Plant | ITP-008 Embankment Construction | ITP-008 Embankment Construction-PP-003 |  |  | ITP-008 Embankment Construction
cl:62bc3b8f-7bba-4d2a-9590-a2eacee51cfc | AWP-1B | Process Plant | ITP-008 Embankment Construction | ITP-008 Embankment Construction-PP-004 |  |  | ITP-008 Embankment Construction
cl:6d7cd6c4-190a-4308-89f3-2f5727f1a541 | AWP-1B | Process Plant | ITP-008 Embankment Construction | ITP-008 Embankment Construction-PP-005 |  |  | ITP-008 Embankment Construction
cl:36c50743-d7f9-4c31-9411-9c7dfd700e26 | AWP-1B | Process Plant | ITP-008 Embankment Construction | ITP-008 Embankment Construction-PP-006 |  |  | ITP-008 Embankment Construction
fo:ee077d69-b805-4d7a-b62b-ff9302d003b2 | AWP-1B | Process Plant | ITP-009 Unbound Gravel Pavements
cl:e5240338-56e4-487c-b409-020c3bff2d7e | AWP-1B | Process Plant | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-001 |  |  | ITP-009 Unbound Gravel Pavements
cl:1413e480-0f68-49b0-a36b-fd35f6e91974 | AWP-1B | Process Plant | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-002 |  |  | ITP-009 Unbound Gravel Pavements
cl:189e3c23-6d1e-4997-a42a-ccab401c7352 | AWP-1B | Process Plant | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-003 |  |  | ITP-009 Unbound Gravel Pavements
cl:8c7ea01e-ab45-4fcd-8e50-1b5d4302be9c | AWP-1B | Process Plant | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-004 |  |  | ITP-009 Unbound Gravel Pavements
cl:769af0f8-c942-4998-9524-7e8b1acf89a8 | AWP-1B | Process Plant | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-005 |  |  | ITP-009 Unbound Gravel Pavements
cl:f1f0156b-a60c-48c3-b0ee-4780306e1fa8 | AWP-1B | Process Plant | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-006 |  |  | ITP-009 Unbound Gravel Pavements
fo:60bb873f-cd50-4758-b6db-747b91e911bd | AWP-1B | Quarry
fo:f1847459-6995-4fe3-8759-bdcf566dddb7 | AWP-1B | Quarry | ITP-000 Pre-construction
fo:c91758dd-e159-4ce1-9172-fa374e4f40bc | AWP-1B | Quarry | ITP-001 Clear & Grub
fo:ae3f602c-ed36-45f0-95cb-19be014399ea | AWP-1B | Quarry | ITP-002 Topsoil Stripping
fo:4e3f0fcd-9ee8-4cf9-9716-65fb48456d8f | AWP-1B | Quarry | ITP-003 Subgrade/Foundation Preparation
fo:9931e61c-63d9-4071-b8df-9f887532a4f5 | AWP-1B | Quarry | ITP-004 RCP Installation
fo:721da968-82b5-4e1b-9392-3a215a7d8141 | AWP-1B | Quarry | ITP-008 Embankment Construction
fo:0e68f1fd-452b-41d2-b52d-719d8e806bba | AWP-1B | Quarry | ITP-008 Subgrade
fo:5e9cc9e8-16de-48d2-b855-25c423ff999a | AWP-1B | Quarry | ITP-009 Unbound Gravel Pavements
fo:55df4b49-b25e-4fe6-a052-48a151ff1aea | AWP-1B | Quarry | ITP-00X Road Signs

## Checklists
Id | Project | Location | Checklist Name | Status | Checklist Template | Tier 1 | Tier 2 | Tier 3 | Tier 4 | Tier 5 | Tier 6
cl:1ad3dc41-7de9-484f-b0ff-7327d7431f2f | EVA Copper Mine Project | A1401 Eva Copper Bulk Earthworks | ITP-000 Pre-construction - Construction Management Plan | In progress | ITP-000 Pre-construction - CMP | A1401 Eva Copper Bulk Earthworks | ITP-000 Pre-construction - Construction Management Plan
cl:3e96928c-d37e-4e84-bb43-759794579864 | EVA Copper Mine Project | Main Access Road (MAR) | MAR-Pre Construction (ITP-000) | In progress | ITP-000 Pre-construction | Main Access Road (MAR) | MAR-Pre Construction (ITP-000)
cl:601429a2-74bf-453d-a25e-49aedf0e3811 | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | MAR_C&G | In progress | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | MAR_C&G
cl:b1e3edb5-2407-40c6-b3ea-2e777d5dfc1f | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-003 CH1190 to CH1690 | In progress | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-003 CH1190 to CH1690
cl:b406a2c5-97ef-41e2-9979-075f7c835861 | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-004 | In progress | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-004
cl:f1e4f780-fc73-44c7-ae56-24c8a8f51645 | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-005 | In progress | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-005
cl:3721ff4f-dbd9-4750-bcc4-9b5b2922141c | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-006 | In progress | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-006
cl:42eb673b-7480-418c-9ff4-deae157d50bf | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-007 | In progress | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-007
cl:e33db8cf-01ab-4374-ac31-dc1e054bc56e | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-008 | Not started | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-008
cl:4f77e1ab-6019-4331-8b69-828314b7b4e9 | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-009 | In progress | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-009
cl:fab03817-8be3-4a5b-bb6e-7b609a819c21 | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-010 | In progress | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-010
cl:1674f482-e023-4aad-a33a-5e7a7c690be6 | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-011 | In progress | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-011
cl:0c070f07-ec98-4b78-97f1-d77ed3524865 | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-012 | In progress | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-012
cl:cd9dfc60-45c5-4236-8353-d2b31a85ac10 | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-013 | In progress | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-013
cl:0effada5-ca7a-4b98-a8c6-6a9c073614b4 | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-014 | In progress | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-014
cl:85d28f37-2ea1-4ea6-b9a0-7d7e71e0a0cf | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-015 | In progress | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-015
cl:a72b0ea7-6afe-4cc0-b964-01304723282a | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-016 | In progress | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-016
cl:051c9f1d-d8c1-464a-bda4-bb415b94b705 | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-017 | In progress | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-017
cl:d1b56c72-d57c-4afd-b716-5641d17210b7 | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-018 | In progress | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-018
cl:dde51873-c2b5-4bea-b167-82115f1a2514 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-002 Topsoil Stripping | MAR_Topsoil Strip | In progress | ITP-002 Topsoil Stripping | Main Access Road (MAR) | ITP-002 Topsoil Stripping | MAR_Topsoil Strip
cl:8317e097-e36c-4786-909c-0676614fd2f0 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-002 | Not started | ITP-002 Topsoil Stripping | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-002
cl:2bda6402-ac23-4e73-be43-03c89c1031bc | EVA Copper Mine Project | Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-003 | Not started | ITP-002 Topsoil Stripping | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-003
cl:4f8d8ae6-4e61-4fe7-85fd-c923ce0a90b4 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-004 | Not started | ITP-002 Topsoil Stripping | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-004
cl:bde07827-3e74-4f9c-ac80-4be5ff966004 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-005 | Not started | ITP-002 Topsoil Stripping | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-005
cl:098b6870-213c-4c04-b4b8-a728d554843f | EVA Copper Mine Project | Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-006 | Not started | ITP-002 Topsoil Stripping | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-006
cl:cd3ee4c6-dc94-48db-95dd-856df713ad3b | EVA Copper Mine Project | Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-007 | Not started | ITP-002 Topsoil Stripping | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-007
cl:890586ba-3090-4dbf-9301-4c42131e6071 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-008 | Not started | ITP-002 Topsoil Stripping | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-008
cl:8d598f4d-ceaa-45b0-8440-e65f16dd4594 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-009 | Not started | ITP-002 Topsoil Stripping | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-009
cl:5e887b02-4eff-475f-88ec-1338b04019ac | EVA Copper Mine Project | Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-010 | Not started | ITP-002 Topsoil Stripping | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-010
cl:e7d0f507-3ba6-4741-888e-5b243a81ba4a | EVA Copper Mine Project | Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-011 | Not started | ITP-002 Topsoil Stripping | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-011
cl:498fa056-53e6-4adf-836a-db22afe3c868 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-012 | Not started | ITP-002 Topsoil Stripping | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-012
cl:22b7127d-bfb7-4635-a01d-3fdec26b5a48 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-013 | Not started | ITP-002 Topsoil Stripping | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-013
cl:c05fcc86-fd09-437f-b001-613dac76b03b | EVA Copper Mine Project | Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-014 | Not started | ITP-002 Topsoil Stripping | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-014
cl:a48b81b5-f8da-4249-a9ba-d92a49debb55 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-015 | Not started | ITP-002 Topsoil Stripping | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-015
cl:6f3bc2e6-9027-42ca-b7d0-ad548a1c31db | EVA Copper Mine Project | Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-016 | Not started | ITP-002 Topsoil Stripping | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-016
cl:32331128-a4ca-4fcd-ad45-79bcd149cee1 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-017 | Not started | ITP-002 Topsoil Stripping | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-017
cl:5faede6d-452d-473d-9d83-053657020978 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-001 CH192 to CH265 | In progress | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-001 CH192 to CH265
cl:dd921dce-64f6-4358-8403-c80cd07d931b | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-002 | In progress | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-002
cl:dfd435c3-f0c0-4b2f-b551-fc40fbf36967 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-003 | In progress | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-003
cl:daf905da-f777-4c54-a111-92e86f98d02b | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-004 CH732 to CH1050 | In progress | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-004 CH732 to CH1050
cl:8c4c1f20-301a-4faa-82ae-3a21fb30320b | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-005 | Not started | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-005
cl:8a8758d6-38e3-445b-b0be-0ebd2130b1a2 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-006 | Not started | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-006
cl:c3a4e319-d9e4-4abf-8ab0-310e329d8dfb | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-007 | Not started | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-007
cl:e2120dd6-877c-4aca-ab5a-3f38539ba750 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-008 | Not started | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-008
cl:9e446b56-5b71-414c-b651-c19177db5219 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-009 | Not started | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-009
cl:0c6af84e-b3e2-4e3d-8a46-279a72951b31 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-010 | Not started | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-010
cl:16292971-d3e5-4945-b32c-5b65fd414654 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-011 | Not started | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-011
cl:e7554a30-6ea5-4fa1-b698-ffcee940ce63 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-012 | Not started | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-012
cl:12f8a2b1-6bca-4b5a-97fd-c5bfbfceb333 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-013 | Not started | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-013
cl:87ce06d5-dab0-4bd6-a3eb-f91859570e1c | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-014 | Not started | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-014
cl:87a11975-8cc5-4b0b-bf54-fa5714dfd860 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-015 | Not started | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-015
cl:f93d9f8c-c94e-4d09-a0e1-8375e5292ea7 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-016 | Not started | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-016
cl:0a32f121-dd2d-4b60-8836-1f780e04db42 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-017 | Not started | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-017
cl:eb4aa3a2-74b6-428c-9b75-1400a2dcc6c5 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-001 | In progress | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-001
cl:72b6fca6-3997-40a7-ad4f-c5f8f57abcac | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-002 | In progress | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-002
cl:ef0d1275-885b-4ee9-b427-9f5bbda141ad | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-003 | In progress | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-003
cl:a1582baf-1390-4cee-8145-7bd0946116f2 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-004 | In progress | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-004
cl:56672165-5146-4425-9bd6-510c095ba0d3 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-005_1415 | In progress | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-005_1415
cl:e0b7a3cf-bb64-4ec4-8455-5da0e1444bdc | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-006_CH1564 | In progress | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-006_CH1564
cl:54aef0c1-90a6-42ab-b32f-50385b4126e4 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-007_2355 | In progress | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-007_2355
cl:334a960a-bfaf-4175-a384-024b6765292d | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-008_CH2385 | In progress | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-008_CH2385
cl:ef206ea2-e824-42ff-9ec1-9cbca5556483 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-009_2715 | In progress | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-009_2715
cl:d7fe2708-d0db-468e-8422-c639bfc5cca0 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-010 | In progress | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-010
cl:8584bee6-a760-4608-9e42-1727da0b9fed | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-011 | Not started | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-011
cl:9dbc8f4c-c2f4-4fe6-9994-249789a85e2f | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-012 | Not started | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-012
cl:2717c2dd-f499-4b9b-a7d1-e4e58773c9b5 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-013 | Not started | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-013
cl:3097c0b9-989c-4421-b2eb-94085d48b7d9 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-014 | Not started | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-014
cl:b9f58684-3edb-42e5-8a7d-cc6530eeea36 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-015 | Not started | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-015
cl:74498f1b-f1b4-4d43-a846-ed5ebaf88e1a | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-016 | Not started | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-016
cl:0876f56a-2c12-48dc-8a0f-0e0c0dd35b52 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-017 | Not started | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-017
cl:422980e3-ac79-4913-b4ad-54ef63cf0d32 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation > Global RCP | ITP-004 RCP Installation-MAR-018 - Global | In progress | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | Global RCP | ITP-004 RCP Installation-MAR-018 - Global
cl:677bd369-096a-4938-9fa5-fc2031fac91e | EVA Copper Mine Project | Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-001 | In progress | ITP-008 Embankment Construction | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-001
cl:55dd702f-9ef0-4d44-b31c-11f4a89a057c | EVA Copper Mine Project | Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-002 | Not started | ITP-008 Embankment Construction | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-002
cl:21ed1d63-15df-421c-8ea0-1662ef191936 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-003 | Not started | ITP-008 Embankment Construction | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-003
cl:72b1db10-1292-4f46-b3bf-822d4bc53073 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-004 | Not started | ITP-008 Embankment Construction | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-004
cl:71558f67-7388-476c-b403-7bdf8ca4578b | EVA Copper Mine Project | Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-005 | Not started | ITP-008 Embankment Construction | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-005
cl:8815128e-ec87-48da-a663-0f168a937a26 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-006 | Not started | ITP-008 Embankment Construction | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-006
cl:b5312136-2d65-40fb-a4ea-3adcb065938b | EVA Copper Mine Project | Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-007 | Not started | ITP-008 Embankment Construction | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-007
cl:16667826-9565-4d11-b909-c2201b54448b | EVA Copper Mine Project | Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-008 | Not started | ITP-008 Embankment Construction | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-008
cl:c7b6301c-1383-4a62-b466-ac1369643971 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-009 | Not started | ITP-008 Embankment Construction | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-009
cl:48f8a636-f478-4fde-b1b2-bd0342c530df | EVA Copper Mine Project | Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-010 | Not started | ITP-008 Embankment Construction | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-010
cl:1d69aa48-b390-4956-ace2-858e4bcf6c56 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-011 | Not started | ITP-008 Embankment Construction | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-011
cl:a8234618-0e56-45ee-8c35-e5aa30bb12cb | EVA Copper Mine Project | Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-012 | Not started | ITP-008 Embankment Construction | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-012
cl:edde45ff-09a9-49cc-b485-0fd70ebadf74 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-013 | Not started | ITP-008 Embankment Construction | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-013
cl:c9959181-8906-4731-9758-8476ccbc2ae4 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-014 | Not started | ITP-008 Embankment Construction | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-014
cl:1d851afd-6473-4983-86ff-3944ee158b12 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-015 | Not started | ITP-008 Embankment Construction | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-015
cl:b88a7678-4b1d-4d3f-b470-553e064a93e4 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-016 | Not started | ITP-008 Embankment Construction | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-016
cl:40473b7b-e086-45dd-a85c-dc23e476f2f3 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-017 | Not started | ITP-008 Embankment Construction | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-017
cl:3ab8f4bf-0aba-4f15-9b6a-18f0b2f28529 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-001 | Not started | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-001
cl:7d8b619b-e51f-4180-943b-6f39301cd46e | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-002 | Not started | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-002
cl:9c2e4830-6b5e-4d6d-9ece-69056bc38f4d | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-003 | Not started | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-003
cl:ded39db4-f2a2-4925-b6ab-9cb39d7a8bf4 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-004 | Not started | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-004
cl:5c51972b-e8fc-4c9e-b95a-77776cedcf01 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-005 | Not started | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-005
cl:cd26b24b-154d-4209-bd7f-c15eaa603b5d | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-006 | Not started | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-006
cl:d2221e0e-7fec-4435-b9e9-ce8c59a00f43 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-007 | Not started | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-007
cl:8bf7387d-1f7f-49cc-91b0-9d65f23d51ae | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-008 | Not started | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-008
cl:4135d0fd-e369-4db5-8b1d-64b555bface3 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-009 | Not started | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-009
cl:cd217768-3a25-4510-9a00-4a324a6b7d53 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-010 | Not started | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-010
cl:60e52ec7-e21f-4914-989d-dab702e49363 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-011 | Not started | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-011
cl:cd8e4393-0349-44c2-b395-3fa06e343cc2 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-012 | Not started | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-012
cl:782443f2-4ab3-4828-bbf1-0077f779e483 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-013 | Not started | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-013
cl:799a734d-2a84-4459-bef2-728a6f1a1fd0 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-014 | Not started | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-014
cl:102244ca-aa1f-4286-9f8d-e192b970b302 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-015 | Not started | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-015
cl:2109d4a3-b736-4722-97b9-3f90f38d7a11 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-016 | Not started | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-016
cl:c791f107-4611-4016-950b-83138e3a4a0e | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-017 | Not started | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-017
cl:3e96928c-d37e-4e84-bb43-759794579864 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) | MAR-Pre Construction (ITP-000) | In progress | ITP-000 Pre-construction | AWP-1A | Main Access Road (MAR) | MAR-Pre Construction (ITP-000)
cl:601429a2-74bf-453d-a25e-49aedf0e3811 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | MAR_C&G | In progress | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | MAR_C&G
cl:b1e3edb5-2407-40c6-b3ea-2e777d5dfc1f | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-003 CH1190 to CH1690 | In progress | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-003 CH1190 to CH1690
cl:b406a2c5-97ef-41e2-9979-075f7c835861 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-004 | In progress | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-004
cl:f1e4f780-fc73-44c7-ae56-24c8a8f51645 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-005 | In progress | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-005
cl:3721ff4f-dbd9-4750-bcc4-9b5b2922141c | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-006 | In progress | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-006
cl:42eb673b-7480-418c-9ff4-deae157d50bf | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-007 | In progress | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-007
cl:e33db8cf-01ab-4374-ac31-dc1e054bc56e | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-008 | Not started | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-008
cl:4f77e1ab-6019-4331-8b69-828314b7b4e9 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-009 | In progress | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-009
cl:fab03817-8be3-4a5b-bb6e-7b609a819c21 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-010 | In progress | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-010
cl:1674f482-e023-4aad-a33a-5e7a7c690be6 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-011 | In progress | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-011
cl:0c070f07-ec98-4b78-97f1-d77ed3524865 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-012 | In progress | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-012
cl:cd9dfc60-45c5-4236-8353-d2b31a85ac10 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-013 | In progress | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-013
cl:0effada5-ca7a-4b98-a8c6-6a9c073614b4 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-014 | In progress | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-014
cl:85d28f37-2ea1-4ea6-b9a0-7d7e71e0a0cf | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-015 | In progress | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-015
cl:a72b0ea7-6afe-4cc0-b964-01304723282a | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-016 | In progress | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-016
cl:051c9f1d-d8c1-464a-bda4-bb415b94b705 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-017 | In progress | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-017
cl:d1b56c72-d57c-4afd-b716-5641d17210b7 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-018 | In progress | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-018
cl:dde51873-c2b5-4bea-b167-82115f1a2514 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-002 Topsoil Stripping | MAR_Topsoil Strip | In progress | ITP-002 Topsoil Stripping | AWP-1A | Main Access Road (MAR) | ITP-002 Topsoil Stripping | MAR_Topsoil Strip
cl:8317e097-e36c-4786-909c-0676614fd2f0 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-002 | Not started | ITP-002 Topsoil Stripping | AWP-1A | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-002
cl:2bda6402-ac23-4e73-be43-03c89c1031bc | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-003 | Not started | ITP-002 Topsoil Stripping | AWP-1A | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-003
cl:4f8d8ae6-4e61-4fe7-85fd-c923ce0a90b4 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-004 | Not started | ITP-002 Topsoil Stripping | AWP-1A | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-004
cl:bde07827-3e74-4f9c-ac80-4be5ff966004 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-005 | Not started | ITP-002 Topsoil Stripping | AWP-1A | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-005
cl:098b6870-213c-4c04-b4b8-a728d554843f | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-006 | Not started | ITP-002 Topsoil Stripping | AWP-1A | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-006
cl:cd3ee4c6-dc94-48db-95dd-856df713ad3b | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-007 | Not started | ITP-002 Topsoil Stripping | AWP-1A | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-007
cl:890586ba-3090-4dbf-9301-4c42131e6071 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-008 | Not started | ITP-002 Topsoil Stripping | AWP-1A | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-008
cl:8d598f4d-ceaa-45b0-8440-e65f16dd4594 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-009 | Not started | ITP-002 Topsoil Stripping | AWP-1A | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-009
cl:5e887b02-4eff-475f-88ec-1338b04019ac | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-010 | Not started | ITP-002 Topsoil Stripping | AWP-1A | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-010
cl:e7d0f507-3ba6-4741-888e-5b243a81ba4a | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-011 | Not started | ITP-002 Topsoil Stripping | AWP-1A | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-011
cl:498fa056-53e6-4adf-836a-db22afe3c868 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-012 | Not started | ITP-002 Topsoil Stripping | AWP-1A | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-012
cl:22b7127d-bfb7-4635-a01d-3fdec26b5a48 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-013 | Not started | ITP-002 Topsoil Stripping | AWP-1A | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-013
cl:c05fcc86-fd09-437f-b001-613dac76b03b | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-014 | Not started | ITP-002 Topsoil Stripping | AWP-1A | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-014
cl:a48b81b5-f8da-4249-a9ba-d92a49debb55 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-015 | Not started | ITP-002 Topsoil Stripping | AWP-1A | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-015
cl:6f3bc2e6-9027-42ca-b7d0-ad548a1c31db | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-016 | Not started | ITP-002 Topsoil Stripping | AWP-1A | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-016
cl:32331128-a4ca-4fcd-ad45-79bcd149cee1 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-017 | Not started | ITP-002 Topsoil Stripping | AWP-1A | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-017
cl:5faede6d-452d-473d-9d83-053657020978 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-001 CH192 to CH265 | In progress | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-001 CH192 to CH265
cl:dd921dce-64f6-4358-8403-c80cd07d931b | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-002 | In progress | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-002
cl:dfd435c3-f0c0-4b2f-b551-fc40fbf36967 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-003 | In progress | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-003
cl:daf905da-f777-4c54-a111-92e86f98d02b | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-004 CH732 to CH1050 | In progress | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-004 CH732 to CH1050
cl:8c4c1f20-301a-4faa-82ae-3a21fb30320b | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-005 | Not started | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-005
cl:8a8758d6-38e3-445b-b0be-0ebd2130b1a2 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-006 | Not started | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-006
cl:c3a4e319-d9e4-4abf-8ab0-310e329d8dfb | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-007 | Not started | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-007
cl:e2120dd6-877c-4aca-ab5a-3f38539ba750 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-008 | Not started | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-008
cl:9e446b56-5b71-414c-b651-c19177db5219 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-009 | Not started | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-009
cl:0c6af84e-b3e2-4e3d-8a46-279a72951b31 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-010 | Not started | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-010
cl:16292971-d3e5-4945-b32c-5b65fd414654 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-011 | Not started | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-011
cl:e7554a30-6ea5-4fa1-b698-ffcee940ce63 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-012 | Not started | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-012
cl:12f8a2b1-6bca-4b5a-97fd-c5bfbfceb333 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-013 | Not started | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-013
cl:87ce06d5-dab0-4bd6-a3eb-f91859570e1c | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-014 | Not started | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-014
cl:87a11975-8cc5-4b0b-bf54-fa5714dfd860 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-015 | Not started | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-015
cl:f93d9f8c-c94e-4d09-a0e1-8375e5292ea7 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-016 | Not started | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-016
cl:0a32f121-dd2d-4b60-8836-1f780e04db42 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-017 | Not started | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-017
cl:eb4aa3a2-74b6-428c-9b75-1400a2dcc6c5 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-001 | In progress | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-001
cl:72b6fca6-3997-40a7-ad4f-c5f8f57abcac | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-002 | In progress | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-002
cl:ef0d1275-885b-4ee9-b427-9f5bbda141ad | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-003 | In progress | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-003
cl:a1582baf-1390-4cee-8145-7bd0946116f2 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-004 | In progress | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-004
cl:56672165-5146-4425-9bd6-510c095ba0d3 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-005_1415 | In progress | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-005_1415
cl:e0b7a3cf-bb64-4ec4-8455-5da0e1444bdc | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-006_CH1564 | In progress | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-006_CH1564
cl:54aef0c1-90a6-42ab-b32f-50385b4126e4 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-007_2355 | In progress | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-007_2355
cl:334a960a-bfaf-4175-a384-024b6765292d | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-008_CH2385 | In progress | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-008_CH2385
cl:ef206ea2-e824-42ff-9ec1-9cbca5556483 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-009_2715 | In progress | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-009_2715
cl:d7fe2708-d0db-468e-8422-c639bfc5cca0 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-010 | In progress | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-010
cl:8584bee6-a760-4608-9e42-1727da0b9fed | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-011 | Not started | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-011
cl:9dbc8f4c-c2f4-4fe6-9994-249789a85e2f | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-012 | Not started | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-012
cl:2717c2dd-f499-4b9b-a7d1-e4e58773c9b5 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-013 | Not started | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-013
cl:3097c0b9-989c-4421-b2eb-94085d48b7d9 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-014 | Not started | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-014
cl:b9f58684-3edb-42e5-8a7d-cc6530eeea36 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-015 | Not started | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-015
cl:74498f1b-f1b4-4d43-a846-ed5ebaf88e1a | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-016 | Not started | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-016
cl:0876f56a-2c12-48dc-8a0f-0e0c0dd35b52 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-017 | Not started | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-017
cl:422980e3-ac79-4913-b4ad-54ef63cf0d32 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation > Global RCP | ITP-004 RCP Installation-MAR-018 - Global | In progress | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | Global RCP | ITP-004 RCP Installation-MAR-018 - Global
cl:677bd369-096a-4938-9fa5-fc2031fac91e | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-001 | In progress | ITP-008 Embankment Construction | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-001
cl:55dd702f-9ef0-4d44-b31c-11f4a89a057c | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-002 | Not started | ITP-008 Embankment Construction | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-002
cl:21ed1d63-15df-421c-8ea0-1662ef191936 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-003 | Not started | ITP-008 Embankment Construction | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-003
cl:72b1db10-1292-4f46-b3bf-822d4bc53073 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-004 | Not started | ITP-008 Embankment Construction | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-004
cl:71558f67-7388-476c-b403-7bdf8ca4578b | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-005 | Not started | ITP-008 Embankment Construction | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-005
cl:8815128e-ec87-48da-a663-0f168a937a26 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-006 | Not started | ITP-008 Embankment Construction | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-006
cl:b5312136-2d65-40fb-a4ea-3adcb065938b | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-007 | Not started | ITP-008 Embankment Construction | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-007
cl:16667826-9565-4d11-b909-c2201b54448b | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-008 | Not started | ITP-008 Embankment Construction | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-008
cl:c7b6301c-1383-4a62-b466-ac1369643971 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-009 | Not started | ITP-008 Embankment Construction | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-009
cl:48f8a636-f478-4fde-b1b2-bd0342c530df | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-010 | Not started | ITP-008 Embankment Construction | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-010
cl:1d69aa48-b390-4956-ace2-858e4bcf6c56 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-011 | Not started | ITP-008 Embankment Construction | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-011
cl:a8234618-0e56-45ee-8c35-e5aa30bb12cb | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-012 | Not started | ITP-008 Embankment Construction | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-012
cl:edde45ff-09a9-49cc-b485-0fd70ebadf74 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-013 | Not started | ITP-008 Embankment Construction | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-013
cl:c9959181-8906-4731-9758-8476ccbc2ae4 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-014 | Not started | ITP-008 Embankment Construction | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-014
cl:1d851afd-6473-4983-86ff-3944ee158b12 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-015 | Not started | ITP-008 Embankment Construction | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-015
cl:b88a7678-4b1d-4d3f-b470-553e064a93e4 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-016 | Not started | ITP-008 Embankment Construction | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-016
cl:40473b7b-e086-45dd-a85c-dc23e476f2f3 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-017 | Not started | ITP-008 Embankment Construction | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-017
cl:3ab8f4bf-0aba-4f15-9b6a-18f0b2f28529 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-001 | Not started | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-001
cl:7d8b619b-e51f-4180-943b-6f39301cd46e | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-002 | Not started | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-002
cl:9c2e4830-6b5e-4d6d-9ece-69056bc38f4d | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-003 | Not started | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-003
cl:ded39db4-f2a2-4925-b6ab-9cb39d7a8bf4 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-004 | Not started | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-004
cl:5c51972b-e8fc-4c9e-b95a-77776cedcf01 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-005 | Not started | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-005
cl:cd26b24b-154d-4209-bd7f-c15eaa603b5d | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-006 | Not started | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-006
cl:d2221e0e-7fec-4435-b9e9-ce8c59a00f43 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-007 | Not started | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-007
cl:8bf7387d-1f7f-49cc-91b0-9d65f23d51ae | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-008 | Not started | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-008
cl:4135d0fd-e369-4db5-8b1d-64b555bface3 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-009 | Not started | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-009
cl:cd217768-3a25-4510-9a00-4a324a6b7d53 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-010 | Not started | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-010
cl:60e52ec7-e21f-4914-989d-dab702e49363 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-011 | Not started | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-011
cl:cd8e4393-0349-44c2-b395-3fa06e343cc2 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-012 | Not started | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-012
cl:782443f2-4ab3-4828-bbf1-0077f779e483 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-013 | Not started | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-013
cl:799a734d-2a84-4459-bef2-728a6f1a1fd0 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-014 | Not started | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-014
cl:102244ca-aa1f-4286-9f8d-e192b970b302 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-015 | Not started | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-015
cl:2109d4a3-b736-4722-97b9-3f90f38d7a11 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-016 | Not started | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-016
cl:c791f107-4611-4016-950b-83138e3a4a0e | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-017 | Not started | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-017
cl:ce5f8716-8a08-452a-83f4-ab67299b6b5f | EVA Copper Mine Project | AWP-1A > Village Access Road | ITP-000 Pre-construction-VAR | Not started | ITP-000 Pre-construction | AWP-1A | Village Access Road | ITP-000 Pre-construction-VAR
cl:eec82efc-3ac4-44da-a09b-e7aa54d50a73 | EVA Copper Mine Project | AWP-1A > Village Access Road > ITP-001 Clear & Grub | ITP-001 Clear & Grub-VAR-001 | In progress | ITP-001 Clear & Grub | AWP-1A | Village Access Road | ITP-001 Clear & Grub | ITP-001 Clear & Grub-VAR-001
cl:96088604-9e73-4737-92c8-b182ebea7e73 | EVA Copper Mine Project | AWP-1A > Village Access Road > ITP-001 Clear & Grub | ITP-001 Clear & Grub-VAR-002 | Not started | ITP-001 Clear & Grub | AWP-1A | Village Access Road | ITP-001 Clear & Grub | ITP-001 Clear & Grub-VAR-002
cl:2f7f622b-dee3-40fa-b4d4-d11aff2d618f | EVA Copper Mine Project | AWP-1A > Village Access Road > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-VAR-001 | Not started | ITP-002 Topsoil Stripping | AWP-1A | Village Access Road | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-VAR-001
cl:b06d0ba7-4979-4431-8a84-397bacc12308 | EVA Copper Mine Project | AWP-1A > Village Access Road > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-VAR-002 | Not started | ITP-002 Topsoil Stripping | AWP-1A | Village Access Road | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-VAR-002
cl:2addc368-ad46-4a60-8a50-f442ecc3a00c | EVA Copper Mine Project | AWP-1A > Village Access Road > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-VAR-001 | In progress | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Village Access Road | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-VAR-001
cl:8700bf87-789c-42c6-962c-8599ed772427 | EVA Copper Mine Project | AWP-1A > Village Access Road > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-VAR-002 | Not started | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Village Access Road | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-VAR-002
cl:8203d441-4a86-407c-bb91-4c1aab0c5def | EVA Copper Mine Project | AWP-1A > Village Access Road > ITP-004 RCP Installation | ITP-004 RCP Installation-VAR-001 | Not started | ITP-004 RCP Installation | AWP-1A | Village Access Road | ITP-004 RCP Installation | ITP-004 RCP Installation-VAR-001
cl:9dd4ae65-c256-4d9b-a28e-98dfe0a92616 | EVA Copper Mine Project | AWP-1A > Village Access Road > ITP-004 RCP Installation | ITP-004 RCP Installation-VAR-002 | Not started | ITP-004 RCP Installation | AWP-1A | Village Access Road | ITP-004 RCP Installation | ITP-004 RCP Installation-VAR-002
cl:d03a27b9-4791-498b-a7b0-88ddcb11e7f0 | EVA Copper Mine Project | AWP-1A > Village Access Road > ITP-008 Embankment Construction | ITP-008 Embankment Construction-VAR-001 | Not started | ITP-008 Embankment Construction | AWP-1A | Village Access Road | ITP-008 Embankment Construction | ITP-008 Embankment Construction-VAR-001
cl:08b4f1e7-d822-4d9f-88b2-748d2d979e83 | EVA Copper Mine Project | AWP-1A > Village Access Road > ITP-008 Embankment Construction | ITP-008 Embankment Construction-VAR-002 | Not started | ITP-008 Embankment Construction | AWP-1A | Village Access Road | ITP-008 Embankment Construction | ITP-008 Embankment Construction-VAR-002
cl:eaa0e5ad-0014-4d40-91d4-2543189b840d | EVA Copper Mine Project | AWP-1A > Village Access Road > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-VAR-001 | Not started | ITP-009 Unbound Gravel Pavements | AWP-1A | Village Access Road | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-VAR-001
cl:12ac3408-6f63-41d1-9325-bd7fd5d5c990 | EVA Copper Mine Project | AWP-1A > Village Access Road > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-VAR-002 | Not started | ITP-009 Unbound Gravel Pavements | AWP-1A | Village Access Road | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-VAR-002
cl:863b5df0-70cf-44bb-81d8-1398c8f7ace6 | EVA Copper Mine Project | AWP-1A > Turkeys Nest | ITP-000 Pre-construction-TN | Not started | ITP-000 Pre-construction | AWP-1A | Turkeys Nest | ITP-000 Pre-construction-TN
cl:9c1e0124-17e1-4f0d-9222-fb83608c0278 | EVA Copper Mine Project | AWP-1A > Turkeys Nest > ITP-001 Clear & Grub | ITP-001 Clear & Grub-TN-001 | Not started | ITP-001 Clear & Grub | AWP-1A | Turkeys Nest | ITP-001 Clear & Grub | ITP-001 Clear & Grub-TN-001
cl:c785cedb-987d-47ed-a39c-68580156cfef | EVA Copper Mine Project | AWP-1A > Turkeys Nest > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-TN-001 | Not started | ITP-002 Topsoil Stripping | AWP-1A | Turkeys Nest | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-TN-001
cl:a1d00da8-7c41-42d6-b580-d852ad6f4015 | EVA Copper Mine Project | AWP-1A > Turkeys Nest > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-TN-001 | Not started | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Turkeys Nest | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-TN-001
cl:a68f9673-a993-4460-aef7-eb828693691b | EVA Copper Mine Project | AWP-1A > Turkeys Nest > ITP-004 RCP Installation | ITP-004 RCP Installation-TN-001 | Not started | ITP-004 RCP Installation | AWP-1A | Turkeys Nest | ITP-004 RCP Installation | ITP-004 RCP Installation-TN-001
cl:bf9e7e0d-5416-4121-9d39-cd434327914b | EVA Copper Mine Project | AWP-1A > Turkeys Nest > ITP-008 Embankment Construction | ITP-008 Embankment Construction-TN-001 | Not started | ITP-008 Embankment Construction | AWP-1A | Turkeys Nest | ITP-008 Embankment Construction | ITP-008 Embankment Construction-TN-001
cl:4c018e8a-b33e-468b-b03a-7a98da8469f8 | EVA Copper Mine Project | AWP-1A > Turkeys Nest > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-TN-001 | Not started | ITP-009 Unbound Gravel Pavements | AWP-1A | Turkeys Nest | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-TN-001
cl:a873b51e-ed65-44d2-a656-be824629281a | EVA Copper Mine Project | AWP-1A > Village Pad | ITP-000 Pre-construction-VP | In progress | ITP-000 Pre-construction | AWP-1A | Village Pad | ITP-000 Pre-construction-VP
cl:dcd0b356-bcb7-492f-8bd8-1f03b6a49c33 | EVA Copper Mine Project | AWP-1A > Village Pad > ITP-001 Clear & Grub | ITP-001 Clear & Grub-VP-001 | Not started | ITP-001 Clear & Grub | AWP-1A | Village Pad | ITP-001 Clear & Grub | ITP-001 Clear & Grub-VP-001
cl:7b5ca7e4-80a1-4638-8249-e4f8e6871ba4 | EVA Copper Mine Project | AWP-1A > Village Pad > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-VP-001 | Not started | ITP-002 Topsoil Stripping | AWP-1A | Village Pad | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-VP-001
cl:b49cbe14-4567-4781-bde0-d751a945ad52 | EVA Copper Mine Project | AWP-1A > Village Pad > ITP-003 Foundation Preparation-VP | ITP-003 Foundation Preparation-VP002.003.010.011.014.015_FP1 | In progress | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Village Pad | ITP-003 Foundation Preparation-VP | ITP-003 Foundation Preparation-VP002.003.010.011.014.015_FP1
cl:190640f7-fe77-42dd-9dcf-f0dc4cc8569f | EVA Copper Mine Project | AWP-1A > Village Pad > ITP-003 Foundation Preparation-VP | ITP-003 Foundation Preparation-VP004.005.006.007.008.017.018_FP2 | Not started | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Village Pad | ITP-003 Foundation Preparation-VP | ITP-003 Foundation Preparation-VP004.005.006.007.008.017.018_FP2
cl:8fe28aa9-4762-4573-ad1f-c93fd32862a6 | EVA Copper Mine Project | AWP-1A > Village Pad > ITP-003 Foundation Preparation-VP | ITP-003 Foundation Preparation-VP001.012.013_FP3 | Not started | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Village Pad | ITP-003 Foundation Preparation-VP | ITP-003 Foundation Preparation-VP001.012.013_FP3
cl:cda7526f-5945-417c-a387-8dae7b459a1f | EVA Copper Mine Project | AWP-1A > Village Pad > ITP-004 RCP Installation | ITP-004 RCP Installation-VP-001 | Not started | ITP-004 RCP Installation | AWP-1A | Village Pad | ITP-004 RCP Installation | ITP-004 RCP Installation-VP-001
cl:b212dd87-d68c-47b0-a5e5-6bdbcc3b5473 | EVA Copper Mine Project | AWP-1A > Village Pad > ITP-008 Embankment Construction | ITP-008 Embankment Construction-VP-001 | Not started | ITP-008 Embankment Construction | AWP-1A | Village Pad | ITP-008 Embankment Construction | ITP-008 Embankment Construction-VP-001
cl:3fe0627c-caaf-4216-b936-e959750e1735 | EVA Copper Mine Project | AWP-1A > Village Pad > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-VP-001 | Not started | ITP-009 Unbound Gravel Pavements | AWP-1A | Village Pad | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-VP-001
cl:bcfe35ca-d308-438a-9c66-9112a48dc484 | EVA Copper Mine Project | AWP-1A > Village Pad > ITP-009 Unbound Gravel Pavements | ITP-003 Subgrade/Foundation Preparation-VP-008 - 008/017_FP5,FP7 | Not started | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Village Pad | ITP-009 Unbound Gravel Pavements | ITP-003 Subgrade/Foundation Preparation-VP-008 - 008/017_FP5,FP7
cl:ce5f8716-8a08-452a-83f4-ab67299b6b5f | EVA Copper Mine Project | Village Access Road | ITP-000 Pre-construction-VAR | Not started | ITP-000 Pre-construction | Village Access Road | ITP-000 Pre-construction-VAR
cl:eec82efc-3ac4-44da-a09b-e7aa54d50a73 | EVA Copper Mine Project | Village Access Road > ITP-001 Clear & Grub | ITP-001 Clear & Grub-VAR-001 | In progress | ITP-001 Clear & Grub | Village Access Road | ITP-001 Clear & Grub | ITP-001 Clear & Grub-VAR-001
cl:96088604-9e73-4737-92c8-b182ebea7e73 | EVA Copper Mine Project | Village Access Road > ITP-001 Clear & Grub | ITP-001 Clear & Grub-VAR-002 | Not started | ITP-001 Clear & Grub | Village Access Road | ITP-001 Clear & Grub | ITP-001 Clear & Grub-VAR-002
cl:2f7f622b-dee3-40fa-b4d4-d11aff2d618f | EVA Copper Mine Project | Village Access Road > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-VAR-001 | Not started | ITP-002 Topsoil Stripping | Village Access Road | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-VAR-001
cl:b06d0ba7-4979-4431-8a84-397bacc12308 | EVA Copper Mine Project | Village Access Road > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-VAR-002 | Not started | ITP-002 Topsoil Stripping | Village Access Road | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-VAR-002
cl:2addc368-ad46-4a60-8a50-f442ecc3a00c | EVA Copper Mine Project | Village Access Road > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-VAR-001 | In progress | ITP-003 Subgrade/Foundation Preparation | Village Access Road | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-VAR-001
cl:8700bf87-789c-42c6-962c-8599ed772427 | EVA Copper Mine Project | Village Access Road > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-VAR-002 | Not started | ITP-003 Subgrade/Foundation Preparation | Village Access Road | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-VAR-002
cl:8203d441-4a86-407c-bb91-4c1aab0c5def | EVA Copper Mine Project | Village Access Road > ITP-004 RCP Installation | ITP-004 RCP Installation-VAR-001 | Not started | ITP-004 RCP Installation | Village Access Road | ITP-004 RCP Installation | ITP-004 RCP Installation-VAR-001
cl:9dd4ae65-c256-4d9b-a28e-98dfe0a92616 | EVA Copper Mine Project | Village Access Road > ITP-004 RCP Installation | ITP-004 RCP Installation-VAR-002 | Not started | ITP-004 RCP Installation | Village Access Road | ITP-004 RCP Installation | ITP-004 RCP Installation-VAR-002
cl:d03a27b9-4791-498b-a7b0-88ddcb11e7f0 | EVA Copper Mine Project | Village Access Road > ITP-008 Embankment Construction | ITP-008 Embankment Construction-VAR-001 | Not started | ITP-008 Embankment Construction | Village Access Road | ITP-008 Embankment Construction | ITP-008 Embankment Construction-VAR-001
cl:08b4f1e7-d822-4d9f-88b2-748d2d979e83 | EVA Copper Mine Project | Village Access Road > ITP-008 Embankment Construction | ITP-008 Embankment Construction-VAR-002 | Not started | ITP-008 Embankment Construction | Village Access Road | ITP-008 Embankment Construction | ITP-008 Embankment Construction-VAR-002
cl:eaa0e5ad-0014-4d40-91d4-2543189b840d | EVA Copper Mine Project | Village Access Road > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-VAR-001 | Not started | ITP-009 Unbound Gravel Pavements | Village Access Road | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-VAR-001
cl:12ac3408-6f63-41d1-9325-bd7fd5d5c990 | EVA Copper Mine Project | Village Access Road > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-VAR-002 | Not started | ITP-009 Unbound Gravel Pavements | Village Access Road | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-VAR-002
cl:dbbb96c4-cbaf-4489-9dc8-5cca11326792 | EVA Copper Mine Project | AWP-1B > Process Plant | ITP-000 Pre-construction-PP | Not started | ITP-000 Pre-construction | AWP-1B | Process Plant | ITP-000 Pre-construction-PP
cl:9b3084a9-2ff3-4c55-a4cf-1ef6945702b5 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-001 | Not started | ITP-001 Clear & Grub | AWP-1B | Process Plant | ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-001
cl:263d5a5c-0e10-4f86-b4d7-e052179fb61d | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-002 | Not started | ITP-001 Clear & Grub | AWP-1B | Process Plant | ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-002
cl:45cb3de9-b82e-4bcd-b795-eb8fc7c59f10 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-003 | Not started | ITP-001 Clear & Grub | AWP-1B | Process Plant | ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-003
cl:4941b796-b809-4e6d-bbb0-cdb857d5144e | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-004 | Not started | ITP-001 Clear & Grub | AWP-1B | Process Plant | ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-004
cl:e94c4960-c452-405f-956e-1f03cd758a70 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-005 | Not started | ITP-001 Clear & Grub | AWP-1B | Process Plant | ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-005
cl:79d2a2d6-46cf-4299-9604-afcd416acd33 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-006 | Not started | ITP-001 Clear & Grub | AWP-1B | Process Plant | ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-006
cl:87d789b1-653f-43e1-b6a0-1fc2c40e8973 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-PP-001 | Not started | ITP-002 Topsoil Stripping | AWP-1B | Process Plant | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-PP-001
cl:112ff002-8ffb-443f-b91d-8cda3058e037 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-PP-002 | Not started | ITP-002 Topsoil Stripping | AWP-1B | Process Plant | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-PP-002
cl:d98da602-4a75-4ac3-9326-9818772e906c | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-PP-003 | Not started | ITP-002 Topsoil Stripping | AWP-1B | Process Plant | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-PP-003
cl:ab80b72a-3510-4f6a-bca7-c488e1578588 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-PP-004 | Not started | ITP-002 Topsoil Stripping | AWP-1B | Process Plant | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-PP-004
cl:b995c116-cc00-483d-a290-50f2c7deeb2c | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-PP-005 | Not started | ITP-002 Topsoil Stripping | AWP-1B | Process Plant | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-PP-005
cl:bce65fde-c703-4ac8-9b3b-17e5b4eeb76a | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-PP-006 | Not started | ITP-002 Topsoil Stripping | AWP-1B | Process Plant | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-PP-006
cl:7d2202b9-930d-41a4-a326-190917c09d4f | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-PP-001 | Not started | ITP-003 Subgrade/Foundation Preparation | AWP-1B | Process Plant | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-PP-001
cl:1d16e40f-dbc0-4e18-9127-6c88e225c757 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-PP-002 | Not started | ITP-003 Subgrade/Foundation Preparation | AWP-1B | Process Plant | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-PP-002
cl:8647b7b5-ffd1-4566-8a6d-f4ebbd94e6ac | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-PP-003 | Not started | ITP-003 Subgrade/Foundation Preparation | AWP-1B | Process Plant | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-PP-003
cl:559c6287-adee-4dfa-8ec7-b979dad2fb7c | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-PP-004 | Not started | ITP-003 Subgrade/Foundation Preparation | AWP-1B | Process Plant | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-PP-004
cl:0065894c-41ff-4c17-8285-413a35f383ae | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-PP-005 | Not started | ITP-003 Subgrade/Foundation Preparation | AWP-1B | Process Plant | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-PP-005
cl:cf3526a3-39c6-4ed8-b27a-160122a63181 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-PP-006 | Not started | ITP-003 Subgrade/Foundation Preparation | AWP-1B | Process Plant | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-PP-006
cl:327686f6-4cfc-42c5-bb1a-33d56d1d6b82 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-004 RCP Installation | ITP-004 RCP Installation-PP-001 | Not started | ITP-004 RCP Installation | AWP-1B | Process Plant | ITP-004 RCP Installation | ITP-004 RCP Installation-PP-001
cl:78c12252-ccdc-44f0-8ec8-a1e7a7add732 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-004 RCP Installation | ITP-004 RCP Installation-PP-002 | Not started | ITP-004 RCP Installation | AWP-1B | Process Plant | ITP-004 RCP Installation | ITP-004 RCP Installation-PP-002
cl:ea5712bd-2726-4f90-aef1-88828567cfab | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-004 RCP Installation | ITP-004 RCP Installation-PP-003 | Not started | ITP-004 RCP Installation | AWP-1B | Process Plant | ITP-004 RCP Installation | ITP-004 RCP Installation-PP-003
cl:b3da67de-d5f8-4307-9505-6854525fd8b5 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-004 RCP Installation | ITP-004 RCP Installation-PP-004 | Not started | ITP-004 RCP Installation | AWP-1B | Process Plant | ITP-004 RCP Installation | ITP-004 RCP Installation-PP-004
cl:716ed9c9-4c7b-482b-a67d-0b6da1f448f3 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-004 RCP Installation | ITP-004 RCP Installation-PP-005 | Not started | ITP-004 RCP Installation | AWP-1B | Process Plant | ITP-004 RCP Installation | ITP-004 RCP Installation-PP-005
cl:0ec6dbf8-4c10-4c45-998d-72abcbf29ad6 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-004 RCP Installation | ITP-004 RCP Installation-PP-006 | Not started | ITP-004 RCP Installation | AWP-1B | Process Plant | ITP-004 RCP Installation | ITP-004 RCP Installation-PP-006
cl:34a0f8ef-207f-4f96-9919-9e5c4749c252 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-008 Embankment Construction | ITP-008 Embankment Construction-PP-001 | Not started | ITP-008 Embankment Construction | AWP-1B | Process Plant | ITP-008 Embankment Construction | ITP-008 Embankment Construction-PP-001
cl:9386c9cd-c572-49f2-b0db-9a4e30c5081e | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-008 Embankment Construction | ITP-008 Embankment Construction-PP-002 | Not started | ITP-008 Embankment Construction | AWP-1B | Process Plant | ITP-008 Embankment Construction | ITP-008 Embankment Construction-PP-002
cl:35a4ec69-97d7-430c-90f4-cfab9eeccef8 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-008 Embankment Construction | ITP-008 Embankment Construction-PP-003 | Not started | ITP-008 Embankment Construction | AWP-1B | Process Plant | ITP-008 Embankment Construction | ITP-008 Embankment Construction-PP-003
cl:62bc3b8f-7bba-4d2a-9590-a2eacee51cfc | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-008 Embankment Construction | ITP-008 Embankment Construction-PP-004 | Not started | ITP-008 Embankment Construction | AWP-1B | Process Plant | ITP-008 Embankment Construction | ITP-008 Embankment Construction-PP-004
cl:6d7cd6c4-190a-4308-89f3-2f5727f1a541 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-008 Embankment Construction | ITP-008 Embankment Construction-PP-005 | Not started | ITP-008 Embankment Construction | AWP-1B | Process Plant | ITP-008 Embankment Construction | ITP-008 Embankment Construction-PP-005
cl:36c50743-d7f9-4c31-9411-9c7dfd700e26 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-008 Embankment Construction | ITP-008 Embankment Construction-PP-006 | Not started | ITP-008 Embankment Construction | AWP-1B | Process Plant | ITP-008 Embankment Construction | ITP-008 Embankment Construction-PP-006
cl:e5240338-56e4-487c-b409-020c3bff2d7e | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-001 | Not started | ITP-009 Unbound Gravel Pavements | AWP-1B | Process Plant | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-001
cl:1413e480-0f68-49b0-a36b-fd35f6e91974 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-002 | Not started | ITP-009 Unbound Gravel Pavements | AWP-1B | Process Plant | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-002
cl:189e3c23-6d1e-4997-a42a-ccab401c7352 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-003 | Not started | ITP-009 Unbound Gravel Pavements | AWP-1B | Process Plant | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-003
cl:8c7ea01e-ab45-4fcd-8e50-1b5d4302be9c | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-004 | Not started | ITP-009 Unbound Gravel Pavements | AWP-1B | Process Plant | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-004
cl:769af0f8-c942-4998-9524-7e8b1acf89a8 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-005 | Not started | ITP-009 Unbound Gravel Pavements | AWP-1B | Process Plant | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-005
cl:f1f0156b-a60c-48c3-b0ee-4780306e1fa8 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-006 | Not started | ITP-009 Unbound Gravel Pavements | AWP-1B | Process Plant | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-006

## Checkpoints
Checklist Id | Project | Location | Checklist Name | Section Name | Checkpoint Name | Checkpoint Status | Signoff Status | Checklist Template | Tier 1 | Tier 2 | Tier 3 | Tier 4 | Tier 5 | Tier 6
cl:1ad3dc41-7de9-484f-b0ff-7327d7431f2f | EVA Copper Mine Project | A1401 Eva Copper Bulk Earthworks | ITP-000 Pre-construction - Construction Management Plan | Pre-construction | PC1.1 - Construction Management Plan | In progress | Open | ITP-000 Pre-construction - CMP | A1401 Eva Copper Bulk Earthworks | ITP-000 Pre-construction - Construction Management Plan
cl:3e96928c-d37e-4e84-bb43-759794579864 | EVA Copper Mine Project | Main Access Road (MAR) | MAR-Pre Construction (ITP-000) | Pre-construction | PC1.2 - Lot Register/ WBS | In progress | Open | ITP-000 Pre-construction | Main Access Road (MAR) | MAR-Pre Construction (ITP-000)
cl:3e96928c-d37e-4e84-bb43-759794579864 | EVA Copper Mine Project | Main Access Road (MAR) | MAR-Pre Construction (ITP-000) | Pre-construction | PC1.3 - Construction procedures | In progress | Open | ITP-000 Pre-construction | Main Access Road (MAR) | MAR-Pre Construction (ITP-000)
cl:3e96928c-d37e-4e84-bb43-759794579864 | EVA Copper Mine Project | Main Access Road (MAR) | MAR-Pre Construction (ITP-000) | Pre-construction | PC1.4 - Excavation permit | In progress | Open | ITP-000 Pre-construction | Main Access Road (MAR) | MAR-Pre Construction (ITP-000)
cl:3e96928c-d37e-4e84-bb43-759794579864 | EVA Copper Mine Project | Main Access Road (MAR) | MAR-Pre Construction (ITP-000) | Pre-construction | PC1.5 - Dial before you dig check | In progress | Open | ITP-000 Pre-construction | Main Access Road (MAR) | MAR-Pre Construction (ITP-000)
cl:3e96928c-d37e-4e84-bb43-759794579864 | EVA Copper Mine Project | Main Access Road (MAR) | MAR-Pre Construction (ITP-000) | Pre-construction | PC1.6 - Traffic control plan | In progress | Open | ITP-000 Pre-construction | Main Access Road (MAR) | MAR-Pre Construction (ITP-000)
cl:3e96928c-d37e-4e84-bb43-759794579864 | EVA Copper Mine Project | Main Access Road (MAR) | MAR-Pre Construction (ITP-000) | Pre-construction | PC1.7 - Inspection Test Plan (ITP) submitted and approved | In progress | Open | ITP-000 Pre-construction | Main Access Road (MAR) | MAR-Pre Construction (ITP-000)
cl:3e96928c-d37e-4e84-bb43-759794579864 | EVA Copper Mine Project | Main Access Road (MAR) | MAR-Pre Construction (ITP-000) | Pre-construction | PC1.8 - IFC drawings | In progress | Open | ITP-000 Pre-construction | Main Access Road (MAR) | MAR-Pre Construction (ITP-000)
cl:3e96928c-d37e-4e84-bb43-759794579864 | EVA Copper Mine Project | Main Access Road (MAR) | MAR-Pre Construction (ITP-000) | Pre-construction | PC1.9 - Erosion and sediment control plan | In progress | Open | ITP-000 Pre-construction | Main Access Road (MAR) | MAR-Pre Construction (ITP-000)
cl:3e96928c-d37e-4e84-bb43-759794579864 | EVA Copper Mine Project | Main Access Road (MAR) | MAR-Pre Construction (ITP-000) | Pre-construction | PC1.10 - Approved stockpile locations | Not started | Open | ITP-000 Pre-construction | Main Access Road (MAR) | MAR-Pre Construction (ITP-000)
cl:3e96928c-d37e-4e84-bb43-759794579864 | EVA Copper Mine Project | Main Access Road (MAR) | MAR-Pre Construction (ITP-000) | Pre-construction | PC1.11 - Embankment fill materials | Not started | Open | ITP-000 Pre-construction | Main Access Road (MAR) | MAR-Pre Construction (ITP-000)
cl:3e96928c-d37e-4e84-bb43-759794579864 | EVA Copper Mine Project | Main Access Road (MAR) | MAR-Pre Construction (ITP-000) | Pre-construction | PC1.12 - QA close out | Not started | Open | ITP-000 Pre-construction | Main Access Road (MAR) | MAR-Pre Construction (ITP-000)
cl:601429a2-74bf-453d-a25e-49aedf0e3811 | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | MAR_C&G | Clear & Grub | GC1.1 - Underlying lot & ITP signed off and conforming | Not started |  | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | MAR_C&G
cl:601429a2-74bf-453d-a25e-49aedf0e3811 | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | MAR_C&G | Clear & Grub | GC1.2 - Ground Disturbance Permit (GDP) | In progress | Open | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | MAR_C&G
cl:601429a2-74bf-453d-a25e-49aedf0e3811 | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | MAR_C&G | Clear & Grub | GC1.3 - Cultural Heritage(CH) Clearance Survey | In progress | Open | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | MAR_C&G
cl:601429a2-74bf-453d-a25e-49aedf0e3811 | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | MAR_C&G | Clear & Grub | GC1.4 - GDP survey set out | In progress | Open | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | MAR_C&G
cl:601429a2-74bf-453d-a25e-49aedf0e3811 | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | MAR_C&G | Clear & Grub | GC1.5 - Survey of pegs to confirm correct GDP survey set out | In progress | Open | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | MAR_C&G
cl:601429a2-74bf-453d-a25e-49aedf0e3811 | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | MAR_C&G | Clear & Grub | GC1.6 - Survey natural surface | In progress | Open | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | MAR_C&G
cl:601429a2-74bf-453d-a25e-49aedf0e3811 | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | MAR_C&G | Clear & Grub | GC1.7 - Fauna Spotter Catcher (FSC) Pre-Clearance Survey | In progress | Open | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | MAR_C&G
cl:601429a2-74bf-453d-a25e-49aedf0e3811 | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | MAR_C&G | Clear & Grub | GC1.8 - Mandatory GDP Pre-Clearing walk | In progress | Open | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | MAR_C&G
cl:601429a2-74bf-453d-a25e-49aedf0e3811 | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | MAR_C&G | Clear & Grub | GC1.9 - Clearing of vegetation | Not started | Open | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | MAR_C&G
cl:601429a2-74bf-453d-a25e-49aedf0e3811 | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | MAR_C&G | Clear & Grub | GC1.10 - Stockpile Cleared Vegetation | In progress | Open | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | MAR_C&G
cl:601429a2-74bf-453d-a25e-49aedf0e3811 | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | MAR_C&G | Clear & Grub | GC1.11 - Erosion and sediment control | In progress | Open | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | MAR_C&G
cl:601429a2-74bf-453d-a25e-49aedf0e3811 | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | MAR_C&G | Clear & Grub | GC1.12 - QA close out | Not started | Open | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | MAR_C&G
cl:b1e3edb5-2407-40c6-b3ea-2e777d5dfc1f | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-003 CH1190 to CH1690 | Clear & Grub | GC1.1 - Underlying lot & ITP signed off and conforming | Not started |  | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-003 CH1190 to CH1690
cl:b1e3edb5-2407-40c6-b3ea-2e777d5dfc1f | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-003 CH1190 to CH1690 | Clear & Grub | GC1.2 - Ground Disturbance Permit (GDP) | In progress | Open | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-003 CH1190 to CH1690
cl:b1e3edb5-2407-40c6-b3ea-2e777d5dfc1f | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-003 CH1190 to CH1690 | Clear & Grub | GC1.3 - Cultural Heritage(CH) Clearance Survey | Not started | Open | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-003 CH1190 to CH1690
cl:b1e3edb5-2407-40c6-b3ea-2e777d5dfc1f | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-003 CH1190 to CH1690 | Clear & Grub | GC1.4 - GDP survey set out | Not started | Requested | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-003 CH1190 to CH1690
cl:b1e3edb5-2407-40c6-b3ea-2e777d5dfc1f | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-003 CH1190 to CH1690 | Clear & Grub | GC1.5 - Survey of pegs to confirm correct GDP survey set out | Not started | Open | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-003 CH1190 to CH1690
cl:b1e3edb5-2407-40c6-b3ea-2e777d5dfc1f | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-003 CH1190 to CH1690 | Clear & Grub | GC1.6 - Survey natural surface | Not started | Open | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-003 CH1190 to CH1690
cl:b1e3edb5-2407-40c6-b3ea-2e777d5dfc1f | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-003 CH1190 to CH1690 | Clear & Grub | GC1.7 - Fauna Spotter Catcher (FSC) Pre-Clearance Survey | Not started | Open | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-003 CH1190 to CH1690
cl:b1e3edb5-2407-40c6-b3ea-2e777d5dfc1f | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-003 CH1190 to CH1690 | Clear & Grub | GC1.8 - Mandatory GDP Pre-Clearing walk | Not started | Open | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-003 CH1190 to CH1690
cl:b1e3edb5-2407-40c6-b3ea-2e777d5dfc1f | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-003 CH1190 to CH1690 | Clear & Grub | GC1.9 - Clearing of vegetation | Not started | Open | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-003 CH1190 to CH1690
cl:b1e3edb5-2407-40c6-b3ea-2e777d5dfc1f | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-003 CH1190 to CH1690 | Clear & Grub | GC1.10 - Stockpile Cleared Vegetation | Not started | Open | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-003 CH1190 to CH1690
cl:b1e3edb5-2407-40c6-b3ea-2e777d5dfc1f | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-003 CH1190 to CH1690 | Clear & Grub | GC1.11 - Erosion and sediment control | Not started | Requested | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-003 CH1190 to CH1690
cl:b1e3edb5-2407-40c6-b3ea-2e777d5dfc1f | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-003 CH1190 to CH1690 | Clear & Grub | GC1.12 - QA close out | Not started | Open | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-003 CH1190 to CH1690
cl:b406a2c5-97ef-41e2-9979-075f7c835861 | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-004 | Clear & Grub | GC1.1 - Underlying lot & ITP signed off and conforming | Not started |  | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-004
cl:b406a2c5-97ef-41e2-9979-075f7c835861 | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-004 | Clear & Grub | GC1.2 - Ground Disturbance Permit (GDP) | In progress | Open | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-004
cl:b406a2c5-97ef-41e2-9979-075f7c835861 | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-004 | Clear & Grub | GC1.3 - Cultural Heritage(CH) Clearance Survey | Not started | Open | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-004
cl:b406a2c5-97ef-41e2-9979-075f7c835861 | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-004 | Clear & Grub | GC1.4 - GDP survey set out | Not started | Open | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-004
cl:b406a2c5-97ef-41e2-9979-075f7c835861 | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-004 | Clear & Grub | GC1.5 - Survey of pegs to confirm correct GDP survey set out | Not started | Open | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-004
cl:b406a2c5-97ef-41e2-9979-075f7c835861 | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-004 | Clear & Grub | GC1.6 - Survey natural surface | Not started | Requested | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-004
cl:b406a2c5-97ef-41e2-9979-075f7c835861 | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-004 | Clear & Grub | GC1.7 - Fauna Spotter Catcher (FSC) Pre-Clearance Survey | Not started | Open | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-004
cl:b406a2c5-97ef-41e2-9979-075f7c835861 | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-004 | Clear & Grub | GC1.8 - Mandatory GDP Pre-Clearing walk | Not started | Open | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-004
cl:b406a2c5-97ef-41e2-9979-075f7c835861 | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-004 | Clear & Grub | GC1.9 - Clearing of vegetation | Not started | Open | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-004
cl:b406a2c5-97ef-41e2-9979-075f7c835861 | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-004 | Clear & Grub | GC1.10 - Stockpile Cleared Vegetation | Not started | Open | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-004
cl:b406a2c5-97ef-41e2-9979-075f7c835861 | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-004 | Clear & Grub | GC1.11 - Erosion and sediment control | Not started | Requested | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-004
cl:b406a2c5-97ef-41e2-9979-075f7c835861 | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-004 | Clear & Grub | GC1.12 - QA close out | Not started | Open | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-004
cl:f1e4f780-fc73-44c7-ae56-24c8a8f51645 | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-005 | Clear & Grub | GC1.1 - Underlying lot & ITP signed off and conforming | Not started |  | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-005
cl:f1e4f780-fc73-44c7-ae56-24c8a8f51645 | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-005 | Clear & Grub | GC1.2 - Ground Disturbance Permit (GDP) | In progress | Open | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-005
cl:f1e4f780-fc73-44c7-ae56-24c8a8f51645 | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-005 | Clear & Grub | GC1.3 - Cultural Heritage(CH) Clearance Survey | Not started | Open | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-005
cl:f1e4f780-fc73-44c7-ae56-24c8a8f51645 | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-005 | Clear & Grub | GC1.4 - GDP survey set out | Not started | Open | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-005
cl:f1e4f780-fc73-44c7-ae56-24c8a8f51645 | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-005 | Clear & Grub | GC1.5 - Survey of pegs to confirm correct GDP survey set out | Not started | Open | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-005
cl:f1e4f780-fc73-44c7-ae56-24c8a8f51645 | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-005 | Clear & Grub | GC1.6 - Survey natural surface | Not started | Open | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-005
cl:f1e4f780-fc73-44c7-ae56-24c8a8f51645 | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-005 | Clear & Grub | GC1.7 - Fauna Spotter Catcher (FSC) Pre-Clearance Survey | Not started | Open | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-005
cl:f1e4f780-fc73-44c7-ae56-24c8a8f51645 | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-005 | Clear & Grub | GC1.8 - Mandatory GDP Pre-Clearing walk | Not started | Open | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-005
cl:f1e4f780-fc73-44c7-ae56-24c8a8f51645 | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-005 | Clear & Grub | GC1.9 - Clearing of vegetation | Not started | Open | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-005
cl:f1e4f780-fc73-44c7-ae56-24c8a8f51645 | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-005 | Clear & Grub | GC1.10 - Stockpile Cleared Vegetation | Not started | Open | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-005
cl:f1e4f780-fc73-44c7-ae56-24c8a8f51645 | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-005 | Clear & Grub | GC1.11 - Erosion and sediment control | Not started | Requested | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-005
cl:f1e4f780-fc73-44c7-ae56-24c8a8f51645 | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-005 | Clear & Grub | GC1.12 - QA close out | Not started | Open | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-005
cl:3721ff4f-dbd9-4750-bcc4-9b5b2922141c | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-006 | Clear & Grub | GC1.1 - Underlying lot & ITP signed off and conforming | Not started |  | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-006
cl:3721ff4f-dbd9-4750-bcc4-9b5b2922141c | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-006 | Clear & Grub | GC1.2 - Ground Disturbance Permit (GDP) | In progress | Open | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-006
cl:3721ff4f-dbd9-4750-bcc4-9b5b2922141c | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-006 | Clear & Grub | GC1.3 - Cultural Heritage(CH) Clearance Survey | Not started | Open | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-006
cl:3721ff4f-dbd9-4750-bcc4-9b5b2922141c | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-006 | Clear & Grub | GC1.4 - GDP survey set out | Not started | Open | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-006
cl:3721ff4f-dbd9-4750-bcc4-9b5b2922141c | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-006 | Clear & Grub | GC1.5 - Survey of pegs to confirm correct GDP survey set out | Not started | Open | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-006
cl:3721ff4f-dbd9-4750-bcc4-9b5b2922141c | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-006 | Clear & Grub | GC1.6 - Survey natural surface | Not started | Requested | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-006
cl:3721ff4f-dbd9-4750-bcc4-9b5b2922141c | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-006 | Clear & Grub | GC1.7 - Fauna Spotter Catcher (FSC) Pre-Clearance Survey | Not started | Open | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-006
cl:3721ff4f-dbd9-4750-bcc4-9b5b2922141c | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-006 | Clear & Grub | GC1.8 - Mandatory GDP Pre-Clearing walk | Not started | Open | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-006
cl:3721ff4f-dbd9-4750-bcc4-9b5b2922141c | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-006 | Clear & Grub | GC1.9 - Clearing of vegetation | Not started | Open | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-006
cl:3721ff4f-dbd9-4750-bcc4-9b5b2922141c | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-006 | Clear & Grub | GC1.10 - Stockpile Cleared Vegetation | Not started | Open | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-006
cl:3721ff4f-dbd9-4750-bcc4-9b5b2922141c | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-006 | Clear & Grub | GC1.11 - Erosion and sediment control | Not started | Requested | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-006
cl:3721ff4f-dbd9-4750-bcc4-9b5b2922141c | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-006 | Clear & Grub | GC1.12 - QA close out | Not started | Open | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-006
cl:42eb673b-7480-418c-9ff4-deae157d50bf | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-007 | Clear & Grub | GC1.1 - Underlying lot & ITP signed off and conforming | Not started |  | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-007
cl:42eb673b-7480-418c-9ff4-deae157d50bf | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-007 | Clear & Grub | GC1.2 - Ground Disturbance Permit (GDP) | In progress | Open | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-007
cl:42eb673b-7480-418c-9ff4-deae157d50bf | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-007 | Clear & Grub | GC1.3 - Cultural Heritage(CH) Clearance Survey | Not started | Open | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-007
cl:42eb673b-7480-418c-9ff4-deae157d50bf | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-007 | Clear & Grub | GC1.4 - GDP survey set out | Not started | Open | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-007
cl:42eb673b-7480-418c-9ff4-deae157d50bf | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-007 | Clear & Grub | GC1.5 - Survey of pegs to confirm correct GDP survey set out | Not started | Open | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-007
cl:42eb673b-7480-418c-9ff4-deae157d50bf | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-007 | Clear & Grub | GC1.6 - Survey natural surface | Not started | Requested | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-007
cl:42eb673b-7480-418c-9ff4-deae157d50bf | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-007 | Clear & Grub | GC1.7 - Fauna Spotter Catcher (FSC) Pre-Clearance Survey | Not started | Open | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-007
cl:42eb673b-7480-418c-9ff4-deae157d50bf | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-007 | Clear & Grub | GC1.8 - Mandatory GDP Pre-Clearing walk | Not started | Open | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-007
cl:42eb673b-7480-418c-9ff4-deae157d50bf | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-007 | Clear & Grub | GC1.9 - Clearing of vegetation | Not started | Requested | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-007
cl:42eb673b-7480-418c-9ff4-deae157d50bf | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-007 | Clear & Grub | GC1.10 - Stockpile Cleared Vegetation | Not started | Requested | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-007
cl:42eb673b-7480-418c-9ff4-deae157d50bf | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-007 | Clear & Grub | GC1.11 - Erosion and sediment control | Not started | Requested | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-007
cl:42eb673b-7480-418c-9ff4-deae157d50bf | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-007 | Clear & Grub | GC1.12 - QA close out | Not started | Open | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-007
cl:e33db8cf-01ab-4374-ac31-dc1e054bc56e | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-008 | Clear & Grub | GC1.1 - Underlying lot & ITP signed off and conforming | Not started |  | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-008
cl:e33db8cf-01ab-4374-ac31-dc1e054bc56e | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-008 | Clear & Grub | GC1.2 - Ground Disturbance Permit (GDP) | Not started | Open | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-008
cl:e33db8cf-01ab-4374-ac31-dc1e054bc56e | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-008 | Clear & Grub | GC1.3 - Cultural Heritage(CH) Clearance Survey | Not started | Open | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-008
cl:e33db8cf-01ab-4374-ac31-dc1e054bc56e | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-008 | Clear & Grub | GC1.4 - GDP survey set out | Not started | Open | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-008
cl:e33db8cf-01ab-4374-ac31-dc1e054bc56e | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-008 | Clear & Grub | GC1.5 - Survey of pegs to confirm correct GDP survey set out | Not started | Open | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-008
cl:e33db8cf-01ab-4374-ac31-dc1e054bc56e | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-008 | Clear & Grub | GC1.6 - Survey natural surface | Not started | Open | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-008
cl:e33db8cf-01ab-4374-ac31-dc1e054bc56e | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-008 | Clear & Grub | GC1.7 - Fauna Spotter Catcher (FSC) Pre-Clearance Survey | Not started | Open | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-008
cl:e33db8cf-01ab-4374-ac31-dc1e054bc56e | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-008 | Clear & Grub | GC1.8 - Mandatory GDP Pre-Clearing walk | Not started | Open | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-008
cl:e33db8cf-01ab-4374-ac31-dc1e054bc56e | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-008 | Clear & Grub | GC1.9 - Clearing of vegetation | Not started | Open | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-008
cl:e33db8cf-01ab-4374-ac31-dc1e054bc56e | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-008 | Clear & Grub | GC1.10 - Stockpile Cleared Vegetation | Not started | Open | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-008
cl:e33db8cf-01ab-4374-ac31-dc1e054bc56e | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-008 | Clear & Grub | GC1.11 - Erosion and sediment control | Not started | Open | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-008
cl:e33db8cf-01ab-4374-ac31-dc1e054bc56e | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-008 | Clear & Grub | GC1.12 - QA close out | Not started | Open | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-008
cl:4f77e1ab-6019-4331-8b69-828314b7b4e9 | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-009 | Clear & Grub | GC1.1 - Underlying lot & ITP signed off and conforming | Not started |  | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-009
cl:4f77e1ab-6019-4331-8b69-828314b7b4e9 | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-009 | Clear & Grub | GC1.2 - Ground Disturbance Permit (GDP) | In progress | Open | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-009
cl:4f77e1ab-6019-4331-8b69-828314b7b4e9 | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-009 | Clear & Grub | GC1.3 - Cultural Heritage(CH) Clearance Survey | Not started | Open | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-009
cl:4f77e1ab-6019-4331-8b69-828314b7b4e9 | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-009 | Clear & Grub | GC1.4 - GDP survey set out | Not started | Requested | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-009
cl:4f77e1ab-6019-4331-8b69-828314b7b4e9 | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-009 | Clear & Grub | GC1.5 - Survey of pegs to confirm correct GDP survey set out | Not started | Open | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-009
cl:4f77e1ab-6019-4331-8b69-828314b7b4e9 | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-009 | Clear & Grub | GC1.6 - Survey natural surface | Not started | Requested | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-009
cl:4f77e1ab-6019-4331-8b69-828314b7b4e9 | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-009 | Clear & Grub | GC1.7 - Fauna Spotter Catcher (FSC) Pre-Clearance Survey | Not started | Open | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-009
cl:4f77e1ab-6019-4331-8b69-828314b7b4e9 | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-009 | Clear & Grub | GC1.8 - Mandatory GDP Pre-Clearing walk | Not started | Open | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-009
cl:4f77e1ab-6019-4331-8b69-828314b7b4e9 | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-009 | Clear & Grub | GC1.9 - Clearing of vegetation | Not started | Open | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-009
cl:4f77e1ab-6019-4331-8b69-828314b7b4e9 | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-009 | Clear & Grub | GC1.10 - Stockpile Cleared Vegetation | Not started | Open | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-009
cl:4f77e1ab-6019-4331-8b69-828314b7b4e9 | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-009 | Clear & Grub | GC1.11 - Erosion and sediment control | Not started | Requested | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-009
cl:4f77e1ab-6019-4331-8b69-828314b7b4e9 | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-009 | Clear & Grub | GC1.12 - QA close out | Not started | Open | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-009
cl:fab03817-8be3-4a5b-bb6e-7b609a819c21 | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-010 | Clear & Grub | GC1.1 - Underlying lot & ITP signed off and conforming | Not started |  | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-010
cl:fab03817-8be3-4a5b-bb6e-7b609a819c21 | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-010 | Clear & Grub | GC1.2 - Ground Disturbance Permit (GDP) | In progress | Approved | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-010
cl:fab03817-8be3-4a5b-bb6e-7b609a819c21 | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-010 | Clear & Grub | GC1.3 - Cultural Heritage(CH) Clearance Survey | Not started | Open | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-010
cl:fab03817-8be3-4a5b-bb6e-7b609a819c21 | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-010 | Clear & Grub | GC1.4 - GDP survey set out | Not started | Requested | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-010
cl:fab03817-8be3-4a5b-bb6e-7b609a819c21 | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-010 | Clear & Grub | GC1.5 - Survey of pegs to confirm correct GDP survey set out | Not started | Open | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-010
cl:fab03817-8be3-4a5b-bb6e-7b609a819c21 | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-010 | Clear & Grub | GC1.6 - Survey natural surface | Not started | Requested | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-010
cl:fab03817-8be3-4a5b-bb6e-7b609a819c21 | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-010 | Clear & Grub | GC1.7 - Fauna Spotter Catcher (FSC) Pre-Clearance Survey | Not started | Open | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-010
cl:fab03817-8be3-4a5b-bb6e-7b609a819c21 | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-010 | Clear & Grub | GC1.8 - Mandatory GDP Pre-Clearing walk | Not started | Open | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-010
cl:fab03817-8be3-4a5b-bb6e-7b609a819c21 | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-010 | Clear & Grub | GC1.9 - Clearing of vegetation | Not started | Requested | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-010
cl:fab03817-8be3-4a5b-bb6e-7b609a819c21 | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-010 | Clear & Grub | GC1.10 - Stockpile Cleared Vegetation | Not started | Open | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-010
cl:fab03817-8be3-4a5b-bb6e-7b609a819c21 | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-010 | Clear & Grub | GC1.11 - Erosion and sediment control | Not started | Open | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-010
cl:fab03817-8be3-4a5b-bb6e-7b609a819c21 | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-010 | Clear & Grub | GC1.12 - QA close out | Not started | Open | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-010
cl:1674f482-e023-4aad-a33a-5e7a7c690be6 | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-011 | Clear & Grub | GC1.1 - Underlying lot & ITP signed off and conforming | Not started |  | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-011
cl:1674f482-e023-4aad-a33a-5e7a7c690be6 | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-011 | Clear & Grub | GC1.2 - Ground Disturbance Permit (GDP) | In progress | Open | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-011
cl:1674f482-e023-4aad-a33a-5e7a7c690be6 | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-011 | Clear & Grub | GC1.3 - Cultural Heritage(CH) Clearance Survey | Not started | Open | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-011
cl:1674f482-e023-4aad-a33a-5e7a7c690be6 | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-011 | Clear & Grub | GC1.4 - GDP survey set out | Not started | Open | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-011
cl:1674f482-e023-4aad-a33a-5e7a7c690be6 | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-011 | Clear & Grub | GC1.5 - Survey of pegs to confirm correct GDP survey set out | Not started | Open | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-011
cl:1674f482-e023-4aad-a33a-5e7a7c690be6 | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-011 | Clear & Grub | GC1.6 - Survey natural surface | Not started | Requested | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-011
cl:1674f482-e023-4aad-a33a-5e7a7c690be6 | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-011 | Clear & Grub | GC1.7 - Fauna Spotter Catcher (FSC) Pre-Clearance Survey | Not started | Open | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-011
cl:1674f482-e023-4aad-a33a-5e7a7c690be6 | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-011 | Clear & Grub | GC1.8 - Mandatory GDP Pre-Clearing walk | Not started | Open | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-011
cl:1674f482-e023-4aad-a33a-5e7a7c690be6 | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-011 | Clear & Grub | GC1.9 - Clearing of vegetation | Not started | Open | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-011
cl:1674f482-e023-4aad-a33a-5e7a7c690be6 | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-011 | Clear & Grub | GC1.10 - Stockpile Cleared Vegetation | Not started | Open | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-011
cl:1674f482-e023-4aad-a33a-5e7a7c690be6 | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-011 | Clear & Grub | GC1.11 - Erosion and sediment control | Not started | Rejected | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-011
cl:1674f482-e023-4aad-a33a-5e7a7c690be6 | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-011 | Clear & Grub | GC1.12 - QA close out | Not started | Open | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-011
cl:0c070f07-ec98-4b78-97f1-d77ed3524865 | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-012 | Clear & Grub | GC1.1 - Underlying lot & ITP signed off and conforming | Not started |  | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-012
cl:0c070f07-ec98-4b78-97f1-d77ed3524865 | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-012 | Clear & Grub | GC1.2 - Ground Disturbance Permit (GDP) | In progress | Open | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-012
cl:0c070f07-ec98-4b78-97f1-d77ed3524865 | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-012 | Clear & Grub | GC1.3 - Cultural Heritage(CH) Clearance Survey | Not started | Open | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-012
cl:0c070f07-ec98-4b78-97f1-d77ed3524865 | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-012 | Clear & Grub | GC1.4 - GDP survey set out | Not started | Requested | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-012
cl:0c070f07-ec98-4b78-97f1-d77ed3524865 | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-012 | Clear & Grub | GC1.5 - Survey of pegs to confirm correct GDP survey set out | Not started | Open | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-012
cl:0c070f07-ec98-4b78-97f1-d77ed3524865 | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-012 | Clear & Grub | GC1.6 - Survey natural surface | Not started | Requested | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-012
cl:0c070f07-ec98-4b78-97f1-d77ed3524865 | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-012 | Clear & Grub | GC1.7 - Fauna Spotter Catcher (FSC) Pre-Clearance Survey | Not started | Open | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-012
cl:0c070f07-ec98-4b78-97f1-d77ed3524865 | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-012 | Clear & Grub | GC1.8 - Mandatory GDP Pre-Clearing walk | Not started | Open | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-012
cl:0c070f07-ec98-4b78-97f1-d77ed3524865 | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-012 | Clear & Grub | GC1.9 - Clearing of vegetation | Not started | Open | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-012
cl:0c070f07-ec98-4b78-97f1-d77ed3524865 | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-012 | Clear & Grub | GC1.10 - Stockpile Cleared Vegetation | Not started | Open | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-012
cl:0c070f07-ec98-4b78-97f1-d77ed3524865 | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-012 | Clear & Grub | GC1.11 - Erosion and sediment control | Not started | Requested | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-012
cl:0c070f07-ec98-4b78-97f1-d77ed3524865 | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-012 | Clear & Grub | GC1.12 - QA close out | Not started | Open | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-012
cl:cd9dfc60-45c5-4236-8353-d2b31a85ac10 | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-013 | Clear & Grub | GC1.1 - Underlying lot & ITP signed off and conforming | Not started |  | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-013
cl:cd9dfc60-45c5-4236-8353-d2b31a85ac10 | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-013 | Clear & Grub | GC1.2 - Ground Disturbance Permit (GDP) | In progress | Open | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-013
cl:cd9dfc60-45c5-4236-8353-d2b31a85ac10 | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-013 | Clear & Grub | GC1.3 - Cultural Heritage(CH) Clearance Survey | Not started | Open | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-013
cl:cd9dfc60-45c5-4236-8353-d2b31a85ac10 | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-013 | Clear & Grub | GC1.4 - GDP survey set out | Not started | Requested | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-013
cl:cd9dfc60-45c5-4236-8353-d2b31a85ac10 | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-013 | Clear & Grub | GC1.5 - Survey of pegs to confirm correct GDP survey set out | Not started | Open | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-013
cl:cd9dfc60-45c5-4236-8353-d2b31a85ac10 | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-013 | Clear & Grub | GC1.6 - Survey natural surface | Not started | Requested | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-013
cl:cd9dfc60-45c5-4236-8353-d2b31a85ac10 | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-013 | Clear & Grub | GC1.7 - Fauna Spotter Catcher (FSC) Pre-Clearance Survey | Not started | Open | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-013
cl:cd9dfc60-45c5-4236-8353-d2b31a85ac10 | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-013 | Clear & Grub | GC1.8 - Mandatory GDP Pre-Clearing walk | Not started | Open | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-013
cl:cd9dfc60-45c5-4236-8353-d2b31a85ac10 | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-013 | Clear & Grub | GC1.9 - Clearing of vegetation | Not started | Open | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-013
cl:cd9dfc60-45c5-4236-8353-d2b31a85ac10 | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-013 | Clear & Grub | GC1.10 - Stockpile Cleared Vegetation | Not started | Open | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-013
cl:cd9dfc60-45c5-4236-8353-d2b31a85ac10 | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-013 | Clear & Grub | GC1.11 - Erosion and sediment control | Not started | Requested | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-013
cl:cd9dfc60-45c5-4236-8353-d2b31a85ac10 | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-013 | Clear & Grub | GC1.12 - QA close out | Not started | Open | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-013
cl:0effada5-ca7a-4b98-a8c6-6a9c073614b4 | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-014 | Clear & Grub | GC1.1 - Underlying lot & ITP signed off and conforming | Not started |  | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-014
cl:0effada5-ca7a-4b98-a8c6-6a9c073614b4 | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-014 | Clear & Grub | GC1.2 - Ground Disturbance Permit (GDP) | In progress | Open | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-014
cl:0effada5-ca7a-4b98-a8c6-6a9c073614b4 | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-014 | Clear & Grub | GC1.3 - Cultural Heritage(CH) Clearance Survey | Not started | Open | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-014
cl:0effada5-ca7a-4b98-a8c6-6a9c073614b4 | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-014 | Clear & Grub | GC1.4 - GDP survey set out | Not started | Requested | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-014
cl:0effada5-ca7a-4b98-a8c6-6a9c073614b4 | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-014 | Clear & Grub | GC1.5 - Survey of pegs to confirm correct GDP survey set out | Not started | Open | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-014
cl:0effada5-ca7a-4b98-a8c6-6a9c073614b4 | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-014 | Clear & Grub | GC1.6 - Survey natural surface | Not started | Requested | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-014
cl:0effada5-ca7a-4b98-a8c6-6a9c073614b4 | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-014 | Clear & Grub | GC1.7 - Fauna Spotter Catcher (FSC) Pre-Clearance Survey | Not started | Open | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-014
cl:0effada5-ca7a-4b98-a8c6-6a9c073614b4 | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-014 | Clear & Grub | GC1.8 - Mandatory GDP Pre-Clearing walk | Not started | Open | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-014
cl:0effada5-ca7a-4b98-a8c6-6a9c073614b4 | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-014 | Clear & Grub | GC1.9 - Clearing of vegetation | Not started | Open | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-014
cl:0effada5-ca7a-4b98-a8c6-6a9c073614b4 | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-014 | Clear & Grub | GC1.10 - Stockpile Cleared Vegetation | Not started | Open | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-014
cl:0effada5-ca7a-4b98-a8c6-6a9c073614b4 | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-014 | Clear & Grub | GC1.11 - Erosion and sediment control | Not started | Open | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-014
cl:0effada5-ca7a-4b98-a8c6-6a9c073614b4 | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-014 | Clear & Grub | GC1.12 - QA close out | Not started | Open | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-014
cl:85d28f37-2ea1-4ea6-b9a0-7d7e71e0a0cf | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-015 | Clear & Grub | GC1.1 - Underlying lot & ITP signed off and conforming | Not started |  | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-015
cl:85d28f37-2ea1-4ea6-b9a0-7d7e71e0a0cf | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-015 | Clear & Grub | GC1.2 - Ground Disturbance Permit (GDP) | In progress | Open | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-015
cl:85d28f37-2ea1-4ea6-b9a0-7d7e71e0a0cf | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-015 | Clear & Grub | GC1.3 - Cultural Heritage(CH) Clearance Survey | Not started | Open | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-015
cl:85d28f37-2ea1-4ea6-b9a0-7d7e71e0a0cf | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-015 | Clear & Grub | GC1.4 - GDP survey set out | Not started | Requested | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-015
cl:85d28f37-2ea1-4ea6-b9a0-7d7e71e0a0cf | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-015 | Clear & Grub | GC1.5 - Survey of pegs to confirm correct GDP survey set out | Not started | Open | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-015
cl:85d28f37-2ea1-4ea6-b9a0-7d7e71e0a0cf | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-015 | Clear & Grub | GC1.6 - Survey natural surface | Not started | Requested | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-015
cl:85d28f37-2ea1-4ea6-b9a0-7d7e71e0a0cf | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-015 | Clear & Grub | GC1.7 - Fauna Spotter Catcher (FSC) Pre-Clearance Survey | Not started | Open | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-015
cl:85d28f37-2ea1-4ea6-b9a0-7d7e71e0a0cf | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-015 | Clear & Grub | GC1.8 - Mandatory GDP Pre-Clearing walk | Not started | Open | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-015
cl:85d28f37-2ea1-4ea6-b9a0-7d7e71e0a0cf | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-015 | Clear & Grub | GC1.9 - Clearing of vegetation | Not started | Open | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-015
cl:85d28f37-2ea1-4ea6-b9a0-7d7e71e0a0cf | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-015 | Clear & Grub | GC1.10 - Stockpile Cleared Vegetation | Not started | Open | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-015
cl:85d28f37-2ea1-4ea6-b9a0-7d7e71e0a0cf | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-015 | Clear & Grub | GC1.11 - Erosion and sediment control | Not started | Requested | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-015
cl:85d28f37-2ea1-4ea6-b9a0-7d7e71e0a0cf | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-015 | Clear & Grub | GC1.12 - QA close out | Not started | Open | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-015
cl:a72b0ea7-6afe-4cc0-b964-01304723282a | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-016 | Clear & Grub | GC1.1 - Underlying lot & ITP signed off and conforming | Not started |  | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-016
cl:a72b0ea7-6afe-4cc0-b964-01304723282a | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-016 | Clear & Grub | GC1.2 - Ground Disturbance Permit (GDP) | In progress | Open | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-016
cl:a72b0ea7-6afe-4cc0-b964-01304723282a | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-016 | Clear & Grub | GC1.3 - Cultural Heritage(CH) Clearance Survey | Not started | Open | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-016
cl:a72b0ea7-6afe-4cc0-b964-01304723282a | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-016 | Clear & Grub | GC1.4 - GDP survey set out | Not started | Requested | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-016
cl:a72b0ea7-6afe-4cc0-b964-01304723282a | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-016 | Clear & Grub | GC1.5 - Survey of pegs to confirm correct GDP survey set out | Not started | Open | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-016
cl:a72b0ea7-6afe-4cc0-b964-01304723282a | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-016 | Clear & Grub | GC1.6 - Survey natural surface | Not started | Open | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-016
cl:a72b0ea7-6afe-4cc0-b964-01304723282a | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-016 | Clear & Grub | GC1.7 - Fauna Spotter Catcher (FSC) Pre-Clearance Survey | Not started | Open | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-016
cl:a72b0ea7-6afe-4cc0-b964-01304723282a | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-016 | Clear & Grub | GC1.8 - Mandatory GDP Pre-Clearing walk | Not started | Open | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-016
cl:a72b0ea7-6afe-4cc0-b964-01304723282a | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-016 | Clear & Grub | GC1.9 - Clearing of vegetation | Not started | Open | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-016
cl:a72b0ea7-6afe-4cc0-b964-01304723282a | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-016 | Clear & Grub | GC1.10 - Stockpile Cleared Vegetation | Not started | Open | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-016
cl:a72b0ea7-6afe-4cc0-b964-01304723282a | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-016 | Clear & Grub | GC1.11 - Erosion and sediment control | Not started | Open | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-016
cl:a72b0ea7-6afe-4cc0-b964-01304723282a | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-016 | Clear & Grub | GC1.12 - QA close out | Not started | Open | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-016
cl:051c9f1d-d8c1-464a-bda4-bb415b94b705 | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-017 | Clear & Grub | GC1.1 - Underlying lot & ITP signed off and conforming | Not started |  | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-017
cl:051c9f1d-d8c1-464a-bda4-bb415b94b705 | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-017 | Clear & Grub | GC1.2 - Ground Disturbance Permit (GDP) | In progress | Open | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-017
cl:051c9f1d-d8c1-464a-bda4-bb415b94b705 | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-017 | Clear & Grub | GC1.3 - Cultural Heritage(CH) Clearance Survey | Not started | Open | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-017
cl:051c9f1d-d8c1-464a-bda4-bb415b94b705 | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-017 | Clear & Grub | GC1.4 - GDP survey set out | Not started | Requested | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-017
cl:051c9f1d-d8c1-464a-bda4-bb415b94b705 | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-017 | Clear & Grub | GC1.5 - Survey of pegs to confirm correct GDP survey set out | Not started | Open | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-017
cl:051c9f1d-d8c1-464a-bda4-bb415b94b705 | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-017 | Clear & Grub | GC1.6 - Survey natural surface | Not started | Requested | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-017
cl:051c9f1d-d8c1-464a-bda4-bb415b94b705 | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-017 | Clear & Grub | GC1.7 - Fauna Spotter Catcher (FSC) Pre-Clearance Survey | Not started | Open | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-017
cl:051c9f1d-d8c1-464a-bda4-bb415b94b705 | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-017 | Clear & Grub | GC1.8 - Mandatory GDP Pre-Clearing walk | Not started | Open | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-017
cl:051c9f1d-d8c1-464a-bda4-bb415b94b705 | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-017 | Clear & Grub | GC1.9 - Clearing of vegetation | Not started | Open | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-017
cl:051c9f1d-d8c1-464a-bda4-bb415b94b705 | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-017 | Clear & Grub | GC1.10 - Stockpile Cleared Vegetation | Not started | Open | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-017
cl:051c9f1d-d8c1-464a-bda4-bb415b94b705 | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-017 | Clear & Grub | GC1.11 - Erosion and sediment control | Not started | Requested | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-017
cl:051c9f1d-d8c1-464a-bda4-bb415b94b705 | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-017 | Clear & Grub | GC1.12 - QA close out | Not started | Open | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-017
cl:d1b56c72-d57c-4afd-b716-5641d17210b7 | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-018 | Clear & Grub | GC1.1 - Underlying lot & ITP signed off and conforming | Not started |  | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-018
cl:d1b56c72-d57c-4afd-b716-5641d17210b7 | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-018 | Clear & Grub | GC1.2 - Ground Disturbance Permit (GDP) | In progress | Open | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-018
cl:d1b56c72-d57c-4afd-b716-5641d17210b7 | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-018 | Clear & Grub | GC1.3 - Cultural Heritage(CH) Clearance Survey | Not started | Open | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-018
cl:d1b56c72-d57c-4afd-b716-5641d17210b7 | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-018 | Clear & Grub | GC1.4 - GDP survey set out | Not started | Requested | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-018
cl:d1b56c72-d57c-4afd-b716-5641d17210b7 | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-018 | Clear & Grub | GC1.5 - Survey of pegs to confirm correct GDP survey set out | Not started | Open | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-018
cl:d1b56c72-d57c-4afd-b716-5641d17210b7 | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-018 | Clear & Grub | GC1.6 - Survey natural surface | Not started | Open | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-018
cl:d1b56c72-d57c-4afd-b716-5641d17210b7 | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-018 | Clear & Grub | GC1.7 - Fauna Spotter Catcher (FSC) Pre-Clearance Survey | Not started | Open | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-018
cl:d1b56c72-d57c-4afd-b716-5641d17210b7 | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-018 | Clear & Grub | GC1.8 - Mandatory GDP Pre-Clearing walk | Not started | Open | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-018
cl:d1b56c72-d57c-4afd-b716-5641d17210b7 | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-018 | Clear & Grub | GC1.9 - Clearing of vegetation | Not started | Open | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-018
cl:d1b56c72-d57c-4afd-b716-5641d17210b7 | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-018 | Clear & Grub | GC1.10 - Stockpile Cleared Vegetation | Not started | Open | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-018
cl:d1b56c72-d57c-4afd-b716-5641d17210b7 | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-018 | Clear & Grub | GC1.11 - Erosion and sediment control | Not started | Requested | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-018
cl:d1b56c72-d57c-4afd-b716-5641d17210b7 | EVA Copper Mine Project | Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-018 | Clear & Grub | GC1.12 - QA close out | Not started | Open | ITP-001 Clear & Grub | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-018
cl:dde51873-c2b5-4bea-b167-82115f1a2514 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-002 Topsoil Stripping | MAR_Topsoil Strip | Topsoil Stripping | TS1.1 - Underlying lot & ITP signed off and conforming | N/A |  | ITP-002 Topsoil Stripping | Main Access Road (MAR) | ITP-002 Topsoil Stripping | MAR_Topsoil Strip
cl:dde51873-c2b5-4bea-b167-82115f1a2514 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-002 Topsoil Stripping | MAR_Topsoil Strip | Topsoil Stripping | TS1.2 - Survey Set out | Not started | Rejected | ITP-002 Topsoil Stripping | Main Access Road (MAR) | ITP-002 Topsoil Stripping | MAR_Topsoil Strip
cl:dde51873-c2b5-4bea-b167-82115f1a2514 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-002 Topsoil Stripping | MAR_Topsoil Strip | Topsoil Stripping | TS1.3 - Strip topsoil, load & haul to approved stockpile location | In progress | Open | ITP-002 Topsoil Stripping | Main Access Road (MAR) | ITP-002 Topsoil Stripping | MAR_Topsoil Strip
cl:dde51873-c2b5-4bea-b167-82115f1a2514 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-002 Topsoil Stripping | MAR_Topsoil Strip | Topsoil Stripping | TS1.4 - Topsoil location, destination and quantity catalogued. | In progress | Open | ITP-002 Topsoil Stripping | Main Access Road (MAR) | ITP-002 Topsoil Stripping | MAR_Topsoil Strip
cl:dde51873-c2b5-4bea-b167-82115f1a2514 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-002 Topsoil Stripping | MAR_Topsoil Strip | Topsoil Stripping | TS1.5 - Surface level check and survey pick-up | Not started | Requested | ITP-002 Topsoil Stripping | Main Access Road (MAR) | ITP-002 Topsoil Stripping | MAR_Topsoil Strip
cl:dde51873-c2b5-4bea-b167-82115f1a2514 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-002 Topsoil Stripping | MAR_Topsoil Strip | Topsoil Stripping | TS1.6 - QA close out | Not started | Open | ITP-002 Topsoil Stripping | Main Access Road (MAR) | ITP-002 Topsoil Stripping | MAR_Topsoil Strip
cl:8317e097-e36c-4786-909c-0676614fd2f0 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-002 | Topsoil Stripping | TS1.1 - Underlying lot & ITP signed off and conforming | Not started |  | ITP-002 Topsoil Stripping | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-002
cl:8317e097-e36c-4786-909c-0676614fd2f0 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-002 | Topsoil Stripping | TS1.2 - Survey Set out | Not started | Open | ITP-002 Topsoil Stripping | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-002
cl:8317e097-e36c-4786-909c-0676614fd2f0 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-002 | Topsoil Stripping | TS1.3 - Strip topsoil, load & haul to approved stockpile location | Not started | Open | ITP-002 Topsoil Stripping | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-002
cl:8317e097-e36c-4786-909c-0676614fd2f0 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-002 | Topsoil Stripping | TS1.4 - Topsoil location, destination and quantity catalogued. | Not started | Open | ITP-002 Topsoil Stripping | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-002
cl:8317e097-e36c-4786-909c-0676614fd2f0 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-002 | Topsoil Stripping | TS1.5 - Surface level check and survey pick-up | Not started | Open | ITP-002 Topsoil Stripping | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-002
cl:8317e097-e36c-4786-909c-0676614fd2f0 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-002 | Topsoil Stripping | TS1.6 - QA close out | Not started | Open | ITP-002 Topsoil Stripping | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-002
cl:2bda6402-ac23-4e73-be43-03c89c1031bc | EVA Copper Mine Project | Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-003 | Topsoil Stripping | TS1.1 - Underlying lot & ITP signed off and conforming | Not started |  | ITP-002 Topsoil Stripping | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-003
cl:2bda6402-ac23-4e73-be43-03c89c1031bc | EVA Copper Mine Project | Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-003 | Topsoil Stripping | TS1.2 - Survey Set out | Not started | Open | ITP-002 Topsoil Stripping | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-003
cl:2bda6402-ac23-4e73-be43-03c89c1031bc | EVA Copper Mine Project | Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-003 | Topsoil Stripping | TS1.3 - Strip topsoil, load & haul to approved stockpile location | Not started | Open | ITP-002 Topsoil Stripping | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-003
cl:2bda6402-ac23-4e73-be43-03c89c1031bc | EVA Copper Mine Project | Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-003 | Topsoil Stripping | TS1.4 - Topsoil location, destination and quantity catalogued. | Not started | Open | ITP-002 Topsoil Stripping | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-003
cl:2bda6402-ac23-4e73-be43-03c89c1031bc | EVA Copper Mine Project | Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-003 | Topsoil Stripping | TS1.5 - Surface level check and survey pick-up | Not started | Open | ITP-002 Topsoil Stripping | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-003
cl:2bda6402-ac23-4e73-be43-03c89c1031bc | EVA Copper Mine Project | Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-003 | Topsoil Stripping | TS1.6 - QA close out | Not started | Open | ITP-002 Topsoil Stripping | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-003
cl:4f8d8ae6-4e61-4fe7-85fd-c923ce0a90b4 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-004 | Topsoil Stripping | TS1.1 - Underlying lot & ITP signed off and conforming | Not started |  | ITP-002 Topsoil Stripping | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-004
cl:4f8d8ae6-4e61-4fe7-85fd-c923ce0a90b4 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-004 | Topsoil Stripping | TS1.2 - Survey Set out | Not started | Open | ITP-002 Topsoil Stripping | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-004
cl:4f8d8ae6-4e61-4fe7-85fd-c923ce0a90b4 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-004 | Topsoil Stripping | TS1.3 - Strip topsoil, load & haul to approved stockpile location | Not started | Open | ITP-002 Topsoil Stripping | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-004
cl:4f8d8ae6-4e61-4fe7-85fd-c923ce0a90b4 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-004 | Topsoil Stripping | TS1.4 - Topsoil location, destination and quantity catalogued. | Not started | Open | ITP-002 Topsoil Stripping | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-004
cl:4f8d8ae6-4e61-4fe7-85fd-c923ce0a90b4 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-004 | Topsoil Stripping | TS1.5 - Surface level check and survey pick-up | Not started | Open | ITP-002 Topsoil Stripping | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-004
cl:4f8d8ae6-4e61-4fe7-85fd-c923ce0a90b4 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-004 | Topsoil Stripping | TS1.6 - QA close out | Not started | Open | ITP-002 Topsoil Stripping | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-004
cl:bde07827-3e74-4f9c-ac80-4be5ff966004 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-005 | Topsoil Stripping | TS1.1 - Underlying lot & ITP signed off and conforming | Not started |  | ITP-002 Topsoil Stripping | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-005
cl:bde07827-3e74-4f9c-ac80-4be5ff966004 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-005 | Topsoil Stripping | TS1.2 - Survey Set out | Not started | Open | ITP-002 Topsoil Stripping | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-005
cl:bde07827-3e74-4f9c-ac80-4be5ff966004 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-005 | Topsoil Stripping | TS1.3 - Strip topsoil, load & haul to approved stockpile location | Not started | Open | ITP-002 Topsoil Stripping | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-005
cl:bde07827-3e74-4f9c-ac80-4be5ff966004 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-005 | Topsoil Stripping | TS1.4 - Topsoil location, destination and quantity catalogued. | Not started | Open | ITP-002 Topsoil Stripping | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-005
cl:bde07827-3e74-4f9c-ac80-4be5ff966004 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-005 | Topsoil Stripping | TS1.5 - Surface level check and survey pick-up | Not started | Open | ITP-002 Topsoil Stripping | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-005
cl:bde07827-3e74-4f9c-ac80-4be5ff966004 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-005 | Topsoil Stripping | TS1.6 - QA close out | Not started | Open | ITP-002 Topsoil Stripping | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-005
cl:098b6870-213c-4c04-b4b8-a728d554843f | EVA Copper Mine Project | Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-006 | Topsoil Stripping | TS1.1 - Underlying lot & ITP signed off and conforming | Not started |  | ITP-002 Topsoil Stripping | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-006
cl:098b6870-213c-4c04-b4b8-a728d554843f | EVA Copper Mine Project | Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-006 | Topsoil Stripping | TS1.2 - Survey Set out | Not started | Open | ITP-002 Topsoil Stripping | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-006
cl:098b6870-213c-4c04-b4b8-a728d554843f | EVA Copper Mine Project | Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-006 | Topsoil Stripping | TS1.3 - Strip topsoil, load & haul to approved stockpile location | Not started | Open | ITP-002 Topsoil Stripping | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-006
cl:098b6870-213c-4c04-b4b8-a728d554843f | EVA Copper Mine Project | Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-006 | Topsoil Stripping | TS1.4 - Topsoil location, destination and quantity catalogued. | Not started | Open | ITP-002 Topsoil Stripping | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-006
cl:098b6870-213c-4c04-b4b8-a728d554843f | EVA Copper Mine Project | Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-006 | Topsoil Stripping | TS1.5 - Surface level check and survey pick-up | Not started | Open | ITP-002 Topsoil Stripping | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-006
cl:098b6870-213c-4c04-b4b8-a728d554843f | EVA Copper Mine Project | Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-006 | Topsoil Stripping | TS1.6 - QA close out | Not started | Open | ITP-002 Topsoil Stripping | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-006
cl:cd3ee4c6-dc94-48db-95dd-856df713ad3b | EVA Copper Mine Project | Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-007 | Topsoil Stripping | TS1.1 - Underlying lot & ITP signed off and conforming | Not started |  | ITP-002 Topsoil Stripping | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-007
cl:cd3ee4c6-dc94-48db-95dd-856df713ad3b | EVA Copper Mine Project | Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-007 | Topsoil Stripping | TS1.2 - Survey Set out | Not started | Open | ITP-002 Topsoil Stripping | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-007
cl:cd3ee4c6-dc94-48db-95dd-856df713ad3b | EVA Copper Mine Project | Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-007 | Topsoil Stripping | TS1.3 - Strip topsoil, load & haul to approved stockpile location | Not started | Open | ITP-002 Topsoil Stripping | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-007
cl:cd3ee4c6-dc94-48db-95dd-856df713ad3b | EVA Copper Mine Project | Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-007 | Topsoil Stripping | TS1.4 - Topsoil location, destination and quantity catalogued. | Not started | Open | ITP-002 Topsoil Stripping | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-007
cl:cd3ee4c6-dc94-48db-95dd-856df713ad3b | EVA Copper Mine Project | Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-007 | Topsoil Stripping | TS1.5 - Surface level check and survey pick-up | Not started | Open | ITP-002 Topsoil Stripping | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-007
cl:cd3ee4c6-dc94-48db-95dd-856df713ad3b | EVA Copper Mine Project | Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-007 | Topsoil Stripping | TS1.6 - QA close out | Not started | Open | ITP-002 Topsoil Stripping | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-007
cl:890586ba-3090-4dbf-9301-4c42131e6071 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-008 | Topsoil Stripping | TS1.1 - Underlying lot & ITP signed off and conforming | Not started |  | ITP-002 Topsoil Stripping | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-008
cl:890586ba-3090-4dbf-9301-4c42131e6071 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-008 | Topsoil Stripping | TS1.2 - Survey Set out | Not started | Open | ITP-002 Topsoil Stripping | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-008
cl:890586ba-3090-4dbf-9301-4c42131e6071 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-008 | Topsoil Stripping | TS1.3 - Strip topsoil, load & haul to approved stockpile location | Not started | Open | ITP-002 Topsoil Stripping | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-008
cl:890586ba-3090-4dbf-9301-4c42131e6071 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-008 | Topsoil Stripping | TS1.4 - Topsoil location, destination and quantity catalogued. | Not started | Open | ITP-002 Topsoil Stripping | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-008
cl:890586ba-3090-4dbf-9301-4c42131e6071 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-008 | Topsoil Stripping | TS1.5 - Surface level check and survey pick-up | Not started | Open | ITP-002 Topsoil Stripping | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-008
cl:890586ba-3090-4dbf-9301-4c42131e6071 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-008 | Topsoil Stripping | TS1.6 - QA close out | Not started | Open | ITP-002 Topsoil Stripping | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-008
cl:8d598f4d-ceaa-45b0-8440-e65f16dd4594 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-009 | Topsoil Stripping | TS1.1 - Underlying lot & ITP signed off and conforming | Not started |  | ITP-002 Topsoil Stripping | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-009
cl:8d598f4d-ceaa-45b0-8440-e65f16dd4594 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-009 | Topsoil Stripping | TS1.2 - Survey Set out | Not started | Open | ITP-002 Topsoil Stripping | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-009
cl:8d598f4d-ceaa-45b0-8440-e65f16dd4594 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-009 | Topsoil Stripping | TS1.3 - Strip topsoil, load & haul to approved stockpile location | Not started | Open | ITP-002 Topsoil Stripping | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-009
cl:8d598f4d-ceaa-45b0-8440-e65f16dd4594 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-009 | Topsoil Stripping | TS1.4 - Topsoil location, destination and quantity catalogued. | Not started | Open | ITP-002 Topsoil Stripping | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-009
cl:8d598f4d-ceaa-45b0-8440-e65f16dd4594 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-009 | Topsoil Stripping | TS1.5 - Surface level check and survey pick-up | Not started | Open | ITP-002 Topsoil Stripping | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-009
cl:8d598f4d-ceaa-45b0-8440-e65f16dd4594 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-009 | Topsoil Stripping | TS1.6 - QA close out | Not started | Open | ITP-002 Topsoil Stripping | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-009
cl:5e887b02-4eff-475f-88ec-1338b04019ac | EVA Copper Mine Project | Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-010 | Topsoil Stripping | TS1.1 - Underlying lot & ITP signed off and conforming | Not started |  | ITP-002 Topsoil Stripping | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-010
cl:5e887b02-4eff-475f-88ec-1338b04019ac | EVA Copper Mine Project | Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-010 | Topsoil Stripping | TS1.2 - Survey Set out | Not started | Open | ITP-002 Topsoil Stripping | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-010
cl:5e887b02-4eff-475f-88ec-1338b04019ac | EVA Copper Mine Project | Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-010 | Topsoil Stripping | TS1.3 - Strip topsoil, load & haul to approved stockpile location | Not started | Open | ITP-002 Topsoil Stripping | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-010
cl:5e887b02-4eff-475f-88ec-1338b04019ac | EVA Copper Mine Project | Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-010 | Topsoil Stripping | TS1.4 - Topsoil location, destination and quantity catalogued. | Not started | Open | ITP-002 Topsoil Stripping | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-010
cl:5e887b02-4eff-475f-88ec-1338b04019ac | EVA Copper Mine Project | Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-010 | Topsoil Stripping | TS1.5 - Surface level check and survey pick-up | Not started | Open | ITP-002 Topsoil Stripping | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-010
cl:5e887b02-4eff-475f-88ec-1338b04019ac | EVA Copper Mine Project | Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-010 | Topsoil Stripping | TS1.6 - QA close out | Not started | Open | ITP-002 Topsoil Stripping | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-010
cl:e7d0f507-3ba6-4741-888e-5b243a81ba4a | EVA Copper Mine Project | Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-011 | Topsoil Stripping | TS1.1 - Underlying lot & ITP signed off and conforming | Not started |  | ITP-002 Topsoil Stripping | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-011
cl:e7d0f507-3ba6-4741-888e-5b243a81ba4a | EVA Copper Mine Project | Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-011 | Topsoil Stripping | TS1.2 - Survey Set out | Not started | Open | ITP-002 Topsoil Stripping | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-011
cl:e7d0f507-3ba6-4741-888e-5b243a81ba4a | EVA Copper Mine Project | Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-011 | Topsoil Stripping | TS1.3 - Strip topsoil, load & haul to approved stockpile location | Not started | Open | ITP-002 Topsoil Stripping | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-011
cl:e7d0f507-3ba6-4741-888e-5b243a81ba4a | EVA Copper Mine Project | Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-011 | Topsoil Stripping | TS1.4 - Topsoil location, destination and quantity catalogued. | Not started | Open | ITP-002 Topsoil Stripping | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-011
cl:e7d0f507-3ba6-4741-888e-5b243a81ba4a | EVA Copper Mine Project | Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-011 | Topsoil Stripping | TS1.5 - Surface level check and survey pick-up | Not started | Open | ITP-002 Topsoil Stripping | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-011
cl:e7d0f507-3ba6-4741-888e-5b243a81ba4a | EVA Copper Mine Project | Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-011 | Topsoil Stripping | TS1.6 - QA close out | Not started | Open | ITP-002 Topsoil Stripping | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-011
cl:498fa056-53e6-4adf-836a-db22afe3c868 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-012 | Topsoil Stripping | TS1.1 - Underlying lot & ITP signed off and conforming | Not started |  | ITP-002 Topsoil Stripping | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-012
cl:498fa056-53e6-4adf-836a-db22afe3c868 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-012 | Topsoil Stripping | TS1.2 - Survey Set out | Not started | Open | ITP-002 Topsoil Stripping | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-012
cl:498fa056-53e6-4adf-836a-db22afe3c868 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-012 | Topsoil Stripping | TS1.3 - Strip topsoil, load & haul to approved stockpile location | Not started | Open | ITP-002 Topsoil Stripping | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-012
cl:498fa056-53e6-4adf-836a-db22afe3c868 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-012 | Topsoil Stripping | TS1.4 - Topsoil location, destination and quantity catalogued. | Not started | Open | ITP-002 Topsoil Stripping | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-012
cl:498fa056-53e6-4adf-836a-db22afe3c868 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-012 | Topsoil Stripping | TS1.5 - Surface level check and survey pick-up | Not started | Open | ITP-002 Topsoil Stripping | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-012
cl:498fa056-53e6-4adf-836a-db22afe3c868 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-012 | Topsoil Stripping | TS1.6 - QA close out | Not started | Open | ITP-002 Topsoil Stripping | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-012
cl:22b7127d-bfb7-4635-a01d-3fdec26b5a48 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-013 | Topsoil Stripping | TS1.1 - Underlying lot & ITP signed off and conforming | Not started |  | ITP-002 Topsoil Stripping | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-013
cl:22b7127d-bfb7-4635-a01d-3fdec26b5a48 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-013 | Topsoil Stripping | TS1.2 - Survey Set out | Not started | Open | ITP-002 Topsoil Stripping | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-013
cl:22b7127d-bfb7-4635-a01d-3fdec26b5a48 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-013 | Topsoil Stripping | TS1.3 - Strip topsoil, load & haul to approved stockpile location | Not started | Open | ITP-002 Topsoil Stripping | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-013
cl:22b7127d-bfb7-4635-a01d-3fdec26b5a48 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-013 | Topsoil Stripping | TS1.4 - Topsoil location, destination and quantity catalogued. | Not started | Open | ITP-002 Topsoil Stripping | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-013
cl:22b7127d-bfb7-4635-a01d-3fdec26b5a48 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-013 | Topsoil Stripping | TS1.5 - Surface level check and survey pick-up | Not started | Open | ITP-002 Topsoil Stripping | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-013
cl:22b7127d-bfb7-4635-a01d-3fdec26b5a48 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-013 | Topsoil Stripping | TS1.6 - QA close out | Not started | Open | ITP-002 Topsoil Stripping | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-013
cl:c05fcc86-fd09-437f-b001-613dac76b03b | EVA Copper Mine Project | Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-014 | Topsoil Stripping | TS1.1 - Underlying lot & ITP signed off and conforming | Not started |  | ITP-002 Topsoil Stripping | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-014
cl:c05fcc86-fd09-437f-b001-613dac76b03b | EVA Copper Mine Project | Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-014 | Topsoil Stripping | TS1.2 - Survey Set out | Not started | Open | ITP-002 Topsoil Stripping | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-014
cl:c05fcc86-fd09-437f-b001-613dac76b03b | EVA Copper Mine Project | Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-014 | Topsoil Stripping | TS1.3 - Strip topsoil, load & haul to approved stockpile location | Not started | Open | ITP-002 Topsoil Stripping | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-014
cl:c05fcc86-fd09-437f-b001-613dac76b03b | EVA Copper Mine Project | Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-014 | Topsoil Stripping | TS1.4 - Topsoil location, destination and quantity catalogued. | Not started | Open | ITP-002 Topsoil Stripping | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-014
cl:c05fcc86-fd09-437f-b001-613dac76b03b | EVA Copper Mine Project | Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-014 | Topsoil Stripping | TS1.5 - Surface level check and survey pick-up | Not started | Open | ITP-002 Topsoil Stripping | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-014
cl:c05fcc86-fd09-437f-b001-613dac76b03b | EVA Copper Mine Project | Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-014 | Topsoil Stripping | TS1.6 - QA close out | Not started | Open | ITP-002 Topsoil Stripping | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-014
cl:a48b81b5-f8da-4249-a9ba-d92a49debb55 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-015 | Topsoil Stripping | TS1.1 - Underlying lot & ITP signed off and conforming | Not started |  | ITP-002 Topsoil Stripping | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-015
cl:a48b81b5-f8da-4249-a9ba-d92a49debb55 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-015 | Topsoil Stripping | TS1.2 - Survey Set out | Not started | Open | ITP-002 Topsoil Stripping | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-015
cl:a48b81b5-f8da-4249-a9ba-d92a49debb55 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-015 | Topsoil Stripping | TS1.3 - Strip topsoil, load & haul to approved stockpile location | Not started | Open | ITP-002 Topsoil Stripping | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-015
cl:a48b81b5-f8da-4249-a9ba-d92a49debb55 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-015 | Topsoil Stripping | TS1.4 - Topsoil location, destination and quantity catalogued. | Not started | Open | ITP-002 Topsoil Stripping | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-015
cl:a48b81b5-f8da-4249-a9ba-d92a49debb55 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-015 | Topsoil Stripping | TS1.5 - Surface level check and survey pick-up | Not started | Open | ITP-002 Topsoil Stripping | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-015
cl:a48b81b5-f8da-4249-a9ba-d92a49debb55 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-015 | Topsoil Stripping | TS1.6 - QA close out | Not started | Open | ITP-002 Topsoil Stripping | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-015
cl:6f3bc2e6-9027-42ca-b7d0-ad548a1c31db | EVA Copper Mine Project | Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-016 | Topsoil Stripping | TS1.1 - Underlying lot & ITP signed off and conforming | Not started |  | ITP-002 Topsoil Stripping | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-016
cl:6f3bc2e6-9027-42ca-b7d0-ad548a1c31db | EVA Copper Mine Project | Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-016 | Topsoil Stripping | TS1.2 - Survey Set out | Not started | Open | ITP-002 Topsoil Stripping | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-016
cl:6f3bc2e6-9027-42ca-b7d0-ad548a1c31db | EVA Copper Mine Project | Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-016 | Topsoil Stripping | TS1.3 - Strip topsoil, load & haul to approved stockpile location | Not started | Open | ITP-002 Topsoil Stripping | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-016
cl:6f3bc2e6-9027-42ca-b7d0-ad548a1c31db | EVA Copper Mine Project | Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-016 | Topsoil Stripping | TS1.4 - Topsoil location, destination and quantity catalogued. | Not started | Open | ITP-002 Topsoil Stripping | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-016
cl:6f3bc2e6-9027-42ca-b7d0-ad548a1c31db | EVA Copper Mine Project | Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-016 | Topsoil Stripping | TS1.5 - Surface level check and survey pick-up | Not started | Open | ITP-002 Topsoil Stripping | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-016
cl:6f3bc2e6-9027-42ca-b7d0-ad548a1c31db | EVA Copper Mine Project | Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-016 | Topsoil Stripping | TS1.6 - QA close out | Not started | Open | ITP-002 Topsoil Stripping | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-016
cl:32331128-a4ca-4fcd-ad45-79bcd149cee1 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-017 | Topsoil Stripping | TS1.1 - Underlying lot & ITP signed off and conforming | Not started |  | ITP-002 Topsoil Stripping | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-017
cl:32331128-a4ca-4fcd-ad45-79bcd149cee1 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-017 | Topsoil Stripping | TS1.2 - Survey Set out | Not started | Open | ITP-002 Topsoil Stripping | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-017
cl:32331128-a4ca-4fcd-ad45-79bcd149cee1 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-017 | Topsoil Stripping | TS1.3 - Strip topsoil, load & haul to approved stockpile location | Not started | Open | ITP-002 Topsoil Stripping | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-017
cl:32331128-a4ca-4fcd-ad45-79bcd149cee1 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-017 | Topsoil Stripping | TS1.4 - Topsoil location, destination and quantity catalogued. | Not started | Open | ITP-002 Topsoil Stripping | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-017
cl:32331128-a4ca-4fcd-ad45-79bcd149cee1 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-017 | Topsoil Stripping | TS1.5 - Surface level check and survey pick-up | Not started | Open | ITP-002 Topsoil Stripping | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-017
cl:32331128-a4ca-4fcd-ad45-79bcd149cee1 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-017 | Topsoil Stripping | TS1.6 - QA close out | Not started | Open | ITP-002 Topsoil Stripping | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-017
cl:5faede6d-452d-473d-9d83-053657020978 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-001 CH192 to CH265 | Subgrade/Foundation Preparation | SP.1.1 - Underlying lot & ITP signed off and conforming | N/A |  | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-001 CH192 to CH265
cl:5faede6d-452d-473d-9d83-053657020978 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-001 CH192 to CH265 | Subgrade/Foundation Preparation | SP.1.2 - Embankment fill material | Not started | Open | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-001 CH192 to CH265
cl:5faede6d-452d-473d-9d83-053657020978 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-001 CH192 to CH265 | Subgrade/Foundation Preparation | SP.1.3 - Survey Set out | Not started | Open | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-001 CH192 to CH265
cl:5faede6d-452d-473d-9d83-053657020978 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-001 CH192 to CH265 | Subgrade/Foundation Preparation | SP.1.4 - Removal and replacement of unsuitable material | Not started | Open | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-001 CH192 to CH265
cl:5faede6d-452d-473d-9d83-053657020978 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-001 CH192 to CH265 | Subgrade/Foundation Preparation | SP.1.5 - Subgrade/Foundation preparation | Not started | Open | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-001 CH192 to CH265
cl:5faede6d-452d-473d-9d83-053657020978 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-001 CH192 to CH265 | Subgrade/Foundation Preparation | SP.1.6 - Trim subgrade | Not started | Open | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-001 CH192 to CH265
cl:5faede6d-452d-473d-9d83-053657020978 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-001 CH192 to CH265 | Subgrade/Foundation Preparation | SP.1.7 - Proof rolling | In progress | Open | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-001 CH192 to CH265
cl:5faede6d-452d-473d-9d83-053657020978 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-001 CH192 to CH265 | Subgrade/Foundation Preparation | SP.1.8 - Surface level check and survey pick-up | Not started | Open | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-001 CH192 to CH265
cl:5faede6d-452d-473d-9d83-053657020978 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-001 CH192 to CH265 | Subgrade/Foundation Preparation | SP.1.9 - QA close out | Not started | Open | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-001 CH192 to CH265
cl:dd921dce-64f6-4358-8403-c80cd07d931b | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-002 | Subgrade/Foundation Preparation | SP.1.1 - Underlying lot & ITP signed off and conforming | N/A |  | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-002
cl:dd921dce-64f6-4358-8403-c80cd07d931b | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-002 | Subgrade/Foundation Preparation | SP.1.2 - Embankment fill material | Not started | Open | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-002
cl:dd921dce-64f6-4358-8403-c80cd07d931b | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-002 | Subgrade/Foundation Preparation | SP.1.3 - Survey Set out | Not started | Open | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-002
cl:dd921dce-64f6-4358-8403-c80cd07d931b | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-002 | Subgrade/Foundation Preparation | SP.1.4 - Removal and replacement of unsuitable material | Not started | Open | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-002
cl:dd921dce-64f6-4358-8403-c80cd07d931b | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-002 | Subgrade/Foundation Preparation | SP.1.5 - Subgrade/Foundation preparation | Not started | Requested | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-002
cl:dd921dce-64f6-4358-8403-c80cd07d931b | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-002 | Subgrade/Foundation Preparation | SP.1.6 - Trim subgrade | Not started | Open | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-002
cl:dd921dce-64f6-4358-8403-c80cd07d931b | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-002 | Subgrade/Foundation Preparation | SP.1.7 - Proof rolling | Not started | Open | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-002
cl:dd921dce-64f6-4358-8403-c80cd07d931b | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-002 | Subgrade/Foundation Preparation | SP.1.8 - Surface level check and survey pick-up | Not started | Open | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-002
cl:dd921dce-64f6-4358-8403-c80cd07d931b | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-002 | Subgrade/Foundation Preparation | SP.1.9 - QA close out | Not started | Open | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-002
cl:dfd435c3-f0c0-4b2f-b551-fc40fbf36967 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-003 | Subgrade/Foundation Preparation | SP.1.1 - Underlying lot & ITP signed off and conforming | Not started |  | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-003
cl:dfd435c3-f0c0-4b2f-b551-fc40fbf36967 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-003 | Subgrade/Foundation Preparation | SP.1.2 - Embankment fill material | Not started | Open | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-003
cl:dfd435c3-f0c0-4b2f-b551-fc40fbf36967 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-003 | Subgrade/Foundation Preparation | SP.1.3 - Survey Set out | Not started | Open | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-003
cl:dfd435c3-f0c0-4b2f-b551-fc40fbf36967 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-003 | Subgrade/Foundation Preparation | SP.1.4 - Removal and replacement of unsuitable material | N/A | Requested | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-003
cl:dfd435c3-f0c0-4b2f-b551-fc40fbf36967 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-003 | Subgrade/Foundation Preparation | SP.1.5 - Subgrade/Foundation preparation | Not started | Open | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-003
cl:dfd435c3-f0c0-4b2f-b551-fc40fbf36967 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-003 | Subgrade/Foundation Preparation | SP.1.6 - Trim subgrade | Not started | Open | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-003
cl:dfd435c3-f0c0-4b2f-b551-fc40fbf36967 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-003 | Subgrade/Foundation Preparation | SP.1.7 - Proof rolling | Not started | Approved | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-003
cl:dfd435c3-f0c0-4b2f-b551-fc40fbf36967 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-003 | Subgrade/Foundation Preparation | SP.1.8 - Surface level check and survey pick-up | Not started | Rejected | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-003
cl:dfd435c3-f0c0-4b2f-b551-fc40fbf36967 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-003 | Subgrade/Foundation Preparation | SP.1.9 - QA close out | Not started | Open | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-003
cl:daf905da-f777-4c54-a111-92e86f98d02b | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-004 CH732 to CH1050 | Subgrade/Foundation Preparation | SP.1.1 - Underlying lot & ITP signed off and conforming | N/A |  | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-004 CH732 to CH1050
cl:daf905da-f777-4c54-a111-92e86f98d02b | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-004 CH732 to CH1050 | Subgrade/Foundation Preparation | SP.1.2 - Embankment fill material | Not started | Open | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-004 CH732 to CH1050
cl:daf905da-f777-4c54-a111-92e86f98d02b | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-004 CH732 to CH1050 | Subgrade/Foundation Preparation | SP.1.3 - Survey Set out | Not started | Open | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-004 CH732 to CH1050
cl:daf905da-f777-4c54-a111-92e86f98d02b | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-004 CH732 to CH1050 | Subgrade/Foundation Preparation | SP.1.4 - Removal and replacement of unsuitable material | Not started | Open | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-004 CH732 to CH1050
cl:daf905da-f777-4c54-a111-92e86f98d02b | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-004 CH732 to CH1050 | Subgrade/Foundation Preparation | SP.1.5 - Subgrade/Foundation preparation | Not started | Open | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-004 CH732 to CH1050
cl:daf905da-f777-4c54-a111-92e86f98d02b | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-004 CH732 to CH1050 | Subgrade/Foundation Preparation | SP.1.6 - Trim subgrade | Not started | Open | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-004 CH732 to CH1050
cl:daf905da-f777-4c54-a111-92e86f98d02b | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-004 CH732 to CH1050 | Subgrade/Foundation Preparation | SP.1.7 - Proof rolling | Not started | Open | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-004 CH732 to CH1050
cl:daf905da-f777-4c54-a111-92e86f98d02b | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-004 CH732 to CH1050 | Subgrade/Foundation Preparation | SP.1.8 - Surface level check and survey pick-up | Not started | Rejected | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-004 CH732 to CH1050
cl:daf905da-f777-4c54-a111-92e86f98d02b | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-004 CH732 to CH1050 | Subgrade/Foundation Preparation | SP.1.9 - QA close out | Not started | Open | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-004 CH732 to CH1050
cl:8c4c1f20-301a-4faa-82ae-3a21fb30320b | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-005 | Subgrade/Foundation Preparation | SP.1.1 - Underlying lot & ITP signed off and conforming | Not started |  | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-005
cl:8c4c1f20-301a-4faa-82ae-3a21fb30320b | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-005 | Subgrade/Foundation Preparation | SP.1.2 - Embankment fill material | Not started | Open | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-005
cl:8c4c1f20-301a-4faa-82ae-3a21fb30320b | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-005 | Subgrade/Foundation Preparation | SP.1.3 - Survey Set out | Not started | Open | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-005
cl:8c4c1f20-301a-4faa-82ae-3a21fb30320b | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-005 | Subgrade/Foundation Preparation | SP.1.4 - Removal and replacement of unsuitable material | Not started | Open | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-005
cl:8c4c1f20-301a-4faa-82ae-3a21fb30320b | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-005 | Subgrade/Foundation Preparation | SP.1.5 - Subgrade/Foundation preparation | Not started | Open | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-005
cl:8c4c1f20-301a-4faa-82ae-3a21fb30320b | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-005 | Subgrade/Foundation Preparation | SP.1.6 - Trim subgrade | Not started | Open | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-005
cl:8c4c1f20-301a-4faa-82ae-3a21fb30320b | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-005 | Subgrade/Foundation Preparation | SP.1.7 - Proof rolling | Not started | Open | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-005
cl:8c4c1f20-301a-4faa-82ae-3a21fb30320b | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-005 | Subgrade/Foundation Preparation | SP.1.8 - Surface level check and survey pick-up | Not started | Open | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-005
cl:8c4c1f20-301a-4faa-82ae-3a21fb30320b | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-005 | Subgrade/Foundation Preparation | SP.1.9 - QA close out | Not started | Open | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-005
cl:8a8758d6-38e3-445b-b0be-0ebd2130b1a2 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-006 | Subgrade/Foundation Preparation | SP.1.1 - Underlying lot & ITP signed off and conforming | Not started |  | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-006
cl:8a8758d6-38e3-445b-b0be-0ebd2130b1a2 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-006 | Subgrade/Foundation Preparation | SP.1.2 - Embankment fill material | Not started | Open | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-006
cl:8a8758d6-38e3-445b-b0be-0ebd2130b1a2 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-006 | Subgrade/Foundation Preparation | SP.1.3 - Survey Set out | Not started | Open | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-006
cl:8a8758d6-38e3-445b-b0be-0ebd2130b1a2 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-006 | Subgrade/Foundation Preparation | SP.1.4 - Removal and replacement of unsuitable material | Not started | Open | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-006
cl:8a8758d6-38e3-445b-b0be-0ebd2130b1a2 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-006 | Subgrade/Foundation Preparation | SP.1.5 - Subgrade/Foundation preparation | Not started | Open | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-006
cl:8a8758d6-38e3-445b-b0be-0ebd2130b1a2 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-006 | Subgrade/Foundation Preparation | SP.1.6 - Trim subgrade | Not started | Open | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-006
cl:8a8758d6-38e3-445b-b0be-0ebd2130b1a2 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-006 | Subgrade/Foundation Preparation | SP.1.7 - Proof rolling | Not started | Open | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-006
cl:8a8758d6-38e3-445b-b0be-0ebd2130b1a2 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-006 | Subgrade/Foundation Preparation | SP.1.8 - Surface level check and survey pick-up | Not started | Open | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-006
cl:8a8758d6-38e3-445b-b0be-0ebd2130b1a2 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-006 | Subgrade/Foundation Preparation | SP.1.9 - QA close out | Not started | Open | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-006
cl:c3a4e319-d9e4-4abf-8ab0-310e329d8dfb | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-007 | Subgrade/Foundation Preparation | SP.1.1 - Underlying lot & ITP signed off and conforming | Not started |  | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-007
cl:c3a4e319-d9e4-4abf-8ab0-310e329d8dfb | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-007 | Subgrade/Foundation Preparation | SP.1.2 - Embankment fill material | Not started | Open | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-007
cl:c3a4e319-d9e4-4abf-8ab0-310e329d8dfb | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-007 | Subgrade/Foundation Preparation | SP.1.3 - Survey Set out | Not started | Open | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-007
cl:c3a4e319-d9e4-4abf-8ab0-310e329d8dfb | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-007 | Subgrade/Foundation Preparation | SP.1.4 - Removal and replacement of unsuitable material | Not started | Open | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-007
cl:c3a4e319-d9e4-4abf-8ab0-310e329d8dfb | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-007 | Subgrade/Foundation Preparation | SP.1.5 - Subgrade/Foundation preparation | Not started | Open | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-007
cl:c3a4e319-d9e4-4abf-8ab0-310e329d8dfb | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-007 | Subgrade/Foundation Preparation | SP.1.6 - Trim subgrade | Not started | Open | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-007
cl:c3a4e319-d9e4-4abf-8ab0-310e329d8dfb | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-007 | Subgrade/Foundation Preparation | SP.1.7 - Proof rolling | Not started | Open | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-007
cl:c3a4e319-d9e4-4abf-8ab0-310e329d8dfb | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-007 | Subgrade/Foundation Preparation | SP.1.8 - Surface level check and survey pick-up | Not started | Open | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-007
cl:c3a4e319-d9e4-4abf-8ab0-310e329d8dfb | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-007 | Subgrade/Foundation Preparation | SP.1.9 - QA close out | Not started | Open | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-007
cl:e2120dd6-877c-4aca-ab5a-3f38539ba750 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-008 | Subgrade/Foundation Preparation | SP.1.1 - Underlying lot & ITP signed off and conforming | Not started |  | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-008
cl:e2120dd6-877c-4aca-ab5a-3f38539ba750 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-008 | Subgrade/Foundation Preparation | SP.1.2 - Embankment fill material | Not started | Open | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-008
cl:e2120dd6-877c-4aca-ab5a-3f38539ba750 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-008 | Subgrade/Foundation Preparation | SP.1.3 - Survey Set out | Not started | Open | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-008
cl:e2120dd6-877c-4aca-ab5a-3f38539ba750 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-008 | Subgrade/Foundation Preparation | SP.1.4 - Removal and replacement of unsuitable material | Not started | Open | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-008
cl:e2120dd6-877c-4aca-ab5a-3f38539ba750 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-008 | Subgrade/Foundation Preparation | SP.1.5 - Subgrade/Foundation preparation | Not started | Open | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-008
cl:e2120dd6-877c-4aca-ab5a-3f38539ba750 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-008 | Subgrade/Foundation Preparation | SP.1.6 - Trim subgrade | Not started | Open | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-008
cl:e2120dd6-877c-4aca-ab5a-3f38539ba750 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-008 | Subgrade/Foundation Preparation | SP.1.7 - Proof rolling | Not started | Open | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-008
cl:e2120dd6-877c-4aca-ab5a-3f38539ba750 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-008 | Subgrade/Foundation Preparation | SP.1.8 - Surface level check and survey pick-up | Not started | Open | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-008
cl:e2120dd6-877c-4aca-ab5a-3f38539ba750 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-008 | Subgrade/Foundation Preparation | SP.1.9 - QA close out | Not started | Open | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-008
cl:9e446b56-5b71-414c-b651-c19177db5219 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-009 | Subgrade/Foundation Preparation | SP.1.1 - Underlying lot & ITP signed off and conforming | Not started |  | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-009
cl:9e446b56-5b71-414c-b651-c19177db5219 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-009 | Subgrade/Foundation Preparation | SP.1.2 - Embankment fill material | Not started | Open | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-009
cl:9e446b56-5b71-414c-b651-c19177db5219 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-009 | Subgrade/Foundation Preparation | SP.1.3 - Survey Set out | Not started | Open | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-009
cl:9e446b56-5b71-414c-b651-c19177db5219 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-009 | Subgrade/Foundation Preparation | SP.1.4 - Removal and replacement of unsuitable material | Not started | Open | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-009
cl:9e446b56-5b71-414c-b651-c19177db5219 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-009 | Subgrade/Foundation Preparation | SP.1.5 - Subgrade/Foundation preparation | Not started | Open | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-009
cl:9e446b56-5b71-414c-b651-c19177db5219 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-009 | Subgrade/Foundation Preparation | SP.1.6 - Trim subgrade | Not started | Open | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-009
cl:9e446b56-5b71-414c-b651-c19177db5219 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-009 | Subgrade/Foundation Preparation | SP.1.7 - Proof rolling | Not started | Open | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-009
cl:9e446b56-5b71-414c-b651-c19177db5219 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-009 | Subgrade/Foundation Preparation | SP.1.8 - Surface level check and survey pick-up | Not started | Open | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-009
cl:9e446b56-5b71-414c-b651-c19177db5219 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-009 | Subgrade/Foundation Preparation | SP.1.9 - QA close out | Not started | Open | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-009
cl:0c6af84e-b3e2-4e3d-8a46-279a72951b31 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-010 | Subgrade/Foundation Preparation | SP.1.1 - Underlying lot & ITP signed off and conforming | Not started |  | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-010
cl:0c6af84e-b3e2-4e3d-8a46-279a72951b31 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-010 | Subgrade/Foundation Preparation | SP.1.2 - Embankment fill material | Not started | Open | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-010
cl:0c6af84e-b3e2-4e3d-8a46-279a72951b31 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-010 | Subgrade/Foundation Preparation | SP.1.3 - Survey Set out | Not started | Open | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-010
cl:0c6af84e-b3e2-4e3d-8a46-279a72951b31 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-010 | Subgrade/Foundation Preparation | SP.1.4 - Removal and replacement of unsuitable material | Not started | Open | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-010
cl:0c6af84e-b3e2-4e3d-8a46-279a72951b31 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-010 | Subgrade/Foundation Preparation | SP.1.5 - Subgrade/Foundation preparation | Not started | Open | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-010
cl:0c6af84e-b3e2-4e3d-8a46-279a72951b31 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-010 | Subgrade/Foundation Preparation | SP.1.6 - Trim subgrade | Not started | Open | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-010
cl:0c6af84e-b3e2-4e3d-8a46-279a72951b31 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-010 | Subgrade/Foundation Preparation | SP.1.7 - Proof rolling | Not started | Open | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-010
cl:0c6af84e-b3e2-4e3d-8a46-279a72951b31 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-010 | Subgrade/Foundation Preparation | SP.1.8 - Surface level check and survey pick-up | Not started | Open | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-010
cl:0c6af84e-b3e2-4e3d-8a46-279a72951b31 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-010 | Subgrade/Foundation Preparation | SP.1.9 - QA close out | Not started | Open | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-010
cl:16292971-d3e5-4945-b32c-5b65fd414654 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-011 | Subgrade/Foundation Preparation | SP.1.1 - Underlying lot & ITP signed off and conforming | Not started |  | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-011
cl:16292971-d3e5-4945-b32c-5b65fd414654 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-011 | Subgrade/Foundation Preparation | SP.1.2 - Embankment fill material | Not started | Open | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-011
cl:16292971-d3e5-4945-b32c-5b65fd414654 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-011 | Subgrade/Foundation Preparation | SP.1.3 - Survey Set out | Not started | Open | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-011
cl:16292971-d3e5-4945-b32c-5b65fd414654 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-011 | Subgrade/Foundation Preparation | SP.1.4 - Removal and replacement of unsuitable material | Not started | Open | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-011
cl:16292971-d3e5-4945-b32c-5b65fd414654 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-011 | Subgrade/Foundation Preparation | SP.1.5 - Subgrade/Foundation preparation | Not started | Open | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-011
cl:16292971-d3e5-4945-b32c-5b65fd414654 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-011 | Subgrade/Foundation Preparation | SP.1.6 - Trim subgrade | Not started | Open | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-011
cl:16292971-d3e5-4945-b32c-5b65fd414654 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-011 | Subgrade/Foundation Preparation | SP.1.7 - Proof rolling | Not started | Open | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-011
cl:16292971-d3e5-4945-b32c-5b65fd414654 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-011 | Subgrade/Foundation Preparation | SP.1.8 - Surface level check and survey pick-up | Not started | Open | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-011
cl:16292971-d3e5-4945-b32c-5b65fd414654 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-011 | Subgrade/Foundation Preparation | SP.1.9 - QA close out | Not started | Open | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-011
cl:e7554a30-6ea5-4fa1-b698-ffcee940ce63 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-012 | Subgrade/Foundation Preparation | SP.1.1 - Underlying lot & ITP signed off and conforming | Not started |  | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-012
cl:e7554a30-6ea5-4fa1-b698-ffcee940ce63 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-012 | Subgrade/Foundation Preparation | SP.1.2 - Embankment fill material | Not started | Open | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-012
cl:e7554a30-6ea5-4fa1-b698-ffcee940ce63 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-012 | Subgrade/Foundation Preparation | SP.1.3 - Survey Set out | Not started | Open | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-012
cl:e7554a30-6ea5-4fa1-b698-ffcee940ce63 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-012 | Subgrade/Foundation Preparation | SP.1.4 - Removal and replacement of unsuitable material | Not started | Open | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-012
cl:e7554a30-6ea5-4fa1-b698-ffcee940ce63 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-012 | Subgrade/Foundation Preparation | SP.1.5 - Subgrade/Foundation preparation | Not started | Open | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-012
cl:e7554a30-6ea5-4fa1-b698-ffcee940ce63 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-012 | Subgrade/Foundation Preparation | SP.1.6 - Trim subgrade | Not started | Open | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-012
cl:e7554a30-6ea5-4fa1-b698-ffcee940ce63 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-012 | Subgrade/Foundation Preparation | SP.1.7 - Proof rolling | Not started | Open | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-012
cl:e7554a30-6ea5-4fa1-b698-ffcee940ce63 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-012 | Subgrade/Foundation Preparation | SP.1.8 - Surface level check and survey pick-up | Not started | Open | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-012
cl:e7554a30-6ea5-4fa1-b698-ffcee940ce63 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-012 | Subgrade/Foundation Preparation | SP.1.9 - QA close out | Not started | Open | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-012
cl:12f8a2b1-6bca-4b5a-97fd-c5bfbfceb333 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-013 | Subgrade/Foundation Preparation | SP.1.1 - Underlying lot & ITP signed off and conforming | Not started |  | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-013
cl:12f8a2b1-6bca-4b5a-97fd-c5bfbfceb333 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-013 | Subgrade/Foundation Preparation | SP.1.2 - Embankment fill material | Not started | Open | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-013
cl:12f8a2b1-6bca-4b5a-97fd-c5bfbfceb333 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-013 | Subgrade/Foundation Preparation | SP.1.3 - Survey Set out | Not started | Open | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-013
cl:12f8a2b1-6bca-4b5a-97fd-c5bfbfceb333 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-013 | Subgrade/Foundation Preparation | SP.1.4 - Removal and replacement of unsuitable material | Not started | Open | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-013
cl:12f8a2b1-6bca-4b5a-97fd-c5bfbfceb333 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-013 | Subgrade/Foundation Preparation | SP.1.5 - Subgrade/Foundation preparation | Not started | Open | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-013
cl:12f8a2b1-6bca-4b5a-97fd-c5bfbfceb333 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-013 | Subgrade/Foundation Preparation | SP.1.6 - Trim subgrade | Not started | Open | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-013
cl:12f8a2b1-6bca-4b5a-97fd-c5bfbfceb333 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-013 | Subgrade/Foundation Preparation | SP.1.7 - Proof rolling | Not started | Open | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-013
cl:12f8a2b1-6bca-4b5a-97fd-c5bfbfceb333 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-013 | Subgrade/Foundation Preparation | SP.1.8 - Surface level check and survey pick-up | Not started | Open | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-013
cl:12f8a2b1-6bca-4b5a-97fd-c5bfbfceb333 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-013 | Subgrade/Foundation Preparation | SP.1.9 - QA close out | Not started | Open | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-013
cl:87ce06d5-dab0-4bd6-a3eb-f91859570e1c | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-014 | Subgrade/Foundation Preparation | SP.1.1 - Underlying lot & ITP signed off and conforming | Not started |  | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-014
cl:87ce06d5-dab0-4bd6-a3eb-f91859570e1c | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-014 | Subgrade/Foundation Preparation | SP.1.2 - Embankment fill material | Not started | Open | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-014
cl:87ce06d5-dab0-4bd6-a3eb-f91859570e1c | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-014 | Subgrade/Foundation Preparation | SP.1.3 - Survey Set out | Not started | Open | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-014
cl:87ce06d5-dab0-4bd6-a3eb-f91859570e1c | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-014 | Subgrade/Foundation Preparation | SP.1.4 - Removal and replacement of unsuitable material | Not started | Open | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-014
cl:87ce06d5-dab0-4bd6-a3eb-f91859570e1c | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-014 | Subgrade/Foundation Preparation | SP.1.5 - Subgrade/Foundation preparation | Not started | Open | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-014
cl:87ce06d5-dab0-4bd6-a3eb-f91859570e1c | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-014 | Subgrade/Foundation Preparation | SP.1.6 - Trim subgrade | Not started | Open | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-014
cl:87ce06d5-dab0-4bd6-a3eb-f91859570e1c | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-014 | Subgrade/Foundation Preparation | SP.1.7 - Proof rolling | Not started | Open | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-014
cl:87ce06d5-dab0-4bd6-a3eb-f91859570e1c | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-014 | Subgrade/Foundation Preparation | SP.1.8 - Surface level check and survey pick-up | Not started | Open | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-014
cl:87ce06d5-dab0-4bd6-a3eb-f91859570e1c | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-014 | Subgrade/Foundation Preparation | SP.1.9 - QA close out | Not started | Open | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-014
cl:87a11975-8cc5-4b0b-bf54-fa5714dfd860 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-015 | Subgrade/Foundation Preparation | SP.1.1 - Underlying lot & ITP signed off and conforming | Not started |  | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-015
cl:87a11975-8cc5-4b0b-bf54-fa5714dfd860 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-015 | Subgrade/Foundation Preparation | SP.1.2 - Embankment fill material | Not started | Open | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-015
cl:87a11975-8cc5-4b0b-bf54-fa5714dfd860 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-015 | Subgrade/Foundation Preparation | SP.1.3 - Survey Set out | Not started | Open | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-015
cl:87a11975-8cc5-4b0b-bf54-fa5714dfd860 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-015 | Subgrade/Foundation Preparation | SP.1.4 - Removal and replacement of unsuitable material | Not started | Open | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-015
cl:87a11975-8cc5-4b0b-bf54-fa5714dfd860 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-015 | Subgrade/Foundation Preparation | SP.1.5 - Subgrade/Foundation preparation | Not started | Open | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-015
cl:87a11975-8cc5-4b0b-bf54-fa5714dfd860 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-015 | Subgrade/Foundation Preparation | SP.1.6 - Trim subgrade | Not started | Open | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-015
cl:87a11975-8cc5-4b0b-bf54-fa5714dfd860 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-015 | Subgrade/Foundation Preparation | SP.1.7 - Proof rolling | Not started | Open | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-015
cl:87a11975-8cc5-4b0b-bf54-fa5714dfd860 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-015 | Subgrade/Foundation Preparation | SP.1.8 - Surface level check and survey pick-up | Not started | Open | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-015
cl:87a11975-8cc5-4b0b-bf54-fa5714dfd860 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-015 | Subgrade/Foundation Preparation | SP.1.9 - QA close out | Not started | Open | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-015
cl:f93d9f8c-c94e-4d09-a0e1-8375e5292ea7 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-016 | Subgrade/Foundation Preparation | SP.1.1 - Underlying lot & ITP signed off and conforming | Not started |  | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-016
cl:f93d9f8c-c94e-4d09-a0e1-8375e5292ea7 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-016 | Subgrade/Foundation Preparation | SP.1.2 - Embankment fill material | Not started | Open | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-016
cl:f93d9f8c-c94e-4d09-a0e1-8375e5292ea7 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-016 | Subgrade/Foundation Preparation | SP.1.3 - Survey Set out | Not started | Open | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-016
cl:f93d9f8c-c94e-4d09-a0e1-8375e5292ea7 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-016 | Subgrade/Foundation Preparation | SP.1.4 - Removal and replacement of unsuitable material | Not started | Open | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-016
cl:f93d9f8c-c94e-4d09-a0e1-8375e5292ea7 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-016 | Subgrade/Foundation Preparation | SP.1.5 - Subgrade/Foundation preparation | Not started | Open | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-016
cl:f93d9f8c-c94e-4d09-a0e1-8375e5292ea7 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-016 | Subgrade/Foundation Preparation | SP.1.6 - Trim subgrade | Not started | Open | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-016
cl:f93d9f8c-c94e-4d09-a0e1-8375e5292ea7 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-016 | Subgrade/Foundation Preparation | SP.1.7 - Proof rolling | Not started | Open | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-016
cl:f93d9f8c-c94e-4d09-a0e1-8375e5292ea7 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-016 | Subgrade/Foundation Preparation | SP.1.8 - Surface level check and survey pick-up | Not started | Open | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-016
cl:f93d9f8c-c94e-4d09-a0e1-8375e5292ea7 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-016 | Subgrade/Foundation Preparation | SP.1.9 - QA close out | Not started | Open | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-016
cl:0a32f121-dd2d-4b60-8836-1f780e04db42 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-017 | Subgrade/Foundation Preparation | SP.1.1 - Underlying lot & ITP signed off and conforming | Not started |  | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-017
cl:0a32f121-dd2d-4b60-8836-1f780e04db42 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-017 | Subgrade/Foundation Preparation | SP.1.2 - Embankment fill material | Not started | Open | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-017
cl:0a32f121-dd2d-4b60-8836-1f780e04db42 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-017 | Subgrade/Foundation Preparation | SP.1.3 - Survey Set out | Not started | Open | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-017
cl:0a32f121-dd2d-4b60-8836-1f780e04db42 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-017 | Subgrade/Foundation Preparation | SP.1.4 - Removal and replacement of unsuitable material | Not started | Open | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-017
cl:0a32f121-dd2d-4b60-8836-1f780e04db42 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-017 | Subgrade/Foundation Preparation | SP.1.5 - Subgrade/Foundation preparation | Not started | Open | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-017
cl:0a32f121-dd2d-4b60-8836-1f780e04db42 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-017 | Subgrade/Foundation Preparation | SP.1.6 - Trim subgrade | Not started | Open | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-017
cl:0a32f121-dd2d-4b60-8836-1f780e04db42 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-017 | Subgrade/Foundation Preparation | SP.1.7 - Proof rolling | Not started | Open | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-017
cl:0a32f121-dd2d-4b60-8836-1f780e04db42 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-017 | Subgrade/Foundation Preparation | SP.1.8 - Surface level check and survey pick-up | Not started | Open | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-017
cl:0a32f121-dd2d-4b60-8836-1f780e04db42 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-017 | Subgrade/Foundation Preparation | SP.1.9 - QA close out | Not started | Open | ITP-003 Subgrade/Foundation Preparation | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-017
cl:eb4aa3a2-74b6-428c-9b75-1400a2dcc6c5 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-001 | 1.0 Pre-Construction | RCP1.1 - Drawings supplied most current IFC | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-001
cl:eb4aa3a2-74b6-428c-9b75-1400a2dcc6c5 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-001 | 1.0 Pre-Construction | RCP1.2 - Define RCP ID | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-001
cl:eb4aa3a2-74b6-428c-9b75-1400a2dcc6c5 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-001 | 1.0 Pre-Construction | RCP1.3 - Lot Register/ WBS submitted and approved | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-001
cl:eb4aa3a2-74b6-428c-9b75-1400a2dcc6c5 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-001 | 1.0 Pre-Construction | RCP1.4 - Underlying lot & ITP signed off and conforming | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-001
cl:eb4aa3a2-74b6-428c-9b75-1400a2dcc6c5 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-001 | 1.0 Pre-Construction | RCP1.5 - Certificate of compliance for RCP Material | N/A | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-001
cl:eb4aa3a2-74b6-428c-9b75-1400a2dcc6c5 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-001 | 1.0 Pre-Construction | RCP1.6 - Inspect reinforced pipe culverts for damage | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-001
cl:eb4aa3a2-74b6-428c-9b75-1400a2dcc6c5 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-001 | 2.0 Construction | RCP2.7 - Trench Excavation | In progress | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-001
cl:eb4aa3a2-74b6-428c-9b75-1400a2dcc6c5 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-001 | 2.0 Construction | RCP2.8 - Bedding | In progress | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-001
cl:eb4aa3a2-74b6-428c-9b75-1400a2dcc6c5 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-001 | 2.0 Construction | RCP2.9 - RCP Installation | In progress | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-001
cl:eb4aa3a2-74b6-428c-9b75-1400a2dcc6c5 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-001 | 2.0 Construction | RCP2.10 - Backfilling of culvert | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-001
cl:eb4aa3a2-74b6-428c-9b75-1400a2dcc6c5 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-001 | 2.0 Construction | RCP2.11 - End Treatment – Headwall & Wingwalls (Reinforcement) | In progress | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-001
cl:eb4aa3a2-74b6-428c-9b75-1400a2dcc6c5 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-001 | 2.0 Construction | RCP2.12 - End Treatment – Headwall & Wingwalls (Formwork) | N/A | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-001
cl:eb4aa3a2-74b6-428c-9b75-1400a2dcc6c5 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-001 | 2.0 Construction | RCP2.13 - End Treatment – Headwall & Wingwalls (Concrete) | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-001
cl:eb4aa3a2-74b6-428c-9b75-1400a2dcc6c5 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-001 | 2.0 Construction | RCP2.14 - Rock Protection | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-001
cl:eb4aa3a2-74b6-428c-9b75-1400a2dcc6c5 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-001 | 3.0 Post Construction | RCP3.15 - Works completed and update ITP/ Lot Register/ MDR and close out of GDP | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-001
cl:72b6fca6-3997-40a7-ad4f-c5f8f57abcac | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-002 | 1.0 Pre-Construction | RCP1.1 - Drawings supplied most current IFC | N/A | Approved | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-002
cl:72b6fca6-3997-40a7-ad4f-c5f8f57abcac | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-002 | 1.0 Pre-Construction | RCP1.2 - Define RCP ID | N/A | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-002
cl:72b6fca6-3997-40a7-ad4f-c5f8f57abcac | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-002 | 1.0 Pre-Construction | RCP1.3 - Lot Register/ WBS submitted and approved | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-002
cl:72b6fca6-3997-40a7-ad4f-c5f8f57abcac | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-002 | 1.0 Pre-Construction | RCP1.4 - Underlying lot & ITP signed off and conforming | In progress | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-002
cl:72b6fca6-3997-40a7-ad4f-c5f8f57abcac | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-002 | 1.0 Pre-Construction | RCP1.5 - Certificate of compliance for RCP Material | N/A | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-002
cl:72b6fca6-3997-40a7-ad4f-c5f8f57abcac | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-002 | 1.0 Pre-Construction | RCP1.6 - Inspect reinforced pipe culverts for damage | N/A | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-002
cl:72b6fca6-3997-40a7-ad4f-c5f8f57abcac | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-002 | 2.0 Construction | RCP2.7 - Trench Excavation | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-002
cl:72b6fca6-3997-40a7-ad4f-c5f8f57abcac | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-002 | 2.0 Construction | RCP2.8 - Bedding | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-002
cl:72b6fca6-3997-40a7-ad4f-c5f8f57abcac | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-002 | 2.0 Construction | RCP2.9 - RCP Installation | In progress | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-002
cl:72b6fca6-3997-40a7-ad4f-c5f8f57abcac | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-002 | 2.0 Construction | RCP2.10 - Backfilling of culvert | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-002
cl:72b6fca6-3997-40a7-ad4f-c5f8f57abcac | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-002 | 2.0 Construction | RCP2.11 - End Treatment – Headwall & Wingwalls (Reinforcement) | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-002
cl:72b6fca6-3997-40a7-ad4f-c5f8f57abcac | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-002 | 2.0 Construction | RCP2.12 - End Treatment – Headwall & Wingwalls (Formwork) | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-002
cl:72b6fca6-3997-40a7-ad4f-c5f8f57abcac | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-002 | 2.0 Construction | RCP2.13 - End Treatment – Headwall & Wingwalls (Concrete) | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-002
cl:72b6fca6-3997-40a7-ad4f-c5f8f57abcac | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-002 | 2.0 Construction | RCP2.14 - Rock Protection | In progress | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-002
cl:72b6fca6-3997-40a7-ad4f-c5f8f57abcac | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-002 | 3.0 Post Construction | RCP3.15 - Works completed and update ITP/ Lot Register/ MDR and close out of GDP | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-002
cl:ef0d1275-885b-4ee9-b427-9f5bbda141ad | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-003 | 1.0 Pre-Construction | RCP1.1 - Drawings supplied most current IFC | Passed | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-003
cl:ef0d1275-885b-4ee9-b427-9f5bbda141ad | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-003 | 1.0 Pre-Construction | RCP1.2 - Define RCP ID | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-003
cl:ef0d1275-885b-4ee9-b427-9f5bbda141ad | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-003 | 1.0 Pre-Construction | RCP1.3 - Lot Register/ WBS submitted and approved | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-003
cl:ef0d1275-885b-4ee9-b427-9f5bbda141ad | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-003 | 1.0 Pre-Construction | RCP1.4 - Underlying lot & ITP signed off and conforming | N/A | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-003
cl:ef0d1275-885b-4ee9-b427-9f5bbda141ad | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-003 | 1.0 Pre-Construction | RCP1.5 - Certificate of compliance for RCP Material | Passed | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-003
cl:ef0d1275-885b-4ee9-b427-9f5bbda141ad | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-003 | 1.0 Pre-Construction | RCP1.6 - Inspect reinforced pipe culverts for damage | Passed | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-003
cl:ef0d1275-885b-4ee9-b427-9f5bbda141ad | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-003 | 2.0 Construction | RCP2.7 - Trench Excavation | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-003
cl:ef0d1275-885b-4ee9-b427-9f5bbda141ad | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-003 | 2.0 Construction | RCP2.8 - Bedding | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-003
cl:ef0d1275-885b-4ee9-b427-9f5bbda141ad | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-003 | 2.0 Construction | RCP2.9 - RCP Installation | In progress | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-003
cl:ef0d1275-885b-4ee9-b427-9f5bbda141ad | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-003 | 2.0 Construction | RCP2.10 - Backfilling of culvert | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-003
cl:ef0d1275-885b-4ee9-b427-9f5bbda141ad | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-003 | 2.0 Construction | RCP2.11 - End Treatment – Headwall & Wingwalls (Reinforcement) | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-003
cl:ef0d1275-885b-4ee9-b427-9f5bbda141ad | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-003 | 2.0 Construction | RCP2.12 - End Treatment – Headwall & Wingwalls (Formwork) | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-003
cl:ef0d1275-885b-4ee9-b427-9f5bbda141ad | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-003 | 2.0 Construction | RCP2.13 - End Treatment – Headwall & Wingwalls (Concrete) | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-003
cl:ef0d1275-885b-4ee9-b427-9f5bbda141ad | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-003 | 2.0 Construction | RCP2.14 - Rock Protection | Passed | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-003
cl:ef0d1275-885b-4ee9-b427-9f5bbda141ad | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-003 | 3.0 Post Construction | RCP3.15 - Works completed and update ITP/ Lot Register/ MDR and close out of GDP | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-003
cl:a1582baf-1390-4cee-8145-7bd0946116f2 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-004 | 1.0 Pre-Construction | RCP1.1 - Drawings supplied most current IFC | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-004
cl:a1582baf-1390-4cee-8145-7bd0946116f2 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-004 | 1.0 Pre-Construction | RCP1.2 - Define RCP ID | Passed | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-004
cl:a1582baf-1390-4cee-8145-7bd0946116f2 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-004 | 1.0 Pre-Construction | RCP1.3 - Lot Register/ WBS submitted and approved | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-004
cl:a1582baf-1390-4cee-8145-7bd0946116f2 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-004 | 1.0 Pre-Construction | RCP1.4 - Underlying lot & ITP signed off and conforming | Passed | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-004
cl:a1582baf-1390-4cee-8145-7bd0946116f2 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-004 | 1.0 Pre-Construction | RCP1.5 - Certificate of compliance for RCP Material | Passed | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-004
cl:a1582baf-1390-4cee-8145-7bd0946116f2 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-004 | 1.0 Pre-Construction | RCP1.6 - Inspect reinforced pipe culverts for damage | Passed | Approved | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-004
cl:a1582baf-1390-4cee-8145-7bd0946116f2 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-004 | 2.0 Construction | RCP2.7 - Trench Excavation | In progress | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-004
cl:a1582baf-1390-4cee-8145-7bd0946116f2 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-004 | 2.0 Construction | RCP2.8 - Bedding | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-004
cl:a1582baf-1390-4cee-8145-7bd0946116f2 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-004 | 2.0 Construction | RCP2.9 - RCP Installation | In progress | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-004
cl:a1582baf-1390-4cee-8145-7bd0946116f2 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-004 | 2.0 Construction | RCP2.10 - Backfilling of culvert | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-004
cl:a1582baf-1390-4cee-8145-7bd0946116f2 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-004 | 2.0 Construction | RCP2.11 - End Treatment – Headwall & Wingwalls (Reinforcement) | Passed | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-004
cl:a1582baf-1390-4cee-8145-7bd0946116f2 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-004 | 2.0 Construction | RCP2.12 - End Treatment – Headwall & Wingwalls (Formwork) | N/A | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-004
cl:a1582baf-1390-4cee-8145-7bd0946116f2 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-004 | 2.0 Construction | RCP2.13 - End Treatment – Headwall & Wingwalls (Concrete) | N/A | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-004
cl:a1582baf-1390-4cee-8145-7bd0946116f2 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-004 | 2.0 Construction | RCP2.14 - Rock Protection | In progress | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-004
cl:a1582baf-1390-4cee-8145-7bd0946116f2 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-004 | 3.0 Post Construction | RCP3.15 - Works completed and update ITP/ Lot Register/ MDR and close out of GDP | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-004
cl:56672165-5146-4425-9bd6-510c095ba0d3 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-005_1415 | 1.0 Pre-Construction | RCP1.1 - Drawings supplied most current IFC | Passed | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-005_1415
cl:56672165-5146-4425-9bd6-510c095ba0d3 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-005_1415 | 1.0 Pre-Construction | RCP1.2 - Define RCP ID | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-005_1415
cl:56672165-5146-4425-9bd6-510c095ba0d3 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-005_1415 | 1.0 Pre-Construction | RCP1.3 - Lot Register/ WBS submitted and approved | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-005_1415
cl:56672165-5146-4425-9bd6-510c095ba0d3 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-005_1415 | 1.0 Pre-Construction | RCP1.4 - Underlying lot & ITP signed off and conforming | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-005_1415
cl:56672165-5146-4425-9bd6-510c095ba0d3 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-005_1415 | 1.0 Pre-Construction | RCP1.5 - Certificate of compliance for RCP Material | Passed | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-005_1415
cl:56672165-5146-4425-9bd6-510c095ba0d3 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-005_1415 | 1.0 Pre-Construction | RCP1.6 - Inspect reinforced pipe culverts for damage | Passed | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-005_1415
cl:56672165-5146-4425-9bd6-510c095ba0d3 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-005_1415 | 2.0 Construction | RCP2.7 - Trench Excavation | In progress | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-005_1415
cl:56672165-5146-4425-9bd6-510c095ba0d3 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-005_1415 | 2.0 Construction | RCP2.8 - Bedding | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-005_1415
cl:56672165-5146-4425-9bd6-510c095ba0d3 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-005_1415 | 2.0 Construction | RCP2.9 - RCP Installation | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-005_1415
cl:56672165-5146-4425-9bd6-510c095ba0d3 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-005_1415 | 2.0 Construction | RCP2.10 - Backfilling of culvert | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-005_1415
cl:56672165-5146-4425-9bd6-510c095ba0d3 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-005_1415 | 2.0 Construction | RCP2.11 - End Treatment – Headwall & Wingwalls (Reinforcement) | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-005_1415
cl:56672165-5146-4425-9bd6-510c095ba0d3 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-005_1415 | 2.0 Construction | RCP2.12 - End Treatment – Headwall & Wingwalls (Formwork) | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-005_1415
cl:56672165-5146-4425-9bd6-510c095ba0d3 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-005_1415 | 2.0 Construction | RCP2.13 - End Treatment – Headwall & Wingwalls (Concrete) | N/A | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-005_1415
cl:56672165-5146-4425-9bd6-510c095ba0d3 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-005_1415 | 2.0 Construction | RCP2.14 - Rock Protection | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-005_1415
cl:56672165-5146-4425-9bd6-510c095ba0d3 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-005_1415 | 3.0 Post Construction | RCP3.15 - Works completed and update ITP/ Lot Register/ MDR and close out of GDP | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-005_1415
cl:e0b7a3cf-bb64-4ec4-8455-5da0e1444bdc | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-006_CH1564 | 1.0 Pre-Construction | RCP1.1 - Drawings supplied most current IFC | Passed | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-006_CH1564
cl:e0b7a3cf-bb64-4ec4-8455-5da0e1444bdc | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-006_CH1564 | 1.0 Pre-Construction | RCP1.2 - Define RCP ID | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-006_CH1564
cl:e0b7a3cf-bb64-4ec4-8455-5da0e1444bdc | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-006_CH1564 | 1.0 Pre-Construction | RCP1.3 - Lot Register/ WBS submitted and approved | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-006_CH1564
cl:e0b7a3cf-bb64-4ec4-8455-5da0e1444bdc | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-006_CH1564 | 1.0 Pre-Construction | RCP1.4 - Underlying lot & ITP signed off and conforming | N/A | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-006_CH1564
cl:e0b7a3cf-bb64-4ec4-8455-5da0e1444bdc | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-006_CH1564 | 1.0 Pre-Construction | RCP1.5 - Certificate of compliance for RCP Material | Passed | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-006_CH1564
cl:e0b7a3cf-bb64-4ec4-8455-5da0e1444bdc | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-006_CH1564 | 1.0 Pre-Construction | RCP1.6 - Inspect reinforced pipe culverts for damage | Passed | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-006_CH1564
cl:e0b7a3cf-bb64-4ec4-8455-5da0e1444bdc | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-006_CH1564 | 2.0 Construction | RCP2.7 - Trench Excavation | Passed | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-006_CH1564
cl:e0b7a3cf-bb64-4ec4-8455-5da0e1444bdc | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-006_CH1564 | 2.0 Construction | RCP2.8 - Bedding | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-006_CH1564
cl:e0b7a3cf-bb64-4ec4-8455-5da0e1444bdc | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-006_CH1564 | 2.0 Construction | RCP2.9 - RCP Installation | In progress | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-006_CH1564
cl:e0b7a3cf-bb64-4ec4-8455-5da0e1444bdc | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-006_CH1564 | 2.0 Construction | RCP2.10 - Backfilling of culvert | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-006_CH1564
cl:e0b7a3cf-bb64-4ec4-8455-5da0e1444bdc | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-006_CH1564 | 2.0 Construction | RCP2.11 - End Treatment – Headwall & Wingwalls (Reinforcement) | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-006_CH1564
cl:e0b7a3cf-bb64-4ec4-8455-5da0e1444bdc | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-006_CH1564 | 2.0 Construction | RCP2.12 - End Treatment – Headwall & Wingwalls (Formwork) | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-006_CH1564
cl:e0b7a3cf-bb64-4ec4-8455-5da0e1444bdc | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-006_CH1564 | 2.0 Construction | RCP2.13 - End Treatment – Headwall & Wingwalls (Concrete) | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-006_CH1564
cl:e0b7a3cf-bb64-4ec4-8455-5da0e1444bdc | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-006_CH1564 | 2.0 Construction | RCP2.14 - Rock Protection | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-006_CH1564
cl:e0b7a3cf-bb64-4ec4-8455-5da0e1444bdc | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-006_CH1564 | 3.0 Post Construction | RCP3.15 - Works completed and update ITP/ Lot Register/ MDR and close out of GDP | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-006_CH1564
cl:54aef0c1-90a6-42ab-b32f-50385b4126e4 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-007_2355 | 1.0 Pre-Construction | RCP1.1 - Drawings supplied most current IFC | Passed | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-007_2355
cl:54aef0c1-90a6-42ab-b32f-50385b4126e4 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-007_2355 | 1.0 Pre-Construction | RCP1.2 - Define RCP ID | Passed | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-007_2355
cl:54aef0c1-90a6-42ab-b32f-50385b4126e4 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-007_2355 | 1.0 Pre-Construction | RCP1.3 - Lot Register/ WBS submitted and approved | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-007_2355
cl:54aef0c1-90a6-42ab-b32f-50385b4126e4 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-007_2355 | 1.0 Pre-Construction | RCP1.4 - Underlying lot & ITP signed off and conforming | N/A | Approved | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-007_2355
cl:54aef0c1-90a6-42ab-b32f-50385b4126e4 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-007_2355 | 1.0 Pre-Construction | RCP1.5 - Certificate of compliance for RCP Material | In progress | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-007_2355
cl:54aef0c1-90a6-42ab-b32f-50385b4126e4 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-007_2355 | 1.0 Pre-Construction | RCP1.6 - Inspect reinforced pipe culverts for damage | Passed | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-007_2355
cl:54aef0c1-90a6-42ab-b32f-50385b4126e4 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-007_2355 | 2.0 Construction | RCP2.7 - Trench Excavation | Passed | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-007_2355
cl:54aef0c1-90a6-42ab-b32f-50385b4126e4 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-007_2355 | 2.0 Construction | RCP2.8 - Bedding | Passed | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-007_2355
cl:54aef0c1-90a6-42ab-b32f-50385b4126e4 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-007_2355 | 2.0 Construction | RCP2.9 - RCP Installation | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-007_2355
cl:54aef0c1-90a6-42ab-b32f-50385b4126e4 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-007_2355 | 2.0 Construction | RCP2.10 - Backfilling of culvert | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-007_2355
cl:54aef0c1-90a6-42ab-b32f-50385b4126e4 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-007_2355 | 2.0 Construction | RCP2.11 - End Treatment – Headwall & Wingwalls (Reinforcement) | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-007_2355
cl:54aef0c1-90a6-42ab-b32f-50385b4126e4 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-007_2355 | 2.0 Construction | RCP2.12 - End Treatment – Headwall & Wingwalls (Formwork) | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-007_2355
cl:54aef0c1-90a6-42ab-b32f-50385b4126e4 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-007_2355 | 2.0 Construction | RCP2.13 - End Treatment – Headwall & Wingwalls (Concrete) | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-007_2355
cl:54aef0c1-90a6-42ab-b32f-50385b4126e4 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-007_2355 | 2.0 Construction | RCP2.14 - Rock Protection | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-007_2355
cl:54aef0c1-90a6-42ab-b32f-50385b4126e4 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-007_2355 | 3.0 Post Construction | RCP3.15 - Works completed and update ITP/ Lot Register/ MDR and close out of GDP | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-007_2355
cl:334a960a-bfaf-4175-a384-024b6765292d | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-008_CH2385 | 1.0 Pre-Construction | RCP1.1 - Drawings supplied most current IFC | Passed | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-008_CH2385
cl:334a960a-bfaf-4175-a384-024b6765292d | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-008_CH2385 | 1.0 Pre-Construction | RCP1.2 - Define RCP ID | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-008_CH2385
cl:334a960a-bfaf-4175-a384-024b6765292d | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-008_CH2385 | 1.0 Pre-Construction | RCP1.3 - Lot Register/ WBS submitted and approved | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-008_CH2385
cl:334a960a-bfaf-4175-a384-024b6765292d | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-008_CH2385 | 1.0 Pre-Construction | RCP1.4 - Underlying lot & ITP signed off and conforming | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-008_CH2385
cl:334a960a-bfaf-4175-a384-024b6765292d | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-008_CH2385 | 1.0 Pre-Construction | RCP1.5 - Certificate of compliance for RCP Material | In progress | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-008_CH2385
cl:334a960a-bfaf-4175-a384-024b6765292d | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-008_CH2385 | 1.0 Pre-Construction | RCP1.6 - Inspect reinforced pipe culverts for damage | Passed | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-008_CH2385
cl:334a960a-bfaf-4175-a384-024b6765292d | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-008_CH2385 | 2.0 Construction | RCP2.7 - Trench Excavation | In progress | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-008_CH2385
cl:334a960a-bfaf-4175-a384-024b6765292d | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-008_CH2385 | 2.0 Construction | RCP2.8 - Bedding | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-008_CH2385
cl:334a960a-bfaf-4175-a384-024b6765292d | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-008_CH2385 | 2.0 Construction | RCP2.9 - RCP Installation | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-008_CH2385
cl:334a960a-bfaf-4175-a384-024b6765292d | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-008_CH2385 | 2.0 Construction | RCP2.10 - Backfilling of culvert | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-008_CH2385
cl:334a960a-bfaf-4175-a384-024b6765292d | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-008_CH2385 | 2.0 Construction | RCP2.11 - End Treatment – Headwall & Wingwalls (Reinforcement) | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-008_CH2385
cl:334a960a-bfaf-4175-a384-024b6765292d | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-008_CH2385 | 2.0 Construction | RCP2.12 - End Treatment – Headwall & Wingwalls (Formwork) | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-008_CH2385
cl:334a960a-bfaf-4175-a384-024b6765292d | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-008_CH2385 | 2.0 Construction | RCP2.13 - End Treatment – Headwall & Wingwalls (Concrete) | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-008_CH2385
cl:334a960a-bfaf-4175-a384-024b6765292d | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-008_CH2385 | 2.0 Construction | RCP2.14 - Rock Protection | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-008_CH2385
cl:334a960a-bfaf-4175-a384-024b6765292d | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-008_CH2385 | 3.0 Post Construction | RCP3.15 - Works completed and update ITP/ Lot Register/ MDR and close out of GDP | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-008_CH2385
cl:ef206ea2-e824-42ff-9ec1-9cbca5556483 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-009_2715 | 1.0 Pre-Construction | RCP1.1 - Drawings supplied most current IFC | In progress | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-009_2715
cl:ef206ea2-e824-42ff-9ec1-9cbca5556483 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-009_2715 | 1.0 Pre-Construction | RCP1.2 - Define RCP ID | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-009_2715
cl:ef206ea2-e824-42ff-9ec1-9cbca5556483 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-009_2715 | 1.0 Pre-Construction | RCP1.3 - Lot Register/ WBS submitted and approved | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-009_2715
cl:ef206ea2-e824-42ff-9ec1-9cbca5556483 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-009_2715 | 1.0 Pre-Construction | RCP1.4 - Underlying lot & ITP signed off and conforming | N/A | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-009_2715
cl:ef206ea2-e824-42ff-9ec1-9cbca5556483 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-009_2715 | 1.0 Pre-Construction | RCP1.5 - Certificate of compliance for RCP Material | In progress | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-009_2715
cl:ef206ea2-e824-42ff-9ec1-9cbca5556483 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-009_2715 | 1.0 Pre-Construction | RCP1.6 - Inspect reinforced pipe culverts for damage | Passed | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-009_2715
cl:ef206ea2-e824-42ff-9ec1-9cbca5556483 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-009_2715 | 2.0 Construction | RCP2.7 - Trench Excavation | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-009_2715
cl:ef206ea2-e824-42ff-9ec1-9cbca5556483 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-009_2715 | 2.0 Construction | RCP2.8 - Bedding | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-009_2715
cl:ef206ea2-e824-42ff-9ec1-9cbca5556483 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-009_2715 | 2.0 Construction | RCP2.9 - RCP Installation | In progress | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-009_2715
cl:ef206ea2-e824-42ff-9ec1-9cbca5556483 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-009_2715 | 2.0 Construction | RCP2.10 - Backfilling of culvert | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-009_2715
cl:ef206ea2-e824-42ff-9ec1-9cbca5556483 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-009_2715 | 2.0 Construction | RCP2.11 - End Treatment – Headwall & Wingwalls (Reinforcement) | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-009_2715
cl:ef206ea2-e824-42ff-9ec1-9cbca5556483 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-009_2715 | 2.0 Construction | RCP2.12 - End Treatment – Headwall & Wingwalls (Formwork) | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-009_2715
cl:ef206ea2-e824-42ff-9ec1-9cbca5556483 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-009_2715 | 2.0 Construction | RCP2.13 - End Treatment – Headwall & Wingwalls (Concrete) | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-009_2715
cl:ef206ea2-e824-42ff-9ec1-9cbca5556483 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-009_2715 | 2.0 Construction | RCP2.14 - Rock Protection | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-009_2715
cl:ef206ea2-e824-42ff-9ec1-9cbca5556483 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-009_2715 | 3.0 Post Construction | RCP3.15 - Works completed and update ITP/ Lot Register/ MDR and close out of GDP | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-009_2715
cl:d7fe2708-d0db-468e-8422-c639bfc5cca0 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-010 | 1.0 Pre-Construction | RCP1.1 - Drawings supplied most current IFC | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-010
cl:d7fe2708-d0db-468e-8422-c639bfc5cca0 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-010 | 1.0 Pre-Construction | RCP1.2 - Define RCP ID | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-010
cl:d7fe2708-d0db-468e-8422-c639bfc5cca0 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-010 | 1.0 Pre-Construction | RCP1.3 - Lot Register/ WBS submitted and approved | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-010
cl:d7fe2708-d0db-468e-8422-c639bfc5cca0 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-010 | 1.0 Pre-Construction | RCP1.4 - Underlying lot & ITP signed off and conforming | N/A | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-010
cl:d7fe2708-d0db-468e-8422-c639bfc5cca0 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-010 | 1.0 Pre-Construction | RCP1.5 - Certificate of compliance for RCP Material | In progress | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-010
cl:d7fe2708-d0db-468e-8422-c639bfc5cca0 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-010 | 1.0 Pre-Construction | RCP1.6 - Inspect reinforced pipe culverts for damage | Passed | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-010
cl:d7fe2708-d0db-468e-8422-c639bfc5cca0 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-010 | 2.0 Construction | RCP2.7 - Trench Excavation | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-010
cl:d7fe2708-d0db-468e-8422-c639bfc5cca0 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-010 | 2.0 Construction | RCP2.8 - Bedding | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-010
cl:d7fe2708-d0db-468e-8422-c639bfc5cca0 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-010 | 2.0 Construction | RCP2.9 - RCP Installation | In progress | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-010
cl:d7fe2708-d0db-468e-8422-c639bfc5cca0 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-010 | 2.0 Construction | RCP2.10 - Backfilling of culvert | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-010
cl:d7fe2708-d0db-468e-8422-c639bfc5cca0 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-010 | 2.0 Construction | RCP2.11 - End Treatment – Headwall & Wingwalls (Reinforcement) | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-010
cl:d7fe2708-d0db-468e-8422-c639bfc5cca0 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-010 | 2.0 Construction | RCP2.12 - End Treatment – Headwall & Wingwalls (Formwork) | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-010
cl:d7fe2708-d0db-468e-8422-c639bfc5cca0 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-010 | 2.0 Construction | RCP2.13 - End Treatment – Headwall & Wingwalls (Concrete) | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-010
cl:d7fe2708-d0db-468e-8422-c639bfc5cca0 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-010 | 2.0 Construction | RCP2.14 - Rock Protection | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-010
cl:d7fe2708-d0db-468e-8422-c639bfc5cca0 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-010 | 3.0 Post Construction | RCP3.15 - Works completed and update ITP/ Lot Register/ MDR and close out of GDP | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-010
cl:8584bee6-a760-4608-9e42-1727da0b9fed | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-011 | 1.0 Pre-Construction | RCP1.1 - Drawings supplied most current IFC | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-011
cl:8584bee6-a760-4608-9e42-1727da0b9fed | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-011 | 1.0 Pre-Construction | RCP1.2 - Define RCP ID | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-011
cl:8584bee6-a760-4608-9e42-1727da0b9fed | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-011 | 1.0 Pre-Construction | RCP1.3 - Lot Register/ WBS submitted and approved | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-011
cl:8584bee6-a760-4608-9e42-1727da0b9fed | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-011 | 1.0 Pre-Construction | RCP1.4 - Underlying lot & ITP signed off and conforming | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-011
cl:8584bee6-a760-4608-9e42-1727da0b9fed | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-011 | 1.0 Pre-Construction | RCP1.5 - Certificate of compliance for RCP Material | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-011
cl:8584bee6-a760-4608-9e42-1727da0b9fed | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-011 | 1.0 Pre-Construction | RCP1.6 - Inspect reinforced pipe culverts for damage | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-011
cl:8584bee6-a760-4608-9e42-1727da0b9fed | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-011 | 2.0 Construction | RCP2.7 - Trench Excavation | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-011
cl:8584bee6-a760-4608-9e42-1727da0b9fed | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-011 | 2.0 Construction | RCP2.8 - Bedding | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-011
cl:8584bee6-a760-4608-9e42-1727da0b9fed | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-011 | 2.0 Construction | RCP2.9 - RCP Installation | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-011
cl:8584bee6-a760-4608-9e42-1727da0b9fed | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-011 | 2.0 Construction | RCP2.10 - Backfilling of culvert | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-011
cl:8584bee6-a760-4608-9e42-1727da0b9fed | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-011 | 2.0 Construction | RCP2.11 - End Treatment – Headwall & Wingwalls (Reinforcement) | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-011
cl:8584bee6-a760-4608-9e42-1727da0b9fed | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-011 | 2.0 Construction | RCP2.12 - End Treatment – Headwall & Wingwalls (Formwork) | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-011
cl:8584bee6-a760-4608-9e42-1727da0b9fed | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-011 | 2.0 Construction | RCP2.13 - End Treatment – Headwall & Wingwalls (Concrete) | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-011
cl:8584bee6-a760-4608-9e42-1727da0b9fed | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-011 | 2.0 Construction | RCP2.14 - Rock Protection | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-011
cl:8584bee6-a760-4608-9e42-1727da0b9fed | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-011 | 3.0 Post Construction | RCP3.15 - Works completed and update ITP/ Lot Register/ MDR and close out of GDP | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-011
cl:9dbc8f4c-c2f4-4fe6-9994-249789a85e2f | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-012 | 1.0 Pre-Construction | RCP1.1 - Drawings supplied most current IFC | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-012
cl:9dbc8f4c-c2f4-4fe6-9994-249789a85e2f | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-012 | 1.0 Pre-Construction | RCP1.2 - Define RCP ID | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-012
cl:9dbc8f4c-c2f4-4fe6-9994-249789a85e2f | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-012 | 1.0 Pre-Construction | RCP1.3 - Lot Register/ WBS submitted and approved | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-012
cl:9dbc8f4c-c2f4-4fe6-9994-249789a85e2f | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-012 | 1.0 Pre-Construction | RCP1.4 - Underlying lot & ITP signed off and conforming | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-012
cl:9dbc8f4c-c2f4-4fe6-9994-249789a85e2f | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-012 | 1.0 Pre-Construction | RCP1.5 - Certificate of compliance for RCP Material | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-012
cl:9dbc8f4c-c2f4-4fe6-9994-249789a85e2f | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-012 | 1.0 Pre-Construction | RCP1.6 - Inspect reinforced pipe culverts for damage | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-012
cl:9dbc8f4c-c2f4-4fe6-9994-249789a85e2f | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-012 | 2.0 Construction | RCP2.7 - Trench Excavation | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-012
cl:9dbc8f4c-c2f4-4fe6-9994-249789a85e2f | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-012 | 2.0 Construction | RCP2.8 - Bedding | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-012
cl:9dbc8f4c-c2f4-4fe6-9994-249789a85e2f | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-012 | 2.0 Construction | RCP2.9 - RCP Installation | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-012
cl:9dbc8f4c-c2f4-4fe6-9994-249789a85e2f | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-012 | 2.0 Construction | RCP2.10 - Backfilling of culvert | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-012
cl:9dbc8f4c-c2f4-4fe6-9994-249789a85e2f | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-012 | 2.0 Construction | RCP2.11 - End Treatment – Headwall & Wingwalls (Reinforcement) | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-012
cl:9dbc8f4c-c2f4-4fe6-9994-249789a85e2f | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-012 | 2.0 Construction | RCP2.12 - End Treatment – Headwall & Wingwalls (Formwork) | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-012
cl:9dbc8f4c-c2f4-4fe6-9994-249789a85e2f | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-012 | 2.0 Construction | RCP2.13 - End Treatment – Headwall & Wingwalls (Concrete) | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-012
cl:9dbc8f4c-c2f4-4fe6-9994-249789a85e2f | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-012 | 2.0 Construction | RCP2.14 - Rock Protection | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-012
cl:9dbc8f4c-c2f4-4fe6-9994-249789a85e2f | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-012 | 3.0 Post Construction | RCP3.15 - Works completed and update ITP/ Lot Register/ MDR and close out of GDP | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-012
cl:2717c2dd-f499-4b9b-a7d1-e4e58773c9b5 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-013 | 1.0 Pre-Construction | RCP1.1 - Drawings supplied most current IFC | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-013
cl:2717c2dd-f499-4b9b-a7d1-e4e58773c9b5 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-013 | 1.0 Pre-Construction | RCP1.2 - Define RCP ID | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-013
cl:2717c2dd-f499-4b9b-a7d1-e4e58773c9b5 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-013 | 1.0 Pre-Construction | RCP1.3 - Lot Register/ WBS submitted and approved | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-013
cl:2717c2dd-f499-4b9b-a7d1-e4e58773c9b5 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-013 | 1.0 Pre-Construction | RCP1.4 - Underlying lot & ITP signed off and conforming | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-013
cl:2717c2dd-f499-4b9b-a7d1-e4e58773c9b5 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-013 | 1.0 Pre-Construction | RCP1.5 - Certificate of compliance for RCP Material | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-013
cl:2717c2dd-f499-4b9b-a7d1-e4e58773c9b5 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-013 | 1.0 Pre-Construction | RCP1.6 - Inspect reinforced pipe culverts for damage | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-013
cl:2717c2dd-f499-4b9b-a7d1-e4e58773c9b5 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-013 | 2.0 Construction | RCP2.7 - Trench Excavation | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-013
cl:2717c2dd-f499-4b9b-a7d1-e4e58773c9b5 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-013 | 2.0 Construction | RCP2.8 - Bedding | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-013
cl:2717c2dd-f499-4b9b-a7d1-e4e58773c9b5 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-013 | 2.0 Construction | RCP2.9 - RCP Installation | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-013
cl:2717c2dd-f499-4b9b-a7d1-e4e58773c9b5 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-013 | 2.0 Construction | RCP2.10 - Backfilling of culvert | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-013
cl:2717c2dd-f499-4b9b-a7d1-e4e58773c9b5 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-013 | 2.0 Construction | RCP2.11 - End Treatment – Headwall & Wingwalls (Reinforcement) | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-013
cl:2717c2dd-f499-4b9b-a7d1-e4e58773c9b5 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-013 | 2.0 Construction | RCP2.12 - End Treatment – Headwall & Wingwalls (Formwork) | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-013
cl:2717c2dd-f499-4b9b-a7d1-e4e58773c9b5 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-013 | 2.0 Construction | RCP2.13 - End Treatment – Headwall & Wingwalls (Concrete) | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-013
cl:2717c2dd-f499-4b9b-a7d1-e4e58773c9b5 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-013 | 2.0 Construction | RCP2.14 - Rock Protection | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-013
cl:2717c2dd-f499-4b9b-a7d1-e4e58773c9b5 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-013 | 3.0 Post Construction | RCP3.15 - Works completed and update ITP/ Lot Register/ MDR and close out of GDP | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-013
cl:3097c0b9-989c-4421-b2eb-94085d48b7d9 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-014 | 1.0 Pre-Construction | RCP1.1 - Drawings supplied most current IFC | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-014
cl:3097c0b9-989c-4421-b2eb-94085d48b7d9 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-014 | 1.0 Pre-Construction | RCP1.2 - Define RCP ID | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-014
cl:3097c0b9-989c-4421-b2eb-94085d48b7d9 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-014 | 1.0 Pre-Construction | RCP1.3 - Lot Register/ WBS submitted and approved | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-014
cl:3097c0b9-989c-4421-b2eb-94085d48b7d9 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-014 | 1.0 Pre-Construction | RCP1.4 - Underlying lot & ITP signed off and conforming | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-014
cl:3097c0b9-989c-4421-b2eb-94085d48b7d9 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-014 | 1.0 Pre-Construction | RCP1.5 - Certificate of compliance for RCP Material | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-014
cl:3097c0b9-989c-4421-b2eb-94085d48b7d9 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-014 | 1.0 Pre-Construction | RCP1.6 - Inspect reinforced pipe culverts for damage | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-014
cl:3097c0b9-989c-4421-b2eb-94085d48b7d9 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-014 | 2.0 Construction | RCP2.7 - Trench Excavation | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-014
cl:3097c0b9-989c-4421-b2eb-94085d48b7d9 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-014 | 2.0 Construction | RCP2.8 - Bedding | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-014
cl:3097c0b9-989c-4421-b2eb-94085d48b7d9 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-014 | 2.0 Construction | RCP2.9 - RCP Installation | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-014
cl:3097c0b9-989c-4421-b2eb-94085d48b7d9 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-014 | 2.0 Construction | RCP2.10 - Backfilling of culvert | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-014
cl:3097c0b9-989c-4421-b2eb-94085d48b7d9 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-014 | 2.0 Construction | RCP2.11 - End Treatment – Headwall & Wingwalls (Reinforcement) | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-014
cl:3097c0b9-989c-4421-b2eb-94085d48b7d9 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-014 | 2.0 Construction | RCP2.12 - End Treatment – Headwall & Wingwalls (Formwork) | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-014
cl:3097c0b9-989c-4421-b2eb-94085d48b7d9 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-014 | 2.0 Construction | RCP2.13 - End Treatment – Headwall & Wingwalls (Concrete) | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-014
cl:3097c0b9-989c-4421-b2eb-94085d48b7d9 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-014 | 2.0 Construction | RCP2.14 - Rock Protection | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-014
cl:3097c0b9-989c-4421-b2eb-94085d48b7d9 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-014 | 3.0 Post Construction | RCP3.15 - Works completed and update ITP/ Lot Register/ MDR and close out of GDP | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-014
cl:b9f58684-3edb-42e5-8a7d-cc6530eeea36 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-015 | 1.0 Pre-Construction | RCP1.1 - Drawings supplied most current IFC | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-015
cl:b9f58684-3edb-42e5-8a7d-cc6530eeea36 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-015 | 1.0 Pre-Construction | RCP1.2 - Define RCP ID | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-015
cl:b9f58684-3edb-42e5-8a7d-cc6530eeea36 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-015 | 1.0 Pre-Construction | RCP1.3 - Lot Register/ WBS submitted and approved | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-015
cl:b9f58684-3edb-42e5-8a7d-cc6530eeea36 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-015 | 1.0 Pre-Construction | RCP1.4 - Underlying lot & ITP signed off and conforming | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-015
cl:b9f58684-3edb-42e5-8a7d-cc6530eeea36 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-015 | 1.0 Pre-Construction | RCP1.5 - Certificate of compliance for RCP Material | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-015
cl:b9f58684-3edb-42e5-8a7d-cc6530eeea36 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-015 | 1.0 Pre-Construction | RCP1.6 - Inspect reinforced pipe culverts for damage | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-015
cl:b9f58684-3edb-42e5-8a7d-cc6530eeea36 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-015 | 2.0 Construction | RCP2.7 - Trench Excavation | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-015
cl:b9f58684-3edb-42e5-8a7d-cc6530eeea36 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-015 | 2.0 Construction | RCP2.8 - Bedding | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-015
cl:b9f58684-3edb-42e5-8a7d-cc6530eeea36 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-015 | 2.0 Construction | RCP2.9 - RCP Installation | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-015
cl:b9f58684-3edb-42e5-8a7d-cc6530eeea36 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-015 | 2.0 Construction | RCP2.10 - Backfilling of culvert | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-015
cl:b9f58684-3edb-42e5-8a7d-cc6530eeea36 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-015 | 2.0 Construction | RCP2.11 - End Treatment – Headwall & Wingwalls (Reinforcement) | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-015
cl:b9f58684-3edb-42e5-8a7d-cc6530eeea36 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-015 | 2.0 Construction | RCP2.12 - End Treatment – Headwall & Wingwalls (Formwork) | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-015
cl:b9f58684-3edb-42e5-8a7d-cc6530eeea36 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-015 | 2.0 Construction | RCP2.13 - End Treatment – Headwall & Wingwalls (Concrete) | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-015
cl:b9f58684-3edb-42e5-8a7d-cc6530eeea36 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-015 | 2.0 Construction | RCP2.14 - Rock Protection | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-015
cl:b9f58684-3edb-42e5-8a7d-cc6530eeea36 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-015 | 3.0 Post Construction | RCP3.15 - Works completed and update ITP/ Lot Register/ MDR and close out of GDP | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-015
cl:74498f1b-f1b4-4d43-a846-ed5ebaf88e1a | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-016 | 1.0 Pre-Construction | RCP1.1 - Drawings supplied most current IFC | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-016
cl:74498f1b-f1b4-4d43-a846-ed5ebaf88e1a | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-016 | 1.0 Pre-Construction | RCP1.2 - Define RCP ID | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-016
cl:74498f1b-f1b4-4d43-a846-ed5ebaf88e1a | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-016 | 1.0 Pre-Construction | RCP1.3 - Lot Register/ WBS submitted and approved | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-016
cl:74498f1b-f1b4-4d43-a846-ed5ebaf88e1a | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-016 | 1.0 Pre-Construction | RCP1.4 - Underlying lot & ITP signed off and conforming | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-016
cl:74498f1b-f1b4-4d43-a846-ed5ebaf88e1a | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-016 | 1.0 Pre-Construction | RCP1.5 - Certificate of compliance for RCP Material | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-016
cl:74498f1b-f1b4-4d43-a846-ed5ebaf88e1a | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-016 | 1.0 Pre-Construction | RCP1.6 - Inspect reinforced pipe culverts for damage | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-016
cl:74498f1b-f1b4-4d43-a846-ed5ebaf88e1a | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-016 | 2.0 Construction | RCP2.7 - Trench Excavation | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-016
cl:74498f1b-f1b4-4d43-a846-ed5ebaf88e1a | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-016 | 2.0 Construction | RCP2.8 - Bedding | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-016
cl:74498f1b-f1b4-4d43-a846-ed5ebaf88e1a | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-016 | 2.0 Construction | RCP2.9 - RCP Installation | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-016
cl:74498f1b-f1b4-4d43-a846-ed5ebaf88e1a | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-016 | 2.0 Construction | RCP2.10 - Backfilling of culvert | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-016
cl:74498f1b-f1b4-4d43-a846-ed5ebaf88e1a | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-016 | 2.0 Construction | RCP2.11 - End Treatment – Headwall & Wingwalls (Reinforcement) | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-016
cl:74498f1b-f1b4-4d43-a846-ed5ebaf88e1a | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-016 | 2.0 Construction | RCP2.12 - End Treatment – Headwall & Wingwalls (Formwork) | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-016
cl:74498f1b-f1b4-4d43-a846-ed5ebaf88e1a | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-016 | 2.0 Construction | RCP2.13 - End Treatment – Headwall & Wingwalls (Concrete) | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-016
cl:74498f1b-f1b4-4d43-a846-ed5ebaf88e1a | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-016 | 2.0 Construction | RCP2.14 - Rock Protection | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-016
cl:74498f1b-f1b4-4d43-a846-ed5ebaf88e1a | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-016 | 3.0 Post Construction | RCP3.15 - Works completed and update ITP/ Lot Register/ MDR and close out of GDP | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-016
cl:0876f56a-2c12-48dc-8a0f-0e0c0dd35b52 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-017 | 1.0 Pre-Construction | RCP1.1 - Drawings supplied most current IFC | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-017
cl:0876f56a-2c12-48dc-8a0f-0e0c0dd35b52 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-017 | 1.0 Pre-Construction | RCP1.2 - Define RCP ID | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-017
cl:0876f56a-2c12-48dc-8a0f-0e0c0dd35b52 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-017 | 1.0 Pre-Construction | RCP1.3 - Lot Register/ WBS submitted and approved | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-017
cl:0876f56a-2c12-48dc-8a0f-0e0c0dd35b52 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-017 | 1.0 Pre-Construction | RCP1.4 - Underlying lot & ITP signed off and conforming | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-017
cl:0876f56a-2c12-48dc-8a0f-0e0c0dd35b52 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-017 | 1.0 Pre-Construction | RCP1.5 - Certificate of compliance for RCP Material | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-017
cl:0876f56a-2c12-48dc-8a0f-0e0c0dd35b52 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-017 | 1.0 Pre-Construction | RCP1.6 - Inspect reinforced pipe culverts for damage | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-017
cl:0876f56a-2c12-48dc-8a0f-0e0c0dd35b52 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-017 | 2.0 Construction | RCP2.7 - Trench Excavation | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-017
cl:0876f56a-2c12-48dc-8a0f-0e0c0dd35b52 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-017 | 2.0 Construction | RCP2.8 - Bedding | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-017
cl:0876f56a-2c12-48dc-8a0f-0e0c0dd35b52 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-017 | 2.0 Construction | RCP2.9 - RCP Installation | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-017
cl:0876f56a-2c12-48dc-8a0f-0e0c0dd35b52 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-017 | 2.0 Construction | RCP2.10 - Backfilling of culvert | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-017
cl:0876f56a-2c12-48dc-8a0f-0e0c0dd35b52 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-017 | 2.0 Construction | RCP2.11 - End Treatment – Headwall & Wingwalls (Reinforcement) | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-017
cl:0876f56a-2c12-48dc-8a0f-0e0c0dd35b52 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-017 | 2.0 Construction | RCP2.12 - End Treatment – Headwall & Wingwalls (Formwork) | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-017
cl:0876f56a-2c12-48dc-8a0f-0e0c0dd35b52 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-017 | 2.0 Construction | RCP2.13 - End Treatment – Headwall & Wingwalls (Concrete) | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-017
cl:0876f56a-2c12-48dc-8a0f-0e0c0dd35b52 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-017 | 2.0 Construction | RCP2.14 - Rock Protection | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-017
cl:0876f56a-2c12-48dc-8a0f-0e0c0dd35b52 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-017 | 3.0 Post Construction | RCP3.15 - Works completed and update ITP/ Lot Register/ MDR and close out of GDP | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-017
cl:422980e3-ac79-4913-b4ad-54ef63cf0d32 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation > Global RCP | ITP-004 RCP Installation-MAR-018 - Global | 1.0 Pre-Construction | RCP1.1 - Drawings supplied most current IFC | In progress | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | Global RCP | ITP-004 RCP Installation-MAR-018 - Global
cl:422980e3-ac79-4913-b4ad-54ef63cf0d32 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation > Global RCP | ITP-004 RCP Installation-MAR-018 - Global | 1.0 Pre-Construction | RCP1.2 - Define RCP ID | Passed | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | Global RCP | ITP-004 RCP Installation-MAR-018 - Global
cl:422980e3-ac79-4913-b4ad-54ef63cf0d32 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation > Global RCP | ITP-004 RCP Installation-MAR-018 - Global | 1.0 Pre-Construction | RCP1.3 - Lot Register/ WBS submitted and approved | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | Global RCP | ITP-004 RCP Installation-MAR-018 - Global
cl:422980e3-ac79-4913-b4ad-54ef63cf0d32 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation > Global RCP | ITP-004 RCP Installation-MAR-018 - Global | 1.0 Pre-Construction | RCP1.4 - Underlying lot & ITP signed off and conforming | N/A | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | Global RCP | ITP-004 RCP Installation-MAR-018 - Global
cl:422980e3-ac79-4913-b4ad-54ef63cf0d32 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation > Global RCP | ITP-004 RCP Installation-MAR-018 - Global | 1.0 Pre-Construction | RCP1.5 - Certificate of compliance for RCP Material | Passed | Approved | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | Global RCP | ITP-004 RCP Installation-MAR-018 - Global
cl:422980e3-ac79-4913-b4ad-54ef63cf0d32 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation > Global RCP | ITP-004 RCP Installation-MAR-018 - Global | 1.0 Pre-Construction | RCP1.6 - Inspect reinforced pipe culverts for damage | Passed | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | Global RCP | ITP-004 RCP Installation-MAR-018 - Global
cl:422980e3-ac79-4913-b4ad-54ef63cf0d32 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation > Global RCP | ITP-004 RCP Installation-MAR-018 - Global | 2.0 Construction | RCP2.7 - Trench Excavation | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | Global RCP | ITP-004 RCP Installation-MAR-018 - Global
cl:422980e3-ac79-4913-b4ad-54ef63cf0d32 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation > Global RCP | ITP-004 RCP Installation-MAR-018 - Global | 2.0 Construction | RCP2.8 - Bedding | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | Global RCP | ITP-004 RCP Installation-MAR-018 - Global
cl:422980e3-ac79-4913-b4ad-54ef63cf0d32 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation > Global RCP | ITP-004 RCP Installation-MAR-018 - Global | 2.0 Construction | RCP2.9 - RCP Installation | In progress | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | Global RCP | ITP-004 RCP Installation-MAR-018 - Global
cl:422980e3-ac79-4913-b4ad-54ef63cf0d32 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation > Global RCP | ITP-004 RCP Installation-MAR-018 - Global | 2.0 Construction | RCP2.10 - Backfilling of culvert | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | Global RCP | ITP-004 RCP Installation-MAR-018 - Global
cl:422980e3-ac79-4913-b4ad-54ef63cf0d32 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation > Global RCP | ITP-004 RCP Installation-MAR-018 - Global | 2.0 Construction | RCP2.11 - End Treatment – Headwall & Wingwalls (Reinforcement) | Passed | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | Global RCP | ITP-004 RCP Installation-MAR-018 - Global
cl:422980e3-ac79-4913-b4ad-54ef63cf0d32 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation > Global RCP | ITP-004 RCP Installation-MAR-018 - Global | 2.0 Construction | RCP2.12 - End Treatment – Headwall & Wingwalls (Formwork) | N/A | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | Global RCP | ITP-004 RCP Installation-MAR-018 - Global
cl:422980e3-ac79-4913-b4ad-54ef63cf0d32 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation > Global RCP | ITP-004 RCP Installation-MAR-018 - Global | 2.0 Construction | RCP2.13 - End Treatment – Headwall & Wingwalls (Concrete) | N/A | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | Global RCP | ITP-004 RCP Installation-MAR-018 - Global
cl:422980e3-ac79-4913-b4ad-54ef63cf0d32 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation > Global RCP | ITP-004 RCP Installation-MAR-018 - Global | 2.0 Construction | RCP2.14 - Rock Protection | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | Global RCP | ITP-004 RCP Installation-MAR-018 - Global
cl:422980e3-ac79-4913-b4ad-54ef63cf0d32 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-004 RCP Installation > Global RCP | ITP-004 RCP Installation-MAR-018 - Global | 3.0 Post Construction | RCP3.15 - Works completed and update ITP/ Lot Register/ MDR and close out of GDP | Not started | Open | ITP-004 RCP Installation | Main Access Road (MAR) | ITP-004 RCP Installation | Global RCP | ITP-004 RCP Installation-MAR-018 - Global
cl:677bd369-096a-4938-9fa5-fc2031fac91e | EVA Copper Mine Project | Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-001 | Embankment Construction | EC1.1 - Underlying lot & ITP signed off and conforming | In progress | Open | ITP-008 Embankment Construction | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-001
cl:677bd369-096a-4938-9fa5-fc2031fac91e | EVA Copper Mine Project | Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-001 | Embankment Construction | EC1.2 - Embankment fill material | Passed | Open | ITP-008 Embankment Construction | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-001
cl:677bd369-096a-4938-9fa5-fc2031fac91e | EVA Copper Mine Project | Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-001 | Embankment Construction | EC1.3 - Survey Set out | Not started | Open | ITP-008 Embankment Construction | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-001
cl:677bd369-096a-4938-9fa5-fc2031fac91e | EVA Copper Mine Project | Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-001 | Embankment Construction | EC1.4 - Place, moisture condition & compact embankment fill | Not started | Open | ITP-008 Embankment Construction | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-001
cl:677bd369-096a-4938-9fa5-fc2031fac91e | EVA Copper Mine Project | Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-001 | Embankment Construction | EC1.5 - Trim embankment | Not started | Open | ITP-008 Embankment Construction | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-001
cl:677bd369-096a-4938-9fa5-fc2031fac91e | EVA Copper Mine Project | Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-001 | Embankment Construction | EC1.6 - Proof rolling | Not started | Open | ITP-008 Embankment Construction | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-001
cl:677bd369-096a-4938-9fa5-fc2031fac91e | EVA Copper Mine Project | Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-001 | Embankment Construction | EC1.7 - Surface level check and survey pick-up | Not started | Open | ITP-008 Embankment Construction | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-001
cl:677bd369-096a-4938-9fa5-fc2031fac91e | EVA Copper Mine Project | Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-001 | Embankment Construction | EC1.8 - QA close out | Not started | Open | ITP-008 Embankment Construction | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-001
cl:55dd702f-9ef0-4d44-b31c-11f4a89a057c | EVA Copper Mine Project | Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-002 | Embankment Construction | EC1.1 - Underlying lot & ITP signed off and conforming | Not started | Open | ITP-008 Embankment Construction | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-002
cl:55dd702f-9ef0-4d44-b31c-11f4a89a057c | EVA Copper Mine Project | Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-002 | Embankment Construction | EC1.2 - Embankment fill material | Not started | Open | ITP-008 Embankment Construction | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-002
cl:55dd702f-9ef0-4d44-b31c-11f4a89a057c | EVA Copper Mine Project | Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-002 | Embankment Construction | EC1.3 - Survey Set out | Not started | Open | ITP-008 Embankment Construction | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-002
cl:55dd702f-9ef0-4d44-b31c-11f4a89a057c | EVA Copper Mine Project | Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-002 | Embankment Construction | EC1.4 - Place, moisture condition & compact embankment fill | Not started | Open | ITP-008 Embankment Construction | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-002
cl:55dd702f-9ef0-4d44-b31c-11f4a89a057c | EVA Copper Mine Project | Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-002 | Embankment Construction | EC1.5 - Trim embankment | Not started | Open | ITP-008 Embankment Construction | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-002
cl:55dd702f-9ef0-4d44-b31c-11f4a89a057c | EVA Copper Mine Project | Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-002 | Embankment Construction | EC1.6 - Proof rolling | Not started | Open | ITP-008 Embankment Construction | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-002
cl:55dd702f-9ef0-4d44-b31c-11f4a89a057c | EVA Copper Mine Project | Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-002 | Embankment Construction | EC1.7 - Surface level check and survey pick-up | Not started | Open | ITP-008 Embankment Construction | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-002
cl:55dd702f-9ef0-4d44-b31c-11f4a89a057c | EVA Copper Mine Project | Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-002 | Embankment Construction | EC1.8 - QA close out | Not started | Open | ITP-008 Embankment Construction | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-002
cl:21ed1d63-15df-421c-8ea0-1662ef191936 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-003 | Embankment Construction | EC1.1 - Underlying lot & ITP signed off and conforming | Not started | Open | ITP-008 Embankment Construction | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-003
cl:21ed1d63-15df-421c-8ea0-1662ef191936 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-003 | Embankment Construction | EC1.2 - Embankment fill material | Not started | Open | ITP-008 Embankment Construction | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-003
cl:21ed1d63-15df-421c-8ea0-1662ef191936 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-003 | Embankment Construction | EC1.3 - Survey Set out | Not started | Open | ITP-008 Embankment Construction | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-003
cl:21ed1d63-15df-421c-8ea0-1662ef191936 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-003 | Embankment Construction | EC1.4 - Place, moisture condition & compact embankment fill | Not started | Open | ITP-008 Embankment Construction | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-003
cl:21ed1d63-15df-421c-8ea0-1662ef191936 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-003 | Embankment Construction | EC1.5 - Trim embankment | Not started | Open | ITP-008 Embankment Construction | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-003
cl:21ed1d63-15df-421c-8ea0-1662ef191936 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-003 | Embankment Construction | EC1.6 - Proof rolling | Not started | Open | ITP-008 Embankment Construction | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-003
cl:21ed1d63-15df-421c-8ea0-1662ef191936 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-003 | Embankment Construction | EC1.7 - Surface level check and survey pick-up | Not started | Open | ITP-008 Embankment Construction | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-003
cl:21ed1d63-15df-421c-8ea0-1662ef191936 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-003 | Embankment Construction | EC1.8 - QA close out | Not started | Open | ITP-008 Embankment Construction | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-003
cl:72b1db10-1292-4f46-b3bf-822d4bc53073 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-004 | Embankment Construction | EC1.1 - Underlying lot & ITP signed off and conforming | Not started | Open | ITP-008 Embankment Construction | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-004
cl:72b1db10-1292-4f46-b3bf-822d4bc53073 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-004 | Embankment Construction | EC1.2 - Embankment fill material | Not started | Open | ITP-008 Embankment Construction | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-004
cl:72b1db10-1292-4f46-b3bf-822d4bc53073 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-004 | Embankment Construction | EC1.3 - Survey Set out | Not started | Open | ITP-008 Embankment Construction | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-004
cl:72b1db10-1292-4f46-b3bf-822d4bc53073 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-004 | Embankment Construction | EC1.4 - Place, moisture condition & compact embankment fill | Not started | Open | ITP-008 Embankment Construction | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-004
cl:72b1db10-1292-4f46-b3bf-822d4bc53073 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-004 | Embankment Construction | EC1.5 - Trim embankment | Not started | Open | ITP-008 Embankment Construction | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-004
cl:72b1db10-1292-4f46-b3bf-822d4bc53073 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-004 | Embankment Construction | EC1.6 - Proof rolling | Not started | Open | ITP-008 Embankment Construction | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-004
cl:72b1db10-1292-4f46-b3bf-822d4bc53073 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-004 | Embankment Construction | EC1.7 - Surface level check and survey pick-up | Not started | Open | ITP-008 Embankment Construction | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-004
cl:72b1db10-1292-4f46-b3bf-822d4bc53073 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-004 | Embankment Construction | EC1.8 - QA close out | Not started | Open | ITP-008 Embankment Construction | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-004
cl:71558f67-7388-476c-b403-7bdf8ca4578b | EVA Copper Mine Project | Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-005 | Embankment Construction | EC1.1 - Underlying lot & ITP signed off and conforming | Not started | Open | ITP-008 Embankment Construction | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-005
cl:71558f67-7388-476c-b403-7bdf8ca4578b | EVA Copper Mine Project | Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-005 | Embankment Construction | EC1.2 - Embankment fill material | Not started | Open | ITP-008 Embankment Construction | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-005
cl:71558f67-7388-476c-b403-7bdf8ca4578b | EVA Copper Mine Project | Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-005 | Embankment Construction | EC1.3 - Survey Set out | Not started | Open | ITP-008 Embankment Construction | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-005
cl:71558f67-7388-476c-b403-7bdf8ca4578b | EVA Copper Mine Project | Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-005 | Embankment Construction | EC1.4 - Place, moisture condition & compact embankment fill | Not started | Open | ITP-008 Embankment Construction | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-005
cl:71558f67-7388-476c-b403-7bdf8ca4578b | EVA Copper Mine Project | Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-005 | Embankment Construction | EC1.5 - Trim embankment | Not started | Open | ITP-008 Embankment Construction | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-005
cl:71558f67-7388-476c-b403-7bdf8ca4578b | EVA Copper Mine Project | Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-005 | Embankment Construction | EC1.6 - Proof rolling | Not started | Open | ITP-008 Embankment Construction | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-005
cl:71558f67-7388-476c-b403-7bdf8ca4578b | EVA Copper Mine Project | Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-005 | Embankment Construction | EC1.7 - Surface level check and survey pick-up | Not started | Open | ITP-008 Embankment Construction | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-005
cl:71558f67-7388-476c-b403-7bdf8ca4578b | EVA Copper Mine Project | Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-005 | Embankment Construction | EC1.8 - QA close out | Not started | Open | ITP-008 Embankment Construction | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-005
cl:8815128e-ec87-48da-a663-0f168a937a26 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-006 | Embankment Construction | EC1.1 - Underlying lot & ITP signed off and conforming | Not started | Open | ITP-008 Embankment Construction | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-006
cl:8815128e-ec87-48da-a663-0f168a937a26 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-006 | Embankment Construction | EC1.2 - Embankment fill material | Not started | Open | ITP-008 Embankment Construction | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-006
cl:8815128e-ec87-48da-a663-0f168a937a26 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-006 | Embankment Construction | EC1.3 - Survey Set out | Not started | Open | ITP-008 Embankment Construction | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-006
cl:8815128e-ec87-48da-a663-0f168a937a26 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-006 | Embankment Construction | EC1.4 - Place, moisture condition & compact embankment fill | Not started | Open | ITP-008 Embankment Construction | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-006
cl:8815128e-ec87-48da-a663-0f168a937a26 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-006 | Embankment Construction | EC1.5 - Trim embankment | Not started | Open | ITP-008 Embankment Construction | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-006
cl:8815128e-ec87-48da-a663-0f168a937a26 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-006 | Embankment Construction | EC1.6 - Proof rolling | Not started | Open | ITP-008 Embankment Construction | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-006
cl:8815128e-ec87-48da-a663-0f168a937a26 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-006 | Embankment Construction | EC1.7 - Surface level check and survey pick-up | Not started | Open | ITP-008 Embankment Construction | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-006
cl:8815128e-ec87-48da-a663-0f168a937a26 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-006 | Embankment Construction | EC1.8 - QA close out | Not started | Open | ITP-008 Embankment Construction | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-006
cl:b5312136-2d65-40fb-a4ea-3adcb065938b | EVA Copper Mine Project | Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-007 | Embankment Construction | EC1.1 - Underlying lot & ITP signed off and conforming | Not started | Open | ITP-008 Embankment Construction | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-007
cl:b5312136-2d65-40fb-a4ea-3adcb065938b | EVA Copper Mine Project | Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-007 | Embankment Construction | EC1.2 - Embankment fill material | Not started | Open | ITP-008 Embankment Construction | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-007
cl:b5312136-2d65-40fb-a4ea-3adcb065938b | EVA Copper Mine Project | Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-007 | Embankment Construction | EC1.3 - Survey Set out | Not started | Open | ITP-008 Embankment Construction | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-007
cl:b5312136-2d65-40fb-a4ea-3adcb065938b | EVA Copper Mine Project | Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-007 | Embankment Construction | EC1.4 - Place, moisture condition & compact embankment fill | Not started | Open | ITP-008 Embankment Construction | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-007
cl:b5312136-2d65-40fb-a4ea-3adcb065938b | EVA Copper Mine Project | Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-007 | Embankment Construction | EC1.5 - Trim embankment | Not started | Open | ITP-008 Embankment Construction | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-007
cl:b5312136-2d65-40fb-a4ea-3adcb065938b | EVA Copper Mine Project | Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-007 | Embankment Construction | EC1.6 - Proof rolling | Not started | Open | ITP-008 Embankment Construction | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-007
cl:b5312136-2d65-40fb-a4ea-3adcb065938b | EVA Copper Mine Project | Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-007 | Embankment Construction | EC1.7 - Surface level check and survey pick-up | Not started | Open | ITP-008 Embankment Construction | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-007
cl:b5312136-2d65-40fb-a4ea-3adcb065938b | EVA Copper Mine Project | Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-007 | Embankment Construction | EC1.8 - QA close out | Not started | Open | ITP-008 Embankment Construction | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-007
cl:16667826-9565-4d11-b909-c2201b54448b | EVA Copper Mine Project | Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-008 | Embankment Construction | EC1.1 - Underlying lot & ITP signed off and conforming | Not started | Open | ITP-008 Embankment Construction | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-008
cl:16667826-9565-4d11-b909-c2201b54448b | EVA Copper Mine Project | Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-008 | Embankment Construction | EC1.2 - Embankment fill material | Not started | Open | ITP-008 Embankment Construction | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-008
cl:16667826-9565-4d11-b909-c2201b54448b | EVA Copper Mine Project | Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-008 | Embankment Construction | EC1.3 - Survey Set out | Not started | Open | ITP-008 Embankment Construction | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-008
cl:16667826-9565-4d11-b909-c2201b54448b | EVA Copper Mine Project | Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-008 | Embankment Construction | EC1.4 - Place, moisture condition & compact embankment fill | Not started | Open | ITP-008 Embankment Construction | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-008
cl:16667826-9565-4d11-b909-c2201b54448b | EVA Copper Mine Project | Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-008 | Embankment Construction | EC1.5 - Trim embankment | Not started | Open | ITP-008 Embankment Construction | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-008
cl:16667826-9565-4d11-b909-c2201b54448b | EVA Copper Mine Project | Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-008 | Embankment Construction | EC1.6 - Proof rolling | Not started | Open | ITP-008 Embankment Construction | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-008
cl:16667826-9565-4d11-b909-c2201b54448b | EVA Copper Mine Project | Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-008 | Embankment Construction | EC1.7 - Surface level check and survey pick-up | Not started | Open | ITP-008 Embankment Construction | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-008
cl:16667826-9565-4d11-b909-c2201b54448b | EVA Copper Mine Project | Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-008 | Embankment Construction | EC1.8 - QA close out | Not started | Open | ITP-008 Embankment Construction | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-008
cl:c7b6301c-1383-4a62-b466-ac1369643971 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-009 | Embankment Construction | EC1.1 - Underlying lot & ITP signed off and conforming | Not started | Open | ITP-008 Embankment Construction | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-009
cl:c7b6301c-1383-4a62-b466-ac1369643971 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-009 | Embankment Construction | EC1.2 - Embankment fill material | Not started | Open | ITP-008 Embankment Construction | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-009
cl:c7b6301c-1383-4a62-b466-ac1369643971 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-009 | Embankment Construction | EC1.3 - Survey Set out | Not started | Open | ITP-008 Embankment Construction | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-009
cl:c7b6301c-1383-4a62-b466-ac1369643971 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-009 | Embankment Construction | EC1.4 - Place, moisture condition & compact embankment fill | Not started | Open | ITP-008 Embankment Construction | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-009
cl:c7b6301c-1383-4a62-b466-ac1369643971 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-009 | Embankment Construction | EC1.5 - Trim embankment | Not started | Open | ITP-008 Embankment Construction | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-009
cl:c7b6301c-1383-4a62-b466-ac1369643971 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-009 | Embankment Construction | EC1.6 - Proof rolling | Not started | Open | ITP-008 Embankment Construction | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-009
cl:c7b6301c-1383-4a62-b466-ac1369643971 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-009 | Embankment Construction | EC1.7 - Surface level check and survey pick-up | Not started | Open | ITP-008 Embankment Construction | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-009
cl:c7b6301c-1383-4a62-b466-ac1369643971 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-009 | Embankment Construction | EC1.8 - QA close out | Not started | Open | ITP-008 Embankment Construction | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-009
cl:48f8a636-f478-4fde-b1b2-bd0342c530df | EVA Copper Mine Project | Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-010 | Embankment Construction | EC1.1 - Underlying lot & ITP signed off and conforming | Not started | Open | ITP-008 Embankment Construction | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-010
cl:48f8a636-f478-4fde-b1b2-bd0342c530df | EVA Copper Mine Project | Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-010 | Embankment Construction | EC1.2 - Embankment fill material | Not started | Open | ITP-008 Embankment Construction | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-010
cl:48f8a636-f478-4fde-b1b2-bd0342c530df | EVA Copper Mine Project | Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-010 | Embankment Construction | EC1.3 - Survey Set out | Not started | Open | ITP-008 Embankment Construction | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-010
cl:48f8a636-f478-4fde-b1b2-bd0342c530df | EVA Copper Mine Project | Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-010 | Embankment Construction | EC1.4 - Place, moisture condition & compact embankment fill | Not started | Open | ITP-008 Embankment Construction | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-010
cl:48f8a636-f478-4fde-b1b2-bd0342c530df | EVA Copper Mine Project | Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-010 | Embankment Construction | EC1.5 - Trim embankment | Not started | Open | ITP-008 Embankment Construction | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-010
cl:48f8a636-f478-4fde-b1b2-bd0342c530df | EVA Copper Mine Project | Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-010 | Embankment Construction | EC1.6 - Proof rolling | Not started | Open | ITP-008 Embankment Construction | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-010
cl:48f8a636-f478-4fde-b1b2-bd0342c530df | EVA Copper Mine Project | Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-010 | Embankment Construction | EC1.7 - Surface level check and survey pick-up | Not started | Open | ITP-008 Embankment Construction | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-010
cl:48f8a636-f478-4fde-b1b2-bd0342c530df | EVA Copper Mine Project | Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-010 | Embankment Construction | EC1.8 - QA close out | Not started | Open | ITP-008 Embankment Construction | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-010
cl:1d69aa48-b390-4956-ace2-858e4bcf6c56 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-011 | Embankment Construction | EC1.1 - Underlying lot & ITP signed off and conforming | Not started | Open | ITP-008 Embankment Construction | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-011
cl:1d69aa48-b390-4956-ace2-858e4bcf6c56 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-011 | Embankment Construction | EC1.2 - Embankment fill material | Not started | Open | ITP-008 Embankment Construction | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-011
cl:1d69aa48-b390-4956-ace2-858e4bcf6c56 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-011 | Embankment Construction | EC1.3 - Survey Set out | Not started | Open | ITP-008 Embankment Construction | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-011
cl:1d69aa48-b390-4956-ace2-858e4bcf6c56 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-011 | Embankment Construction | EC1.4 - Place, moisture condition & compact embankment fill | Not started | Open | ITP-008 Embankment Construction | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-011
cl:1d69aa48-b390-4956-ace2-858e4bcf6c56 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-011 | Embankment Construction | EC1.5 - Trim embankment | Not started | Open | ITP-008 Embankment Construction | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-011
cl:1d69aa48-b390-4956-ace2-858e4bcf6c56 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-011 | Embankment Construction | EC1.6 - Proof rolling | Not started | Open | ITP-008 Embankment Construction | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-011
cl:1d69aa48-b390-4956-ace2-858e4bcf6c56 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-011 | Embankment Construction | EC1.7 - Surface level check and survey pick-up | Not started | Open | ITP-008 Embankment Construction | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-011
cl:1d69aa48-b390-4956-ace2-858e4bcf6c56 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-011 | Embankment Construction | EC1.8 - QA close out | Not started | Open | ITP-008 Embankment Construction | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-011
cl:a8234618-0e56-45ee-8c35-e5aa30bb12cb | EVA Copper Mine Project | Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-012 | Embankment Construction | EC1.1 - Underlying lot & ITP signed off and conforming | Not started | Open | ITP-008 Embankment Construction | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-012
cl:a8234618-0e56-45ee-8c35-e5aa30bb12cb | EVA Copper Mine Project | Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-012 | Embankment Construction | EC1.2 - Embankment fill material | Not started | Open | ITP-008 Embankment Construction | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-012
cl:a8234618-0e56-45ee-8c35-e5aa30bb12cb | EVA Copper Mine Project | Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-012 | Embankment Construction | EC1.3 - Survey Set out | Not started | Open | ITP-008 Embankment Construction | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-012
cl:a8234618-0e56-45ee-8c35-e5aa30bb12cb | EVA Copper Mine Project | Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-012 | Embankment Construction | EC1.4 - Place, moisture condition & compact embankment fill | Not started | Open | ITP-008 Embankment Construction | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-012
cl:a8234618-0e56-45ee-8c35-e5aa30bb12cb | EVA Copper Mine Project | Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-012 | Embankment Construction | EC1.5 - Trim embankment | Not started | Open | ITP-008 Embankment Construction | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-012
cl:a8234618-0e56-45ee-8c35-e5aa30bb12cb | EVA Copper Mine Project | Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-012 | Embankment Construction | EC1.6 - Proof rolling | Not started | Open | ITP-008 Embankment Construction | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-012
cl:a8234618-0e56-45ee-8c35-e5aa30bb12cb | EVA Copper Mine Project | Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-012 | Embankment Construction | EC1.7 - Surface level check and survey pick-up | Not started | Open | ITP-008 Embankment Construction | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-012
cl:a8234618-0e56-45ee-8c35-e5aa30bb12cb | EVA Copper Mine Project | Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-012 | Embankment Construction | EC1.8 - QA close out | Not started | Open | ITP-008 Embankment Construction | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-012
cl:edde45ff-09a9-49cc-b485-0fd70ebadf74 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-013 | Embankment Construction | EC1.1 - Underlying lot & ITP signed off and conforming | Not started | Open | ITP-008 Embankment Construction | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-013
cl:edde45ff-09a9-49cc-b485-0fd70ebadf74 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-013 | Embankment Construction | EC1.2 - Embankment fill material | Not started | Open | ITP-008 Embankment Construction | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-013
cl:edde45ff-09a9-49cc-b485-0fd70ebadf74 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-013 | Embankment Construction | EC1.3 - Survey Set out | Not started | Open | ITP-008 Embankment Construction | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-013
cl:edde45ff-09a9-49cc-b485-0fd70ebadf74 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-013 | Embankment Construction | EC1.4 - Place, moisture condition & compact embankment fill | Not started | Open | ITP-008 Embankment Construction | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-013
cl:edde45ff-09a9-49cc-b485-0fd70ebadf74 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-013 | Embankment Construction | EC1.5 - Trim embankment | Not started | Open | ITP-008 Embankment Construction | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-013
cl:edde45ff-09a9-49cc-b485-0fd70ebadf74 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-013 | Embankment Construction | EC1.6 - Proof rolling | Not started | Open | ITP-008 Embankment Construction | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-013
cl:edde45ff-09a9-49cc-b485-0fd70ebadf74 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-013 | Embankment Construction | EC1.7 - Surface level check and survey pick-up | Not started | Open | ITP-008 Embankment Construction | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-013
cl:edde45ff-09a9-49cc-b485-0fd70ebadf74 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-013 | Embankment Construction | EC1.8 - QA close out | Not started | Open | ITP-008 Embankment Construction | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-013
cl:c9959181-8906-4731-9758-8476ccbc2ae4 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-014 | Embankment Construction | EC1.1 - Underlying lot & ITP signed off and conforming | Not started | Open | ITP-008 Embankment Construction | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-014
cl:c9959181-8906-4731-9758-8476ccbc2ae4 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-014 | Embankment Construction | EC1.2 - Embankment fill material | Not started | Open | ITP-008 Embankment Construction | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-014
cl:c9959181-8906-4731-9758-8476ccbc2ae4 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-014 | Embankment Construction | EC1.3 - Survey Set out | Not started | Open | ITP-008 Embankment Construction | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-014
cl:c9959181-8906-4731-9758-8476ccbc2ae4 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-014 | Embankment Construction | EC1.4 - Place, moisture condition & compact embankment fill | Not started | Open | ITP-008 Embankment Construction | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-014
cl:c9959181-8906-4731-9758-8476ccbc2ae4 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-014 | Embankment Construction | EC1.5 - Trim embankment | Not started | Open | ITP-008 Embankment Construction | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-014
cl:c9959181-8906-4731-9758-8476ccbc2ae4 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-014 | Embankment Construction | EC1.6 - Proof rolling | Not started | Open | ITP-008 Embankment Construction | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-014
cl:c9959181-8906-4731-9758-8476ccbc2ae4 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-014 | Embankment Construction | EC1.7 - Surface level check and survey pick-up | Not started | Open | ITP-008 Embankment Construction | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-014
cl:c9959181-8906-4731-9758-8476ccbc2ae4 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-014 | Embankment Construction | EC1.8 - QA close out | Not started | Open | ITP-008 Embankment Construction | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-014
cl:1d851afd-6473-4983-86ff-3944ee158b12 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-015 | Embankment Construction | EC1.1 - Underlying lot & ITP signed off and conforming | Not started | Open | ITP-008 Embankment Construction | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-015
cl:1d851afd-6473-4983-86ff-3944ee158b12 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-015 | Embankment Construction | EC1.2 - Embankment fill material | Not started | Open | ITP-008 Embankment Construction | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-015
cl:1d851afd-6473-4983-86ff-3944ee158b12 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-015 | Embankment Construction | EC1.3 - Survey Set out | Not started | Open | ITP-008 Embankment Construction | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-015
cl:1d851afd-6473-4983-86ff-3944ee158b12 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-015 | Embankment Construction | EC1.4 - Place, moisture condition & compact embankment fill | Not started | Open | ITP-008 Embankment Construction | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-015
cl:1d851afd-6473-4983-86ff-3944ee158b12 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-015 | Embankment Construction | EC1.5 - Trim embankment | Not started | Open | ITP-008 Embankment Construction | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-015
cl:1d851afd-6473-4983-86ff-3944ee158b12 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-015 | Embankment Construction | EC1.6 - Proof rolling | Not started | Open | ITP-008 Embankment Construction | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-015
cl:1d851afd-6473-4983-86ff-3944ee158b12 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-015 | Embankment Construction | EC1.7 - Surface level check and survey pick-up | Not started | Open | ITP-008 Embankment Construction | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-015
cl:1d851afd-6473-4983-86ff-3944ee158b12 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-015 | Embankment Construction | EC1.8 - QA close out | Not started | Open | ITP-008 Embankment Construction | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-015
cl:b88a7678-4b1d-4d3f-b470-553e064a93e4 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-016 | Embankment Construction | EC1.1 - Underlying lot & ITP signed off and conforming | Not started | Open | ITP-008 Embankment Construction | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-016
cl:b88a7678-4b1d-4d3f-b470-553e064a93e4 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-016 | Embankment Construction | EC1.2 - Embankment fill material | Not started | Open | ITP-008 Embankment Construction | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-016
cl:b88a7678-4b1d-4d3f-b470-553e064a93e4 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-016 | Embankment Construction | EC1.3 - Survey Set out | Not started | Open | ITP-008 Embankment Construction | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-016
cl:b88a7678-4b1d-4d3f-b470-553e064a93e4 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-016 | Embankment Construction | EC1.4 - Place, moisture condition & compact embankment fill | Not started | Open | ITP-008 Embankment Construction | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-016
cl:b88a7678-4b1d-4d3f-b470-553e064a93e4 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-016 | Embankment Construction | EC1.5 - Trim embankment | Not started | Open | ITP-008 Embankment Construction | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-016
cl:b88a7678-4b1d-4d3f-b470-553e064a93e4 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-016 | Embankment Construction | EC1.6 - Proof rolling | Not started | Open | ITP-008 Embankment Construction | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-016
cl:b88a7678-4b1d-4d3f-b470-553e064a93e4 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-016 | Embankment Construction | EC1.7 - Surface level check and survey pick-up | Not started | Open | ITP-008 Embankment Construction | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-016
cl:b88a7678-4b1d-4d3f-b470-553e064a93e4 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-016 | Embankment Construction | EC1.8 - QA close out | Not started | Open | ITP-008 Embankment Construction | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-016
cl:40473b7b-e086-45dd-a85c-dc23e476f2f3 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-017 | Embankment Construction | EC1.1 - Underlying lot & ITP signed off and conforming | Not started | Open | ITP-008 Embankment Construction | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-017
cl:40473b7b-e086-45dd-a85c-dc23e476f2f3 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-017 | Embankment Construction | EC1.2 - Embankment fill material | Not started | Open | ITP-008 Embankment Construction | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-017
cl:40473b7b-e086-45dd-a85c-dc23e476f2f3 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-017 | Embankment Construction | EC1.3 - Survey Set out | Not started | Open | ITP-008 Embankment Construction | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-017
cl:40473b7b-e086-45dd-a85c-dc23e476f2f3 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-017 | Embankment Construction | EC1.4 - Place, moisture condition & compact embankment fill | Not started | Open | ITP-008 Embankment Construction | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-017
cl:40473b7b-e086-45dd-a85c-dc23e476f2f3 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-017 | Embankment Construction | EC1.5 - Trim embankment | Not started | Open | ITP-008 Embankment Construction | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-017
cl:40473b7b-e086-45dd-a85c-dc23e476f2f3 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-017 | Embankment Construction | EC1.6 - Proof rolling | Not started | Open | ITP-008 Embankment Construction | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-017
cl:40473b7b-e086-45dd-a85c-dc23e476f2f3 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-017 | Embankment Construction | EC1.7 - Surface level check and survey pick-up | Not started | Open | ITP-008 Embankment Construction | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-017
cl:40473b7b-e086-45dd-a85c-dc23e476f2f3 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-017 | Embankment Construction | EC1.8 - QA close out | Not started | Open | ITP-008 Embankment Construction | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-017
cl:3ab8f4bf-0aba-4f15-9b6a-18f0b2f28529 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-001 | 1.0 Pre-Construction | GP1.1 - Drawings supplied most current IFC | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-001
cl:3ab8f4bf-0aba-4f15-9b6a-18f0b2f28529 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-001 | 1.0 Pre-Construction | GP1.2 - Management Plans submitted and approved as per PMP | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-001
cl:3ab8f4bf-0aba-4f15-9b6a-18f0b2f28529 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-001 | 1.0 Pre-Construction | GP1.3 - Inspection Test Plan (ITP) submitted and approved | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-001
cl:3ab8f4bf-0aba-4f15-9b6a-18f0b2f28529 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-001 | 1.0 Pre-Construction | GP1.4 - Lot Register/ WBS submitted and approved | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-001
cl:3ab8f4bf-0aba-4f15-9b6a-18f0b2f28529 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-001 | 1.0 Pre-Construction | GP1.5 - Pavement material compliance testing | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-001
cl:3ab8f4bf-0aba-4f15-9b6a-18f0b2f28529 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-001 | 1.0 Pre-Construction | GP1.6 - Stockpile locations | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-001
cl:3ab8f4bf-0aba-4f15-9b6a-18f0b2f28529 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-001 | 1.0 Pre-Construction | GP1.7 - Underlying lot & ITP signed off and conforming | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-001
cl:3ab8f4bf-0aba-4f15-9b6a-18f0b2f28529 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-001 | 2.0 Construction | GP2.8 - Subgrade preparation under pavements | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-001
cl:3ab8f4bf-0aba-4f15-9b6a-18f0b2f28529 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-001 | 2.0 Construction | EC2.9 - Surface level check/ and survey pick-up | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-001
cl:3ab8f4bf-0aba-4f15-9b6a-18f0b2f28529 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-001 | 2.0 Construction | EC2.10 - Proof roll subgrade prior to placement of pavement materials | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-001
cl:3ab8f4bf-0aba-4f15-9b6a-18f0b2f28529 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-001 | 2.0 Construction | EC2.11 - Placement of pavement material layers | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-001
cl:3ab8f4bf-0aba-4f15-9b6a-18f0b2f28529 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-001 | 2.0 Construction | EC2.12 - Surface level check/ and survey pick-up | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-001
cl:3ab8f4bf-0aba-4f15-9b6a-18f0b2f28529 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-001 | 3.0 Post Construction | EC3.13 - Works completed and update ITP/ Lot Register/ MDR and close out of GDP | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-001
cl:7d8b619b-e51f-4180-943b-6f39301cd46e | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-002 | 1.0 Pre-Construction | GP1.1 - Drawings supplied most current IFC | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-002
cl:7d8b619b-e51f-4180-943b-6f39301cd46e | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-002 | 1.0 Pre-Construction | GP1.2 - Management Plans submitted and approved as per PMP | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-002
cl:7d8b619b-e51f-4180-943b-6f39301cd46e | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-002 | 1.0 Pre-Construction | GP1.3 - Inspection Test Plan (ITP) submitted and approved | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-002
cl:7d8b619b-e51f-4180-943b-6f39301cd46e | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-002 | 1.0 Pre-Construction | GP1.4 - Lot Register/ WBS submitted and approved | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-002
cl:7d8b619b-e51f-4180-943b-6f39301cd46e | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-002 | 1.0 Pre-Construction | GP1.5 - Pavement material compliance testing | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-002
cl:7d8b619b-e51f-4180-943b-6f39301cd46e | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-002 | 1.0 Pre-Construction | GP1.6 - Stockpile locations | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-002
cl:7d8b619b-e51f-4180-943b-6f39301cd46e | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-002 | 1.0 Pre-Construction | GP1.7 - Underlying lot & ITP signed off and conforming | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-002
cl:7d8b619b-e51f-4180-943b-6f39301cd46e | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-002 | 2.0 Construction | GP2.8 - Subgrade preparation under pavements | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-002
cl:7d8b619b-e51f-4180-943b-6f39301cd46e | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-002 | 2.0 Construction | EC2.9 - Surface level check/ and survey pick-up | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-002
cl:7d8b619b-e51f-4180-943b-6f39301cd46e | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-002 | 2.0 Construction | EC2.10 - Proof roll subgrade prior to placement of pavement materials | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-002
cl:7d8b619b-e51f-4180-943b-6f39301cd46e | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-002 | 2.0 Construction | EC2.11 - Placement of pavement material layers | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-002
cl:7d8b619b-e51f-4180-943b-6f39301cd46e | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-002 | 2.0 Construction | EC2.12 - Surface level check/ and survey pick-up | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-002
cl:7d8b619b-e51f-4180-943b-6f39301cd46e | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-002 | 3.0 Post Construction | EC3.13 - Works completed and update ITP/ Lot Register/ MDR and close out of GDP | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-002
cl:9c2e4830-6b5e-4d6d-9ece-69056bc38f4d | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-003 | 1.0 Pre-Construction | GP1.1 - Drawings supplied most current IFC | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-003
cl:9c2e4830-6b5e-4d6d-9ece-69056bc38f4d | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-003 | 1.0 Pre-Construction | GP1.2 - Management Plans submitted and approved as per PMP | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-003
cl:9c2e4830-6b5e-4d6d-9ece-69056bc38f4d | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-003 | 1.0 Pre-Construction | GP1.3 - Inspection Test Plan (ITP) submitted and approved | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-003
cl:9c2e4830-6b5e-4d6d-9ece-69056bc38f4d | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-003 | 1.0 Pre-Construction | GP1.4 - Lot Register/ WBS submitted and approved | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-003
cl:9c2e4830-6b5e-4d6d-9ece-69056bc38f4d | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-003 | 1.0 Pre-Construction | GP1.5 - Pavement material compliance testing | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-003
cl:9c2e4830-6b5e-4d6d-9ece-69056bc38f4d | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-003 | 1.0 Pre-Construction | GP1.6 - Stockpile locations | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-003
cl:9c2e4830-6b5e-4d6d-9ece-69056bc38f4d | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-003 | 1.0 Pre-Construction | GP1.7 - Underlying lot & ITP signed off and conforming | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-003
cl:9c2e4830-6b5e-4d6d-9ece-69056bc38f4d | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-003 | 2.0 Construction | GP2.8 - Subgrade preparation under pavements | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-003
cl:9c2e4830-6b5e-4d6d-9ece-69056bc38f4d | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-003 | 2.0 Construction | EC2.9 - Surface level check/ and survey pick-up | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-003
cl:9c2e4830-6b5e-4d6d-9ece-69056bc38f4d | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-003 | 2.0 Construction | EC2.10 - Proof roll subgrade prior to placement of pavement materials | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-003
cl:9c2e4830-6b5e-4d6d-9ece-69056bc38f4d | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-003 | 2.0 Construction | EC2.11 - Placement of pavement material layers | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-003
cl:9c2e4830-6b5e-4d6d-9ece-69056bc38f4d | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-003 | 2.0 Construction | EC2.12 - Surface level check/ and survey pick-up | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-003
cl:9c2e4830-6b5e-4d6d-9ece-69056bc38f4d | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-003 | 3.0 Post Construction | EC3.13 - Works completed and update ITP/ Lot Register/ MDR and close out of GDP | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-003
cl:ded39db4-f2a2-4925-b6ab-9cb39d7a8bf4 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-004 | 1.0 Pre-Construction | GP1.1 - Drawings supplied most current IFC | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-004
cl:ded39db4-f2a2-4925-b6ab-9cb39d7a8bf4 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-004 | 1.0 Pre-Construction | GP1.2 - Management Plans submitted and approved as per PMP | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-004
cl:ded39db4-f2a2-4925-b6ab-9cb39d7a8bf4 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-004 | 1.0 Pre-Construction | GP1.3 - Inspection Test Plan (ITP) submitted and approved | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-004
cl:ded39db4-f2a2-4925-b6ab-9cb39d7a8bf4 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-004 | 1.0 Pre-Construction | GP1.4 - Lot Register/ WBS submitted and approved | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-004
cl:ded39db4-f2a2-4925-b6ab-9cb39d7a8bf4 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-004 | 1.0 Pre-Construction | GP1.5 - Pavement material compliance testing | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-004
cl:ded39db4-f2a2-4925-b6ab-9cb39d7a8bf4 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-004 | 1.0 Pre-Construction | GP1.6 - Stockpile locations | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-004
cl:ded39db4-f2a2-4925-b6ab-9cb39d7a8bf4 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-004 | 1.0 Pre-Construction | GP1.7 - Underlying lot & ITP signed off and conforming | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-004
cl:ded39db4-f2a2-4925-b6ab-9cb39d7a8bf4 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-004 | 2.0 Construction | GP2.8 - Subgrade preparation under pavements | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-004
cl:ded39db4-f2a2-4925-b6ab-9cb39d7a8bf4 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-004 | 2.0 Construction | EC2.9 - Surface level check/ and survey pick-up | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-004
cl:ded39db4-f2a2-4925-b6ab-9cb39d7a8bf4 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-004 | 2.0 Construction | EC2.10 - Proof roll subgrade prior to placement of pavement materials | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-004
cl:ded39db4-f2a2-4925-b6ab-9cb39d7a8bf4 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-004 | 2.0 Construction | EC2.11 - Placement of pavement material layers | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-004
cl:ded39db4-f2a2-4925-b6ab-9cb39d7a8bf4 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-004 | 2.0 Construction | EC2.12 - Surface level check/ and survey pick-up | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-004
cl:ded39db4-f2a2-4925-b6ab-9cb39d7a8bf4 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-004 | 3.0 Post Construction | EC3.13 - Works completed and update ITP/ Lot Register/ MDR and close out of GDP | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-004
cl:5c51972b-e8fc-4c9e-b95a-77776cedcf01 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-005 | 1.0 Pre-Construction | GP1.1 - Drawings supplied most current IFC | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-005
cl:5c51972b-e8fc-4c9e-b95a-77776cedcf01 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-005 | 1.0 Pre-Construction | GP1.2 - Management Plans submitted and approved as per PMP | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-005
cl:5c51972b-e8fc-4c9e-b95a-77776cedcf01 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-005 | 1.0 Pre-Construction | GP1.3 - Inspection Test Plan (ITP) submitted and approved | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-005
cl:5c51972b-e8fc-4c9e-b95a-77776cedcf01 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-005 | 1.0 Pre-Construction | GP1.4 - Lot Register/ WBS submitted and approved | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-005
cl:5c51972b-e8fc-4c9e-b95a-77776cedcf01 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-005 | 1.0 Pre-Construction | GP1.5 - Pavement material compliance testing | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-005
cl:5c51972b-e8fc-4c9e-b95a-77776cedcf01 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-005 | 1.0 Pre-Construction | GP1.6 - Stockpile locations | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-005
cl:5c51972b-e8fc-4c9e-b95a-77776cedcf01 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-005 | 1.0 Pre-Construction | GP1.7 - Underlying lot & ITP signed off and conforming | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-005
cl:5c51972b-e8fc-4c9e-b95a-77776cedcf01 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-005 | 2.0 Construction | GP2.8 - Subgrade preparation under pavements | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-005
cl:5c51972b-e8fc-4c9e-b95a-77776cedcf01 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-005 | 2.0 Construction | EC2.9 - Surface level check/ and survey pick-up | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-005
cl:5c51972b-e8fc-4c9e-b95a-77776cedcf01 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-005 | 2.0 Construction | EC2.10 - Proof roll subgrade prior to placement of pavement materials | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-005
cl:5c51972b-e8fc-4c9e-b95a-77776cedcf01 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-005 | 2.0 Construction | EC2.11 - Placement of pavement material layers | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-005
cl:5c51972b-e8fc-4c9e-b95a-77776cedcf01 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-005 | 2.0 Construction | EC2.12 - Surface level check/ and survey pick-up | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-005
cl:5c51972b-e8fc-4c9e-b95a-77776cedcf01 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-005 | 3.0 Post Construction | EC3.13 - Works completed and update ITP/ Lot Register/ MDR and close out of GDP | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-005
cl:cd26b24b-154d-4209-bd7f-c15eaa603b5d | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-006 | 1.0 Pre-Construction | GP1.1 - Drawings supplied most current IFC | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-006
cl:cd26b24b-154d-4209-bd7f-c15eaa603b5d | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-006 | 1.0 Pre-Construction | GP1.2 - Management Plans submitted and approved as per PMP | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-006
cl:cd26b24b-154d-4209-bd7f-c15eaa603b5d | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-006 | 1.0 Pre-Construction | GP1.3 - Inspection Test Plan (ITP) submitted and approved | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-006
cl:cd26b24b-154d-4209-bd7f-c15eaa603b5d | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-006 | 1.0 Pre-Construction | GP1.4 - Lot Register/ WBS submitted and approved | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-006
cl:cd26b24b-154d-4209-bd7f-c15eaa603b5d | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-006 | 1.0 Pre-Construction | GP1.5 - Pavement material compliance testing | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-006
cl:cd26b24b-154d-4209-bd7f-c15eaa603b5d | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-006 | 1.0 Pre-Construction | GP1.6 - Stockpile locations | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-006
cl:cd26b24b-154d-4209-bd7f-c15eaa603b5d | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-006 | 1.0 Pre-Construction | GP1.7 - Underlying lot & ITP signed off and conforming | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-006
cl:cd26b24b-154d-4209-bd7f-c15eaa603b5d | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-006 | 2.0 Construction | GP2.8 - Subgrade preparation under pavements | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-006
cl:cd26b24b-154d-4209-bd7f-c15eaa603b5d | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-006 | 2.0 Construction | EC2.9 - Surface level check/ and survey pick-up | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-006
cl:cd26b24b-154d-4209-bd7f-c15eaa603b5d | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-006 | 2.0 Construction | EC2.10 - Proof roll subgrade prior to placement of pavement materials | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-006
cl:cd26b24b-154d-4209-bd7f-c15eaa603b5d | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-006 | 2.0 Construction | EC2.11 - Placement of pavement material layers | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-006
cl:cd26b24b-154d-4209-bd7f-c15eaa603b5d | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-006 | 2.0 Construction | EC2.12 - Surface level check/ and survey pick-up | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-006
cl:cd26b24b-154d-4209-bd7f-c15eaa603b5d | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-006 | 3.0 Post Construction | EC3.13 - Works completed and update ITP/ Lot Register/ MDR and close out of GDP | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-006
cl:d2221e0e-7fec-4435-b9e9-ce8c59a00f43 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-007 | 1.0 Pre-Construction | GP1.1 - Drawings supplied most current IFC | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-007
cl:d2221e0e-7fec-4435-b9e9-ce8c59a00f43 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-007 | 1.0 Pre-Construction | GP1.2 - Management Plans submitted and approved as per PMP | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-007
cl:d2221e0e-7fec-4435-b9e9-ce8c59a00f43 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-007 | 1.0 Pre-Construction | GP1.3 - Inspection Test Plan (ITP) submitted and approved | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-007
cl:d2221e0e-7fec-4435-b9e9-ce8c59a00f43 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-007 | 1.0 Pre-Construction | GP1.4 - Lot Register/ WBS submitted and approved | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-007
cl:d2221e0e-7fec-4435-b9e9-ce8c59a00f43 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-007 | 1.0 Pre-Construction | GP1.5 - Pavement material compliance testing | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-007
cl:d2221e0e-7fec-4435-b9e9-ce8c59a00f43 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-007 | 1.0 Pre-Construction | GP1.6 - Stockpile locations | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-007
cl:d2221e0e-7fec-4435-b9e9-ce8c59a00f43 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-007 | 1.0 Pre-Construction | GP1.7 - Underlying lot & ITP signed off and conforming | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-007
cl:d2221e0e-7fec-4435-b9e9-ce8c59a00f43 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-007 | 2.0 Construction | GP2.8 - Subgrade preparation under pavements | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-007
cl:d2221e0e-7fec-4435-b9e9-ce8c59a00f43 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-007 | 2.0 Construction | EC2.9 - Surface level check/ and survey pick-up | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-007
cl:d2221e0e-7fec-4435-b9e9-ce8c59a00f43 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-007 | 2.0 Construction | EC2.10 - Proof roll subgrade prior to placement of pavement materials | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-007
cl:d2221e0e-7fec-4435-b9e9-ce8c59a00f43 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-007 | 2.0 Construction | EC2.11 - Placement of pavement material layers | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-007
cl:d2221e0e-7fec-4435-b9e9-ce8c59a00f43 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-007 | 2.0 Construction | EC2.12 - Surface level check/ and survey pick-up | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-007
cl:d2221e0e-7fec-4435-b9e9-ce8c59a00f43 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-007 | 3.0 Post Construction | EC3.13 - Works completed and update ITP/ Lot Register/ MDR and close out of GDP | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-007
cl:8bf7387d-1f7f-49cc-91b0-9d65f23d51ae | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-008 | 1.0 Pre-Construction | GP1.1 - Drawings supplied most current IFC | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-008
cl:8bf7387d-1f7f-49cc-91b0-9d65f23d51ae | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-008 | 1.0 Pre-Construction | GP1.2 - Management Plans submitted and approved as per PMP | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-008
cl:8bf7387d-1f7f-49cc-91b0-9d65f23d51ae | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-008 | 1.0 Pre-Construction | GP1.3 - Inspection Test Plan (ITP) submitted and approved | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-008
cl:8bf7387d-1f7f-49cc-91b0-9d65f23d51ae | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-008 | 1.0 Pre-Construction | GP1.4 - Lot Register/ WBS submitted and approved | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-008
cl:8bf7387d-1f7f-49cc-91b0-9d65f23d51ae | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-008 | 1.0 Pre-Construction | GP1.5 - Pavement material compliance testing | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-008
cl:8bf7387d-1f7f-49cc-91b0-9d65f23d51ae | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-008 | 1.0 Pre-Construction | GP1.6 - Stockpile locations | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-008
cl:8bf7387d-1f7f-49cc-91b0-9d65f23d51ae | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-008 | 1.0 Pre-Construction | GP1.7 - Underlying lot & ITP signed off and conforming | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-008
cl:8bf7387d-1f7f-49cc-91b0-9d65f23d51ae | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-008 | 2.0 Construction | GP2.8 - Subgrade preparation under pavements | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-008
cl:8bf7387d-1f7f-49cc-91b0-9d65f23d51ae | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-008 | 2.0 Construction | EC2.9 - Surface level check/ and survey pick-up | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-008
cl:8bf7387d-1f7f-49cc-91b0-9d65f23d51ae | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-008 | 2.0 Construction | EC2.10 - Proof roll subgrade prior to placement of pavement materials | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-008
cl:8bf7387d-1f7f-49cc-91b0-9d65f23d51ae | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-008 | 2.0 Construction | EC2.11 - Placement of pavement material layers | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-008
cl:8bf7387d-1f7f-49cc-91b0-9d65f23d51ae | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-008 | 2.0 Construction | EC2.12 - Surface level check/ and survey pick-up | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-008
cl:8bf7387d-1f7f-49cc-91b0-9d65f23d51ae | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-008 | 3.0 Post Construction | EC3.13 - Works completed and update ITP/ Lot Register/ MDR and close out of GDP | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-008
cl:4135d0fd-e369-4db5-8b1d-64b555bface3 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-009 | 1.0 Pre-Construction | GP1.1 - Drawings supplied most current IFC | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-009
cl:4135d0fd-e369-4db5-8b1d-64b555bface3 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-009 | 1.0 Pre-Construction | GP1.2 - Management Plans submitted and approved as per PMP | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-009
cl:4135d0fd-e369-4db5-8b1d-64b555bface3 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-009 | 1.0 Pre-Construction | GP1.3 - Inspection Test Plan (ITP) submitted and approved | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-009
cl:4135d0fd-e369-4db5-8b1d-64b555bface3 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-009 | 1.0 Pre-Construction | GP1.4 - Lot Register/ WBS submitted and approved | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-009
cl:4135d0fd-e369-4db5-8b1d-64b555bface3 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-009 | 1.0 Pre-Construction | GP1.5 - Pavement material compliance testing | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-009
cl:4135d0fd-e369-4db5-8b1d-64b555bface3 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-009 | 1.0 Pre-Construction | GP1.6 - Stockpile locations | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-009
cl:4135d0fd-e369-4db5-8b1d-64b555bface3 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-009 | 1.0 Pre-Construction | GP1.7 - Underlying lot & ITP signed off and conforming | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-009
cl:4135d0fd-e369-4db5-8b1d-64b555bface3 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-009 | 2.0 Construction | GP2.8 - Subgrade preparation under pavements | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-009
cl:4135d0fd-e369-4db5-8b1d-64b555bface3 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-009 | 2.0 Construction | EC2.9 - Surface level check/ and survey pick-up | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-009
cl:4135d0fd-e369-4db5-8b1d-64b555bface3 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-009 | 2.0 Construction | EC2.10 - Proof roll subgrade prior to placement of pavement materials | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-009
cl:4135d0fd-e369-4db5-8b1d-64b555bface3 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-009 | 2.0 Construction | EC2.11 - Placement of pavement material layers | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-009
cl:4135d0fd-e369-4db5-8b1d-64b555bface3 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-009 | 2.0 Construction | EC2.12 - Surface level check/ and survey pick-up | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-009
cl:4135d0fd-e369-4db5-8b1d-64b555bface3 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-009 | 3.0 Post Construction | EC3.13 - Works completed and update ITP/ Lot Register/ MDR and close out of GDP | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-009
cl:cd217768-3a25-4510-9a00-4a324a6b7d53 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-010 | 1.0 Pre-Construction | GP1.1 - Drawings supplied most current IFC | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-010
cl:cd217768-3a25-4510-9a00-4a324a6b7d53 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-010 | 1.0 Pre-Construction | GP1.2 - Management Plans submitted and approved as per PMP | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-010
cl:cd217768-3a25-4510-9a00-4a324a6b7d53 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-010 | 1.0 Pre-Construction | GP1.3 - Inspection Test Plan (ITP) submitted and approved | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-010
cl:cd217768-3a25-4510-9a00-4a324a6b7d53 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-010 | 1.0 Pre-Construction | GP1.4 - Lot Register/ WBS submitted and approved | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-010
cl:cd217768-3a25-4510-9a00-4a324a6b7d53 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-010 | 1.0 Pre-Construction | GP1.5 - Pavement material compliance testing | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-010
cl:cd217768-3a25-4510-9a00-4a324a6b7d53 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-010 | 1.0 Pre-Construction | GP1.6 - Stockpile locations | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-010
cl:cd217768-3a25-4510-9a00-4a324a6b7d53 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-010 | 1.0 Pre-Construction | GP1.7 - Underlying lot & ITP signed off and conforming | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-010
cl:cd217768-3a25-4510-9a00-4a324a6b7d53 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-010 | 2.0 Construction | GP2.8 - Subgrade preparation under pavements | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-010
cl:cd217768-3a25-4510-9a00-4a324a6b7d53 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-010 | 2.0 Construction | EC2.9 - Surface level check/ and survey pick-up | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-010
cl:cd217768-3a25-4510-9a00-4a324a6b7d53 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-010 | 2.0 Construction | EC2.10 - Proof roll subgrade prior to placement of pavement materials | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-010
cl:cd217768-3a25-4510-9a00-4a324a6b7d53 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-010 | 2.0 Construction | EC2.11 - Placement of pavement material layers | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-010
cl:cd217768-3a25-4510-9a00-4a324a6b7d53 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-010 | 2.0 Construction | EC2.12 - Surface level check/ and survey pick-up | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-010
cl:cd217768-3a25-4510-9a00-4a324a6b7d53 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-010 | 3.0 Post Construction | EC3.13 - Works completed and update ITP/ Lot Register/ MDR and close out of GDP | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-010
cl:60e52ec7-e21f-4914-989d-dab702e49363 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-011 | 1.0 Pre-Construction | GP1.1 - Drawings supplied most current IFC | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-011
cl:60e52ec7-e21f-4914-989d-dab702e49363 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-011 | 1.0 Pre-Construction | GP1.2 - Management Plans submitted and approved as per PMP | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-011
cl:60e52ec7-e21f-4914-989d-dab702e49363 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-011 | 1.0 Pre-Construction | GP1.3 - Inspection Test Plan (ITP) submitted and approved | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-011
cl:60e52ec7-e21f-4914-989d-dab702e49363 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-011 | 1.0 Pre-Construction | GP1.4 - Lot Register/ WBS submitted and approved | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-011
cl:60e52ec7-e21f-4914-989d-dab702e49363 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-011 | 1.0 Pre-Construction | GP1.5 - Pavement material compliance testing | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-011
cl:60e52ec7-e21f-4914-989d-dab702e49363 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-011 | 1.0 Pre-Construction | GP1.6 - Stockpile locations | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-011
cl:60e52ec7-e21f-4914-989d-dab702e49363 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-011 | 1.0 Pre-Construction | GP1.7 - Underlying lot & ITP signed off and conforming | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-011
cl:60e52ec7-e21f-4914-989d-dab702e49363 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-011 | 2.0 Construction | GP2.8 - Subgrade preparation under pavements | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-011
cl:60e52ec7-e21f-4914-989d-dab702e49363 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-011 | 2.0 Construction | EC2.9 - Surface level check/ and survey pick-up | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-011
cl:60e52ec7-e21f-4914-989d-dab702e49363 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-011 | 2.0 Construction | EC2.10 - Proof roll subgrade prior to placement of pavement materials | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-011
cl:60e52ec7-e21f-4914-989d-dab702e49363 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-011 | 2.0 Construction | EC2.11 - Placement of pavement material layers | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-011
cl:60e52ec7-e21f-4914-989d-dab702e49363 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-011 | 2.0 Construction | EC2.12 - Surface level check/ and survey pick-up | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-011
cl:60e52ec7-e21f-4914-989d-dab702e49363 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-011 | 3.0 Post Construction | EC3.13 - Works completed and update ITP/ Lot Register/ MDR and close out of GDP | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-011
cl:cd8e4393-0349-44c2-b395-3fa06e343cc2 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-012 | 1.0 Pre-Construction | GP1.1 - Drawings supplied most current IFC | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-012
cl:cd8e4393-0349-44c2-b395-3fa06e343cc2 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-012 | 1.0 Pre-Construction | GP1.2 - Management Plans submitted and approved as per PMP | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-012
cl:cd8e4393-0349-44c2-b395-3fa06e343cc2 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-012 | 1.0 Pre-Construction | GP1.3 - Inspection Test Plan (ITP) submitted and approved | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-012
cl:cd8e4393-0349-44c2-b395-3fa06e343cc2 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-012 | 1.0 Pre-Construction | GP1.4 - Lot Register/ WBS submitted and approved | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-012
cl:cd8e4393-0349-44c2-b395-3fa06e343cc2 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-012 | 1.0 Pre-Construction | GP1.5 - Pavement material compliance testing | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-012
cl:cd8e4393-0349-44c2-b395-3fa06e343cc2 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-012 | 1.0 Pre-Construction | GP1.6 - Stockpile locations | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-012
cl:cd8e4393-0349-44c2-b395-3fa06e343cc2 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-012 | 1.0 Pre-Construction | GP1.7 - Underlying lot & ITP signed off and conforming | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-012
cl:cd8e4393-0349-44c2-b395-3fa06e343cc2 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-012 | 2.0 Construction | GP2.8 - Subgrade preparation under pavements | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-012
cl:cd8e4393-0349-44c2-b395-3fa06e343cc2 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-012 | 2.0 Construction | EC2.9 - Surface level check/ and survey pick-up | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-012
cl:cd8e4393-0349-44c2-b395-3fa06e343cc2 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-012 | 2.0 Construction | EC2.10 - Proof roll subgrade prior to placement of pavement materials | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-012
cl:cd8e4393-0349-44c2-b395-3fa06e343cc2 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-012 | 2.0 Construction | EC2.11 - Placement of pavement material layers | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-012
cl:cd8e4393-0349-44c2-b395-3fa06e343cc2 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-012 | 2.0 Construction | EC2.12 - Surface level check/ and survey pick-up | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-012
cl:cd8e4393-0349-44c2-b395-3fa06e343cc2 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-012 | 3.0 Post Construction | EC3.13 - Works completed and update ITP/ Lot Register/ MDR and close out of GDP | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-012
cl:782443f2-4ab3-4828-bbf1-0077f779e483 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-013 | 1.0 Pre-Construction | GP1.1 - Drawings supplied most current IFC | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-013
cl:782443f2-4ab3-4828-bbf1-0077f779e483 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-013 | 1.0 Pre-Construction | GP1.2 - Management Plans submitted and approved as per PMP | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-013
cl:782443f2-4ab3-4828-bbf1-0077f779e483 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-013 | 1.0 Pre-Construction | GP1.3 - Inspection Test Plan (ITP) submitted and approved | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-013
cl:782443f2-4ab3-4828-bbf1-0077f779e483 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-013 | 1.0 Pre-Construction | GP1.4 - Lot Register/ WBS submitted and approved | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-013
cl:782443f2-4ab3-4828-bbf1-0077f779e483 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-013 | 1.0 Pre-Construction | GP1.5 - Pavement material compliance testing | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-013
cl:782443f2-4ab3-4828-bbf1-0077f779e483 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-013 | 1.0 Pre-Construction | GP1.6 - Stockpile locations | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-013
cl:782443f2-4ab3-4828-bbf1-0077f779e483 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-013 | 1.0 Pre-Construction | GP1.7 - Underlying lot & ITP signed off and conforming | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-013
cl:782443f2-4ab3-4828-bbf1-0077f779e483 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-013 | 2.0 Construction | GP2.8 - Subgrade preparation under pavements | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-013
cl:782443f2-4ab3-4828-bbf1-0077f779e483 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-013 | 2.0 Construction | EC2.9 - Surface level check/ and survey pick-up | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-013
cl:782443f2-4ab3-4828-bbf1-0077f779e483 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-013 | 2.0 Construction | EC2.10 - Proof roll subgrade prior to placement of pavement materials | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-013
cl:782443f2-4ab3-4828-bbf1-0077f779e483 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-013 | 2.0 Construction | EC2.11 - Placement of pavement material layers | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-013
cl:782443f2-4ab3-4828-bbf1-0077f779e483 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-013 | 2.0 Construction | EC2.12 - Surface level check/ and survey pick-up | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-013
cl:782443f2-4ab3-4828-bbf1-0077f779e483 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-013 | 3.0 Post Construction | EC3.13 - Works completed and update ITP/ Lot Register/ MDR and close out of GDP | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-013
cl:799a734d-2a84-4459-bef2-728a6f1a1fd0 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-014 | 1.0 Pre-Construction | GP1.1 - Drawings supplied most current IFC | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-014
cl:799a734d-2a84-4459-bef2-728a6f1a1fd0 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-014 | 1.0 Pre-Construction | GP1.2 - Management Plans submitted and approved as per PMP | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-014
cl:799a734d-2a84-4459-bef2-728a6f1a1fd0 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-014 | 1.0 Pre-Construction | GP1.3 - Inspection Test Plan (ITP) submitted and approved | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-014
cl:799a734d-2a84-4459-bef2-728a6f1a1fd0 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-014 | 1.0 Pre-Construction | GP1.4 - Lot Register/ WBS submitted and approved | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-014
cl:799a734d-2a84-4459-bef2-728a6f1a1fd0 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-014 | 1.0 Pre-Construction | GP1.5 - Pavement material compliance testing | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-014
cl:799a734d-2a84-4459-bef2-728a6f1a1fd0 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-014 | 1.0 Pre-Construction | GP1.6 - Stockpile locations | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-014
cl:799a734d-2a84-4459-bef2-728a6f1a1fd0 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-014 | 1.0 Pre-Construction | GP1.7 - Underlying lot & ITP signed off and conforming | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-014
cl:799a734d-2a84-4459-bef2-728a6f1a1fd0 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-014 | 2.0 Construction | GP2.8 - Subgrade preparation under pavements | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-014
cl:799a734d-2a84-4459-bef2-728a6f1a1fd0 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-014 | 2.0 Construction | EC2.9 - Surface level check/ and survey pick-up | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-014
cl:799a734d-2a84-4459-bef2-728a6f1a1fd0 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-014 | 2.0 Construction | EC2.10 - Proof roll subgrade prior to placement of pavement materials | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-014
cl:799a734d-2a84-4459-bef2-728a6f1a1fd0 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-014 | 2.0 Construction | EC2.11 - Placement of pavement material layers | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-014
cl:799a734d-2a84-4459-bef2-728a6f1a1fd0 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-014 | 2.0 Construction | EC2.12 - Surface level check/ and survey pick-up | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-014
cl:799a734d-2a84-4459-bef2-728a6f1a1fd0 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-014 | 3.0 Post Construction | EC3.13 - Works completed and update ITP/ Lot Register/ MDR and close out of GDP | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-014
cl:102244ca-aa1f-4286-9f8d-e192b970b302 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-015 | 1.0 Pre-Construction | GP1.1 - Drawings supplied most current IFC | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-015
cl:102244ca-aa1f-4286-9f8d-e192b970b302 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-015 | 1.0 Pre-Construction | GP1.2 - Management Plans submitted and approved as per PMP | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-015
cl:102244ca-aa1f-4286-9f8d-e192b970b302 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-015 | 1.0 Pre-Construction | GP1.3 - Inspection Test Plan (ITP) submitted and approved | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-015
cl:102244ca-aa1f-4286-9f8d-e192b970b302 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-015 | 1.0 Pre-Construction | GP1.4 - Lot Register/ WBS submitted and approved | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-015
cl:102244ca-aa1f-4286-9f8d-e192b970b302 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-015 | 1.0 Pre-Construction | GP1.5 - Pavement material compliance testing | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-015
cl:102244ca-aa1f-4286-9f8d-e192b970b302 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-015 | 1.0 Pre-Construction | GP1.6 - Stockpile locations | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-015
cl:102244ca-aa1f-4286-9f8d-e192b970b302 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-015 | 1.0 Pre-Construction | GP1.7 - Underlying lot & ITP signed off and conforming | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-015
cl:102244ca-aa1f-4286-9f8d-e192b970b302 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-015 | 2.0 Construction | GP2.8 - Subgrade preparation under pavements | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-015
cl:102244ca-aa1f-4286-9f8d-e192b970b302 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-015 | 2.0 Construction | EC2.9 - Surface level check/ and survey pick-up | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-015
cl:102244ca-aa1f-4286-9f8d-e192b970b302 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-015 | 2.0 Construction | EC2.10 - Proof roll subgrade prior to placement of pavement materials | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-015
cl:102244ca-aa1f-4286-9f8d-e192b970b302 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-015 | 2.0 Construction | EC2.11 - Placement of pavement material layers | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-015
cl:102244ca-aa1f-4286-9f8d-e192b970b302 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-015 | 2.0 Construction | EC2.12 - Surface level check/ and survey pick-up | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-015
cl:102244ca-aa1f-4286-9f8d-e192b970b302 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-015 | 3.0 Post Construction | EC3.13 - Works completed and update ITP/ Lot Register/ MDR and close out of GDP | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-015
cl:2109d4a3-b736-4722-97b9-3f90f38d7a11 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-016 | 1.0 Pre-Construction | GP1.1 - Drawings supplied most current IFC | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-016
cl:2109d4a3-b736-4722-97b9-3f90f38d7a11 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-016 | 1.0 Pre-Construction | GP1.2 - Management Plans submitted and approved as per PMP | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-016
cl:2109d4a3-b736-4722-97b9-3f90f38d7a11 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-016 | 1.0 Pre-Construction | GP1.3 - Inspection Test Plan (ITP) submitted and approved | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-016
cl:2109d4a3-b736-4722-97b9-3f90f38d7a11 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-016 | 1.0 Pre-Construction | GP1.4 - Lot Register/ WBS submitted and approved | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-016
cl:2109d4a3-b736-4722-97b9-3f90f38d7a11 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-016 | 1.0 Pre-Construction | GP1.5 - Pavement material compliance testing | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-016
cl:2109d4a3-b736-4722-97b9-3f90f38d7a11 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-016 | 1.0 Pre-Construction | GP1.6 - Stockpile locations | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-016
cl:2109d4a3-b736-4722-97b9-3f90f38d7a11 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-016 | 1.0 Pre-Construction | GP1.7 - Underlying lot & ITP signed off and conforming | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-016
cl:2109d4a3-b736-4722-97b9-3f90f38d7a11 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-016 | 2.0 Construction | GP2.8 - Subgrade preparation under pavements | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-016
cl:2109d4a3-b736-4722-97b9-3f90f38d7a11 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-016 | 2.0 Construction | EC2.9 - Surface level check/ and survey pick-up | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-016
cl:2109d4a3-b736-4722-97b9-3f90f38d7a11 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-016 | 2.0 Construction | EC2.10 - Proof roll subgrade prior to placement of pavement materials | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-016
cl:2109d4a3-b736-4722-97b9-3f90f38d7a11 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-016 | 2.0 Construction | EC2.11 - Placement of pavement material layers | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-016
cl:2109d4a3-b736-4722-97b9-3f90f38d7a11 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-016 | 2.0 Construction | EC2.12 - Surface level check/ and survey pick-up | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-016
cl:2109d4a3-b736-4722-97b9-3f90f38d7a11 | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-016 | 3.0 Post Construction | EC3.13 - Works completed and update ITP/ Lot Register/ MDR and close out of GDP | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-016
cl:c791f107-4611-4016-950b-83138e3a4a0e | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-017 | 1.0 Pre-Construction | GP1.1 - Drawings supplied most current IFC | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-017
cl:c791f107-4611-4016-950b-83138e3a4a0e | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-017 | 1.0 Pre-Construction | GP1.2 - Management Plans submitted and approved as per PMP | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-017
cl:c791f107-4611-4016-950b-83138e3a4a0e | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-017 | 1.0 Pre-Construction | GP1.3 - Inspection Test Plan (ITP) submitted and approved | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-017
cl:c791f107-4611-4016-950b-83138e3a4a0e | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-017 | 1.0 Pre-Construction | GP1.4 - Lot Register/ WBS submitted and approved | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-017
cl:c791f107-4611-4016-950b-83138e3a4a0e | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-017 | 1.0 Pre-Construction | GP1.5 - Pavement material compliance testing | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-017
cl:c791f107-4611-4016-950b-83138e3a4a0e | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-017 | 1.0 Pre-Construction | GP1.6 - Stockpile locations | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-017
cl:c791f107-4611-4016-950b-83138e3a4a0e | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-017 | 1.0 Pre-Construction | GP1.7 - Underlying lot & ITP signed off and conforming | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-017
cl:c791f107-4611-4016-950b-83138e3a4a0e | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-017 | 2.0 Construction | GP2.8 - Subgrade preparation under pavements | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-017
cl:c791f107-4611-4016-950b-83138e3a4a0e | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-017 | 2.0 Construction | EC2.9 - Surface level check/ and survey pick-up | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-017
cl:c791f107-4611-4016-950b-83138e3a4a0e | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-017 | 2.0 Construction | EC2.10 - Proof roll subgrade prior to placement of pavement materials | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-017
cl:c791f107-4611-4016-950b-83138e3a4a0e | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-017 | 2.0 Construction | EC2.11 - Placement of pavement material layers | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-017
cl:c791f107-4611-4016-950b-83138e3a4a0e | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-017 | 2.0 Construction | EC2.12 - Surface level check/ and survey pick-up | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-017
cl:c791f107-4611-4016-950b-83138e3a4a0e | EVA Copper Mine Project | Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-017 | 3.0 Post Construction | EC3.13 - Works completed and update ITP/ Lot Register/ MDR and close out of GDP | Not started | Open | ITP-009 Unbound Gravel Pavements | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-017
cl:3e96928c-d37e-4e84-bb43-759794579864 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) | MAR-Pre Construction (ITP-000) | Pre-construction | PC1.2 - Lot Register/ WBS | In progress | Open | ITP-000 Pre-construction | AWP-1A | Main Access Road (MAR) | MAR-Pre Construction (ITP-000)
cl:3e96928c-d37e-4e84-bb43-759794579864 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) | MAR-Pre Construction (ITP-000) | Pre-construction | PC1.3 - Construction procedures | In progress | Open | ITP-000 Pre-construction | AWP-1A | Main Access Road (MAR) | MAR-Pre Construction (ITP-000)
cl:3e96928c-d37e-4e84-bb43-759794579864 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) | MAR-Pre Construction (ITP-000) | Pre-construction | PC1.4 - Excavation permit | In progress | Open | ITP-000 Pre-construction | AWP-1A | Main Access Road (MAR) | MAR-Pre Construction (ITP-000)
cl:3e96928c-d37e-4e84-bb43-759794579864 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) | MAR-Pre Construction (ITP-000) | Pre-construction | PC1.5 - Dial before you dig check | In progress | Open | ITP-000 Pre-construction | AWP-1A | Main Access Road (MAR) | MAR-Pre Construction (ITP-000)
cl:3e96928c-d37e-4e84-bb43-759794579864 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) | MAR-Pre Construction (ITP-000) | Pre-construction | PC1.6 - Traffic control plan | In progress | Open | ITP-000 Pre-construction | AWP-1A | Main Access Road (MAR) | MAR-Pre Construction (ITP-000)
cl:3e96928c-d37e-4e84-bb43-759794579864 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) | MAR-Pre Construction (ITP-000) | Pre-construction | PC1.7 - Inspection Test Plan (ITP) submitted and approved | In progress | Open | ITP-000 Pre-construction | AWP-1A | Main Access Road (MAR) | MAR-Pre Construction (ITP-000)
cl:3e96928c-d37e-4e84-bb43-759794579864 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) | MAR-Pre Construction (ITP-000) | Pre-construction | PC1.8 - IFC drawings | In progress | Open | ITP-000 Pre-construction | AWP-1A | Main Access Road (MAR) | MAR-Pre Construction (ITP-000)
cl:3e96928c-d37e-4e84-bb43-759794579864 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) | MAR-Pre Construction (ITP-000) | Pre-construction | PC1.9 - Erosion and sediment control plan | In progress | Open | ITP-000 Pre-construction | AWP-1A | Main Access Road (MAR) | MAR-Pre Construction (ITP-000)
cl:3e96928c-d37e-4e84-bb43-759794579864 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) | MAR-Pre Construction (ITP-000) | Pre-construction | PC1.10 - Approved stockpile locations | Not started | Open | ITP-000 Pre-construction | AWP-1A | Main Access Road (MAR) | MAR-Pre Construction (ITP-000)
cl:3e96928c-d37e-4e84-bb43-759794579864 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) | MAR-Pre Construction (ITP-000) | Pre-construction | PC1.11 - Embankment fill materials | Not started | Open | ITP-000 Pre-construction | AWP-1A | Main Access Road (MAR) | MAR-Pre Construction (ITP-000)
cl:3e96928c-d37e-4e84-bb43-759794579864 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) | MAR-Pre Construction (ITP-000) | Pre-construction | PC1.12 - QA close out | Not started | Open | ITP-000 Pre-construction | AWP-1A | Main Access Road (MAR) | MAR-Pre Construction (ITP-000)
cl:601429a2-74bf-453d-a25e-49aedf0e3811 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | MAR_C&G | Clear & Grub | GC1.1 - Underlying lot & ITP signed off and conforming | Not started |  | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | MAR_C&G
cl:601429a2-74bf-453d-a25e-49aedf0e3811 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | MAR_C&G | Clear & Grub | GC1.2 - Ground Disturbance Permit (GDP) | In progress | Open | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | MAR_C&G
cl:601429a2-74bf-453d-a25e-49aedf0e3811 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | MAR_C&G | Clear & Grub | GC1.3 - Cultural Heritage(CH) Clearance Survey | In progress | Open | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | MAR_C&G
cl:601429a2-74bf-453d-a25e-49aedf0e3811 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | MAR_C&G | Clear & Grub | GC1.4 - GDP survey set out | In progress | Open | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | MAR_C&G
cl:601429a2-74bf-453d-a25e-49aedf0e3811 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | MAR_C&G | Clear & Grub | GC1.5 - Survey of pegs to confirm correct GDP survey set out | In progress | Open | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | MAR_C&G
cl:601429a2-74bf-453d-a25e-49aedf0e3811 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | MAR_C&G | Clear & Grub | GC1.6 - Survey natural surface | In progress | Open | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | MAR_C&G
cl:601429a2-74bf-453d-a25e-49aedf0e3811 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | MAR_C&G | Clear & Grub | GC1.7 - Fauna Spotter Catcher (FSC) Pre-Clearance Survey | In progress | Open | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | MAR_C&G
cl:601429a2-74bf-453d-a25e-49aedf0e3811 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | MAR_C&G | Clear & Grub | GC1.8 - Mandatory GDP Pre-Clearing walk | In progress | Open | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | MAR_C&G
cl:601429a2-74bf-453d-a25e-49aedf0e3811 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | MAR_C&G | Clear & Grub | GC1.9 - Clearing of vegetation | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | MAR_C&G
cl:601429a2-74bf-453d-a25e-49aedf0e3811 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | MAR_C&G | Clear & Grub | GC1.10 - Stockpile Cleared Vegetation | In progress | Open | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | MAR_C&G
cl:601429a2-74bf-453d-a25e-49aedf0e3811 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | MAR_C&G | Clear & Grub | GC1.11 - Erosion and sediment control | In progress | Open | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | MAR_C&G
cl:601429a2-74bf-453d-a25e-49aedf0e3811 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | MAR_C&G | Clear & Grub | GC1.12 - QA close out | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | MAR_C&G
cl:b1e3edb5-2407-40c6-b3ea-2e777d5dfc1f | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-003 CH1190 to CH1690 | Clear & Grub | GC1.1 - Underlying lot & ITP signed off and conforming | Not started |  | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-003 CH1190 to CH1690
cl:b1e3edb5-2407-40c6-b3ea-2e777d5dfc1f | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-003 CH1190 to CH1690 | Clear & Grub | GC1.2 - Ground Disturbance Permit (GDP) | In progress | Open | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-003 CH1190 to CH1690
cl:b1e3edb5-2407-40c6-b3ea-2e777d5dfc1f | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-003 CH1190 to CH1690 | Clear & Grub | GC1.3 - Cultural Heritage(CH) Clearance Survey | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-003 CH1190 to CH1690
cl:b1e3edb5-2407-40c6-b3ea-2e777d5dfc1f | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-003 CH1190 to CH1690 | Clear & Grub | GC1.4 - GDP survey set out | Not started | Requested | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-003 CH1190 to CH1690
cl:b1e3edb5-2407-40c6-b3ea-2e777d5dfc1f | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-003 CH1190 to CH1690 | Clear & Grub | GC1.5 - Survey of pegs to confirm correct GDP survey set out | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-003 CH1190 to CH1690
cl:b1e3edb5-2407-40c6-b3ea-2e777d5dfc1f | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-003 CH1190 to CH1690 | Clear & Grub | GC1.6 - Survey natural surface | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-003 CH1190 to CH1690
cl:b1e3edb5-2407-40c6-b3ea-2e777d5dfc1f | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-003 CH1190 to CH1690 | Clear & Grub | GC1.7 - Fauna Spotter Catcher (FSC) Pre-Clearance Survey | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-003 CH1190 to CH1690
cl:b1e3edb5-2407-40c6-b3ea-2e777d5dfc1f | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-003 CH1190 to CH1690 | Clear & Grub | GC1.8 - Mandatory GDP Pre-Clearing walk | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-003 CH1190 to CH1690
cl:b1e3edb5-2407-40c6-b3ea-2e777d5dfc1f | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-003 CH1190 to CH1690 | Clear & Grub | GC1.9 - Clearing of vegetation | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-003 CH1190 to CH1690
cl:b1e3edb5-2407-40c6-b3ea-2e777d5dfc1f | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-003 CH1190 to CH1690 | Clear & Grub | GC1.10 - Stockpile Cleared Vegetation | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-003 CH1190 to CH1690
cl:b1e3edb5-2407-40c6-b3ea-2e777d5dfc1f | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-003 CH1190 to CH1690 | Clear & Grub | GC1.11 - Erosion and sediment control | Not started | Requested | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-003 CH1190 to CH1690
cl:b1e3edb5-2407-40c6-b3ea-2e777d5dfc1f | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-003 CH1190 to CH1690 | Clear & Grub | GC1.12 - QA close out | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-003 CH1190 to CH1690
cl:b406a2c5-97ef-41e2-9979-075f7c835861 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-004 | Clear & Grub | GC1.1 - Underlying lot & ITP signed off and conforming | Not started |  | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-004
cl:b406a2c5-97ef-41e2-9979-075f7c835861 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-004 | Clear & Grub | GC1.2 - Ground Disturbance Permit (GDP) | In progress | Open | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-004
cl:b406a2c5-97ef-41e2-9979-075f7c835861 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-004 | Clear & Grub | GC1.3 - Cultural Heritage(CH) Clearance Survey | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-004
cl:b406a2c5-97ef-41e2-9979-075f7c835861 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-004 | Clear & Grub | GC1.4 - GDP survey set out | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-004
cl:b406a2c5-97ef-41e2-9979-075f7c835861 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-004 | Clear & Grub | GC1.5 - Survey of pegs to confirm correct GDP survey set out | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-004
cl:b406a2c5-97ef-41e2-9979-075f7c835861 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-004 | Clear & Grub | GC1.6 - Survey natural surface | Not started | Requested | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-004
cl:b406a2c5-97ef-41e2-9979-075f7c835861 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-004 | Clear & Grub | GC1.7 - Fauna Spotter Catcher (FSC) Pre-Clearance Survey | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-004
cl:b406a2c5-97ef-41e2-9979-075f7c835861 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-004 | Clear & Grub | GC1.8 - Mandatory GDP Pre-Clearing walk | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-004
cl:b406a2c5-97ef-41e2-9979-075f7c835861 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-004 | Clear & Grub | GC1.9 - Clearing of vegetation | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-004
cl:b406a2c5-97ef-41e2-9979-075f7c835861 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-004 | Clear & Grub | GC1.10 - Stockpile Cleared Vegetation | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-004
cl:b406a2c5-97ef-41e2-9979-075f7c835861 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-004 | Clear & Grub | GC1.11 - Erosion and sediment control | Not started | Requested | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-004
cl:b406a2c5-97ef-41e2-9979-075f7c835861 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-004 | Clear & Grub | GC1.12 - QA close out | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-004
cl:f1e4f780-fc73-44c7-ae56-24c8a8f51645 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-005 | Clear & Grub | GC1.1 - Underlying lot & ITP signed off and conforming | Not started |  | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-005
cl:f1e4f780-fc73-44c7-ae56-24c8a8f51645 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-005 | Clear & Grub | GC1.2 - Ground Disturbance Permit (GDP) | In progress | Open | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-005
cl:f1e4f780-fc73-44c7-ae56-24c8a8f51645 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-005 | Clear & Grub | GC1.3 - Cultural Heritage(CH) Clearance Survey | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-005
cl:f1e4f780-fc73-44c7-ae56-24c8a8f51645 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-005 | Clear & Grub | GC1.4 - GDP survey set out | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-005
cl:f1e4f780-fc73-44c7-ae56-24c8a8f51645 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-005 | Clear & Grub | GC1.5 - Survey of pegs to confirm correct GDP survey set out | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-005
cl:f1e4f780-fc73-44c7-ae56-24c8a8f51645 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-005 | Clear & Grub | GC1.6 - Survey natural surface | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-005
cl:f1e4f780-fc73-44c7-ae56-24c8a8f51645 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-005 | Clear & Grub | GC1.7 - Fauna Spotter Catcher (FSC) Pre-Clearance Survey | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-005
cl:f1e4f780-fc73-44c7-ae56-24c8a8f51645 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-005 | Clear & Grub | GC1.8 - Mandatory GDP Pre-Clearing walk | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-005
cl:f1e4f780-fc73-44c7-ae56-24c8a8f51645 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-005 | Clear & Grub | GC1.9 - Clearing of vegetation | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-005
cl:f1e4f780-fc73-44c7-ae56-24c8a8f51645 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-005 | Clear & Grub | GC1.10 - Stockpile Cleared Vegetation | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-005
cl:f1e4f780-fc73-44c7-ae56-24c8a8f51645 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-005 | Clear & Grub | GC1.11 - Erosion and sediment control | Not started | Requested | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-005
cl:f1e4f780-fc73-44c7-ae56-24c8a8f51645 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-005 | Clear & Grub | GC1.12 - QA close out | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-005
cl:3721ff4f-dbd9-4750-bcc4-9b5b2922141c | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-006 | Clear & Grub | GC1.1 - Underlying lot & ITP signed off and conforming | Not started |  | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-006
cl:3721ff4f-dbd9-4750-bcc4-9b5b2922141c | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-006 | Clear & Grub | GC1.2 - Ground Disturbance Permit (GDP) | In progress | Open | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-006
cl:3721ff4f-dbd9-4750-bcc4-9b5b2922141c | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-006 | Clear & Grub | GC1.3 - Cultural Heritage(CH) Clearance Survey | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-006
cl:3721ff4f-dbd9-4750-bcc4-9b5b2922141c | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-006 | Clear & Grub | GC1.4 - GDP survey set out | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-006
cl:3721ff4f-dbd9-4750-bcc4-9b5b2922141c | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-006 | Clear & Grub | GC1.5 - Survey of pegs to confirm correct GDP survey set out | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-006
cl:3721ff4f-dbd9-4750-bcc4-9b5b2922141c | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-006 | Clear & Grub | GC1.6 - Survey natural surface | Not started | Requested | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-006
cl:3721ff4f-dbd9-4750-bcc4-9b5b2922141c | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-006 | Clear & Grub | GC1.7 - Fauna Spotter Catcher (FSC) Pre-Clearance Survey | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-006
cl:3721ff4f-dbd9-4750-bcc4-9b5b2922141c | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-006 | Clear & Grub | GC1.8 - Mandatory GDP Pre-Clearing walk | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-006
cl:3721ff4f-dbd9-4750-bcc4-9b5b2922141c | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-006 | Clear & Grub | GC1.9 - Clearing of vegetation | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-006
cl:3721ff4f-dbd9-4750-bcc4-9b5b2922141c | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-006 | Clear & Grub | GC1.10 - Stockpile Cleared Vegetation | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-006
cl:3721ff4f-dbd9-4750-bcc4-9b5b2922141c | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-006 | Clear & Grub | GC1.11 - Erosion and sediment control | Not started | Requested | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-006
cl:3721ff4f-dbd9-4750-bcc4-9b5b2922141c | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-006 | Clear & Grub | GC1.12 - QA close out | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-006
cl:42eb673b-7480-418c-9ff4-deae157d50bf | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-007 | Clear & Grub | GC1.1 - Underlying lot & ITP signed off and conforming | Not started |  | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-007
cl:42eb673b-7480-418c-9ff4-deae157d50bf | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-007 | Clear & Grub | GC1.2 - Ground Disturbance Permit (GDP) | In progress | Open | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-007
cl:42eb673b-7480-418c-9ff4-deae157d50bf | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-007 | Clear & Grub | GC1.3 - Cultural Heritage(CH) Clearance Survey | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-007
cl:42eb673b-7480-418c-9ff4-deae157d50bf | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-007 | Clear & Grub | GC1.4 - GDP survey set out | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-007
cl:42eb673b-7480-418c-9ff4-deae157d50bf | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-007 | Clear & Grub | GC1.5 - Survey of pegs to confirm correct GDP survey set out | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-007
cl:42eb673b-7480-418c-9ff4-deae157d50bf | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-007 | Clear & Grub | GC1.6 - Survey natural surface | Not started | Requested | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-007
cl:42eb673b-7480-418c-9ff4-deae157d50bf | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-007 | Clear & Grub | GC1.7 - Fauna Spotter Catcher (FSC) Pre-Clearance Survey | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-007
cl:42eb673b-7480-418c-9ff4-deae157d50bf | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-007 | Clear & Grub | GC1.8 - Mandatory GDP Pre-Clearing walk | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-007
cl:42eb673b-7480-418c-9ff4-deae157d50bf | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-007 | Clear & Grub | GC1.9 - Clearing of vegetation | Not started | Requested | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-007
cl:42eb673b-7480-418c-9ff4-deae157d50bf | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-007 | Clear & Grub | GC1.10 - Stockpile Cleared Vegetation | Not started | Requested | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-007
cl:42eb673b-7480-418c-9ff4-deae157d50bf | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-007 | Clear & Grub | GC1.11 - Erosion and sediment control | Not started | Requested | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-007
cl:42eb673b-7480-418c-9ff4-deae157d50bf | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-007 | Clear & Grub | GC1.12 - QA close out | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-007
cl:e33db8cf-01ab-4374-ac31-dc1e054bc56e | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-008 | Clear & Grub | GC1.1 - Underlying lot & ITP signed off and conforming | Not started |  | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-008
cl:e33db8cf-01ab-4374-ac31-dc1e054bc56e | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-008 | Clear & Grub | GC1.2 - Ground Disturbance Permit (GDP) | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-008
cl:e33db8cf-01ab-4374-ac31-dc1e054bc56e | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-008 | Clear & Grub | GC1.3 - Cultural Heritage(CH) Clearance Survey | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-008
cl:e33db8cf-01ab-4374-ac31-dc1e054bc56e | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-008 | Clear & Grub | GC1.4 - GDP survey set out | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-008
cl:e33db8cf-01ab-4374-ac31-dc1e054bc56e | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-008 | Clear & Grub | GC1.5 - Survey of pegs to confirm correct GDP survey set out | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-008
cl:e33db8cf-01ab-4374-ac31-dc1e054bc56e | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-008 | Clear & Grub | GC1.6 - Survey natural surface | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-008
cl:e33db8cf-01ab-4374-ac31-dc1e054bc56e | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-008 | Clear & Grub | GC1.7 - Fauna Spotter Catcher (FSC) Pre-Clearance Survey | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-008
cl:e33db8cf-01ab-4374-ac31-dc1e054bc56e | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-008 | Clear & Grub | GC1.8 - Mandatory GDP Pre-Clearing walk | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-008
cl:e33db8cf-01ab-4374-ac31-dc1e054bc56e | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-008 | Clear & Grub | GC1.9 - Clearing of vegetation | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-008
cl:e33db8cf-01ab-4374-ac31-dc1e054bc56e | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-008 | Clear & Grub | GC1.10 - Stockpile Cleared Vegetation | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-008
cl:e33db8cf-01ab-4374-ac31-dc1e054bc56e | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-008 | Clear & Grub | GC1.11 - Erosion and sediment control | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-008
cl:e33db8cf-01ab-4374-ac31-dc1e054bc56e | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-008 | Clear & Grub | GC1.12 - QA close out | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-008
cl:4f77e1ab-6019-4331-8b69-828314b7b4e9 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-009 | Clear & Grub | GC1.1 - Underlying lot & ITP signed off and conforming | Not started |  | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-009
cl:4f77e1ab-6019-4331-8b69-828314b7b4e9 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-009 | Clear & Grub | GC1.2 - Ground Disturbance Permit (GDP) | In progress | Open | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-009
cl:4f77e1ab-6019-4331-8b69-828314b7b4e9 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-009 | Clear & Grub | GC1.3 - Cultural Heritage(CH) Clearance Survey | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-009
cl:4f77e1ab-6019-4331-8b69-828314b7b4e9 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-009 | Clear & Grub | GC1.4 - GDP survey set out | Not started | Requested | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-009
cl:4f77e1ab-6019-4331-8b69-828314b7b4e9 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-009 | Clear & Grub | GC1.5 - Survey of pegs to confirm correct GDP survey set out | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-009
cl:4f77e1ab-6019-4331-8b69-828314b7b4e9 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-009 | Clear & Grub | GC1.6 - Survey natural surface | Not started | Requested | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-009
cl:4f77e1ab-6019-4331-8b69-828314b7b4e9 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-009 | Clear & Grub | GC1.7 - Fauna Spotter Catcher (FSC) Pre-Clearance Survey | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-009
cl:4f77e1ab-6019-4331-8b69-828314b7b4e9 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-009 | Clear & Grub | GC1.8 - Mandatory GDP Pre-Clearing walk | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-009
cl:4f77e1ab-6019-4331-8b69-828314b7b4e9 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-009 | Clear & Grub | GC1.9 - Clearing of vegetation | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-009
cl:4f77e1ab-6019-4331-8b69-828314b7b4e9 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-009 | Clear & Grub | GC1.10 - Stockpile Cleared Vegetation | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-009
cl:4f77e1ab-6019-4331-8b69-828314b7b4e9 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-009 | Clear & Grub | GC1.11 - Erosion and sediment control | Not started | Requested | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-009
cl:4f77e1ab-6019-4331-8b69-828314b7b4e9 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-009 | Clear & Grub | GC1.12 - QA close out | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-009
cl:fab03817-8be3-4a5b-bb6e-7b609a819c21 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-010 | Clear & Grub | GC1.1 - Underlying lot & ITP signed off and conforming | Not started |  | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-010
cl:fab03817-8be3-4a5b-bb6e-7b609a819c21 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-010 | Clear & Grub | GC1.2 - Ground Disturbance Permit (GDP) | In progress | Approved | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-010
cl:fab03817-8be3-4a5b-bb6e-7b609a819c21 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-010 | Clear & Grub | GC1.3 - Cultural Heritage(CH) Clearance Survey | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-010
cl:fab03817-8be3-4a5b-bb6e-7b609a819c21 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-010 | Clear & Grub | GC1.4 - GDP survey set out | Not started | Requested | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-010
cl:fab03817-8be3-4a5b-bb6e-7b609a819c21 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-010 | Clear & Grub | GC1.5 - Survey of pegs to confirm correct GDP survey set out | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-010
cl:fab03817-8be3-4a5b-bb6e-7b609a819c21 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-010 | Clear & Grub | GC1.6 - Survey natural surface | Not started | Requested | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-010
cl:fab03817-8be3-4a5b-bb6e-7b609a819c21 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-010 | Clear & Grub | GC1.7 - Fauna Spotter Catcher (FSC) Pre-Clearance Survey | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-010
cl:fab03817-8be3-4a5b-bb6e-7b609a819c21 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-010 | Clear & Grub | GC1.8 - Mandatory GDP Pre-Clearing walk | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-010
cl:fab03817-8be3-4a5b-bb6e-7b609a819c21 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-010 | Clear & Grub | GC1.9 - Clearing of vegetation | Not started | Requested | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-010
cl:fab03817-8be3-4a5b-bb6e-7b609a819c21 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-010 | Clear & Grub | GC1.10 - Stockpile Cleared Vegetation | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-010
cl:fab03817-8be3-4a5b-bb6e-7b609a819c21 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-010 | Clear & Grub | GC1.11 - Erosion and sediment control | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-010
cl:fab03817-8be3-4a5b-bb6e-7b609a819c21 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-010 | Clear & Grub | GC1.12 - QA close out | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-010
cl:1674f482-e023-4aad-a33a-5e7a7c690be6 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-011 | Clear & Grub | GC1.1 - Underlying lot & ITP signed off and conforming | Not started |  | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-011
cl:1674f482-e023-4aad-a33a-5e7a7c690be6 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-011 | Clear & Grub | GC1.2 - Ground Disturbance Permit (GDP) | In progress | Open | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-011
cl:1674f482-e023-4aad-a33a-5e7a7c690be6 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-011 | Clear & Grub | GC1.3 - Cultural Heritage(CH) Clearance Survey | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-011
cl:1674f482-e023-4aad-a33a-5e7a7c690be6 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-011 | Clear & Grub | GC1.4 - GDP survey set out | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-011
cl:1674f482-e023-4aad-a33a-5e7a7c690be6 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-011 | Clear & Grub | GC1.5 - Survey of pegs to confirm correct GDP survey set out | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-011
cl:1674f482-e023-4aad-a33a-5e7a7c690be6 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-011 | Clear & Grub | GC1.6 - Survey natural surface | Not started | Requested | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-011
cl:1674f482-e023-4aad-a33a-5e7a7c690be6 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-011 | Clear & Grub | GC1.7 - Fauna Spotter Catcher (FSC) Pre-Clearance Survey | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-011
cl:1674f482-e023-4aad-a33a-5e7a7c690be6 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-011 | Clear & Grub | GC1.8 - Mandatory GDP Pre-Clearing walk | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-011
cl:1674f482-e023-4aad-a33a-5e7a7c690be6 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-011 | Clear & Grub | GC1.9 - Clearing of vegetation | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-011
cl:1674f482-e023-4aad-a33a-5e7a7c690be6 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-011 | Clear & Grub | GC1.10 - Stockpile Cleared Vegetation | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-011
cl:1674f482-e023-4aad-a33a-5e7a7c690be6 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-011 | Clear & Grub | GC1.11 - Erosion and sediment control | Not started | Rejected | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-011
cl:1674f482-e023-4aad-a33a-5e7a7c690be6 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-011 | Clear & Grub | GC1.12 - QA close out | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-011
cl:0c070f07-ec98-4b78-97f1-d77ed3524865 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-012 | Clear & Grub | GC1.1 - Underlying lot & ITP signed off and conforming | Not started |  | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-012
cl:0c070f07-ec98-4b78-97f1-d77ed3524865 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-012 | Clear & Grub | GC1.2 - Ground Disturbance Permit (GDP) | In progress | Open | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-012
cl:0c070f07-ec98-4b78-97f1-d77ed3524865 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-012 | Clear & Grub | GC1.3 - Cultural Heritage(CH) Clearance Survey | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-012
cl:0c070f07-ec98-4b78-97f1-d77ed3524865 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-012 | Clear & Grub | GC1.4 - GDP survey set out | Not started | Requested | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-012
cl:0c070f07-ec98-4b78-97f1-d77ed3524865 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-012 | Clear & Grub | GC1.5 - Survey of pegs to confirm correct GDP survey set out | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-012
cl:0c070f07-ec98-4b78-97f1-d77ed3524865 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-012 | Clear & Grub | GC1.6 - Survey natural surface | Not started | Requested | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-012
cl:0c070f07-ec98-4b78-97f1-d77ed3524865 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-012 | Clear & Grub | GC1.7 - Fauna Spotter Catcher (FSC) Pre-Clearance Survey | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-012
cl:0c070f07-ec98-4b78-97f1-d77ed3524865 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-012 | Clear & Grub | GC1.8 - Mandatory GDP Pre-Clearing walk | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-012
cl:0c070f07-ec98-4b78-97f1-d77ed3524865 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-012 | Clear & Grub | GC1.9 - Clearing of vegetation | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-012
cl:0c070f07-ec98-4b78-97f1-d77ed3524865 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-012 | Clear & Grub | GC1.10 - Stockpile Cleared Vegetation | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-012
cl:0c070f07-ec98-4b78-97f1-d77ed3524865 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-012 | Clear & Grub | GC1.11 - Erosion and sediment control | Not started | Requested | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-012
cl:0c070f07-ec98-4b78-97f1-d77ed3524865 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-012 | Clear & Grub | GC1.12 - QA close out | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-012
cl:cd9dfc60-45c5-4236-8353-d2b31a85ac10 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-013 | Clear & Grub | GC1.1 - Underlying lot & ITP signed off and conforming | Not started |  | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-013
cl:cd9dfc60-45c5-4236-8353-d2b31a85ac10 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-013 | Clear & Grub | GC1.2 - Ground Disturbance Permit (GDP) | In progress | Open | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-013
cl:cd9dfc60-45c5-4236-8353-d2b31a85ac10 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-013 | Clear & Grub | GC1.3 - Cultural Heritage(CH) Clearance Survey | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-013
cl:cd9dfc60-45c5-4236-8353-d2b31a85ac10 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-013 | Clear & Grub | GC1.4 - GDP survey set out | Not started | Requested | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-013
cl:cd9dfc60-45c5-4236-8353-d2b31a85ac10 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-013 | Clear & Grub | GC1.5 - Survey of pegs to confirm correct GDP survey set out | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-013
cl:cd9dfc60-45c5-4236-8353-d2b31a85ac10 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-013 | Clear & Grub | GC1.6 - Survey natural surface | Not started | Requested | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-013
cl:cd9dfc60-45c5-4236-8353-d2b31a85ac10 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-013 | Clear & Grub | GC1.7 - Fauna Spotter Catcher (FSC) Pre-Clearance Survey | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-013
cl:cd9dfc60-45c5-4236-8353-d2b31a85ac10 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-013 | Clear & Grub | GC1.8 - Mandatory GDP Pre-Clearing walk | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-013
cl:cd9dfc60-45c5-4236-8353-d2b31a85ac10 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-013 | Clear & Grub | GC1.9 - Clearing of vegetation | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-013
cl:cd9dfc60-45c5-4236-8353-d2b31a85ac10 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-013 | Clear & Grub | GC1.10 - Stockpile Cleared Vegetation | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-013
cl:cd9dfc60-45c5-4236-8353-d2b31a85ac10 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-013 | Clear & Grub | GC1.11 - Erosion and sediment control | Not started | Requested | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-013
cl:cd9dfc60-45c5-4236-8353-d2b31a85ac10 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-013 | Clear & Grub | GC1.12 - QA close out | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-013
cl:0effada5-ca7a-4b98-a8c6-6a9c073614b4 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-014 | Clear & Grub | GC1.1 - Underlying lot & ITP signed off and conforming | Not started |  | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-014
cl:0effada5-ca7a-4b98-a8c6-6a9c073614b4 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-014 | Clear & Grub | GC1.2 - Ground Disturbance Permit (GDP) | In progress | Open | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-014
cl:0effada5-ca7a-4b98-a8c6-6a9c073614b4 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-014 | Clear & Grub | GC1.3 - Cultural Heritage(CH) Clearance Survey | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-014
cl:0effada5-ca7a-4b98-a8c6-6a9c073614b4 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-014 | Clear & Grub | GC1.4 - GDP survey set out | Not started | Requested | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-014
cl:0effada5-ca7a-4b98-a8c6-6a9c073614b4 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-014 | Clear & Grub | GC1.5 - Survey of pegs to confirm correct GDP survey set out | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-014
cl:0effada5-ca7a-4b98-a8c6-6a9c073614b4 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-014 | Clear & Grub | GC1.6 - Survey natural surface | Not started | Requested | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-014
cl:0effada5-ca7a-4b98-a8c6-6a9c073614b4 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-014 | Clear & Grub | GC1.7 - Fauna Spotter Catcher (FSC) Pre-Clearance Survey | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-014
cl:0effada5-ca7a-4b98-a8c6-6a9c073614b4 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-014 | Clear & Grub | GC1.8 - Mandatory GDP Pre-Clearing walk | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-014
cl:0effada5-ca7a-4b98-a8c6-6a9c073614b4 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-014 | Clear & Grub | GC1.9 - Clearing of vegetation | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-014
cl:0effada5-ca7a-4b98-a8c6-6a9c073614b4 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-014 | Clear & Grub | GC1.10 - Stockpile Cleared Vegetation | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-014
cl:0effada5-ca7a-4b98-a8c6-6a9c073614b4 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-014 | Clear & Grub | GC1.11 - Erosion and sediment control | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-014
cl:0effada5-ca7a-4b98-a8c6-6a9c073614b4 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-014 | Clear & Grub | GC1.12 - QA close out | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-014
cl:85d28f37-2ea1-4ea6-b9a0-7d7e71e0a0cf | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-015 | Clear & Grub | GC1.1 - Underlying lot & ITP signed off and conforming | Not started |  | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-015
cl:85d28f37-2ea1-4ea6-b9a0-7d7e71e0a0cf | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-015 | Clear & Grub | GC1.2 - Ground Disturbance Permit (GDP) | In progress | Open | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-015
cl:85d28f37-2ea1-4ea6-b9a0-7d7e71e0a0cf | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-015 | Clear & Grub | GC1.3 - Cultural Heritage(CH) Clearance Survey | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-015
cl:85d28f37-2ea1-4ea6-b9a0-7d7e71e0a0cf | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-015 | Clear & Grub | GC1.4 - GDP survey set out | Not started | Requested | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-015
cl:85d28f37-2ea1-4ea6-b9a0-7d7e71e0a0cf | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-015 | Clear & Grub | GC1.5 - Survey of pegs to confirm correct GDP survey set out | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-015
cl:85d28f37-2ea1-4ea6-b9a0-7d7e71e0a0cf | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-015 | Clear & Grub | GC1.6 - Survey natural surface | Not started | Requested | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-015
cl:85d28f37-2ea1-4ea6-b9a0-7d7e71e0a0cf | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-015 | Clear & Grub | GC1.7 - Fauna Spotter Catcher (FSC) Pre-Clearance Survey | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-015
cl:85d28f37-2ea1-4ea6-b9a0-7d7e71e0a0cf | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-015 | Clear & Grub | GC1.8 - Mandatory GDP Pre-Clearing walk | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-015
cl:85d28f37-2ea1-4ea6-b9a0-7d7e71e0a0cf | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-015 | Clear & Grub | GC1.9 - Clearing of vegetation | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-015
cl:85d28f37-2ea1-4ea6-b9a0-7d7e71e0a0cf | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-015 | Clear & Grub | GC1.10 - Stockpile Cleared Vegetation | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-015
cl:85d28f37-2ea1-4ea6-b9a0-7d7e71e0a0cf | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-015 | Clear & Grub | GC1.11 - Erosion and sediment control | Not started | Requested | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-015
cl:85d28f37-2ea1-4ea6-b9a0-7d7e71e0a0cf | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-015 | Clear & Grub | GC1.12 - QA close out | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-015
cl:a72b0ea7-6afe-4cc0-b964-01304723282a | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-016 | Clear & Grub | GC1.1 - Underlying lot & ITP signed off and conforming | Not started |  | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-016
cl:a72b0ea7-6afe-4cc0-b964-01304723282a | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-016 | Clear & Grub | GC1.2 - Ground Disturbance Permit (GDP) | In progress | Open | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-016
cl:a72b0ea7-6afe-4cc0-b964-01304723282a | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-016 | Clear & Grub | GC1.3 - Cultural Heritage(CH) Clearance Survey | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-016
cl:a72b0ea7-6afe-4cc0-b964-01304723282a | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-016 | Clear & Grub | GC1.4 - GDP survey set out | Not started | Requested | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-016
cl:a72b0ea7-6afe-4cc0-b964-01304723282a | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-016 | Clear & Grub | GC1.5 - Survey of pegs to confirm correct GDP survey set out | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-016
cl:a72b0ea7-6afe-4cc0-b964-01304723282a | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-016 | Clear & Grub | GC1.6 - Survey natural surface | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-016
cl:a72b0ea7-6afe-4cc0-b964-01304723282a | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-016 | Clear & Grub | GC1.7 - Fauna Spotter Catcher (FSC) Pre-Clearance Survey | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-016
cl:a72b0ea7-6afe-4cc0-b964-01304723282a | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-016 | Clear & Grub | GC1.8 - Mandatory GDP Pre-Clearing walk | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-016
cl:a72b0ea7-6afe-4cc0-b964-01304723282a | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-016 | Clear & Grub | GC1.9 - Clearing of vegetation | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-016
cl:a72b0ea7-6afe-4cc0-b964-01304723282a | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-016 | Clear & Grub | GC1.10 - Stockpile Cleared Vegetation | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-016
cl:a72b0ea7-6afe-4cc0-b964-01304723282a | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-016 | Clear & Grub | GC1.11 - Erosion and sediment control | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-016
cl:a72b0ea7-6afe-4cc0-b964-01304723282a | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-016 | Clear & Grub | GC1.12 - QA close out | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-016
cl:051c9f1d-d8c1-464a-bda4-bb415b94b705 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-017 | Clear & Grub | GC1.1 - Underlying lot & ITP signed off and conforming | Not started |  | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-017
cl:051c9f1d-d8c1-464a-bda4-bb415b94b705 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-017 | Clear & Grub | GC1.2 - Ground Disturbance Permit (GDP) | In progress | Open | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-017
cl:051c9f1d-d8c1-464a-bda4-bb415b94b705 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-017 | Clear & Grub | GC1.3 - Cultural Heritage(CH) Clearance Survey | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-017
cl:051c9f1d-d8c1-464a-bda4-bb415b94b705 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-017 | Clear & Grub | GC1.4 - GDP survey set out | Not started | Requested | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-017
cl:051c9f1d-d8c1-464a-bda4-bb415b94b705 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-017 | Clear & Grub | GC1.5 - Survey of pegs to confirm correct GDP survey set out | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-017
cl:051c9f1d-d8c1-464a-bda4-bb415b94b705 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-017 | Clear & Grub | GC1.6 - Survey natural surface | Not started | Requested | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-017
cl:051c9f1d-d8c1-464a-bda4-bb415b94b705 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-017 | Clear & Grub | GC1.7 - Fauna Spotter Catcher (FSC) Pre-Clearance Survey | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-017
cl:051c9f1d-d8c1-464a-bda4-bb415b94b705 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-017 | Clear & Grub | GC1.8 - Mandatory GDP Pre-Clearing walk | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-017
cl:051c9f1d-d8c1-464a-bda4-bb415b94b705 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-017 | Clear & Grub | GC1.9 - Clearing of vegetation | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-017
cl:051c9f1d-d8c1-464a-bda4-bb415b94b705 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-017 | Clear & Grub | GC1.10 - Stockpile Cleared Vegetation | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-017
cl:051c9f1d-d8c1-464a-bda4-bb415b94b705 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-017 | Clear & Grub | GC1.11 - Erosion and sediment control | Not started | Requested | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-017
cl:051c9f1d-d8c1-464a-bda4-bb415b94b705 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-017 | Clear & Grub | GC1.12 - QA close out | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-017
cl:d1b56c72-d57c-4afd-b716-5641d17210b7 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-018 | Clear & Grub | GC1.1 - Underlying lot & ITP signed off and conforming | Not started |  | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-018
cl:d1b56c72-d57c-4afd-b716-5641d17210b7 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-018 | Clear & Grub | GC1.2 - Ground Disturbance Permit (GDP) | In progress | Open | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-018
cl:d1b56c72-d57c-4afd-b716-5641d17210b7 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-018 | Clear & Grub | GC1.3 - Cultural Heritage(CH) Clearance Survey | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-018
cl:d1b56c72-d57c-4afd-b716-5641d17210b7 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-018 | Clear & Grub | GC1.4 - GDP survey set out | Not started | Requested | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-018
cl:d1b56c72-d57c-4afd-b716-5641d17210b7 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-018 | Clear & Grub | GC1.5 - Survey of pegs to confirm correct GDP survey set out | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-018
cl:d1b56c72-d57c-4afd-b716-5641d17210b7 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-018 | Clear & Grub | GC1.6 - Survey natural surface | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-018
cl:d1b56c72-d57c-4afd-b716-5641d17210b7 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-018 | Clear & Grub | GC1.7 - Fauna Spotter Catcher (FSC) Pre-Clearance Survey | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-018
cl:d1b56c72-d57c-4afd-b716-5641d17210b7 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-018 | Clear & Grub | GC1.8 - Mandatory GDP Pre-Clearing walk | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-018
cl:d1b56c72-d57c-4afd-b716-5641d17210b7 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-018 | Clear & Grub | GC1.9 - Clearing of vegetation | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-018
cl:d1b56c72-d57c-4afd-b716-5641d17210b7 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-018 | Clear & Grub | GC1.10 - Stockpile Cleared Vegetation | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-018
cl:d1b56c72-d57c-4afd-b716-5641d17210b7 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-018 | Clear & Grub | GC1.11 - Erosion and sediment control | Not started | Requested | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-018
cl:d1b56c72-d57c-4afd-b716-5641d17210b7 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-018 | Clear & Grub | GC1.12 - QA close out | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Main Access Road (MAR) | MAR-Clear & Grub (ITP-001) | ITP-001 Clear & Grub-MAR-018
cl:dde51873-c2b5-4bea-b167-82115f1a2514 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-002 Topsoil Stripping | MAR_Topsoil Strip | Topsoil Stripping | TS1.1 - Underlying lot & ITP signed off and conforming | N/A |  | ITP-002 Topsoil Stripping | AWP-1A | Main Access Road (MAR) | ITP-002 Topsoil Stripping | MAR_Topsoil Strip
cl:dde51873-c2b5-4bea-b167-82115f1a2514 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-002 Topsoil Stripping | MAR_Topsoil Strip | Topsoil Stripping | TS1.2 - Survey Set out | Not started | Rejected | ITP-002 Topsoil Stripping | AWP-1A | Main Access Road (MAR) | ITP-002 Topsoil Stripping | MAR_Topsoil Strip
cl:dde51873-c2b5-4bea-b167-82115f1a2514 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-002 Topsoil Stripping | MAR_Topsoil Strip | Topsoil Stripping | TS1.3 - Strip topsoil, load & haul to approved stockpile location | In progress | Open | ITP-002 Topsoil Stripping | AWP-1A | Main Access Road (MAR) | ITP-002 Topsoil Stripping | MAR_Topsoil Strip
cl:dde51873-c2b5-4bea-b167-82115f1a2514 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-002 Topsoil Stripping | MAR_Topsoil Strip | Topsoil Stripping | TS1.4 - Topsoil location, destination and quantity catalogued. | In progress | Open | ITP-002 Topsoil Stripping | AWP-1A | Main Access Road (MAR) | ITP-002 Topsoil Stripping | MAR_Topsoil Strip
cl:dde51873-c2b5-4bea-b167-82115f1a2514 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-002 Topsoil Stripping | MAR_Topsoil Strip | Topsoil Stripping | TS1.5 - Surface level check and survey pick-up | Not started | Requested | ITP-002 Topsoil Stripping | AWP-1A | Main Access Road (MAR) | ITP-002 Topsoil Stripping | MAR_Topsoil Strip
cl:dde51873-c2b5-4bea-b167-82115f1a2514 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-002 Topsoil Stripping | MAR_Topsoil Strip | Topsoil Stripping | TS1.6 - QA close out | Not started | Open | ITP-002 Topsoil Stripping | AWP-1A | Main Access Road (MAR) | ITP-002 Topsoil Stripping | MAR_Topsoil Strip
cl:8317e097-e36c-4786-909c-0676614fd2f0 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-002 | Topsoil Stripping | TS1.1 - Underlying lot & ITP signed off and conforming | Not started |  | ITP-002 Topsoil Stripping | AWP-1A | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-002
cl:8317e097-e36c-4786-909c-0676614fd2f0 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-002 | Topsoil Stripping | TS1.2 - Survey Set out | Not started | Open | ITP-002 Topsoil Stripping | AWP-1A | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-002
cl:8317e097-e36c-4786-909c-0676614fd2f0 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-002 | Topsoil Stripping | TS1.3 - Strip topsoil, load & haul to approved stockpile location | Not started | Open | ITP-002 Topsoil Stripping | AWP-1A | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-002
cl:8317e097-e36c-4786-909c-0676614fd2f0 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-002 | Topsoil Stripping | TS1.4 - Topsoil location, destination and quantity catalogued. | Not started | Open | ITP-002 Topsoil Stripping | AWP-1A | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-002
cl:8317e097-e36c-4786-909c-0676614fd2f0 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-002 | Topsoil Stripping | TS1.5 - Surface level check and survey pick-up | Not started | Open | ITP-002 Topsoil Stripping | AWP-1A | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-002
cl:8317e097-e36c-4786-909c-0676614fd2f0 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-002 | Topsoil Stripping | TS1.6 - QA close out | Not started | Open | ITP-002 Topsoil Stripping | AWP-1A | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-002
cl:2bda6402-ac23-4e73-be43-03c89c1031bc | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-003 | Topsoil Stripping | TS1.1 - Underlying lot & ITP signed off and conforming | Not started |  | ITP-002 Topsoil Stripping | AWP-1A | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-003
cl:2bda6402-ac23-4e73-be43-03c89c1031bc | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-003 | Topsoil Stripping | TS1.2 - Survey Set out | Not started | Open | ITP-002 Topsoil Stripping | AWP-1A | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-003
cl:2bda6402-ac23-4e73-be43-03c89c1031bc | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-003 | Topsoil Stripping | TS1.3 - Strip topsoil, load & haul to approved stockpile location | Not started | Open | ITP-002 Topsoil Stripping | AWP-1A | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-003
cl:2bda6402-ac23-4e73-be43-03c89c1031bc | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-003 | Topsoil Stripping | TS1.4 - Topsoil location, destination and quantity catalogued. | Not started | Open | ITP-002 Topsoil Stripping | AWP-1A | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-003
cl:2bda6402-ac23-4e73-be43-03c89c1031bc | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-003 | Topsoil Stripping | TS1.5 - Surface level check and survey pick-up | Not started | Open | ITP-002 Topsoil Stripping | AWP-1A | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-003
cl:2bda6402-ac23-4e73-be43-03c89c1031bc | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-003 | Topsoil Stripping | TS1.6 - QA close out | Not started | Open | ITP-002 Topsoil Stripping | AWP-1A | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-003
cl:4f8d8ae6-4e61-4fe7-85fd-c923ce0a90b4 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-004 | Topsoil Stripping | TS1.1 - Underlying lot & ITP signed off and conforming | Not started |  | ITP-002 Topsoil Stripping | AWP-1A | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-004
cl:4f8d8ae6-4e61-4fe7-85fd-c923ce0a90b4 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-004 | Topsoil Stripping | TS1.2 - Survey Set out | Not started | Open | ITP-002 Topsoil Stripping | AWP-1A | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-004
cl:4f8d8ae6-4e61-4fe7-85fd-c923ce0a90b4 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-004 | Topsoil Stripping | TS1.3 - Strip topsoil, load & haul to approved stockpile location | Not started | Open | ITP-002 Topsoil Stripping | AWP-1A | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-004
cl:4f8d8ae6-4e61-4fe7-85fd-c923ce0a90b4 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-004 | Topsoil Stripping | TS1.4 - Topsoil location, destination and quantity catalogued. | Not started | Open | ITP-002 Topsoil Stripping | AWP-1A | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-004
cl:4f8d8ae6-4e61-4fe7-85fd-c923ce0a90b4 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-004 | Topsoil Stripping | TS1.5 - Surface level check and survey pick-up | Not started | Open | ITP-002 Topsoil Stripping | AWP-1A | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-004
cl:4f8d8ae6-4e61-4fe7-85fd-c923ce0a90b4 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-004 | Topsoil Stripping | TS1.6 - QA close out | Not started | Open | ITP-002 Topsoil Stripping | AWP-1A | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-004
cl:bde07827-3e74-4f9c-ac80-4be5ff966004 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-005 | Topsoil Stripping | TS1.1 - Underlying lot & ITP signed off and conforming | Not started |  | ITP-002 Topsoil Stripping | AWP-1A | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-005
cl:bde07827-3e74-4f9c-ac80-4be5ff966004 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-005 | Topsoil Stripping | TS1.2 - Survey Set out | Not started | Open | ITP-002 Topsoil Stripping | AWP-1A | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-005
cl:bde07827-3e74-4f9c-ac80-4be5ff966004 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-005 | Topsoil Stripping | TS1.3 - Strip topsoil, load & haul to approved stockpile location | Not started | Open | ITP-002 Topsoil Stripping | AWP-1A | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-005
cl:bde07827-3e74-4f9c-ac80-4be5ff966004 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-005 | Topsoil Stripping | TS1.4 - Topsoil location, destination and quantity catalogued. | Not started | Open | ITP-002 Topsoil Stripping | AWP-1A | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-005
cl:bde07827-3e74-4f9c-ac80-4be5ff966004 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-005 | Topsoil Stripping | TS1.5 - Surface level check and survey pick-up | Not started | Open | ITP-002 Topsoil Stripping | AWP-1A | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-005
cl:bde07827-3e74-4f9c-ac80-4be5ff966004 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-005 | Topsoil Stripping | TS1.6 - QA close out | Not started | Open | ITP-002 Topsoil Stripping | AWP-1A | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-005
cl:098b6870-213c-4c04-b4b8-a728d554843f | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-006 | Topsoil Stripping | TS1.1 - Underlying lot & ITP signed off and conforming | Not started |  | ITP-002 Topsoil Stripping | AWP-1A | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-006
cl:098b6870-213c-4c04-b4b8-a728d554843f | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-006 | Topsoil Stripping | TS1.2 - Survey Set out | Not started | Open | ITP-002 Topsoil Stripping | AWP-1A | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-006
cl:098b6870-213c-4c04-b4b8-a728d554843f | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-006 | Topsoil Stripping | TS1.3 - Strip topsoil, load & haul to approved stockpile location | Not started | Open | ITP-002 Topsoil Stripping | AWP-1A | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-006
cl:098b6870-213c-4c04-b4b8-a728d554843f | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-006 | Topsoil Stripping | TS1.4 - Topsoil location, destination and quantity catalogued. | Not started | Open | ITP-002 Topsoil Stripping | AWP-1A | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-006
cl:098b6870-213c-4c04-b4b8-a728d554843f | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-006 | Topsoil Stripping | TS1.5 - Surface level check and survey pick-up | Not started | Open | ITP-002 Topsoil Stripping | AWP-1A | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-006
cl:098b6870-213c-4c04-b4b8-a728d554843f | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-006 | Topsoil Stripping | TS1.6 - QA close out | Not started | Open | ITP-002 Topsoil Stripping | AWP-1A | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-006
cl:cd3ee4c6-dc94-48db-95dd-856df713ad3b | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-007 | Topsoil Stripping | TS1.1 - Underlying lot & ITP signed off and conforming | Not started |  | ITP-002 Topsoil Stripping | AWP-1A | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-007
cl:cd3ee4c6-dc94-48db-95dd-856df713ad3b | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-007 | Topsoil Stripping | TS1.2 - Survey Set out | Not started | Open | ITP-002 Topsoil Stripping | AWP-1A | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-007
cl:cd3ee4c6-dc94-48db-95dd-856df713ad3b | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-007 | Topsoil Stripping | TS1.3 - Strip topsoil, load & haul to approved stockpile location | Not started | Open | ITP-002 Topsoil Stripping | AWP-1A | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-007
cl:cd3ee4c6-dc94-48db-95dd-856df713ad3b | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-007 | Topsoil Stripping | TS1.4 - Topsoil location, destination and quantity catalogued. | Not started | Open | ITP-002 Topsoil Stripping | AWP-1A | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-007
cl:cd3ee4c6-dc94-48db-95dd-856df713ad3b | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-007 | Topsoil Stripping | TS1.5 - Surface level check and survey pick-up | Not started | Open | ITP-002 Topsoil Stripping | AWP-1A | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-007
cl:cd3ee4c6-dc94-48db-95dd-856df713ad3b | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-007 | Topsoil Stripping | TS1.6 - QA close out | Not started | Open | ITP-002 Topsoil Stripping | AWP-1A | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-007
cl:890586ba-3090-4dbf-9301-4c42131e6071 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-008 | Topsoil Stripping | TS1.1 - Underlying lot & ITP signed off and conforming | Not started |  | ITP-002 Topsoil Stripping | AWP-1A | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-008
cl:890586ba-3090-4dbf-9301-4c42131e6071 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-008 | Topsoil Stripping | TS1.2 - Survey Set out | Not started | Open | ITP-002 Topsoil Stripping | AWP-1A | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-008
cl:890586ba-3090-4dbf-9301-4c42131e6071 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-008 | Topsoil Stripping | TS1.3 - Strip topsoil, load & haul to approved stockpile location | Not started | Open | ITP-002 Topsoil Stripping | AWP-1A | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-008
cl:890586ba-3090-4dbf-9301-4c42131e6071 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-008 | Topsoil Stripping | TS1.4 - Topsoil location, destination and quantity catalogued. | Not started | Open | ITP-002 Topsoil Stripping | AWP-1A | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-008
cl:890586ba-3090-4dbf-9301-4c42131e6071 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-008 | Topsoil Stripping | TS1.5 - Surface level check and survey pick-up | Not started | Open | ITP-002 Topsoil Stripping | AWP-1A | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-008
cl:890586ba-3090-4dbf-9301-4c42131e6071 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-008 | Topsoil Stripping | TS1.6 - QA close out | Not started | Open | ITP-002 Topsoil Stripping | AWP-1A | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-008
cl:8d598f4d-ceaa-45b0-8440-e65f16dd4594 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-009 | Topsoil Stripping | TS1.1 - Underlying lot & ITP signed off and conforming | Not started |  | ITP-002 Topsoil Stripping | AWP-1A | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-009
cl:8d598f4d-ceaa-45b0-8440-e65f16dd4594 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-009 | Topsoil Stripping | TS1.2 - Survey Set out | Not started | Open | ITP-002 Topsoil Stripping | AWP-1A | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-009
cl:8d598f4d-ceaa-45b0-8440-e65f16dd4594 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-009 | Topsoil Stripping | TS1.3 - Strip topsoil, load & haul to approved stockpile location | Not started | Open | ITP-002 Topsoil Stripping | AWP-1A | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-009
cl:8d598f4d-ceaa-45b0-8440-e65f16dd4594 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-009 | Topsoil Stripping | TS1.4 - Topsoil location, destination and quantity catalogued. | Not started | Open | ITP-002 Topsoil Stripping | AWP-1A | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-009
cl:8d598f4d-ceaa-45b0-8440-e65f16dd4594 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-009 | Topsoil Stripping | TS1.5 - Surface level check and survey pick-up | Not started | Open | ITP-002 Topsoil Stripping | AWP-1A | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-009
cl:8d598f4d-ceaa-45b0-8440-e65f16dd4594 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-009 | Topsoil Stripping | TS1.6 - QA close out | Not started | Open | ITP-002 Topsoil Stripping | AWP-1A | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-009
cl:5e887b02-4eff-475f-88ec-1338b04019ac | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-010 | Topsoil Stripping | TS1.1 - Underlying lot & ITP signed off and conforming | Not started |  | ITP-002 Topsoil Stripping | AWP-1A | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-010
cl:5e887b02-4eff-475f-88ec-1338b04019ac | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-010 | Topsoil Stripping | TS1.2 - Survey Set out | Not started | Open | ITP-002 Topsoil Stripping | AWP-1A | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-010
cl:5e887b02-4eff-475f-88ec-1338b04019ac | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-010 | Topsoil Stripping | TS1.3 - Strip topsoil, load & haul to approved stockpile location | Not started | Open | ITP-002 Topsoil Stripping | AWP-1A | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-010
cl:5e887b02-4eff-475f-88ec-1338b04019ac | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-010 | Topsoil Stripping | TS1.4 - Topsoil location, destination and quantity catalogued. | Not started | Open | ITP-002 Topsoil Stripping | AWP-1A | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-010
cl:5e887b02-4eff-475f-88ec-1338b04019ac | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-010 | Topsoil Stripping | TS1.5 - Surface level check and survey pick-up | Not started | Open | ITP-002 Topsoil Stripping | AWP-1A | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-010
cl:5e887b02-4eff-475f-88ec-1338b04019ac | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-010 | Topsoil Stripping | TS1.6 - QA close out | Not started | Open | ITP-002 Topsoil Stripping | AWP-1A | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-010
cl:e7d0f507-3ba6-4741-888e-5b243a81ba4a | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-011 | Topsoil Stripping | TS1.1 - Underlying lot & ITP signed off and conforming | Not started |  | ITP-002 Topsoil Stripping | AWP-1A | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-011
cl:e7d0f507-3ba6-4741-888e-5b243a81ba4a | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-011 | Topsoil Stripping | TS1.2 - Survey Set out | Not started | Open | ITP-002 Topsoil Stripping | AWP-1A | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-011
cl:e7d0f507-3ba6-4741-888e-5b243a81ba4a | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-011 | Topsoil Stripping | TS1.3 - Strip topsoil, load & haul to approved stockpile location | Not started | Open | ITP-002 Topsoil Stripping | AWP-1A | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-011
cl:e7d0f507-3ba6-4741-888e-5b243a81ba4a | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-011 | Topsoil Stripping | TS1.4 - Topsoil location, destination and quantity catalogued. | Not started | Open | ITP-002 Topsoil Stripping | AWP-1A | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-011
cl:e7d0f507-3ba6-4741-888e-5b243a81ba4a | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-011 | Topsoil Stripping | TS1.5 - Surface level check and survey pick-up | Not started | Open | ITP-002 Topsoil Stripping | AWP-1A | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-011
cl:e7d0f507-3ba6-4741-888e-5b243a81ba4a | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-011 | Topsoil Stripping | TS1.6 - QA close out | Not started | Open | ITP-002 Topsoil Stripping | AWP-1A | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-011
cl:498fa056-53e6-4adf-836a-db22afe3c868 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-012 | Topsoil Stripping | TS1.1 - Underlying lot & ITP signed off and conforming | Not started |  | ITP-002 Topsoil Stripping | AWP-1A | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-012
cl:498fa056-53e6-4adf-836a-db22afe3c868 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-012 | Topsoil Stripping | TS1.2 - Survey Set out | Not started | Open | ITP-002 Topsoil Stripping | AWP-1A | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-012
cl:498fa056-53e6-4adf-836a-db22afe3c868 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-012 | Topsoil Stripping | TS1.3 - Strip topsoil, load & haul to approved stockpile location | Not started | Open | ITP-002 Topsoil Stripping | AWP-1A | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-012
cl:498fa056-53e6-4adf-836a-db22afe3c868 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-012 | Topsoil Stripping | TS1.4 - Topsoil location, destination and quantity catalogued. | Not started | Open | ITP-002 Topsoil Stripping | AWP-1A | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-012
cl:498fa056-53e6-4adf-836a-db22afe3c868 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-012 | Topsoil Stripping | TS1.5 - Surface level check and survey pick-up | Not started | Open | ITP-002 Topsoil Stripping | AWP-1A | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-012
cl:498fa056-53e6-4adf-836a-db22afe3c868 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-012 | Topsoil Stripping | TS1.6 - QA close out | Not started | Open | ITP-002 Topsoil Stripping | AWP-1A | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-012
cl:22b7127d-bfb7-4635-a01d-3fdec26b5a48 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-013 | Topsoil Stripping | TS1.1 - Underlying lot & ITP signed off and conforming | Not started |  | ITP-002 Topsoil Stripping | AWP-1A | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-013
cl:22b7127d-bfb7-4635-a01d-3fdec26b5a48 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-013 | Topsoil Stripping | TS1.2 - Survey Set out | Not started | Open | ITP-002 Topsoil Stripping | AWP-1A | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-013
cl:22b7127d-bfb7-4635-a01d-3fdec26b5a48 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-013 | Topsoil Stripping | TS1.3 - Strip topsoil, load & haul to approved stockpile location | Not started | Open | ITP-002 Topsoil Stripping | AWP-1A | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-013
cl:22b7127d-bfb7-4635-a01d-3fdec26b5a48 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-013 | Topsoil Stripping | TS1.4 - Topsoil location, destination and quantity catalogued. | Not started | Open | ITP-002 Topsoil Stripping | AWP-1A | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-013
cl:22b7127d-bfb7-4635-a01d-3fdec26b5a48 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-013 | Topsoil Stripping | TS1.5 - Surface level check and survey pick-up | Not started | Open | ITP-002 Topsoil Stripping | AWP-1A | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-013
cl:22b7127d-bfb7-4635-a01d-3fdec26b5a48 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-013 | Topsoil Stripping | TS1.6 - QA close out | Not started | Open | ITP-002 Topsoil Stripping | AWP-1A | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-013
cl:c05fcc86-fd09-437f-b001-613dac76b03b | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-014 | Topsoil Stripping | TS1.1 - Underlying lot & ITP signed off and conforming | Not started |  | ITP-002 Topsoil Stripping | AWP-1A | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-014
cl:c05fcc86-fd09-437f-b001-613dac76b03b | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-014 | Topsoil Stripping | TS1.2 - Survey Set out | Not started | Open | ITP-002 Topsoil Stripping | AWP-1A | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-014
cl:c05fcc86-fd09-437f-b001-613dac76b03b | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-014 | Topsoil Stripping | TS1.3 - Strip topsoil, load & haul to approved stockpile location | Not started | Open | ITP-002 Topsoil Stripping | AWP-1A | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-014
cl:c05fcc86-fd09-437f-b001-613dac76b03b | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-014 | Topsoil Stripping | TS1.4 - Topsoil location, destination and quantity catalogued. | Not started | Open | ITP-002 Topsoil Stripping | AWP-1A | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-014
cl:c05fcc86-fd09-437f-b001-613dac76b03b | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-014 | Topsoil Stripping | TS1.5 - Surface level check and survey pick-up | Not started | Open | ITP-002 Topsoil Stripping | AWP-1A | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-014
cl:c05fcc86-fd09-437f-b001-613dac76b03b | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-014 | Topsoil Stripping | TS1.6 - QA close out | Not started | Open | ITP-002 Topsoil Stripping | AWP-1A | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-014
cl:a48b81b5-f8da-4249-a9ba-d92a49debb55 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-015 | Topsoil Stripping | TS1.1 - Underlying lot & ITP signed off and conforming | Not started |  | ITP-002 Topsoil Stripping | AWP-1A | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-015
cl:a48b81b5-f8da-4249-a9ba-d92a49debb55 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-015 | Topsoil Stripping | TS1.2 - Survey Set out | Not started | Open | ITP-002 Topsoil Stripping | AWP-1A | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-015
cl:a48b81b5-f8da-4249-a9ba-d92a49debb55 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-015 | Topsoil Stripping | TS1.3 - Strip topsoil, load & haul to approved stockpile location | Not started | Open | ITP-002 Topsoil Stripping | AWP-1A | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-015
cl:a48b81b5-f8da-4249-a9ba-d92a49debb55 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-015 | Topsoil Stripping | TS1.4 - Topsoil location, destination and quantity catalogued. | Not started | Open | ITP-002 Topsoil Stripping | AWP-1A | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-015
cl:a48b81b5-f8da-4249-a9ba-d92a49debb55 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-015 | Topsoil Stripping | TS1.5 - Surface level check and survey pick-up | Not started | Open | ITP-002 Topsoil Stripping | AWP-1A | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-015
cl:a48b81b5-f8da-4249-a9ba-d92a49debb55 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-015 | Topsoil Stripping | TS1.6 - QA close out | Not started | Open | ITP-002 Topsoil Stripping | AWP-1A | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-015
cl:6f3bc2e6-9027-42ca-b7d0-ad548a1c31db | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-016 | Topsoil Stripping | TS1.1 - Underlying lot & ITP signed off and conforming | Not started |  | ITP-002 Topsoil Stripping | AWP-1A | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-016
cl:6f3bc2e6-9027-42ca-b7d0-ad548a1c31db | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-016 | Topsoil Stripping | TS1.2 - Survey Set out | Not started | Open | ITP-002 Topsoil Stripping | AWP-1A | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-016
cl:6f3bc2e6-9027-42ca-b7d0-ad548a1c31db | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-016 | Topsoil Stripping | TS1.3 - Strip topsoil, load & haul to approved stockpile location | Not started | Open | ITP-002 Topsoil Stripping | AWP-1A | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-016
cl:6f3bc2e6-9027-42ca-b7d0-ad548a1c31db | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-016 | Topsoil Stripping | TS1.4 - Topsoil location, destination and quantity catalogued. | Not started | Open | ITP-002 Topsoil Stripping | AWP-1A | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-016
cl:6f3bc2e6-9027-42ca-b7d0-ad548a1c31db | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-016 | Topsoil Stripping | TS1.5 - Surface level check and survey pick-up | Not started | Open | ITP-002 Topsoil Stripping | AWP-1A | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-016
cl:6f3bc2e6-9027-42ca-b7d0-ad548a1c31db | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-016 | Topsoil Stripping | TS1.6 - QA close out | Not started | Open | ITP-002 Topsoil Stripping | AWP-1A | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-016
cl:32331128-a4ca-4fcd-ad45-79bcd149cee1 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-017 | Topsoil Stripping | TS1.1 - Underlying lot & ITP signed off and conforming | Not started |  | ITP-002 Topsoil Stripping | AWP-1A | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-017
cl:32331128-a4ca-4fcd-ad45-79bcd149cee1 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-017 | Topsoil Stripping | TS1.2 - Survey Set out | Not started | Open | ITP-002 Topsoil Stripping | AWP-1A | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-017
cl:32331128-a4ca-4fcd-ad45-79bcd149cee1 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-017 | Topsoil Stripping | TS1.3 - Strip topsoil, load & haul to approved stockpile location | Not started | Open | ITP-002 Topsoil Stripping | AWP-1A | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-017
cl:32331128-a4ca-4fcd-ad45-79bcd149cee1 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-017 | Topsoil Stripping | TS1.4 - Topsoil location, destination and quantity catalogued. | Not started | Open | ITP-002 Topsoil Stripping | AWP-1A | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-017
cl:32331128-a4ca-4fcd-ad45-79bcd149cee1 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-017 | Topsoil Stripping | TS1.5 - Surface level check and survey pick-up | Not started | Open | ITP-002 Topsoil Stripping | AWP-1A | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-017
cl:32331128-a4ca-4fcd-ad45-79bcd149cee1 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-017 | Topsoil Stripping | TS1.6 - QA close out | Not started | Open | ITP-002 Topsoil Stripping | AWP-1A | Main Access Road (MAR) | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-MAR-017
cl:5faede6d-452d-473d-9d83-053657020978 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-001 CH192 to CH265 | Subgrade/Foundation Preparation | SP.1.1 - Underlying lot & ITP signed off and conforming | N/A |  | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-001 CH192 to CH265
cl:5faede6d-452d-473d-9d83-053657020978 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-001 CH192 to CH265 | Subgrade/Foundation Preparation | SP.1.2 - Embankment fill material | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-001 CH192 to CH265
cl:5faede6d-452d-473d-9d83-053657020978 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-001 CH192 to CH265 | Subgrade/Foundation Preparation | SP.1.3 - Survey Set out | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-001 CH192 to CH265
cl:5faede6d-452d-473d-9d83-053657020978 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-001 CH192 to CH265 | Subgrade/Foundation Preparation | SP.1.4 - Removal and replacement of unsuitable material | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-001 CH192 to CH265
cl:5faede6d-452d-473d-9d83-053657020978 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-001 CH192 to CH265 | Subgrade/Foundation Preparation | SP.1.5 - Subgrade/Foundation preparation | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-001 CH192 to CH265
cl:5faede6d-452d-473d-9d83-053657020978 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-001 CH192 to CH265 | Subgrade/Foundation Preparation | SP.1.6 - Trim subgrade | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-001 CH192 to CH265
cl:5faede6d-452d-473d-9d83-053657020978 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-001 CH192 to CH265 | Subgrade/Foundation Preparation | SP.1.7 - Proof rolling | In progress | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-001 CH192 to CH265
cl:5faede6d-452d-473d-9d83-053657020978 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-001 CH192 to CH265 | Subgrade/Foundation Preparation | SP.1.8 - Surface level check and survey pick-up | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-001 CH192 to CH265
cl:5faede6d-452d-473d-9d83-053657020978 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-001 CH192 to CH265 | Subgrade/Foundation Preparation | SP.1.9 - QA close out | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-001 CH192 to CH265
cl:dd921dce-64f6-4358-8403-c80cd07d931b | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-002 | Subgrade/Foundation Preparation | SP.1.1 - Underlying lot & ITP signed off and conforming | N/A |  | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-002
cl:dd921dce-64f6-4358-8403-c80cd07d931b | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-002 | Subgrade/Foundation Preparation | SP.1.2 - Embankment fill material | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-002
cl:dd921dce-64f6-4358-8403-c80cd07d931b | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-002 | Subgrade/Foundation Preparation | SP.1.3 - Survey Set out | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-002
cl:dd921dce-64f6-4358-8403-c80cd07d931b | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-002 | Subgrade/Foundation Preparation | SP.1.4 - Removal and replacement of unsuitable material | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-002
cl:dd921dce-64f6-4358-8403-c80cd07d931b | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-002 | Subgrade/Foundation Preparation | SP.1.5 - Subgrade/Foundation preparation | Not started | Requested | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-002
cl:dd921dce-64f6-4358-8403-c80cd07d931b | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-002 | Subgrade/Foundation Preparation | SP.1.6 - Trim subgrade | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-002
cl:dd921dce-64f6-4358-8403-c80cd07d931b | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-002 | Subgrade/Foundation Preparation | SP.1.7 - Proof rolling | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-002
cl:dd921dce-64f6-4358-8403-c80cd07d931b | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-002 | Subgrade/Foundation Preparation | SP.1.8 - Surface level check and survey pick-up | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-002
cl:dd921dce-64f6-4358-8403-c80cd07d931b | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-002 | Subgrade/Foundation Preparation | SP.1.9 - QA close out | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-002
cl:dfd435c3-f0c0-4b2f-b551-fc40fbf36967 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-003 | Subgrade/Foundation Preparation | SP.1.1 - Underlying lot & ITP signed off and conforming | Not started |  | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-003
cl:dfd435c3-f0c0-4b2f-b551-fc40fbf36967 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-003 | Subgrade/Foundation Preparation | SP.1.2 - Embankment fill material | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-003
cl:dfd435c3-f0c0-4b2f-b551-fc40fbf36967 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-003 | Subgrade/Foundation Preparation | SP.1.3 - Survey Set out | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-003
cl:dfd435c3-f0c0-4b2f-b551-fc40fbf36967 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-003 | Subgrade/Foundation Preparation | SP.1.4 - Removal and replacement of unsuitable material | N/A | Requested | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-003
cl:dfd435c3-f0c0-4b2f-b551-fc40fbf36967 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-003 | Subgrade/Foundation Preparation | SP.1.5 - Subgrade/Foundation preparation | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-003
cl:dfd435c3-f0c0-4b2f-b551-fc40fbf36967 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-003 | Subgrade/Foundation Preparation | SP.1.6 - Trim subgrade | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-003
cl:dfd435c3-f0c0-4b2f-b551-fc40fbf36967 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-003 | Subgrade/Foundation Preparation | SP.1.7 - Proof rolling | Not started | Approved | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-003
cl:dfd435c3-f0c0-4b2f-b551-fc40fbf36967 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-003 | Subgrade/Foundation Preparation | SP.1.8 - Surface level check and survey pick-up | Not started | Rejected | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-003
cl:dfd435c3-f0c0-4b2f-b551-fc40fbf36967 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-003 | Subgrade/Foundation Preparation | SP.1.9 - QA close out | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-003
cl:daf905da-f777-4c54-a111-92e86f98d02b | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-004 CH732 to CH1050 | Subgrade/Foundation Preparation | SP.1.1 - Underlying lot & ITP signed off and conforming | N/A |  | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-004 CH732 to CH1050
cl:daf905da-f777-4c54-a111-92e86f98d02b | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-004 CH732 to CH1050 | Subgrade/Foundation Preparation | SP.1.2 - Embankment fill material | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-004 CH732 to CH1050
cl:daf905da-f777-4c54-a111-92e86f98d02b | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-004 CH732 to CH1050 | Subgrade/Foundation Preparation | SP.1.3 - Survey Set out | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-004 CH732 to CH1050
cl:daf905da-f777-4c54-a111-92e86f98d02b | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-004 CH732 to CH1050 | Subgrade/Foundation Preparation | SP.1.4 - Removal and replacement of unsuitable material | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-004 CH732 to CH1050
cl:daf905da-f777-4c54-a111-92e86f98d02b | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-004 CH732 to CH1050 | Subgrade/Foundation Preparation | SP.1.5 - Subgrade/Foundation preparation | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-004 CH732 to CH1050
cl:daf905da-f777-4c54-a111-92e86f98d02b | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-004 CH732 to CH1050 | Subgrade/Foundation Preparation | SP.1.6 - Trim subgrade | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-004 CH732 to CH1050
cl:daf905da-f777-4c54-a111-92e86f98d02b | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-004 CH732 to CH1050 | Subgrade/Foundation Preparation | SP.1.7 - Proof rolling | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-004 CH732 to CH1050
cl:daf905da-f777-4c54-a111-92e86f98d02b | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-004 CH732 to CH1050 | Subgrade/Foundation Preparation | SP.1.8 - Surface level check and survey pick-up | Not started | Rejected | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-004 CH732 to CH1050
cl:daf905da-f777-4c54-a111-92e86f98d02b | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-004 CH732 to CH1050 | Subgrade/Foundation Preparation | SP.1.9 - QA close out | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-004 CH732 to CH1050
cl:8c4c1f20-301a-4faa-82ae-3a21fb30320b | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-005 | Subgrade/Foundation Preparation | SP.1.1 - Underlying lot & ITP signed off and conforming | Not started |  | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-005
cl:8c4c1f20-301a-4faa-82ae-3a21fb30320b | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-005 | Subgrade/Foundation Preparation | SP.1.2 - Embankment fill material | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-005
cl:8c4c1f20-301a-4faa-82ae-3a21fb30320b | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-005 | Subgrade/Foundation Preparation | SP.1.3 - Survey Set out | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-005
cl:8c4c1f20-301a-4faa-82ae-3a21fb30320b | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-005 | Subgrade/Foundation Preparation | SP.1.4 - Removal and replacement of unsuitable material | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-005
cl:8c4c1f20-301a-4faa-82ae-3a21fb30320b | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-005 | Subgrade/Foundation Preparation | SP.1.5 - Subgrade/Foundation preparation | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-005
cl:8c4c1f20-301a-4faa-82ae-3a21fb30320b | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-005 | Subgrade/Foundation Preparation | SP.1.6 - Trim subgrade | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-005
cl:8c4c1f20-301a-4faa-82ae-3a21fb30320b | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-005 | Subgrade/Foundation Preparation | SP.1.7 - Proof rolling | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-005
cl:8c4c1f20-301a-4faa-82ae-3a21fb30320b | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-005 | Subgrade/Foundation Preparation | SP.1.8 - Surface level check and survey pick-up | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-005
cl:8c4c1f20-301a-4faa-82ae-3a21fb30320b | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-005 | Subgrade/Foundation Preparation | SP.1.9 - QA close out | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-005
cl:8a8758d6-38e3-445b-b0be-0ebd2130b1a2 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-006 | Subgrade/Foundation Preparation | SP.1.1 - Underlying lot & ITP signed off and conforming | Not started |  | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-006
cl:8a8758d6-38e3-445b-b0be-0ebd2130b1a2 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-006 | Subgrade/Foundation Preparation | SP.1.2 - Embankment fill material | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-006
cl:8a8758d6-38e3-445b-b0be-0ebd2130b1a2 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-006 | Subgrade/Foundation Preparation | SP.1.3 - Survey Set out | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-006
cl:8a8758d6-38e3-445b-b0be-0ebd2130b1a2 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-006 | Subgrade/Foundation Preparation | SP.1.4 - Removal and replacement of unsuitable material | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-006
cl:8a8758d6-38e3-445b-b0be-0ebd2130b1a2 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-006 | Subgrade/Foundation Preparation | SP.1.5 - Subgrade/Foundation preparation | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-006
cl:8a8758d6-38e3-445b-b0be-0ebd2130b1a2 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-006 | Subgrade/Foundation Preparation | SP.1.6 - Trim subgrade | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-006
cl:8a8758d6-38e3-445b-b0be-0ebd2130b1a2 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-006 | Subgrade/Foundation Preparation | SP.1.7 - Proof rolling | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-006
cl:8a8758d6-38e3-445b-b0be-0ebd2130b1a2 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-006 | Subgrade/Foundation Preparation | SP.1.8 - Surface level check and survey pick-up | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-006
cl:8a8758d6-38e3-445b-b0be-0ebd2130b1a2 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-006 | Subgrade/Foundation Preparation | SP.1.9 - QA close out | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-006
cl:c3a4e319-d9e4-4abf-8ab0-310e329d8dfb | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-007 | Subgrade/Foundation Preparation | SP.1.1 - Underlying lot & ITP signed off and conforming | Not started |  | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-007
cl:c3a4e319-d9e4-4abf-8ab0-310e329d8dfb | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-007 | Subgrade/Foundation Preparation | SP.1.2 - Embankment fill material | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-007
cl:c3a4e319-d9e4-4abf-8ab0-310e329d8dfb | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-007 | Subgrade/Foundation Preparation | SP.1.3 - Survey Set out | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-007
cl:c3a4e319-d9e4-4abf-8ab0-310e329d8dfb | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-007 | Subgrade/Foundation Preparation | SP.1.4 - Removal and replacement of unsuitable material | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-007
cl:c3a4e319-d9e4-4abf-8ab0-310e329d8dfb | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-007 | Subgrade/Foundation Preparation | SP.1.5 - Subgrade/Foundation preparation | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-007
cl:c3a4e319-d9e4-4abf-8ab0-310e329d8dfb | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-007 | Subgrade/Foundation Preparation | SP.1.6 - Trim subgrade | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-007
cl:c3a4e319-d9e4-4abf-8ab0-310e329d8dfb | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-007 | Subgrade/Foundation Preparation | SP.1.7 - Proof rolling | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-007
cl:c3a4e319-d9e4-4abf-8ab0-310e329d8dfb | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-007 | Subgrade/Foundation Preparation | SP.1.8 - Surface level check and survey pick-up | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-007
cl:c3a4e319-d9e4-4abf-8ab0-310e329d8dfb | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-007 | Subgrade/Foundation Preparation | SP.1.9 - QA close out | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-007
cl:e2120dd6-877c-4aca-ab5a-3f38539ba750 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-008 | Subgrade/Foundation Preparation | SP.1.1 - Underlying lot & ITP signed off and conforming | Not started |  | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-008
cl:e2120dd6-877c-4aca-ab5a-3f38539ba750 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-008 | Subgrade/Foundation Preparation | SP.1.2 - Embankment fill material | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-008
cl:e2120dd6-877c-4aca-ab5a-3f38539ba750 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-008 | Subgrade/Foundation Preparation | SP.1.3 - Survey Set out | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-008
cl:e2120dd6-877c-4aca-ab5a-3f38539ba750 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-008 | Subgrade/Foundation Preparation | SP.1.4 - Removal and replacement of unsuitable material | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-008
cl:e2120dd6-877c-4aca-ab5a-3f38539ba750 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-008 | Subgrade/Foundation Preparation | SP.1.5 - Subgrade/Foundation preparation | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-008
cl:e2120dd6-877c-4aca-ab5a-3f38539ba750 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-008 | Subgrade/Foundation Preparation | SP.1.6 - Trim subgrade | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-008
cl:e2120dd6-877c-4aca-ab5a-3f38539ba750 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-008 | Subgrade/Foundation Preparation | SP.1.7 - Proof rolling | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-008
cl:e2120dd6-877c-4aca-ab5a-3f38539ba750 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-008 | Subgrade/Foundation Preparation | SP.1.8 - Surface level check and survey pick-up | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-008
cl:e2120dd6-877c-4aca-ab5a-3f38539ba750 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-008 | Subgrade/Foundation Preparation | SP.1.9 - QA close out | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-008
cl:9e446b56-5b71-414c-b651-c19177db5219 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-009 | Subgrade/Foundation Preparation | SP.1.1 - Underlying lot & ITP signed off and conforming | Not started |  | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-009
cl:9e446b56-5b71-414c-b651-c19177db5219 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-009 | Subgrade/Foundation Preparation | SP.1.2 - Embankment fill material | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-009
cl:9e446b56-5b71-414c-b651-c19177db5219 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-009 | Subgrade/Foundation Preparation | SP.1.3 - Survey Set out | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-009
cl:9e446b56-5b71-414c-b651-c19177db5219 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-009 | Subgrade/Foundation Preparation | SP.1.4 - Removal and replacement of unsuitable material | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-009
cl:9e446b56-5b71-414c-b651-c19177db5219 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-009 | Subgrade/Foundation Preparation | SP.1.5 - Subgrade/Foundation preparation | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-009
cl:9e446b56-5b71-414c-b651-c19177db5219 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-009 | Subgrade/Foundation Preparation | SP.1.6 - Trim subgrade | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-009
cl:9e446b56-5b71-414c-b651-c19177db5219 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-009 | Subgrade/Foundation Preparation | SP.1.7 - Proof rolling | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-009
cl:9e446b56-5b71-414c-b651-c19177db5219 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-009 | Subgrade/Foundation Preparation | SP.1.8 - Surface level check and survey pick-up | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-009
cl:9e446b56-5b71-414c-b651-c19177db5219 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-009 | Subgrade/Foundation Preparation | SP.1.9 - QA close out | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-009
cl:0c6af84e-b3e2-4e3d-8a46-279a72951b31 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-010 | Subgrade/Foundation Preparation | SP.1.1 - Underlying lot & ITP signed off and conforming | Not started |  | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-010
cl:0c6af84e-b3e2-4e3d-8a46-279a72951b31 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-010 | Subgrade/Foundation Preparation | SP.1.2 - Embankment fill material | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-010
cl:0c6af84e-b3e2-4e3d-8a46-279a72951b31 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-010 | Subgrade/Foundation Preparation | SP.1.3 - Survey Set out | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-010
cl:0c6af84e-b3e2-4e3d-8a46-279a72951b31 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-010 | Subgrade/Foundation Preparation | SP.1.4 - Removal and replacement of unsuitable material | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-010
cl:0c6af84e-b3e2-4e3d-8a46-279a72951b31 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-010 | Subgrade/Foundation Preparation | SP.1.5 - Subgrade/Foundation preparation | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-010
cl:0c6af84e-b3e2-4e3d-8a46-279a72951b31 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-010 | Subgrade/Foundation Preparation | SP.1.6 - Trim subgrade | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-010
cl:0c6af84e-b3e2-4e3d-8a46-279a72951b31 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-010 | Subgrade/Foundation Preparation | SP.1.7 - Proof rolling | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-010
cl:0c6af84e-b3e2-4e3d-8a46-279a72951b31 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-010 | Subgrade/Foundation Preparation | SP.1.8 - Surface level check and survey pick-up | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-010
cl:0c6af84e-b3e2-4e3d-8a46-279a72951b31 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-010 | Subgrade/Foundation Preparation | SP.1.9 - QA close out | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-010
cl:16292971-d3e5-4945-b32c-5b65fd414654 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-011 | Subgrade/Foundation Preparation | SP.1.1 - Underlying lot & ITP signed off and conforming | Not started |  | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-011
cl:16292971-d3e5-4945-b32c-5b65fd414654 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-011 | Subgrade/Foundation Preparation | SP.1.2 - Embankment fill material | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-011
cl:16292971-d3e5-4945-b32c-5b65fd414654 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-011 | Subgrade/Foundation Preparation | SP.1.3 - Survey Set out | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-011
cl:16292971-d3e5-4945-b32c-5b65fd414654 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-011 | Subgrade/Foundation Preparation | SP.1.4 - Removal and replacement of unsuitable material | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-011
cl:16292971-d3e5-4945-b32c-5b65fd414654 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-011 | Subgrade/Foundation Preparation | SP.1.5 - Subgrade/Foundation preparation | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-011
cl:16292971-d3e5-4945-b32c-5b65fd414654 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-011 | Subgrade/Foundation Preparation | SP.1.6 - Trim subgrade | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-011
cl:16292971-d3e5-4945-b32c-5b65fd414654 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-011 | Subgrade/Foundation Preparation | SP.1.7 - Proof rolling | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-011
cl:16292971-d3e5-4945-b32c-5b65fd414654 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-011 | Subgrade/Foundation Preparation | SP.1.8 - Surface level check and survey pick-up | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-011
cl:16292971-d3e5-4945-b32c-5b65fd414654 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-011 | Subgrade/Foundation Preparation | SP.1.9 - QA close out | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-011
cl:e7554a30-6ea5-4fa1-b698-ffcee940ce63 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-012 | Subgrade/Foundation Preparation | SP.1.1 - Underlying lot & ITP signed off and conforming | Not started |  | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-012
cl:e7554a30-6ea5-4fa1-b698-ffcee940ce63 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-012 | Subgrade/Foundation Preparation | SP.1.2 - Embankment fill material | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-012
cl:e7554a30-6ea5-4fa1-b698-ffcee940ce63 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-012 | Subgrade/Foundation Preparation | SP.1.3 - Survey Set out | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-012
cl:e7554a30-6ea5-4fa1-b698-ffcee940ce63 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-012 | Subgrade/Foundation Preparation | SP.1.4 - Removal and replacement of unsuitable material | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-012
cl:e7554a30-6ea5-4fa1-b698-ffcee940ce63 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-012 | Subgrade/Foundation Preparation | SP.1.5 - Subgrade/Foundation preparation | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-012
cl:e7554a30-6ea5-4fa1-b698-ffcee940ce63 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-012 | Subgrade/Foundation Preparation | SP.1.6 - Trim subgrade | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-012
cl:e7554a30-6ea5-4fa1-b698-ffcee940ce63 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-012 | Subgrade/Foundation Preparation | SP.1.7 - Proof rolling | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-012
cl:e7554a30-6ea5-4fa1-b698-ffcee940ce63 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-012 | Subgrade/Foundation Preparation | SP.1.8 - Surface level check and survey pick-up | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-012
cl:e7554a30-6ea5-4fa1-b698-ffcee940ce63 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-012 | Subgrade/Foundation Preparation | SP.1.9 - QA close out | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-012
cl:12f8a2b1-6bca-4b5a-97fd-c5bfbfceb333 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-013 | Subgrade/Foundation Preparation | SP.1.1 - Underlying lot & ITP signed off and conforming | Not started |  | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-013
cl:12f8a2b1-6bca-4b5a-97fd-c5bfbfceb333 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-013 | Subgrade/Foundation Preparation | SP.1.2 - Embankment fill material | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-013
cl:12f8a2b1-6bca-4b5a-97fd-c5bfbfceb333 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-013 | Subgrade/Foundation Preparation | SP.1.3 - Survey Set out | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-013
cl:12f8a2b1-6bca-4b5a-97fd-c5bfbfceb333 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-013 | Subgrade/Foundation Preparation | SP.1.4 - Removal and replacement of unsuitable material | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-013
cl:12f8a2b1-6bca-4b5a-97fd-c5bfbfceb333 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-013 | Subgrade/Foundation Preparation | SP.1.5 - Subgrade/Foundation preparation | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-013
cl:12f8a2b1-6bca-4b5a-97fd-c5bfbfceb333 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-013 | Subgrade/Foundation Preparation | SP.1.6 - Trim subgrade | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-013
cl:12f8a2b1-6bca-4b5a-97fd-c5bfbfceb333 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-013 | Subgrade/Foundation Preparation | SP.1.7 - Proof rolling | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-013
cl:12f8a2b1-6bca-4b5a-97fd-c5bfbfceb333 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-013 | Subgrade/Foundation Preparation | SP.1.8 - Surface level check and survey pick-up | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-013
cl:12f8a2b1-6bca-4b5a-97fd-c5bfbfceb333 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-013 | Subgrade/Foundation Preparation | SP.1.9 - QA close out | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-013
cl:87ce06d5-dab0-4bd6-a3eb-f91859570e1c | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-014 | Subgrade/Foundation Preparation | SP.1.1 - Underlying lot & ITP signed off and conforming | Not started |  | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-014
cl:87ce06d5-dab0-4bd6-a3eb-f91859570e1c | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-014 | Subgrade/Foundation Preparation | SP.1.2 - Embankment fill material | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-014
cl:87ce06d5-dab0-4bd6-a3eb-f91859570e1c | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-014 | Subgrade/Foundation Preparation | SP.1.3 - Survey Set out | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-014
cl:87ce06d5-dab0-4bd6-a3eb-f91859570e1c | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-014 | Subgrade/Foundation Preparation | SP.1.4 - Removal and replacement of unsuitable material | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-014
cl:87ce06d5-dab0-4bd6-a3eb-f91859570e1c | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-014 | Subgrade/Foundation Preparation | SP.1.5 - Subgrade/Foundation preparation | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-014
cl:87ce06d5-dab0-4bd6-a3eb-f91859570e1c | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-014 | Subgrade/Foundation Preparation | SP.1.6 - Trim subgrade | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-014
cl:87ce06d5-dab0-4bd6-a3eb-f91859570e1c | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-014 | Subgrade/Foundation Preparation | SP.1.7 - Proof rolling | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-014
cl:87ce06d5-dab0-4bd6-a3eb-f91859570e1c | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-014 | Subgrade/Foundation Preparation | SP.1.8 - Surface level check and survey pick-up | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-014
cl:87ce06d5-dab0-4bd6-a3eb-f91859570e1c | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-014 | Subgrade/Foundation Preparation | SP.1.9 - QA close out | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-014
cl:87a11975-8cc5-4b0b-bf54-fa5714dfd860 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-015 | Subgrade/Foundation Preparation | SP.1.1 - Underlying lot & ITP signed off and conforming | Not started |  | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-015
cl:87a11975-8cc5-4b0b-bf54-fa5714dfd860 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-015 | Subgrade/Foundation Preparation | SP.1.2 - Embankment fill material | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-015
cl:87a11975-8cc5-4b0b-bf54-fa5714dfd860 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-015 | Subgrade/Foundation Preparation | SP.1.3 - Survey Set out | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-015
cl:87a11975-8cc5-4b0b-bf54-fa5714dfd860 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-015 | Subgrade/Foundation Preparation | SP.1.4 - Removal and replacement of unsuitable material | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-015
cl:87a11975-8cc5-4b0b-bf54-fa5714dfd860 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-015 | Subgrade/Foundation Preparation | SP.1.5 - Subgrade/Foundation preparation | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-015
cl:87a11975-8cc5-4b0b-bf54-fa5714dfd860 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-015 | Subgrade/Foundation Preparation | SP.1.6 - Trim subgrade | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-015
cl:87a11975-8cc5-4b0b-bf54-fa5714dfd860 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-015 | Subgrade/Foundation Preparation | SP.1.7 - Proof rolling | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-015
cl:87a11975-8cc5-4b0b-bf54-fa5714dfd860 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-015 | Subgrade/Foundation Preparation | SP.1.8 - Surface level check and survey pick-up | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-015
cl:87a11975-8cc5-4b0b-bf54-fa5714dfd860 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-015 | Subgrade/Foundation Preparation | SP.1.9 - QA close out | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-015
cl:f93d9f8c-c94e-4d09-a0e1-8375e5292ea7 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-016 | Subgrade/Foundation Preparation | SP.1.1 - Underlying lot & ITP signed off and conforming | Not started |  | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-016
cl:f93d9f8c-c94e-4d09-a0e1-8375e5292ea7 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-016 | Subgrade/Foundation Preparation | SP.1.2 - Embankment fill material | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-016
cl:f93d9f8c-c94e-4d09-a0e1-8375e5292ea7 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-016 | Subgrade/Foundation Preparation | SP.1.3 - Survey Set out | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-016
cl:f93d9f8c-c94e-4d09-a0e1-8375e5292ea7 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-016 | Subgrade/Foundation Preparation | SP.1.4 - Removal and replacement of unsuitable material | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-016
cl:f93d9f8c-c94e-4d09-a0e1-8375e5292ea7 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-016 | Subgrade/Foundation Preparation | SP.1.5 - Subgrade/Foundation preparation | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-016
cl:f93d9f8c-c94e-4d09-a0e1-8375e5292ea7 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-016 | Subgrade/Foundation Preparation | SP.1.6 - Trim subgrade | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-016
cl:f93d9f8c-c94e-4d09-a0e1-8375e5292ea7 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-016 | Subgrade/Foundation Preparation | SP.1.7 - Proof rolling | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-016
cl:f93d9f8c-c94e-4d09-a0e1-8375e5292ea7 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-016 | Subgrade/Foundation Preparation | SP.1.8 - Surface level check and survey pick-up | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-016
cl:f93d9f8c-c94e-4d09-a0e1-8375e5292ea7 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-016 | Subgrade/Foundation Preparation | SP.1.9 - QA close out | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-016
cl:0a32f121-dd2d-4b60-8836-1f780e04db42 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-017 | Subgrade/Foundation Preparation | SP.1.1 - Underlying lot & ITP signed off and conforming | Not started |  | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-017
cl:0a32f121-dd2d-4b60-8836-1f780e04db42 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-017 | Subgrade/Foundation Preparation | SP.1.2 - Embankment fill material | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-017
cl:0a32f121-dd2d-4b60-8836-1f780e04db42 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-017 | Subgrade/Foundation Preparation | SP.1.3 - Survey Set out | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-017
cl:0a32f121-dd2d-4b60-8836-1f780e04db42 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-017 | Subgrade/Foundation Preparation | SP.1.4 - Removal and replacement of unsuitable material | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-017
cl:0a32f121-dd2d-4b60-8836-1f780e04db42 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-017 | Subgrade/Foundation Preparation | SP.1.5 - Subgrade/Foundation preparation | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-017
cl:0a32f121-dd2d-4b60-8836-1f780e04db42 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-017 | Subgrade/Foundation Preparation | SP.1.6 - Trim subgrade | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-017
cl:0a32f121-dd2d-4b60-8836-1f780e04db42 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-017 | Subgrade/Foundation Preparation | SP.1.7 - Proof rolling | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-017
cl:0a32f121-dd2d-4b60-8836-1f780e04db42 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-017 | Subgrade/Foundation Preparation | SP.1.8 - Surface level check and survey pick-up | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-017
cl:0a32f121-dd2d-4b60-8836-1f780e04db42 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-017 | Subgrade/Foundation Preparation | SP.1.9 - QA close out | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Main Access Road (MAR) | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-MAR-017
cl:eb4aa3a2-74b6-428c-9b75-1400a2dcc6c5 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-001 | 1.0 Pre-Construction | RCP1.1 - Drawings supplied most current IFC | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-001
cl:eb4aa3a2-74b6-428c-9b75-1400a2dcc6c5 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-001 | 1.0 Pre-Construction | RCP1.2 - Define RCP ID | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-001
cl:eb4aa3a2-74b6-428c-9b75-1400a2dcc6c5 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-001 | 1.0 Pre-Construction | RCP1.3 - Lot Register/ WBS submitted and approved | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-001
cl:eb4aa3a2-74b6-428c-9b75-1400a2dcc6c5 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-001 | 1.0 Pre-Construction | RCP1.4 - Underlying lot & ITP signed off and conforming | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-001
cl:eb4aa3a2-74b6-428c-9b75-1400a2dcc6c5 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-001 | 1.0 Pre-Construction | RCP1.5 - Certificate of compliance for RCP Material | N/A | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-001
cl:eb4aa3a2-74b6-428c-9b75-1400a2dcc6c5 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-001 | 1.0 Pre-Construction | RCP1.6 - Inspect reinforced pipe culverts for damage | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-001
cl:eb4aa3a2-74b6-428c-9b75-1400a2dcc6c5 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-001 | 2.0 Construction | RCP2.7 - Trench Excavation | In progress | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-001
cl:eb4aa3a2-74b6-428c-9b75-1400a2dcc6c5 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-001 | 2.0 Construction | RCP2.8 - Bedding | In progress | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-001
cl:eb4aa3a2-74b6-428c-9b75-1400a2dcc6c5 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-001 | 2.0 Construction | RCP2.9 - RCP Installation | In progress | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-001
cl:eb4aa3a2-74b6-428c-9b75-1400a2dcc6c5 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-001 | 2.0 Construction | RCP2.10 - Backfilling of culvert | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-001
cl:eb4aa3a2-74b6-428c-9b75-1400a2dcc6c5 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-001 | 2.0 Construction | RCP2.11 - End Treatment – Headwall & Wingwalls (Reinforcement) | In progress | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-001
cl:eb4aa3a2-74b6-428c-9b75-1400a2dcc6c5 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-001 | 2.0 Construction | RCP2.12 - End Treatment – Headwall & Wingwalls (Formwork) | N/A | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-001
cl:eb4aa3a2-74b6-428c-9b75-1400a2dcc6c5 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-001 | 2.0 Construction | RCP2.13 - End Treatment – Headwall & Wingwalls (Concrete) | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-001
cl:eb4aa3a2-74b6-428c-9b75-1400a2dcc6c5 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-001 | 2.0 Construction | RCP2.14 - Rock Protection | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-001
cl:eb4aa3a2-74b6-428c-9b75-1400a2dcc6c5 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-001 | 3.0 Post Construction | RCP3.15 - Works completed and update ITP/ Lot Register/ MDR and close out of GDP | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-001
cl:72b6fca6-3997-40a7-ad4f-c5f8f57abcac | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-002 | 1.0 Pre-Construction | RCP1.1 - Drawings supplied most current IFC | N/A | Approved | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-002
cl:72b6fca6-3997-40a7-ad4f-c5f8f57abcac | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-002 | 1.0 Pre-Construction | RCP1.2 - Define RCP ID | N/A | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-002
cl:72b6fca6-3997-40a7-ad4f-c5f8f57abcac | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-002 | 1.0 Pre-Construction | RCP1.3 - Lot Register/ WBS submitted and approved | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-002
cl:72b6fca6-3997-40a7-ad4f-c5f8f57abcac | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-002 | 1.0 Pre-Construction | RCP1.4 - Underlying lot & ITP signed off and conforming | In progress | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-002
cl:72b6fca6-3997-40a7-ad4f-c5f8f57abcac | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-002 | 1.0 Pre-Construction | RCP1.5 - Certificate of compliance for RCP Material | N/A | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-002
cl:72b6fca6-3997-40a7-ad4f-c5f8f57abcac | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-002 | 1.0 Pre-Construction | RCP1.6 - Inspect reinforced pipe culverts for damage | N/A | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-002
cl:72b6fca6-3997-40a7-ad4f-c5f8f57abcac | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-002 | 2.0 Construction | RCP2.7 - Trench Excavation | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-002
cl:72b6fca6-3997-40a7-ad4f-c5f8f57abcac | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-002 | 2.0 Construction | RCP2.8 - Bedding | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-002
cl:72b6fca6-3997-40a7-ad4f-c5f8f57abcac | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-002 | 2.0 Construction | RCP2.9 - RCP Installation | In progress | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-002
cl:72b6fca6-3997-40a7-ad4f-c5f8f57abcac | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-002 | 2.0 Construction | RCP2.10 - Backfilling of culvert | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-002
cl:72b6fca6-3997-40a7-ad4f-c5f8f57abcac | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-002 | 2.0 Construction | RCP2.11 - End Treatment – Headwall & Wingwalls (Reinforcement) | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-002
cl:72b6fca6-3997-40a7-ad4f-c5f8f57abcac | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-002 | 2.0 Construction | RCP2.12 - End Treatment – Headwall & Wingwalls (Formwork) | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-002
cl:72b6fca6-3997-40a7-ad4f-c5f8f57abcac | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-002 | 2.0 Construction | RCP2.13 - End Treatment – Headwall & Wingwalls (Concrete) | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-002
cl:72b6fca6-3997-40a7-ad4f-c5f8f57abcac | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-002 | 2.0 Construction | RCP2.14 - Rock Protection | In progress | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-002
cl:72b6fca6-3997-40a7-ad4f-c5f8f57abcac | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-002 | 3.0 Post Construction | RCP3.15 - Works completed and update ITP/ Lot Register/ MDR and close out of GDP | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-002
cl:ef0d1275-885b-4ee9-b427-9f5bbda141ad | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-003 | 1.0 Pre-Construction | RCP1.1 - Drawings supplied most current IFC | Passed | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-003
cl:ef0d1275-885b-4ee9-b427-9f5bbda141ad | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-003 | 1.0 Pre-Construction | RCP1.2 - Define RCP ID | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-003
cl:ef0d1275-885b-4ee9-b427-9f5bbda141ad | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-003 | 1.0 Pre-Construction | RCP1.3 - Lot Register/ WBS submitted and approved | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-003
cl:ef0d1275-885b-4ee9-b427-9f5bbda141ad | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-003 | 1.0 Pre-Construction | RCP1.4 - Underlying lot & ITP signed off and conforming | N/A | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-003
cl:ef0d1275-885b-4ee9-b427-9f5bbda141ad | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-003 | 1.0 Pre-Construction | RCP1.5 - Certificate of compliance for RCP Material | Passed | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-003
cl:ef0d1275-885b-4ee9-b427-9f5bbda141ad | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-003 | 1.0 Pre-Construction | RCP1.6 - Inspect reinforced pipe culverts for damage | Passed | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-003
cl:ef0d1275-885b-4ee9-b427-9f5bbda141ad | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-003 | 2.0 Construction | RCP2.7 - Trench Excavation | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-003
cl:ef0d1275-885b-4ee9-b427-9f5bbda141ad | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-003 | 2.0 Construction | RCP2.8 - Bedding | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-003
cl:ef0d1275-885b-4ee9-b427-9f5bbda141ad | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-003 | 2.0 Construction | RCP2.9 - RCP Installation | In progress | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-003
cl:ef0d1275-885b-4ee9-b427-9f5bbda141ad | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-003 | 2.0 Construction | RCP2.10 - Backfilling of culvert | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-003
cl:ef0d1275-885b-4ee9-b427-9f5bbda141ad | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-003 | 2.0 Construction | RCP2.11 - End Treatment – Headwall & Wingwalls (Reinforcement) | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-003
cl:ef0d1275-885b-4ee9-b427-9f5bbda141ad | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-003 | 2.0 Construction | RCP2.12 - End Treatment – Headwall & Wingwalls (Formwork) | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-003
cl:ef0d1275-885b-4ee9-b427-9f5bbda141ad | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-003 | 2.0 Construction | RCP2.13 - End Treatment – Headwall & Wingwalls (Concrete) | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-003
cl:ef0d1275-885b-4ee9-b427-9f5bbda141ad | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-003 | 2.0 Construction | RCP2.14 - Rock Protection | Passed | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-003
cl:ef0d1275-885b-4ee9-b427-9f5bbda141ad | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-003 | 3.0 Post Construction | RCP3.15 - Works completed and update ITP/ Lot Register/ MDR and close out of GDP | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-003
cl:a1582baf-1390-4cee-8145-7bd0946116f2 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-004 | 1.0 Pre-Construction | RCP1.1 - Drawings supplied most current IFC | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-004
cl:a1582baf-1390-4cee-8145-7bd0946116f2 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-004 | 1.0 Pre-Construction | RCP1.2 - Define RCP ID | Passed | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-004
cl:a1582baf-1390-4cee-8145-7bd0946116f2 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-004 | 1.0 Pre-Construction | RCP1.3 - Lot Register/ WBS submitted and approved | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-004
cl:a1582baf-1390-4cee-8145-7bd0946116f2 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-004 | 1.0 Pre-Construction | RCP1.4 - Underlying lot & ITP signed off and conforming | Passed | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-004
cl:a1582baf-1390-4cee-8145-7bd0946116f2 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-004 | 1.0 Pre-Construction | RCP1.5 - Certificate of compliance for RCP Material | Passed | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-004
cl:a1582baf-1390-4cee-8145-7bd0946116f2 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-004 | 1.0 Pre-Construction | RCP1.6 - Inspect reinforced pipe culverts for damage | Passed | Approved | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-004
cl:a1582baf-1390-4cee-8145-7bd0946116f2 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-004 | 2.0 Construction | RCP2.7 - Trench Excavation | In progress | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-004
cl:a1582baf-1390-4cee-8145-7bd0946116f2 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-004 | 2.0 Construction | RCP2.8 - Bedding | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-004
cl:a1582baf-1390-4cee-8145-7bd0946116f2 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-004 | 2.0 Construction | RCP2.9 - RCP Installation | In progress | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-004
cl:a1582baf-1390-4cee-8145-7bd0946116f2 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-004 | 2.0 Construction | RCP2.10 - Backfilling of culvert | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-004
cl:a1582baf-1390-4cee-8145-7bd0946116f2 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-004 | 2.0 Construction | RCP2.11 - End Treatment – Headwall & Wingwalls (Reinforcement) | Passed | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-004
cl:a1582baf-1390-4cee-8145-7bd0946116f2 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-004 | 2.0 Construction | RCP2.12 - End Treatment – Headwall & Wingwalls (Formwork) | N/A | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-004
cl:a1582baf-1390-4cee-8145-7bd0946116f2 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-004 | 2.0 Construction | RCP2.13 - End Treatment – Headwall & Wingwalls (Concrete) | N/A | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-004
cl:a1582baf-1390-4cee-8145-7bd0946116f2 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-004 | 2.0 Construction | RCP2.14 - Rock Protection | In progress | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-004
cl:a1582baf-1390-4cee-8145-7bd0946116f2 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-004 | 3.0 Post Construction | RCP3.15 - Works completed and update ITP/ Lot Register/ MDR and close out of GDP | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-004
cl:56672165-5146-4425-9bd6-510c095ba0d3 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-005_1415 | 1.0 Pre-Construction | RCP1.1 - Drawings supplied most current IFC | Passed | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-005_1415
cl:56672165-5146-4425-9bd6-510c095ba0d3 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-005_1415 | 1.0 Pre-Construction | RCP1.2 - Define RCP ID | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-005_1415
cl:56672165-5146-4425-9bd6-510c095ba0d3 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-005_1415 | 1.0 Pre-Construction | RCP1.3 - Lot Register/ WBS submitted and approved | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-005_1415
cl:56672165-5146-4425-9bd6-510c095ba0d3 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-005_1415 | 1.0 Pre-Construction | RCP1.4 - Underlying lot & ITP signed off and conforming | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-005_1415
cl:56672165-5146-4425-9bd6-510c095ba0d3 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-005_1415 | 1.0 Pre-Construction | RCP1.5 - Certificate of compliance for RCP Material | Passed | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-005_1415
cl:56672165-5146-4425-9bd6-510c095ba0d3 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-005_1415 | 1.0 Pre-Construction | RCP1.6 - Inspect reinforced pipe culverts for damage | Passed | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-005_1415
cl:56672165-5146-4425-9bd6-510c095ba0d3 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-005_1415 | 2.0 Construction | RCP2.7 - Trench Excavation | In progress | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-005_1415
cl:56672165-5146-4425-9bd6-510c095ba0d3 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-005_1415 | 2.0 Construction | RCP2.8 - Bedding | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-005_1415
cl:56672165-5146-4425-9bd6-510c095ba0d3 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-005_1415 | 2.0 Construction | RCP2.9 - RCP Installation | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-005_1415
cl:56672165-5146-4425-9bd6-510c095ba0d3 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-005_1415 | 2.0 Construction | RCP2.10 - Backfilling of culvert | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-005_1415
cl:56672165-5146-4425-9bd6-510c095ba0d3 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-005_1415 | 2.0 Construction | RCP2.11 - End Treatment – Headwall & Wingwalls (Reinforcement) | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-005_1415
cl:56672165-5146-4425-9bd6-510c095ba0d3 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-005_1415 | 2.0 Construction | RCP2.12 - End Treatment – Headwall & Wingwalls (Formwork) | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-005_1415
cl:56672165-5146-4425-9bd6-510c095ba0d3 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-005_1415 | 2.0 Construction | RCP2.13 - End Treatment – Headwall & Wingwalls (Concrete) | N/A | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-005_1415
cl:56672165-5146-4425-9bd6-510c095ba0d3 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-005_1415 | 2.0 Construction | RCP2.14 - Rock Protection | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-005_1415
cl:56672165-5146-4425-9bd6-510c095ba0d3 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-005_1415 | 3.0 Post Construction | RCP3.15 - Works completed and update ITP/ Lot Register/ MDR and close out of GDP | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-005_1415
cl:e0b7a3cf-bb64-4ec4-8455-5da0e1444bdc | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-006_CH1564 | 1.0 Pre-Construction | RCP1.1 - Drawings supplied most current IFC | Passed | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-006_CH1564
cl:e0b7a3cf-bb64-4ec4-8455-5da0e1444bdc | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-006_CH1564 | 1.0 Pre-Construction | RCP1.2 - Define RCP ID | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-006_CH1564
cl:e0b7a3cf-bb64-4ec4-8455-5da0e1444bdc | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-006_CH1564 | 1.0 Pre-Construction | RCP1.3 - Lot Register/ WBS submitted and approved | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-006_CH1564
cl:e0b7a3cf-bb64-4ec4-8455-5da0e1444bdc | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-006_CH1564 | 1.0 Pre-Construction | RCP1.4 - Underlying lot & ITP signed off and conforming | N/A | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-006_CH1564
cl:e0b7a3cf-bb64-4ec4-8455-5da0e1444bdc | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-006_CH1564 | 1.0 Pre-Construction | RCP1.5 - Certificate of compliance for RCP Material | Passed | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-006_CH1564
cl:e0b7a3cf-bb64-4ec4-8455-5da0e1444bdc | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-006_CH1564 | 1.0 Pre-Construction | RCP1.6 - Inspect reinforced pipe culverts for damage | Passed | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-006_CH1564
cl:e0b7a3cf-bb64-4ec4-8455-5da0e1444bdc | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-006_CH1564 | 2.0 Construction | RCP2.7 - Trench Excavation | Passed | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-006_CH1564
cl:e0b7a3cf-bb64-4ec4-8455-5da0e1444bdc | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-006_CH1564 | 2.0 Construction | RCP2.8 - Bedding | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-006_CH1564
cl:e0b7a3cf-bb64-4ec4-8455-5da0e1444bdc | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-006_CH1564 | 2.0 Construction | RCP2.9 - RCP Installation | In progress | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-006_CH1564
cl:e0b7a3cf-bb64-4ec4-8455-5da0e1444bdc | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-006_CH1564 | 2.0 Construction | RCP2.10 - Backfilling of culvert | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-006_CH1564
cl:e0b7a3cf-bb64-4ec4-8455-5da0e1444bdc | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-006_CH1564 | 2.0 Construction | RCP2.11 - End Treatment – Headwall & Wingwalls (Reinforcement) | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-006_CH1564
cl:e0b7a3cf-bb64-4ec4-8455-5da0e1444bdc | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-006_CH1564 | 2.0 Construction | RCP2.12 - End Treatment – Headwall & Wingwalls (Formwork) | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-006_CH1564
cl:e0b7a3cf-bb64-4ec4-8455-5da0e1444bdc | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-006_CH1564 | 2.0 Construction | RCP2.13 - End Treatment – Headwall & Wingwalls (Concrete) | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-006_CH1564
cl:e0b7a3cf-bb64-4ec4-8455-5da0e1444bdc | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-006_CH1564 | 2.0 Construction | RCP2.14 - Rock Protection | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-006_CH1564
cl:e0b7a3cf-bb64-4ec4-8455-5da0e1444bdc | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-006_CH1564 | 3.0 Post Construction | RCP3.15 - Works completed and update ITP/ Lot Register/ MDR and close out of GDP | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-006_CH1564
cl:54aef0c1-90a6-42ab-b32f-50385b4126e4 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-007_2355 | 1.0 Pre-Construction | RCP1.1 - Drawings supplied most current IFC | Passed | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-007_2355
cl:54aef0c1-90a6-42ab-b32f-50385b4126e4 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-007_2355 | 1.0 Pre-Construction | RCP1.2 - Define RCP ID | Passed | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-007_2355
cl:54aef0c1-90a6-42ab-b32f-50385b4126e4 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-007_2355 | 1.0 Pre-Construction | RCP1.3 - Lot Register/ WBS submitted and approved | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-007_2355
cl:54aef0c1-90a6-42ab-b32f-50385b4126e4 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-007_2355 | 1.0 Pre-Construction | RCP1.4 - Underlying lot & ITP signed off and conforming | N/A | Approved | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-007_2355
cl:54aef0c1-90a6-42ab-b32f-50385b4126e4 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-007_2355 | 1.0 Pre-Construction | RCP1.5 - Certificate of compliance for RCP Material | In progress | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-007_2355
cl:54aef0c1-90a6-42ab-b32f-50385b4126e4 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-007_2355 | 1.0 Pre-Construction | RCP1.6 - Inspect reinforced pipe culverts for damage | Passed | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-007_2355
cl:54aef0c1-90a6-42ab-b32f-50385b4126e4 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-007_2355 | 2.0 Construction | RCP2.7 - Trench Excavation | Passed | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-007_2355
cl:54aef0c1-90a6-42ab-b32f-50385b4126e4 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-007_2355 | 2.0 Construction | RCP2.8 - Bedding | Passed | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-007_2355
cl:54aef0c1-90a6-42ab-b32f-50385b4126e4 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-007_2355 | 2.0 Construction | RCP2.9 - RCP Installation | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-007_2355
cl:54aef0c1-90a6-42ab-b32f-50385b4126e4 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-007_2355 | 2.0 Construction | RCP2.10 - Backfilling of culvert | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-007_2355
cl:54aef0c1-90a6-42ab-b32f-50385b4126e4 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-007_2355 | 2.0 Construction | RCP2.11 - End Treatment – Headwall & Wingwalls (Reinforcement) | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-007_2355
cl:54aef0c1-90a6-42ab-b32f-50385b4126e4 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-007_2355 | 2.0 Construction | RCP2.12 - End Treatment – Headwall & Wingwalls (Formwork) | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-007_2355
cl:54aef0c1-90a6-42ab-b32f-50385b4126e4 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-007_2355 | 2.0 Construction | RCP2.13 - End Treatment – Headwall & Wingwalls (Concrete) | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-007_2355
cl:54aef0c1-90a6-42ab-b32f-50385b4126e4 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-007_2355 | 2.0 Construction | RCP2.14 - Rock Protection | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-007_2355
cl:54aef0c1-90a6-42ab-b32f-50385b4126e4 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-007_2355 | 3.0 Post Construction | RCP3.15 - Works completed and update ITP/ Lot Register/ MDR and close out of GDP | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-007_2355
cl:334a960a-bfaf-4175-a384-024b6765292d | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-008_CH2385 | 1.0 Pre-Construction | RCP1.1 - Drawings supplied most current IFC | Passed | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-008_CH2385
cl:334a960a-bfaf-4175-a384-024b6765292d | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-008_CH2385 | 1.0 Pre-Construction | RCP1.2 - Define RCP ID | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-008_CH2385
cl:334a960a-bfaf-4175-a384-024b6765292d | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-008_CH2385 | 1.0 Pre-Construction | RCP1.3 - Lot Register/ WBS submitted and approved | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-008_CH2385
cl:334a960a-bfaf-4175-a384-024b6765292d | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-008_CH2385 | 1.0 Pre-Construction | RCP1.4 - Underlying lot & ITP signed off and conforming | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-008_CH2385
cl:334a960a-bfaf-4175-a384-024b6765292d | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-008_CH2385 | 1.0 Pre-Construction | RCP1.5 - Certificate of compliance for RCP Material | In progress | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-008_CH2385
cl:334a960a-bfaf-4175-a384-024b6765292d | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-008_CH2385 | 1.0 Pre-Construction | RCP1.6 - Inspect reinforced pipe culverts for damage | Passed | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-008_CH2385
cl:334a960a-bfaf-4175-a384-024b6765292d | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-008_CH2385 | 2.0 Construction | RCP2.7 - Trench Excavation | In progress | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-008_CH2385
cl:334a960a-bfaf-4175-a384-024b6765292d | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-008_CH2385 | 2.0 Construction | RCP2.8 - Bedding | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-008_CH2385
cl:334a960a-bfaf-4175-a384-024b6765292d | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-008_CH2385 | 2.0 Construction | RCP2.9 - RCP Installation | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-008_CH2385
cl:334a960a-bfaf-4175-a384-024b6765292d | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-008_CH2385 | 2.0 Construction | RCP2.10 - Backfilling of culvert | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-008_CH2385
cl:334a960a-bfaf-4175-a384-024b6765292d | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-008_CH2385 | 2.0 Construction | RCP2.11 - End Treatment – Headwall & Wingwalls (Reinforcement) | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-008_CH2385
cl:334a960a-bfaf-4175-a384-024b6765292d | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-008_CH2385 | 2.0 Construction | RCP2.12 - End Treatment – Headwall & Wingwalls (Formwork) | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-008_CH2385
cl:334a960a-bfaf-4175-a384-024b6765292d | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-008_CH2385 | 2.0 Construction | RCP2.13 - End Treatment – Headwall & Wingwalls (Concrete) | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-008_CH2385
cl:334a960a-bfaf-4175-a384-024b6765292d | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-008_CH2385 | 2.0 Construction | RCP2.14 - Rock Protection | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-008_CH2385
cl:334a960a-bfaf-4175-a384-024b6765292d | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-008_CH2385 | 3.0 Post Construction | RCP3.15 - Works completed and update ITP/ Lot Register/ MDR and close out of GDP | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-008_CH2385
cl:ef206ea2-e824-42ff-9ec1-9cbca5556483 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-009_2715 | 1.0 Pre-Construction | RCP1.1 - Drawings supplied most current IFC | In progress | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-009_2715
cl:ef206ea2-e824-42ff-9ec1-9cbca5556483 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-009_2715 | 1.0 Pre-Construction | RCP1.2 - Define RCP ID | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-009_2715
cl:ef206ea2-e824-42ff-9ec1-9cbca5556483 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-009_2715 | 1.0 Pre-Construction | RCP1.3 - Lot Register/ WBS submitted and approved | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-009_2715
cl:ef206ea2-e824-42ff-9ec1-9cbca5556483 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-009_2715 | 1.0 Pre-Construction | RCP1.4 - Underlying lot & ITP signed off and conforming | N/A | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-009_2715
cl:ef206ea2-e824-42ff-9ec1-9cbca5556483 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-009_2715 | 1.0 Pre-Construction | RCP1.5 - Certificate of compliance for RCP Material | In progress | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-009_2715
cl:ef206ea2-e824-42ff-9ec1-9cbca5556483 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-009_2715 | 1.0 Pre-Construction | RCP1.6 - Inspect reinforced pipe culverts for damage | Passed | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-009_2715
cl:ef206ea2-e824-42ff-9ec1-9cbca5556483 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-009_2715 | 2.0 Construction | RCP2.7 - Trench Excavation | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-009_2715
cl:ef206ea2-e824-42ff-9ec1-9cbca5556483 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-009_2715 | 2.0 Construction | RCP2.8 - Bedding | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-009_2715
cl:ef206ea2-e824-42ff-9ec1-9cbca5556483 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-009_2715 | 2.0 Construction | RCP2.9 - RCP Installation | In progress | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-009_2715
cl:ef206ea2-e824-42ff-9ec1-9cbca5556483 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-009_2715 | 2.0 Construction | RCP2.10 - Backfilling of culvert | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-009_2715
cl:ef206ea2-e824-42ff-9ec1-9cbca5556483 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-009_2715 | 2.0 Construction | RCP2.11 - End Treatment – Headwall & Wingwalls (Reinforcement) | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-009_2715
cl:ef206ea2-e824-42ff-9ec1-9cbca5556483 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-009_2715 | 2.0 Construction | RCP2.12 - End Treatment – Headwall & Wingwalls (Formwork) | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-009_2715
cl:ef206ea2-e824-42ff-9ec1-9cbca5556483 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-009_2715 | 2.0 Construction | RCP2.13 - End Treatment – Headwall & Wingwalls (Concrete) | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-009_2715
cl:ef206ea2-e824-42ff-9ec1-9cbca5556483 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-009_2715 | 2.0 Construction | RCP2.14 - Rock Protection | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-009_2715
cl:ef206ea2-e824-42ff-9ec1-9cbca5556483 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-009_2715 | 3.0 Post Construction | RCP3.15 - Works completed and update ITP/ Lot Register/ MDR and close out of GDP | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-009_2715
cl:d7fe2708-d0db-468e-8422-c639bfc5cca0 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-010 | 1.0 Pre-Construction | RCP1.1 - Drawings supplied most current IFC | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-010
cl:d7fe2708-d0db-468e-8422-c639bfc5cca0 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-010 | 1.0 Pre-Construction | RCP1.2 - Define RCP ID | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-010
cl:d7fe2708-d0db-468e-8422-c639bfc5cca0 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-010 | 1.0 Pre-Construction | RCP1.3 - Lot Register/ WBS submitted and approved | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-010
cl:d7fe2708-d0db-468e-8422-c639bfc5cca0 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-010 | 1.0 Pre-Construction | RCP1.4 - Underlying lot & ITP signed off and conforming | N/A | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-010
cl:d7fe2708-d0db-468e-8422-c639bfc5cca0 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-010 | 1.0 Pre-Construction | RCP1.5 - Certificate of compliance for RCP Material | In progress | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-010
cl:d7fe2708-d0db-468e-8422-c639bfc5cca0 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-010 | 1.0 Pre-Construction | RCP1.6 - Inspect reinforced pipe culverts for damage | Passed | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-010
cl:d7fe2708-d0db-468e-8422-c639bfc5cca0 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-010 | 2.0 Construction | RCP2.7 - Trench Excavation | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-010
cl:d7fe2708-d0db-468e-8422-c639bfc5cca0 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-010 | 2.0 Construction | RCP2.8 - Bedding | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-010
cl:d7fe2708-d0db-468e-8422-c639bfc5cca0 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-010 | 2.0 Construction | RCP2.9 - RCP Installation | In progress | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-010
cl:d7fe2708-d0db-468e-8422-c639bfc5cca0 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-010 | 2.0 Construction | RCP2.10 - Backfilling of culvert | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-010
cl:d7fe2708-d0db-468e-8422-c639bfc5cca0 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-010 | 2.0 Construction | RCP2.11 - End Treatment – Headwall & Wingwalls (Reinforcement) | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-010
cl:d7fe2708-d0db-468e-8422-c639bfc5cca0 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-010 | 2.0 Construction | RCP2.12 - End Treatment – Headwall & Wingwalls (Formwork) | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-010
cl:d7fe2708-d0db-468e-8422-c639bfc5cca0 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-010 | 2.0 Construction | RCP2.13 - End Treatment – Headwall & Wingwalls (Concrete) | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-010
cl:d7fe2708-d0db-468e-8422-c639bfc5cca0 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-010 | 2.0 Construction | RCP2.14 - Rock Protection | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-010
cl:d7fe2708-d0db-468e-8422-c639bfc5cca0 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-010 | 3.0 Post Construction | RCP3.15 - Works completed and update ITP/ Lot Register/ MDR and close out of GDP | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-010
cl:8584bee6-a760-4608-9e42-1727da0b9fed | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-011 | 1.0 Pre-Construction | RCP1.1 - Drawings supplied most current IFC | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-011
cl:8584bee6-a760-4608-9e42-1727da0b9fed | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-011 | 1.0 Pre-Construction | RCP1.2 - Define RCP ID | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-011
cl:8584bee6-a760-4608-9e42-1727da0b9fed | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-011 | 1.0 Pre-Construction | RCP1.3 - Lot Register/ WBS submitted and approved | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-011
cl:8584bee6-a760-4608-9e42-1727da0b9fed | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-011 | 1.0 Pre-Construction | RCP1.4 - Underlying lot & ITP signed off and conforming | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-011
cl:8584bee6-a760-4608-9e42-1727da0b9fed | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-011 | 1.0 Pre-Construction | RCP1.5 - Certificate of compliance for RCP Material | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-011
cl:8584bee6-a760-4608-9e42-1727da0b9fed | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-011 | 1.0 Pre-Construction | RCP1.6 - Inspect reinforced pipe culverts for damage | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-011
cl:8584bee6-a760-4608-9e42-1727da0b9fed | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-011 | 2.0 Construction | RCP2.7 - Trench Excavation | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-011
cl:8584bee6-a760-4608-9e42-1727da0b9fed | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-011 | 2.0 Construction | RCP2.8 - Bedding | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-011
cl:8584bee6-a760-4608-9e42-1727da0b9fed | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-011 | 2.0 Construction | RCP2.9 - RCP Installation | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-011
cl:8584bee6-a760-4608-9e42-1727da0b9fed | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-011 | 2.0 Construction | RCP2.10 - Backfilling of culvert | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-011
cl:8584bee6-a760-4608-9e42-1727da0b9fed | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-011 | 2.0 Construction | RCP2.11 - End Treatment – Headwall & Wingwalls (Reinforcement) | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-011
cl:8584bee6-a760-4608-9e42-1727da0b9fed | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-011 | 2.0 Construction | RCP2.12 - End Treatment – Headwall & Wingwalls (Formwork) | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-011
cl:8584bee6-a760-4608-9e42-1727da0b9fed | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-011 | 2.0 Construction | RCP2.13 - End Treatment – Headwall & Wingwalls (Concrete) | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-011
cl:8584bee6-a760-4608-9e42-1727da0b9fed | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-011 | 2.0 Construction | RCP2.14 - Rock Protection | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-011
cl:8584bee6-a760-4608-9e42-1727da0b9fed | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-011 | 3.0 Post Construction | RCP3.15 - Works completed and update ITP/ Lot Register/ MDR and close out of GDP | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-011
cl:9dbc8f4c-c2f4-4fe6-9994-249789a85e2f | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-012 | 1.0 Pre-Construction | RCP1.1 - Drawings supplied most current IFC | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-012
cl:9dbc8f4c-c2f4-4fe6-9994-249789a85e2f | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-012 | 1.0 Pre-Construction | RCP1.2 - Define RCP ID | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-012
cl:9dbc8f4c-c2f4-4fe6-9994-249789a85e2f | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-012 | 1.0 Pre-Construction | RCP1.3 - Lot Register/ WBS submitted and approved | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-012
cl:9dbc8f4c-c2f4-4fe6-9994-249789a85e2f | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-012 | 1.0 Pre-Construction | RCP1.4 - Underlying lot & ITP signed off and conforming | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-012
cl:9dbc8f4c-c2f4-4fe6-9994-249789a85e2f | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-012 | 1.0 Pre-Construction | RCP1.5 - Certificate of compliance for RCP Material | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-012
cl:9dbc8f4c-c2f4-4fe6-9994-249789a85e2f | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-012 | 1.0 Pre-Construction | RCP1.6 - Inspect reinforced pipe culverts for damage | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-012
cl:9dbc8f4c-c2f4-4fe6-9994-249789a85e2f | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-012 | 2.0 Construction | RCP2.7 - Trench Excavation | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-012
cl:9dbc8f4c-c2f4-4fe6-9994-249789a85e2f | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-012 | 2.0 Construction | RCP2.8 - Bedding | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-012
cl:9dbc8f4c-c2f4-4fe6-9994-249789a85e2f | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-012 | 2.0 Construction | RCP2.9 - RCP Installation | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-012
cl:9dbc8f4c-c2f4-4fe6-9994-249789a85e2f | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-012 | 2.0 Construction | RCP2.10 - Backfilling of culvert | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-012
cl:9dbc8f4c-c2f4-4fe6-9994-249789a85e2f | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-012 | 2.0 Construction | RCP2.11 - End Treatment – Headwall & Wingwalls (Reinforcement) | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-012
cl:9dbc8f4c-c2f4-4fe6-9994-249789a85e2f | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-012 | 2.0 Construction | RCP2.12 - End Treatment – Headwall & Wingwalls (Formwork) | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-012
cl:9dbc8f4c-c2f4-4fe6-9994-249789a85e2f | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-012 | 2.0 Construction | RCP2.13 - End Treatment – Headwall & Wingwalls (Concrete) | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-012
cl:9dbc8f4c-c2f4-4fe6-9994-249789a85e2f | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-012 | 2.0 Construction | RCP2.14 - Rock Protection | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-012
cl:9dbc8f4c-c2f4-4fe6-9994-249789a85e2f | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-012 | 3.0 Post Construction | RCP3.15 - Works completed and update ITP/ Lot Register/ MDR and close out of GDP | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-012
cl:2717c2dd-f499-4b9b-a7d1-e4e58773c9b5 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-013 | 1.0 Pre-Construction | RCP1.1 - Drawings supplied most current IFC | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-013
cl:2717c2dd-f499-4b9b-a7d1-e4e58773c9b5 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-013 | 1.0 Pre-Construction | RCP1.2 - Define RCP ID | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-013
cl:2717c2dd-f499-4b9b-a7d1-e4e58773c9b5 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-013 | 1.0 Pre-Construction | RCP1.3 - Lot Register/ WBS submitted and approved | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-013
cl:2717c2dd-f499-4b9b-a7d1-e4e58773c9b5 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-013 | 1.0 Pre-Construction | RCP1.4 - Underlying lot & ITP signed off and conforming | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-013
cl:2717c2dd-f499-4b9b-a7d1-e4e58773c9b5 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-013 | 1.0 Pre-Construction | RCP1.5 - Certificate of compliance for RCP Material | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-013
cl:2717c2dd-f499-4b9b-a7d1-e4e58773c9b5 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-013 | 1.0 Pre-Construction | RCP1.6 - Inspect reinforced pipe culverts for damage | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-013
cl:2717c2dd-f499-4b9b-a7d1-e4e58773c9b5 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-013 | 2.0 Construction | RCP2.7 - Trench Excavation | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-013
cl:2717c2dd-f499-4b9b-a7d1-e4e58773c9b5 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-013 | 2.0 Construction | RCP2.8 - Bedding | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-013
cl:2717c2dd-f499-4b9b-a7d1-e4e58773c9b5 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-013 | 2.0 Construction | RCP2.9 - RCP Installation | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-013
cl:2717c2dd-f499-4b9b-a7d1-e4e58773c9b5 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-013 | 2.0 Construction | RCP2.10 - Backfilling of culvert | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-013
cl:2717c2dd-f499-4b9b-a7d1-e4e58773c9b5 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-013 | 2.0 Construction | RCP2.11 - End Treatment – Headwall & Wingwalls (Reinforcement) | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-013
cl:2717c2dd-f499-4b9b-a7d1-e4e58773c9b5 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-013 | 2.0 Construction | RCP2.12 - End Treatment – Headwall & Wingwalls (Formwork) | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-013
cl:2717c2dd-f499-4b9b-a7d1-e4e58773c9b5 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-013 | 2.0 Construction | RCP2.13 - End Treatment – Headwall & Wingwalls (Concrete) | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-013
cl:2717c2dd-f499-4b9b-a7d1-e4e58773c9b5 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-013 | 2.0 Construction | RCP2.14 - Rock Protection | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-013
cl:2717c2dd-f499-4b9b-a7d1-e4e58773c9b5 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-013 | 3.0 Post Construction | RCP3.15 - Works completed and update ITP/ Lot Register/ MDR and close out of GDP | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-013
cl:3097c0b9-989c-4421-b2eb-94085d48b7d9 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-014 | 1.0 Pre-Construction | RCP1.1 - Drawings supplied most current IFC | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-014
cl:3097c0b9-989c-4421-b2eb-94085d48b7d9 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-014 | 1.0 Pre-Construction | RCP1.2 - Define RCP ID | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-014
cl:3097c0b9-989c-4421-b2eb-94085d48b7d9 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-014 | 1.0 Pre-Construction | RCP1.3 - Lot Register/ WBS submitted and approved | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-014
cl:3097c0b9-989c-4421-b2eb-94085d48b7d9 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-014 | 1.0 Pre-Construction | RCP1.4 - Underlying lot & ITP signed off and conforming | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-014
cl:3097c0b9-989c-4421-b2eb-94085d48b7d9 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-014 | 1.0 Pre-Construction | RCP1.5 - Certificate of compliance for RCP Material | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-014
cl:3097c0b9-989c-4421-b2eb-94085d48b7d9 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-014 | 1.0 Pre-Construction | RCP1.6 - Inspect reinforced pipe culverts for damage | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-014
cl:3097c0b9-989c-4421-b2eb-94085d48b7d9 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-014 | 2.0 Construction | RCP2.7 - Trench Excavation | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-014
cl:3097c0b9-989c-4421-b2eb-94085d48b7d9 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-014 | 2.0 Construction | RCP2.8 - Bedding | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-014
cl:3097c0b9-989c-4421-b2eb-94085d48b7d9 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-014 | 2.0 Construction | RCP2.9 - RCP Installation | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-014
cl:3097c0b9-989c-4421-b2eb-94085d48b7d9 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-014 | 2.0 Construction | RCP2.10 - Backfilling of culvert | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-014
cl:3097c0b9-989c-4421-b2eb-94085d48b7d9 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-014 | 2.0 Construction | RCP2.11 - End Treatment – Headwall & Wingwalls (Reinforcement) | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-014
cl:3097c0b9-989c-4421-b2eb-94085d48b7d9 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-014 | 2.0 Construction | RCP2.12 - End Treatment – Headwall & Wingwalls (Formwork) | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-014
cl:3097c0b9-989c-4421-b2eb-94085d48b7d9 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-014 | 2.0 Construction | RCP2.13 - End Treatment – Headwall & Wingwalls (Concrete) | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-014
cl:3097c0b9-989c-4421-b2eb-94085d48b7d9 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-014 | 2.0 Construction | RCP2.14 - Rock Protection | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-014
cl:3097c0b9-989c-4421-b2eb-94085d48b7d9 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-014 | 3.0 Post Construction | RCP3.15 - Works completed and update ITP/ Lot Register/ MDR and close out of GDP | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-014
cl:b9f58684-3edb-42e5-8a7d-cc6530eeea36 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-015 | 1.0 Pre-Construction | RCP1.1 - Drawings supplied most current IFC | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-015
cl:b9f58684-3edb-42e5-8a7d-cc6530eeea36 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-015 | 1.0 Pre-Construction | RCP1.2 - Define RCP ID | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-015
cl:b9f58684-3edb-42e5-8a7d-cc6530eeea36 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-015 | 1.0 Pre-Construction | RCP1.3 - Lot Register/ WBS submitted and approved | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-015
cl:b9f58684-3edb-42e5-8a7d-cc6530eeea36 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-015 | 1.0 Pre-Construction | RCP1.4 - Underlying lot & ITP signed off and conforming | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-015
cl:b9f58684-3edb-42e5-8a7d-cc6530eeea36 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-015 | 1.0 Pre-Construction | RCP1.5 - Certificate of compliance for RCP Material | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-015
cl:b9f58684-3edb-42e5-8a7d-cc6530eeea36 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-015 | 1.0 Pre-Construction | RCP1.6 - Inspect reinforced pipe culverts for damage | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-015
cl:b9f58684-3edb-42e5-8a7d-cc6530eeea36 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-015 | 2.0 Construction | RCP2.7 - Trench Excavation | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-015
cl:b9f58684-3edb-42e5-8a7d-cc6530eeea36 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-015 | 2.0 Construction | RCP2.8 - Bedding | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-015
cl:b9f58684-3edb-42e5-8a7d-cc6530eeea36 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-015 | 2.0 Construction | RCP2.9 - RCP Installation | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-015
cl:b9f58684-3edb-42e5-8a7d-cc6530eeea36 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-015 | 2.0 Construction | RCP2.10 - Backfilling of culvert | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-015
cl:b9f58684-3edb-42e5-8a7d-cc6530eeea36 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-015 | 2.0 Construction | RCP2.11 - End Treatment – Headwall & Wingwalls (Reinforcement) | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-015
cl:b9f58684-3edb-42e5-8a7d-cc6530eeea36 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-015 | 2.0 Construction | RCP2.12 - End Treatment – Headwall & Wingwalls (Formwork) | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-015
cl:b9f58684-3edb-42e5-8a7d-cc6530eeea36 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-015 | 2.0 Construction | RCP2.13 - End Treatment – Headwall & Wingwalls (Concrete) | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-015
cl:b9f58684-3edb-42e5-8a7d-cc6530eeea36 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-015 | 2.0 Construction | RCP2.14 - Rock Protection | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-015
cl:b9f58684-3edb-42e5-8a7d-cc6530eeea36 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-015 | 3.0 Post Construction | RCP3.15 - Works completed and update ITP/ Lot Register/ MDR and close out of GDP | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-015
cl:74498f1b-f1b4-4d43-a846-ed5ebaf88e1a | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-016 | 1.0 Pre-Construction | RCP1.1 - Drawings supplied most current IFC | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-016
cl:74498f1b-f1b4-4d43-a846-ed5ebaf88e1a | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-016 | 1.0 Pre-Construction | RCP1.2 - Define RCP ID | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-016
cl:74498f1b-f1b4-4d43-a846-ed5ebaf88e1a | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-016 | 1.0 Pre-Construction | RCP1.3 - Lot Register/ WBS submitted and approved | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-016
cl:74498f1b-f1b4-4d43-a846-ed5ebaf88e1a | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-016 | 1.0 Pre-Construction | RCP1.4 - Underlying lot & ITP signed off and conforming | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-016
cl:74498f1b-f1b4-4d43-a846-ed5ebaf88e1a | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-016 | 1.0 Pre-Construction | RCP1.5 - Certificate of compliance for RCP Material | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-016
cl:74498f1b-f1b4-4d43-a846-ed5ebaf88e1a | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-016 | 1.0 Pre-Construction | RCP1.6 - Inspect reinforced pipe culverts for damage | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-016
cl:74498f1b-f1b4-4d43-a846-ed5ebaf88e1a | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-016 | 2.0 Construction | RCP2.7 - Trench Excavation | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-016
cl:74498f1b-f1b4-4d43-a846-ed5ebaf88e1a | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-016 | 2.0 Construction | RCP2.8 - Bedding | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-016
cl:74498f1b-f1b4-4d43-a846-ed5ebaf88e1a | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-016 | 2.0 Construction | RCP2.9 - RCP Installation | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-016
cl:74498f1b-f1b4-4d43-a846-ed5ebaf88e1a | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-016 | 2.0 Construction | RCP2.10 - Backfilling of culvert | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-016
cl:74498f1b-f1b4-4d43-a846-ed5ebaf88e1a | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-016 | 2.0 Construction | RCP2.11 - End Treatment – Headwall & Wingwalls (Reinforcement) | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-016
cl:74498f1b-f1b4-4d43-a846-ed5ebaf88e1a | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-016 | 2.0 Construction | RCP2.12 - End Treatment – Headwall & Wingwalls (Formwork) | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-016
cl:74498f1b-f1b4-4d43-a846-ed5ebaf88e1a | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-016 | 2.0 Construction | RCP2.13 - End Treatment – Headwall & Wingwalls (Concrete) | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-016
cl:74498f1b-f1b4-4d43-a846-ed5ebaf88e1a | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-016 | 2.0 Construction | RCP2.14 - Rock Protection | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-016
cl:74498f1b-f1b4-4d43-a846-ed5ebaf88e1a | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-016 | 3.0 Post Construction | RCP3.15 - Works completed and update ITP/ Lot Register/ MDR and close out of GDP | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-016
cl:0876f56a-2c12-48dc-8a0f-0e0c0dd35b52 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-017 | 1.0 Pre-Construction | RCP1.1 - Drawings supplied most current IFC | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-017
cl:0876f56a-2c12-48dc-8a0f-0e0c0dd35b52 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-017 | 1.0 Pre-Construction | RCP1.2 - Define RCP ID | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-017
cl:0876f56a-2c12-48dc-8a0f-0e0c0dd35b52 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-017 | 1.0 Pre-Construction | RCP1.3 - Lot Register/ WBS submitted and approved | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-017
cl:0876f56a-2c12-48dc-8a0f-0e0c0dd35b52 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-017 | 1.0 Pre-Construction | RCP1.4 - Underlying lot & ITP signed off and conforming | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-017
cl:0876f56a-2c12-48dc-8a0f-0e0c0dd35b52 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-017 | 1.0 Pre-Construction | RCP1.5 - Certificate of compliance for RCP Material | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-017
cl:0876f56a-2c12-48dc-8a0f-0e0c0dd35b52 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-017 | 1.0 Pre-Construction | RCP1.6 - Inspect reinforced pipe culverts for damage | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-017
cl:0876f56a-2c12-48dc-8a0f-0e0c0dd35b52 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-017 | 2.0 Construction | RCP2.7 - Trench Excavation | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-017
cl:0876f56a-2c12-48dc-8a0f-0e0c0dd35b52 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-017 | 2.0 Construction | RCP2.8 - Bedding | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-017
cl:0876f56a-2c12-48dc-8a0f-0e0c0dd35b52 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-017 | 2.0 Construction | RCP2.9 - RCP Installation | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-017
cl:0876f56a-2c12-48dc-8a0f-0e0c0dd35b52 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-017 | 2.0 Construction | RCP2.10 - Backfilling of culvert | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-017
cl:0876f56a-2c12-48dc-8a0f-0e0c0dd35b52 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-017 | 2.0 Construction | RCP2.11 - End Treatment – Headwall & Wingwalls (Reinforcement) | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-017
cl:0876f56a-2c12-48dc-8a0f-0e0c0dd35b52 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-017 | 2.0 Construction | RCP2.12 - End Treatment – Headwall & Wingwalls (Formwork) | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-017
cl:0876f56a-2c12-48dc-8a0f-0e0c0dd35b52 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-017 | 2.0 Construction | RCP2.13 - End Treatment – Headwall & Wingwalls (Concrete) | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-017
cl:0876f56a-2c12-48dc-8a0f-0e0c0dd35b52 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-017 | 2.0 Construction | RCP2.14 - Rock Protection | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-017
cl:0876f56a-2c12-48dc-8a0f-0e0c0dd35b52 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-017 | 3.0 Post Construction | RCP3.15 - Works completed and update ITP/ Lot Register/ MDR and close out of GDP | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | ITP-004 RCP Installation-MAR-017
cl:422980e3-ac79-4913-b4ad-54ef63cf0d32 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation > Global RCP | ITP-004 RCP Installation-MAR-018 - Global | 1.0 Pre-Construction | RCP1.1 - Drawings supplied most current IFC | In progress | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | Global RCP | ITP-004 RCP Installation-MAR-018 - Global
cl:422980e3-ac79-4913-b4ad-54ef63cf0d32 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation > Global RCP | ITP-004 RCP Installation-MAR-018 - Global | 1.0 Pre-Construction | RCP1.2 - Define RCP ID | Passed | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | Global RCP | ITP-004 RCP Installation-MAR-018 - Global
cl:422980e3-ac79-4913-b4ad-54ef63cf0d32 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation > Global RCP | ITP-004 RCP Installation-MAR-018 - Global | 1.0 Pre-Construction | RCP1.3 - Lot Register/ WBS submitted and approved | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | Global RCP | ITP-004 RCP Installation-MAR-018 - Global
cl:422980e3-ac79-4913-b4ad-54ef63cf0d32 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation > Global RCP | ITP-004 RCP Installation-MAR-018 - Global | 1.0 Pre-Construction | RCP1.4 - Underlying lot & ITP signed off and conforming | N/A | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | Global RCP | ITP-004 RCP Installation-MAR-018 - Global
cl:422980e3-ac79-4913-b4ad-54ef63cf0d32 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation > Global RCP | ITP-004 RCP Installation-MAR-018 - Global | 1.0 Pre-Construction | RCP1.5 - Certificate of compliance for RCP Material | Passed | Approved | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | Global RCP | ITP-004 RCP Installation-MAR-018 - Global
cl:422980e3-ac79-4913-b4ad-54ef63cf0d32 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation > Global RCP | ITP-004 RCP Installation-MAR-018 - Global | 1.0 Pre-Construction | RCP1.6 - Inspect reinforced pipe culverts for damage | Passed | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | Global RCP | ITP-004 RCP Installation-MAR-018 - Global
cl:422980e3-ac79-4913-b4ad-54ef63cf0d32 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation > Global RCP | ITP-004 RCP Installation-MAR-018 - Global | 2.0 Construction | RCP2.7 - Trench Excavation | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | Global RCP | ITP-004 RCP Installation-MAR-018 - Global
cl:422980e3-ac79-4913-b4ad-54ef63cf0d32 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation > Global RCP | ITP-004 RCP Installation-MAR-018 - Global | 2.0 Construction | RCP2.8 - Bedding | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | Global RCP | ITP-004 RCP Installation-MAR-018 - Global
cl:422980e3-ac79-4913-b4ad-54ef63cf0d32 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation > Global RCP | ITP-004 RCP Installation-MAR-018 - Global | 2.0 Construction | RCP2.9 - RCP Installation | In progress | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | Global RCP | ITP-004 RCP Installation-MAR-018 - Global
cl:422980e3-ac79-4913-b4ad-54ef63cf0d32 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation > Global RCP | ITP-004 RCP Installation-MAR-018 - Global | 2.0 Construction | RCP2.10 - Backfilling of culvert | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | Global RCP | ITP-004 RCP Installation-MAR-018 - Global
cl:422980e3-ac79-4913-b4ad-54ef63cf0d32 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation > Global RCP | ITP-004 RCP Installation-MAR-018 - Global | 2.0 Construction | RCP2.11 - End Treatment – Headwall & Wingwalls (Reinforcement) | Passed | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | Global RCP | ITP-004 RCP Installation-MAR-018 - Global
cl:422980e3-ac79-4913-b4ad-54ef63cf0d32 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation > Global RCP | ITP-004 RCP Installation-MAR-018 - Global | 2.0 Construction | RCP2.12 - End Treatment – Headwall & Wingwalls (Formwork) | N/A | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | Global RCP | ITP-004 RCP Installation-MAR-018 - Global
cl:422980e3-ac79-4913-b4ad-54ef63cf0d32 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation > Global RCP | ITP-004 RCP Installation-MAR-018 - Global | 2.0 Construction | RCP2.13 - End Treatment – Headwall & Wingwalls (Concrete) | N/A | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | Global RCP | ITP-004 RCP Installation-MAR-018 - Global
cl:422980e3-ac79-4913-b4ad-54ef63cf0d32 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation > Global RCP | ITP-004 RCP Installation-MAR-018 - Global | 2.0 Construction | RCP2.14 - Rock Protection | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | Global RCP | ITP-004 RCP Installation-MAR-018 - Global
cl:422980e3-ac79-4913-b4ad-54ef63cf0d32 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-004 RCP Installation > Global RCP | ITP-004 RCP Installation-MAR-018 - Global | 3.0 Post Construction | RCP3.15 - Works completed and update ITP/ Lot Register/ MDR and close out of GDP | Not started | Open | ITP-004 RCP Installation | AWP-1A | Main Access Road (MAR) | ITP-004 RCP Installation | Global RCP | ITP-004 RCP Installation-MAR-018 - Global
cl:677bd369-096a-4938-9fa5-fc2031fac91e | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-001 | Embankment Construction | EC1.1 - Underlying lot & ITP signed off and conforming | In progress | Open | ITP-008 Embankment Construction | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-001
cl:677bd369-096a-4938-9fa5-fc2031fac91e | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-001 | Embankment Construction | EC1.2 - Embankment fill material | Passed | Open | ITP-008 Embankment Construction | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-001
cl:677bd369-096a-4938-9fa5-fc2031fac91e | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-001 | Embankment Construction | EC1.3 - Survey Set out | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-001
cl:677bd369-096a-4938-9fa5-fc2031fac91e | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-001 | Embankment Construction | EC1.4 - Place, moisture condition & compact embankment fill | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-001
cl:677bd369-096a-4938-9fa5-fc2031fac91e | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-001 | Embankment Construction | EC1.5 - Trim embankment | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-001
cl:677bd369-096a-4938-9fa5-fc2031fac91e | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-001 | Embankment Construction | EC1.6 - Proof rolling | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-001
cl:677bd369-096a-4938-9fa5-fc2031fac91e | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-001 | Embankment Construction | EC1.7 - Surface level check and survey pick-up | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-001
cl:677bd369-096a-4938-9fa5-fc2031fac91e | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-001 | Embankment Construction | EC1.8 - QA close out | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-001
cl:55dd702f-9ef0-4d44-b31c-11f4a89a057c | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-002 | Embankment Construction | EC1.1 - Underlying lot & ITP signed off and conforming | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-002
cl:55dd702f-9ef0-4d44-b31c-11f4a89a057c | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-002 | Embankment Construction | EC1.2 - Embankment fill material | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-002
cl:55dd702f-9ef0-4d44-b31c-11f4a89a057c | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-002 | Embankment Construction | EC1.3 - Survey Set out | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-002
cl:55dd702f-9ef0-4d44-b31c-11f4a89a057c | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-002 | Embankment Construction | EC1.4 - Place, moisture condition & compact embankment fill | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-002
cl:55dd702f-9ef0-4d44-b31c-11f4a89a057c | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-002 | Embankment Construction | EC1.5 - Trim embankment | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-002
cl:55dd702f-9ef0-4d44-b31c-11f4a89a057c | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-002 | Embankment Construction | EC1.6 - Proof rolling | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-002
cl:55dd702f-9ef0-4d44-b31c-11f4a89a057c | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-002 | Embankment Construction | EC1.7 - Surface level check and survey pick-up | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-002
cl:55dd702f-9ef0-4d44-b31c-11f4a89a057c | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-002 | Embankment Construction | EC1.8 - QA close out | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-002
cl:21ed1d63-15df-421c-8ea0-1662ef191936 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-003 | Embankment Construction | EC1.1 - Underlying lot & ITP signed off and conforming | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-003
cl:21ed1d63-15df-421c-8ea0-1662ef191936 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-003 | Embankment Construction | EC1.2 - Embankment fill material | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-003
cl:21ed1d63-15df-421c-8ea0-1662ef191936 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-003 | Embankment Construction | EC1.3 - Survey Set out | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-003
cl:21ed1d63-15df-421c-8ea0-1662ef191936 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-003 | Embankment Construction | EC1.4 - Place, moisture condition & compact embankment fill | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-003
cl:21ed1d63-15df-421c-8ea0-1662ef191936 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-003 | Embankment Construction | EC1.5 - Trim embankment | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-003
cl:21ed1d63-15df-421c-8ea0-1662ef191936 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-003 | Embankment Construction | EC1.6 - Proof rolling | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-003
cl:21ed1d63-15df-421c-8ea0-1662ef191936 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-003 | Embankment Construction | EC1.7 - Surface level check and survey pick-up | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-003
cl:21ed1d63-15df-421c-8ea0-1662ef191936 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-003 | Embankment Construction | EC1.8 - QA close out | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-003
cl:72b1db10-1292-4f46-b3bf-822d4bc53073 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-004 | Embankment Construction | EC1.1 - Underlying lot & ITP signed off and conforming | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-004
cl:72b1db10-1292-4f46-b3bf-822d4bc53073 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-004 | Embankment Construction | EC1.2 - Embankment fill material | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-004
cl:72b1db10-1292-4f46-b3bf-822d4bc53073 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-004 | Embankment Construction | EC1.3 - Survey Set out | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-004
cl:72b1db10-1292-4f46-b3bf-822d4bc53073 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-004 | Embankment Construction | EC1.4 - Place, moisture condition & compact embankment fill | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-004
cl:72b1db10-1292-4f46-b3bf-822d4bc53073 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-004 | Embankment Construction | EC1.5 - Trim embankment | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-004
cl:72b1db10-1292-4f46-b3bf-822d4bc53073 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-004 | Embankment Construction | EC1.6 - Proof rolling | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-004
cl:72b1db10-1292-4f46-b3bf-822d4bc53073 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-004 | Embankment Construction | EC1.7 - Surface level check and survey pick-up | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-004
cl:72b1db10-1292-4f46-b3bf-822d4bc53073 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-004 | Embankment Construction | EC1.8 - QA close out | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-004
cl:71558f67-7388-476c-b403-7bdf8ca4578b | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-005 | Embankment Construction | EC1.1 - Underlying lot & ITP signed off and conforming | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-005
cl:71558f67-7388-476c-b403-7bdf8ca4578b | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-005 | Embankment Construction | EC1.2 - Embankment fill material | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-005
cl:71558f67-7388-476c-b403-7bdf8ca4578b | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-005 | Embankment Construction | EC1.3 - Survey Set out | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-005
cl:71558f67-7388-476c-b403-7bdf8ca4578b | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-005 | Embankment Construction | EC1.4 - Place, moisture condition & compact embankment fill | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-005
cl:71558f67-7388-476c-b403-7bdf8ca4578b | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-005 | Embankment Construction | EC1.5 - Trim embankment | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-005
cl:71558f67-7388-476c-b403-7bdf8ca4578b | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-005 | Embankment Construction | EC1.6 - Proof rolling | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-005
cl:71558f67-7388-476c-b403-7bdf8ca4578b | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-005 | Embankment Construction | EC1.7 - Surface level check and survey pick-up | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-005
cl:71558f67-7388-476c-b403-7bdf8ca4578b | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-005 | Embankment Construction | EC1.8 - QA close out | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-005
cl:8815128e-ec87-48da-a663-0f168a937a26 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-006 | Embankment Construction | EC1.1 - Underlying lot & ITP signed off and conforming | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-006
cl:8815128e-ec87-48da-a663-0f168a937a26 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-006 | Embankment Construction | EC1.2 - Embankment fill material | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-006
cl:8815128e-ec87-48da-a663-0f168a937a26 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-006 | Embankment Construction | EC1.3 - Survey Set out | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-006
cl:8815128e-ec87-48da-a663-0f168a937a26 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-006 | Embankment Construction | EC1.4 - Place, moisture condition & compact embankment fill | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-006
cl:8815128e-ec87-48da-a663-0f168a937a26 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-006 | Embankment Construction | EC1.5 - Trim embankment | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-006
cl:8815128e-ec87-48da-a663-0f168a937a26 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-006 | Embankment Construction | EC1.6 - Proof rolling | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-006
cl:8815128e-ec87-48da-a663-0f168a937a26 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-006 | Embankment Construction | EC1.7 - Surface level check and survey pick-up | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-006
cl:8815128e-ec87-48da-a663-0f168a937a26 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-006 | Embankment Construction | EC1.8 - QA close out | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-006
cl:b5312136-2d65-40fb-a4ea-3adcb065938b | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-007 | Embankment Construction | EC1.1 - Underlying lot & ITP signed off and conforming | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-007
cl:b5312136-2d65-40fb-a4ea-3adcb065938b | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-007 | Embankment Construction | EC1.2 - Embankment fill material | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-007
cl:b5312136-2d65-40fb-a4ea-3adcb065938b | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-007 | Embankment Construction | EC1.3 - Survey Set out | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-007
cl:b5312136-2d65-40fb-a4ea-3adcb065938b | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-007 | Embankment Construction | EC1.4 - Place, moisture condition & compact embankment fill | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-007
cl:b5312136-2d65-40fb-a4ea-3adcb065938b | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-007 | Embankment Construction | EC1.5 - Trim embankment | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-007
cl:b5312136-2d65-40fb-a4ea-3adcb065938b | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-007 | Embankment Construction | EC1.6 - Proof rolling | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-007
cl:b5312136-2d65-40fb-a4ea-3adcb065938b | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-007 | Embankment Construction | EC1.7 - Surface level check and survey pick-up | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-007
cl:b5312136-2d65-40fb-a4ea-3adcb065938b | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-007 | Embankment Construction | EC1.8 - QA close out | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-007
cl:16667826-9565-4d11-b909-c2201b54448b | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-008 | Embankment Construction | EC1.1 - Underlying lot & ITP signed off and conforming | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-008
cl:16667826-9565-4d11-b909-c2201b54448b | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-008 | Embankment Construction | EC1.2 - Embankment fill material | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-008
cl:16667826-9565-4d11-b909-c2201b54448b | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-008 | Embankment Construction | EC1.3 - Survey Set out | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-008
cl:16667826-9565-4d11-b909-c2201b54448b | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-008 | Embankment Construction | EC1.4 - Place, moisture condition & compact embankment fill | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-008
cl:16667826-9565-4d11-b909-c2201b54448b | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-008 | Embankment Construction | EC1.5 - Trim embankment | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-008
cl:16667826-9565-4d11-b909-c2201b54448b | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-008 | Embankment Construction | EC1.6 - Proof rolling | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-008
cl:16667826-9565-4d11-b909-c2201b54448b | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-008 | Embankment Construction | EC1.7 - Surface level check and survey pick-up | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-008
cl:16667826-9565-4d11-b909-c2201b54448b | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-008 | Embankment Construction | EC1.8 - QA close out | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-008
cl:c7b6301c-1383-4a62-b466-ac1369643971 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-009 | Embankment Construction | EC1.1 - Underlying lot & ITP signed off and conforming | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-009
cl:c7b6301c-1383-4a62-b466-ac1369643971 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-009 | Embankment Construction | EC1.2 - Embankment fill material | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-009
cl:c7b6301c-1383-4a62-b466-ac1369643971 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-009 | Embankment Construction | EC1.3 - Survey Set out | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-009
cl:c7b6301c-1383-4a62-b466-ac1369643971 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-009 | Embankment Construction | EC1.4 - Place, moisture condition & compact embankment fill | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-009
cl:c7b6301c-1383-4a62-b466-ac1369643971 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-009 | Embankment Construction | EC1.5 - Trim embankment | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-009
cl:c7b6301c-1383-4a62-b466-ac1369643971 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-009 | Embankment Construction | EC1.6 - Proof rolling | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-009
cl:c7b6301c-1383-4a62-b466-ac1369643971 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-009 | Embankment Construction | EC1.7 - Surface level check and survey pick-up | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-009
cl:c7b6301c-1383-4a62-b466-ac1369643971 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-009 | Embankment Construction | EC1.8 - QA close out | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-009
cl:48f8a636-f478-4fde-b1b2-bd0342c530df | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-010 | Embankment Construction | EC1.1 - Underlying lot & ITP signed off and conforming | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-010
cl:48f8a636-f478-4fde-b1b2-bd0342c530df | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-010 | Embankment Construction | EC1.2 - Embankment fill material | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-010
cl:48f8a636-f478-4fde-b1b2-bd0342c530df | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-010 | Embankment Construction | EC1.3 - Survey Set out | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-010
cl:48f8a636-f478-4fde-b1b2-bd0342c530df | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-010 | Embankment Construction | EC1.4 - Place, moisture condition & compact embankment fill | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-010
cl:48f8a636-f478-4fde-b1b2-bd0342c530df | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-010 | Embankment Construction | EC1.5 - Trim embankment | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-010
cl:48f8a636-f478-4fde-b1b2-bd0342c530df | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-010 | Embankment Construction | EC1.6 - Proof rolling | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-010
cl:48f8a636-f478-4fde-b1b2-bd0342c530df | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-010 | Embankment Construction | EC1.7 - Surface level check and survey pick-up | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-010
cl:48f8a636-f478-4fde-b1b2-bd0342c530df | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-010 | Embankment Construction | EC1.8 - QA close out | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-010
cl:1d69aa48-b390-4956-ace2-858e4bcf6c56 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-011 | Embankment Construction | EC1.1 - Underlying lot & ITP signed off and conforming | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-011
cl:1d69aa48-b390-4956-ace2-858e4bcf6c56 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-011 | Embankment Construction | EC1.2 - Embankment fill material | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-011
cl:1d69aa48-b390-4956-ace2-858e4bcf6c56 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-011 | Embankment Construction | EC1.3 - Survey Set out | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-011
cl:1d69aa48-b390-4956-ace2-858e4bcf6c56 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-011 | Embankment Construction | EC1.4 - Place, moisture condition & compact embankment fill | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-011
cl:1d69aa48-b390-4956-ace2-858e4bcf6c56 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-011 | Embankment Construction | EC1.5 - Trim embankment | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-011
cl:1d69aa48-b390-4956-ace2-858e4bcf6c56 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-011 | Embankment Construction | EC1.6 - Proof rolling | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-011
cl:1d69aa48-b390-4956-ace2-858e4bcf6c56 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-011 | Embankment Construction | EC1.7 - Surface level check and survey pick-up | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-011
cl:1d69aa48-b390-4956-ace2-858e4bcf6c56 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-011 | Embankment Construction | EC1.8 - QA close out | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-011
cl:a8234618-0e56-45ee-8c35-e5aa30bb12cb | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-012 | Embankment Construction | EC1.1 - Underlying lot & ITP signed off and conforming | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-012
cl:a8234618-0e56-45ee-8c35-e5aa30bb12cb | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-012 | Embankment Construction | EC1.2 - Embankment fill material | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-012
cl:a8234618-0e56-45ee-8c35-e5aa30bb12cb | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-012 | Embankment Construction | EC1.3 - Survey Set out | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-012
cl:a8234618-0e56-45ee-8c35-e5aa30bb12cb | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-012 | Embankment Construction | EC1.4 - Place, moisture condition & compact embankment fill | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-012
cl:a8234618-0e56-45ee-8c35-e5aa30bb12cb | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-012 | Embankment Construction | EC1.5 - Trim embankment | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-012
cl:a8234618-0e56-45ee-8c35-e5aa30bb12cb | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-012 | Embankment Construction | EC1.6 - Proof rolling | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-012
cl:a8234618-0e56-45ee-8c35-e5aa30bb12cb | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-012 | Embankment Construction | EC1.7 - Surface level check and survey pick-up | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-012
cl:a8234618-0e56-45ee-8c35-e5aa30bb12cb | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-012 | Embankment Construction | EC1.8 - QA close out | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-012
cl:edde45ff-09a9-49cc-b485-0fd70ebadf74 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-013 | Embankment Construction | EC1.1 - Underlying lot & ITP signed off and conforming | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-013
cl:edde45ff-09a9-49cc-b485-0fd70ebadf74 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-013 | Embankment Construction | EC1.2 - Embankment fill material | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-013
cl:edde45ff-09a9-49cc-b485-0fd70ebadf74 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-013 | Embankment Construction | EC1.3 - Survey Set out | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-013
cl:edde45ff-09a9-49cc-b485-0fd70ebadf74 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-013 | Embankment Construction | EC1.4 - Place, moisture condition & compact embankment fill | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-013
cl:edde45ff-09a9-49cc-b485-0fd70ebadf74 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-013 | Embankment Construction | EC1.5 - Trim embankment | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-013
cl:edde45ff-09a9-49cc-b485-0fd70ebadf74 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-013 | Embankment Construction | EC1.6 - Proof rolling | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-013
cl:edde45ff-09a9-49cc-b485-0fd70ebadf74 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-013 | Embankment Construction | EC1.7 - Surface level check and survey pick-up | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-013
cl:edde45ff-09a9-49cc-b485-0fd70ebadf74 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-013 | Embankment Construction | EC1.8 - QA close out | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-013
cl:c9959181-8906-4731-9758-8476ccbc2ae4 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-014 | Embankment Construction | EC1.1 - Underlying lot & ITP signed off and conforming | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-014
cl:c9959181-8906-4731-9758-8476ccbc2ae4 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-014 | Embankment Construction | EC1.2 - Embankment fill material | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-014
cl:c9959181-8906-4731-9758-8476ccbc2ae4 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-014 | Embankment Construction | EC1.3 - Survey Set out | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-014
cl:c9959181-8906-4731-9758-8476ccbc2ae4 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-014 | Embankment Construction | EC1.4 - Place, moisture condition & compact embankment fill | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-014
cl:c9959181-8906-4731-9758-8476ccbc2ae4 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-014 | Embankment Construction | EC1.5 - Trim embankment | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-014
cl:c9959181-8906-4731-9758-8476ccbc2ae4 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-014 | Embankment Construction | EC1.6 - Proof rolling | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-014
cl:c9959181-8906-4731-9758-8476ccbc2ae4 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-014 | Embankment Construction | EC1.7 - Surface level check and survey pick-up | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-014
cl:c9959181-8906-4731-9758-8476ccbc2ae4 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-014 | Embankment Construction | EC1.8 - QA close out | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-014
cl:1d851afd-6473-4983-86ff-3944ee158b12 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-015 | Embankment Construction | EC1.1 - Underlying lot & ITP signed off and conforming | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-015
cl:1d851afd-6473-4983-86ff-3944ee158b12 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-015 | Embankment Construction | EC1.2 - Embankment fill material | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-015
cl:1d851afd-6473-4983-86ff-3944ee158b12 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-015 | Embankment Construction | EC1.3 - Survey Set out | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-015
cl:1d851afd-6473-4983-86ff-3944ee158b12 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-015 | Embankment Construction | EC1.4 - Place, moisture condition & compact embankment fill | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-015
cl:1d851afd-6473-4983-86ff-3944ee158b12 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-015 | Embankment Construction | EC1.5 - Trim embankment | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-015
cl:1d851afd-6473-4983-86ff-3944ee158b12 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-015 | Embankment Construction | EC1.6 - Proof rolling | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-015
cl:1d851afd-6473-4983-86ff-3944ee158b12 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-015 | Embankment Construction | EC1.7 - Surface level check and survey pick-up | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-015
cl:1d851afd-6473-4983-86ff-3944ee158b12 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-015 | Embankment Construction | EC1.8 - QA close out | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-015
cl:b88a7678-4b1d-4d3f-b470-553e064a93e4 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-016 | Embankment Construction | EC1.1 - Underlying lot & ITP signed off and conforming | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-016
cl:b88a7678-4b1d-4d3f-b470-553e064a93e4 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-016 | Embankment Construction | EC1.2 - Embankment fill material | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-016
cl:b88a7678-4b1d-4d3f-b470-553e064a93e4 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-016 | Embankment Construction | EC1.3 - Survey Set out | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-016
cl:b88a7678-4b1d-4d3f-b470-553e064a93e4 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-016 | Embankment Construction | EC1.4 - Place, moisture condition & compact embankment fill | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-016
cl:b88a7678-4b1d-4d3f-b470-553e064a93e4 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-016 | Embankment Construction | EC1.5 - Trim embankment | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-016
cl:b88a7678-4b1d-4d3f-b470-553e064a93e4 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-016 | Embankment Construction | EC1.6 - Proof rolling | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-016
cl:b88a7678-4b1d-4d3f-b470-553e064a93e4 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-016 | Embankment Construction | EC1.7 - Surface level check and survey pick-up | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-016
cl:b88a7678-4b1d-4d3f-b470-553e064a93e4 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-016 | Embankment Construction | EC1.8 - QA close out | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-016
cl:40473b7b-e086-45dd-a85c-dc23e476f2f3 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-017 | Embankment Construction | EC1.1 - Underlying lot & ITP signed off and conforming | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-017
cl:40473b7b-e086-45dd-a85c-dc23e476f2f3 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-017 | Embankment Construction | EC1.2 - Embankment fill material | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-017
cl:40473b7b-e086-45dd-a85c-dc23e476f2f3 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-017 | Embankment Construction | EC1.3 - Survey Set out | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-017
cl:40473b7b-e086-45dd-a85c-dc23e476f2f3 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-017 | Embankment Construction | EC1.4 - Place, moisture condition & compact embankment fill | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-017
cl:40473b7b-e086-45dd-a85c-dc23e476f2f3 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-017 | Embankment Construction | EC1.5 - Trim embankment | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-017
cl:40473b7b-e086-45dd-a85c-dc23e476f2f3 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-017 | Embankment Construction | EC1.6 - Proof rolling | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-017
cl:40473b7b-e086-45dd-a85c-dc23e476f2f3 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-017 | Embankment Construction | EC1.7 - Surface level check and survey pick-up | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-017
cl:40473b7b-e086-45dd-a85c-dc23e476f2f3 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-017 | Embankment Construction | EC1.8 - QA close out | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Main Access Road (MAR) | ITP-008 Embankment Construction | ITP-008 Embankment Construction-MAR-017
cl:3ab8f4bf-0aba-4f15-9b6a-18f0b2f28529 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-001 | 1.0 Pre-Construction | GP1.1 - Drawings supplied most current IFC | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-001
cl:3ab8f4bf-0aba-4f15-9b6a-18f0b2f28529 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-001 | 1.0 Pre-Construction | GP1.2 - Management Plans submitted and approved as per PMP | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-001
cl:3ab8f4bf-0aba-4f15-9b6a-18f0b2f28529 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-001 | 1.0 Pre-Construction | GP1.3 - Inspection Test Plan (ITP) submitted and approved | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-001
cl:3ab8f4bf-0aba-4f15-9b6a-18f0b2f28529 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-001 | 1.0 Pre-Construction | GP1.4 - Lot Register/ WBS submitted and approved | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-001
cl:3ab8f4bf-0aba-4f15-9b6a-18f0b2f28529 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-001 | 1.0 Pre-Construction | GP1.5 - Pavement material compliance testing | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-001
cl:3ab8f4bf-0aba-4f15-9b6a-18f0b2f28529 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-001 | 1.0 Pre-Construction | GP1.6 - Stockpile locations | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-001
cl:3ab8f4bf-0aba-4f15-9b6a-18f0b2f28529 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-001 | 1.0 Pre-Construction | GP1.7 - Underlying lot & ITP signed off and conforming | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-001
cl:3ab8f4bf-0aba-4f15-9b6a-18f0b2f28529 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-001 | 2.0 Construction | GP2.8 - Subgrade preparation under pavements | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-001
cl:3ab8f4bf-0aba-4f15-9b6a-18f0b2f28529 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-001 | 2.0 Construction | EC2.9 - Surface level check/ and survey pick-up | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-001
cl:3ab8f4bf-0aba-4f15-9b6a-18f0b2f28529 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-001 | 2.0 Construction | EC2.10 - Proof roll subgrade prior to placement of pavement materials | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-001
cl:3ab8f4bf-0aba-4f15-9b6a-18f0b2f28529 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-001 | 2.0 Construction | EC2.11 - Placement of pavement material layers | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-001
cl:3ab8f4bf-0aba-4f15-9b6a-18f0b2f28529 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-001 | 2.0 Construction | EC2.12 - Surface level check/ and survey pick-up | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-001
cl:3ab8f4bf-0aba-4f15-9b6a-18f0b2f28529 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-001 | 3.0 Post Construction | EC3.13 - Works completed and update ITP/ Lot Register/ MDR and close out of GDP | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-001
cl:7d8b619b-e51f-4180-943b-6f39301cd46e | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-002 | 1.0 Pre-Construction | GP1.1 - Drawings supplied most current IFC | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-002
cl:7d8b619b-e51f-4180-943b-6f39301cd46e | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-002 | 1.0 Pre-Construction | GP1.2 - Management Plans submitted and approved as per PMP | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-002
cl:7d8b619b-e51f-4180-943b-6f39301cd46e | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-002 | 1.0 Pre-Construction | GP1.3 - Inspection Test Plan (ITP) submitted and approved | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-002
cl:7d8b619b-e51f-4180-943b-6f39301cd46e | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-002 | 1.0 Pre-Construction | GP1.4 - Lot Register/ WBS submitted and approved | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-002
cl:7d8b619b-e51f-4180-943b-6f39301cd46e | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-002 | 1.0 Pre-Construction | GP1.5 - Pavement material compliance testing | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-002
cl:7d8b619b-e51f-4180-943b-6f39301cd46e | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-002 | 1.0 Pre-Construction | GP1.6 - Stockpile locations | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-002
cl:7d8b619b-e51f-4180-943b-6f39301cd46e | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-002 | 1.0 Pre-Construction | GP1.7 - Underlying lot & ITP signed off and conforming | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-002
cl:7d8b619b-e51f-4180-943b-6f39301cd46e | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-002 | 2.0 Construction | GP2.8 - Subgrade preparation under pavements | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-002
cl:7d8b619b-e51f-4180-943b-6f39301cd46e | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-002 | 2.0 Construction | EC2.9 - Surface level check/ and survey pick-up | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-002
cl:7d8b619b-e51f-4180-943b-6f39301cd46e | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-002 | 2.0 Construction | EC2.10 - Proof roll subgrade prior to placement of pavement materials | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-002
cl:7d8b619b-e51f-4180-943b-6f39301cd46e | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-002 | 2.0 Construction | EC2.11 - Placement of pavement material layers | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-002
cl:7d8b619b-e51f-4180-943b-6f39301cd46e | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-002 | 2.0 Construction | EC2.12 - Surface level check/ and survey pick-up | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-002
cl:7d8b619b-e51f-4180-943b-6f39301cd46e | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-002 | 3.0 Post Construction | EC3.13 - Works completed and update ITP/ Lot Register/ MDR and close out of GDP | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-002
cl:9c2e4830-6b5e-4d6d-9ece-69056bc38f4d | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-003 | 1.0 Pre-Construction | GP1.1 - Drawings supplied most current IFC | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-003
cl:9c2e4830-6b5e-4d6d-9ece-69056bc38f4d | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-003 | 1.0 Pre-Construction | GP1.2 - Management Plans submitted and approved as per PMP | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-003
cl:9c2e4830-6b5e-4d6d-9ece-69056bc38f4d | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-003 | 1.0 Pre-Construction | GP1.3 - Inspection Test Plan (ITP) submitted and approved | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-003
cl:9c2e4830-6b5e-4d6d-9ece-69056bc38f4d | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-003 | 1.0 Pre-Construction | GP1.4 - Lot Register/ WBS submitted and approved | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-003
cl:9c2e4830-6b5e-4d6d-9ece-69056bc38f4d | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-003 | 1.0 Pre-Construction | GP1.5 - Pavement material compliance testing | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-003
cl:9c2e4830-6b5e-4d6d-9ece-69056bc38f4d | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-003 | 1.0 Pre-Construction | GP1.6 - Stockpile locations | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-003
cl:9c2e4830-6b5e-4d6d-9ece-69056bc38f4d | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-003 | 1.0 Pre-Construction | GP1.7 - Underlying lot & ITP signed off and conforming | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-003
cl:9c2e4830-6b5e-4d6d-9ece-69056bc38f4d | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-003 | 2.0 Construction | GP2.8 - Subgrade preparation under pavements | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-003
cl:9c2e4830-6b5e-4d6d-9ece-69056bc38f4d | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-003 | 2.0 Construction | EC2.9 - Surface level check/ and survey pick-up | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-003
cl:9c2e4830-6b5e-4d6d-9ece-69056bc38f4d | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-003 | 2.0 Construction | EC2.10 - Proof roll subgrade prior to placement of pavement materials | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-003
cl:9c2e4830-6b5e-4d6d-9ece-69056bc38f4d | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-003 | 2.0 Construction | EC2.11 - Placement of pavement material layers | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-003
cl:9c2e4830-6b5e-4d6d-9ece-69056bc38f4d | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-003 | 2.0 Construction | EC2.12 - Surface level check/ and survey pick-up | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-003
cl:9c2e4830-6b5e-4d6d-9ece-69056bc38f4d | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-003 | 3.0 Post Construction | EC3.13 - Works completed and update ITP/ Lot Register/ MDR and close out of GDP | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-003
cl:ded39db4-f2a2-4925-b6ab-9cb39d7a8bf4 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-004 | 1.0 Pre-Construction | GP1.1 - Drawings supplied most current IFC | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-004
cl:ded39db4-f2a2-4925-b6ab-9cb39d7a8bf4 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-004 | 1.0 Pre-Construction | GP1.2 - Management Plans submitted and approved as per PMP | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-004
cl:ded39db4-f2a2-4925-b6ab-9cb39d7a8bf4 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-004 | 1.0 Pre-Construction | GP1.3 - Inspection Test Plan (ITP) submitted and approved | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-004
cl:ded39db4-f2a2-4925-b6ab-9cb39d7a8bf4 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-004 | 1.0 Pre-Construction | GP1.4 - Lot Register/ WBS submitted and approved | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-004
cl:ded39db4-f2a2-4925-b6ab-9cb39d7a8bf4 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-004 | 1.0 Pre-Construction | GP1.5 - Pavement material compliance testing | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-004
cl:ded39db4-f2a2-4925-b6ab-9cb39d7a8bf4 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-004 | 1.0 Pre-Construction | GP1.6 - Stockpile locations | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-004
cl:ded39db4-f2a2-4925-b6ab-9cb39d7a8bf4 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-004 | 1.0 Pre-Construction | GP1.7 - Underlying lot & ITP signed off and conforming | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-004
cl:ded39db4-f2a2-4925-b6ab-9cb39d7a8bf4 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-004 | 2.0 Construction | GP2.8 - Subgrade preparation under pavements | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-004
cl:ded39db4-f2a2-4925-b6ab-9cb39d7a8bf4 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-004 | 2.0 Construction | EC2.9 - Surface level check/ and survey pick-up | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-004
cl:ded39db4-f2a2-4925-b6ab-9cb39d7a8bf4 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-004 | 2.0 Construction | EC2.10 - Proof roll subgrade prior to placement of pavement materials | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-004
cl:ded39db4-f2a2-4925-b6ab-9cb39d7a8bf4 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-004 | 2.0 Construction | EC2.11 - Placement of pavement material layers | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-004
cl:ded39db4-f2a2-4925-b6ab-9cb39d7a8bf4 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-004 | 2.0 Construction | EC2.12 - Surface level check/ and survey pick-up | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-004
cl:ded39db4-f2a2-4925-b6ab-9cb39d7a8bf4 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-004 | 3.0 Post Construction | EC3.13 - Works completed and update ITP/ Lot Register/ MDR and close out of GDP | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-004
cl:5c51972b-e8fc-4c9e-b95a-77776cedcf01 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-005 | 1.0 Pre-Construction | GP1.1 - Drawings supplied most current IFC | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-005
cl:5c51972b-e8fc-4c9e-b95a-77776cedcf01 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-005 | 1.0 Pre-Construction | GP1.2 - Management Plans submitted and approved as per PMP | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-005
cl:5c51972b-e8fc-4c9e-b95a-77776cedcf01 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-005 | 1.0 Pre-Construction | GP1.3 - Inspection Test Plan (ITP) submitted and approved | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-005
cl:5c51972b-e8fc-4c9e-b95a-77776cedcf01 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-005 | 1.0 Pre-Construction | GP1.4 - Lot Register/ WBS submitted and approved | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-005
cl:5c51972b-e8fc-4c9e-b95a-77776cedcf01 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-005 | 1.0 Pre-Construction | GP1.5 - Pavement material compliance testing | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-005
cl:5c51972b-e8fc-4c9e-b95a-77776cedcf01 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-005 | 1.0 Pre-Construction | GP1.6 - Stockpile locations | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-005
cl:5c51972b-e8fc-4c9e-b95a-77776cedcf01 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-005 | 1.0 Pre-Construction | GP1.7 - Underlying lot & ITP signed off and conforming | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-005
cl:5c51972b-e8fc-4c9e-b95a-77776cedcf01 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-005 | 2.0 Construction | GP2.8 - Subgrade preparation under pavements | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-005
cl:5c51972b-e8fc-4c9e-b95a-77776cedcf01 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-005 | 2.0 Construction | EC2.9 - Surface level check/ and survey pick-up | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-005
cl:5c51972b-e8fc-4c9e-b95a-77776cedcf01 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-005 | 2.0 Construction | EC2.10 - Proof roll subgrade prior to placement of pavement materials | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-005
cl:5c51972b-e8fc-4c9e-b95a-77776cedcf01 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-005 | 2.0 Construction | EC2.11 - Placement of pavement material layers | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-005
cl:5c51972b-e8fc-4c9e-b95a-77776cedcf01 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-005 | 2.0 Construction | EC2.12 - Surface level check/ and survey pick-up | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-005
cl:5c51972b-e8fc-4c9e-b95a-77776cedcf01 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-005 | 3.0 Post Construction | EC3.13 - Works completed and update ITP/ Lot Register/ MDR and close out of GDP | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-005
cl:cd26b24b-154d-4209-bd7f-c15eaa603b5d | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-006 | 1.0 Pre-Construction | GP1.1 - Drawings supplied most current IFC | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-006
cl:cd26b24b-154d-4209-bd7f-c15eaa603b5d | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-006 | 1.0 Pre-Construction | GP1.2 - Management Plans submitted and approved as per PMP | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-006
cl:cd26b24b-154d-4209-bd7f-c15eaa603b5d | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-006 | 1.0 Pre-Construction | GP1.3 - Inspection Test Plan (ITP) submitted and approved | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-006
cl:cd26b24b-154d-4209-bd7f-c15eaa603b5d | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-006 | 1.0 Pre-Construction | GP1.4 - Lot Register/ WBS submitted and approved | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-006
cl:cd26b24b-154d-4209-bd7f-c15eaa603b5d | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-006 | 1.0 Pre-Construction | GP1.5 - Pavement material compliance testing | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-006
cl:cd26b24b-154d-4209-bd7f-c15eaa603b5d | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-006 | 1.0 Pre-Construction | GP1.6 - Stockpile locations | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-006
cl:cd26b24b-154d-4209-bd7f-c15eaa603b5d | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-006 | 1.0 Pre-Construction | GP1.7 - Underlying lot & ITP signed off and conforming | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-006
cl:cd26b24b-154d-4209-bd7f-c15eaa603b5d | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-006 | 2.0 Construction | GP2.8 - Subgrade preparation under pavements | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-006
cl:cd26b24b-154d-4209-bd7f-c15eaa603b5d | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-006 | 2.0 Construction | EC2.9 - Surface level check/ and survey pick-up | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-006
cl:cd26b24b-154d-4209-bd7f-c15eaa603b5d | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-006 | 2.0 Construction | EC2.10 - Proof roll subgrade prior to placement of pavement materials | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-006
cl:cd26b24b-154d-4209-bd7f-c15eaa603b5d | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-006 | 2.0 Construction | EC2.11 - Placement of pavement material layers | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-006
cl:cd26b24b-154d-4209-bd7f-c15eaa603b5d | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-006 | 2.0 Construction | EC2.12 - Surface level check/ and survey pick-up | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-006
cl:cd26b24b-154d-4209-bd7f-c15eaa603b5d | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-006 | 3.0 Post Construction | EC3.13 - Works completed and update ITP/ Lot Register/ MDR and close out of GDP | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-006
cl:d2221e0e-7fec-4435-b9e9-ce8c59a00f43 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-007 | 1.0 Pre-Construction | GP1.1 - Drawings supplied most current IFC | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-007
cl:d2221e0e-7fec-4435-b9e9-ce8c59a00f43 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-007 | 1.0 Pre-Construction | GP1.2 - Management Plans submitted and approved as per PMP | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-007
cl:d2221e0e-7fec-4435-b9e9-ce8c59a00f43 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-007 | 1.0 Pre-Construction | GP1.3 - Inspection Test Plan (ITP) submitted and approved | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-007
cl:d2221e0e-7fec-4435-b9e9-ce8c59a00f43 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-007 | 1.0 Pre-Construction | GP1.4 - Lot Register/ WBS submitted and approved | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-007
cl:d2221e0e-7fec-4435-b9e9-ce8c59a00f43 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-007 | 1.0 Pre-Construction | GP1.5 - Pavement material compliance testing | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-007
cl:d2221e0e-7fec-4435-b9e9-ce8c59a00f43 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-007 | 1.0 Pre-Construction | GP1.6 - Stockpile locations | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-007
cl:d2221e0e-7fec-4435-b9e9-ce8c59a00f43 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-007 | 1.0 Pre-Construction | GP1.7 - Underlying lot & ITP signed off and conforming | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-007
cl:d2221e0e-7fec-4435-b9e9-ce8c59a00f43 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-007 | 2.0 Construction | GP2.8 - Subgrade preparation under pavements | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-007
cl:d2221e0e-7fec-4435-b9e9-ce8c59a00f43 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-007 | 2.0 Construction | EC2.9 - Surface level check/ and survey pick-up | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-007
cl:d2221e0e-7fec-4435-b9e9-ce8c59a00f43 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-007 | 2.0 Construction | EC2.10 - Proof roll subgrade prior to placement of pavement materials | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-007
cl:d2221e0e-7fec-4435-b9e9-ce8c59a00f43 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-007 | 2.0 Construction | EC2.11 - Placement of pavement material layers | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-007
cl:d2221e0e-7fec-4435-b9e9-ce8c59a00f43 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-007 | 2.0 Construction | EC2.12 - Surface level check/ and survey pick-up | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-007
cl:d2221e0e-7fec-4435-b9e9-ce8c59a00f43 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-007 | 3.0 Post Construction | EC3.13 - Works completed and update ITP/ Lot Register/ MDR and close out of GDP | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-007
cl:8bf7387d-1f7f-49cc-91b0-9d65f23d51ae | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-008 | 1.0 Pre-Construction | GP1.1 - Drawings supplied most current IFC | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-008
cl:8bf7387d-1f7f-49cc-91b0-9d65f23d51ae | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-008 | 1.0 Pre-Construction | GP1.2 - Management Plans submitted and approved as per PMP | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-008
cl:8bf7387d-1f7f-49cc-91b0-9d65f23d51ae | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-008 | 1.0 Pre-Construction | GP1.3 - Inspection Test Plan (ITP) submitted and approved | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-008
cl:8bf7387d-1f7f-49cc-91b0-9d65f23d51ae | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-008 | 1.0 Pre-Construction | GP1.4 - Lot Register/ WBS submitted and approved | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-008
cl:8bf7387d-1f7f-49cc-91b0-9d65f23d51ae | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-008 | 1.0 Pre-Construction | GP1.5 - Pavement material compliance testing | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-008
cl:8bf7387d-1f7f-49cc-91b0-9d65f23d51ae | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-008 | 1.0 Pre-Construction | GP1.6 - Stockpile locations | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-008
cl:8bf7387d-1f7f-49cc-91b0-9d65f23d51ae | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-008 | 1.0 Pre-Construction | GP1.7 - Underlying lot & ITP signed off and conforming | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-008
cl:8bf7387d-1f7f-49cc-91b0-9d65f23d51ae | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-008 | 2.0 Construction | GP2.8 - Subgrade preparation under pavements | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-008
cl:8bf7387d-1f7f-49cc-91b0-9d65f23d51ae | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-008 | 2.0 Construction | EC2.9 - Surface level check/ and survey pick-up | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-008
cl:8bf7387d-1f7f-49cc-91b0-9d65f23d51ae | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-008 | 2.0 Construction | EC2.10 - Proof roll subgrade prior to placement of pavement materials | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-008
cl:8bf7387d-1f7f-49cc-91b0-9d65f23d51ae | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-008 | 2.0 Construction | EC2.11 - Placement of pavement material layers | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-008
cl:8bf7387d-1f7f-49cc-91b0-9d65f23d51ae | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-008 | 2.0 Construction | EC2.12 - Surface level check/ and survey pick-up | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-008
cl:8bf7387d-1f7f-49cc-91b0-9d65f23d51ae | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-008 | 3.0 Post Construction | EC3.13 - Works completed and update ITP/ Lot Register/ MDR and close out of GDP | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-008
cl:4135d0fd-e369-4db5-8b1d-64b555bface3 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-009 | 1.0 Pre-Construction | GP1.1 - Drawings supplied most current IFC | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-009
cl:4135d0fd-e369-4db5-8b1d-64b555bface3 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-009 | 1.0 Pre-Construction | GP1.2 - Management Plans submitted and approved as per PMP | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-009
cl:4135d0fd-e369-4db5-8b1d-64b555bface3 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-009 | 1.0 Pre-Construction | GP1.3 - Inspection Test Plan (ITP) submitted and approved | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-009
cl:4135d0fd-e369-4db5-8b1d-64b555bface3 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-009 | 1.0 Pre-Construction | GP1.4 - Lot Register/ WBS submitted and approved | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-009
cl:4135d0fd-e369-4db5-8b1d-64b555bface3 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-009 | 1.0 Pre-Construction | GP1.5 - Pavement material compliance testing | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-009
cl:4135d0fd-e369-4db5-8b1d-64b555bface3 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-009 | 1.0 Pre-Construction | GP1.6 - Stockpile locations | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-009
cl:4135d0fd-e369-4db5-8b1d-64b555bface3 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-009 | 1.0 Pre-Construction | GP1.7 - Underlying lot & ITP signed off and conforming | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-009
cl:4135d0fd-e369-4db5-8b1d-64b555bface3 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-009 | 2.0 Construction | GP2.8 - Subgrade preparation under pavements | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-009
cl:4135d0fd-e369-4db5-8b1d-64b555bface3 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-009 | 2.0 Construction | EC2.9 - Surface level check/ and survey pick-up | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-009
cl:4135d0fd-e369-4db5-8b1d-64b555bface3 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-009 | 2.0 Construction | EC2.10 - Proof roll subgrade prior to placement of pavement materials | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-009
cl:4135d0fd-e369-4db5-8b1d-64b555bface3 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-009 | 2.0 Construction | EC2.11 - Placement of pavement material layers | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-009
cl:4135d0fd-e369-4db5-8b1d-64b555bface3 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-009 | 2.0 Construction | EC2.12 - Surface level check/ and survey pick-up | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-009
cl:4135d0fd-e369-4db5-8b1d-64b555bface3 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-009 | 3.0 Post Construction | EC3.13 - Works completed and update ITP/ Lot Register/ MDR and close out of GDP | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-009
cl:cd217768-3a25-4510-9a00-4a324a6b7d53 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-010 | 1.0 Pre-Construction | GP1.1 - Drawings supplied most current IFC | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-010
cl:cd217768-3a25-4510-9a00-4a324a6b7d53 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-010 | 1.0 Pre-Construction | GP1.2 - Management Plans submitted and approved as per PMP | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-010
cl:cd217768-3a25-4510-9a00-4a324a6b7d53 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-010 | 1.0 Pre-Construction | GP1.3 - Inspection Test Plan (ITP) submitted and approved | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-010
cl:cd217768-3a25-4510-9a00-4a324a6b7d53 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-010 | 1.0 Pre-Construction | GP1.4 - Lot Register/ WBS submitted and approved | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-010
cl:cd217768-3a25-4510-9a00-4a324a6b7d53 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-010 | 1.0 Pre-Construction | GP1.5 - Pavement material compliance testing | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-010
cl:cd217768-3a25-4510-9a00-4a324a6b7d53 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-010 | 1.0 Pre-Construction | GP1.6 - Stockpile locations | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-010
cl:cd217768-3a25-4510-9a00-4a324a6b7d53 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-010 | 1.0 Pre-Construction | GP1.7 - Underlying lot & ITP signed off and conforming | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-010
cl:cd217768-3a25-4510-9a00-4a324a6b7d53 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-010 | 2.0 Construction | GP2.8 - Subgrade preparation under pavements | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-010
cl:cd217768-3a25-4510-9a00-4a324a6b7d53 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-010 | 2.0 Construction | EC2.9 - Surface level check/ and survey pick-up | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-010
cl:cd217768-3a25-4510-9a00-4a324a6b7d53 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-010 | 2.0 Construction | EC2.10 - Proof roll subgrade prior to placement of pavement materials | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-010
cl:cd217768-3a25-4510-9a00-4a324a6b7d53 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-010 | 2.0 Construction | EC2.11 - Placement of pavement material layers | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-010
cl:cd217768-3a25-4510-9a00-4a324a6b7d53 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-010 | 2.0 Construction | EC2.12 - Surface level check/ and survey pick-up | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-010
cl:cd217768-3a25-4510-9a00-4a324a6b7d53 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-010 | 3.0 Post Construction | EC3.13 - Works completed and update ITP/ Lot Register/ MDR and close out of GDP | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-010
cl:60e52ec7-e21f-4914-989d-dab702e49363 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-011 | 1.0 Pre-Construction | GP1.1 - Drawings supplied most current IFC | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-011
cl:60e52ec7-e21f-4914-989d-dab702e49363 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-011 | 1.0 Pre-Construction | GP1.2 - Management Plans submitted and approved as per PMP | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-011
cl:60e52ec7-e21f-4914-989d-dab702e49363 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-011 | 1.0 Pre-Construction | GP1.3 - Inspection Test Plan (ITP) submitted and approved | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-011
cl:60e52ec7-e21f-4914-989d-dab702e49363 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-011 | 1.0 Pre-Construction | GP1.4 - Lot Register/ WBS submitted and approved | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-011
cl:60e52ec7-e21f-4914-989d-dab702e49363 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-011 | 1.0 Pre-Construction | GP1.5 - Pavement material compliance testing | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-011
cl:60e52ec7-e21f-4914-989d-dab702e49363 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-011 | 1.0 Pre-Construction | GP1.6 - Stockpile locations | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-011
cl:60e52ec7-e21f-4914-989d-dab702e49363 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-011 | 1.0 Pre-Construction | GP1.7 - Underlying lot & ITP signed off and conforming | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-011
cl:60e52ec7-e21f-4914-989d-dab702e49363 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-011 | 2.0 Construction | GP2.8 - Subgrade preparation under pavements | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-011
cl:60e52ec7-e21f-4914-989d-dab702e49363 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-011 | 2.0 Construction | EC2.9 - Surface level check/ and survey pick-up | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-011
cl:60e52ec7-e21f-4914-989d-dab702e49363 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-011 | 2.0 Construction | EC2.10 - Proof roll subgrade prior to placement of pavement materials | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-011
cl:60e52ec7-e21f-4914-989d-dab702e49363 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-011 | 2.0 Construction | EC2.11 - Placement of pavement material layers | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-011
cl:60e52ec7-e21f-4914-989d-dab702e49363 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-011 | 2.0 Construction | EC2.12 - Surface level check/ and survey pick-up | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-011
cl:60e52ec7-e21f-4914-989d-dab702e49363 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-011 | 3.0 Post Construction | EC3.13 - Works completed and update ITP/ Lot Register/ MDR and close out of GDP | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-011
cl:cd8e4393-0349-44c2-b395-3fa06e343cc2 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-012 | 1.0 Pre-Construction | GP1.1 - Drawings supplied most current IFC | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-012
cl:cd8e4393-0349-44c2-b395-3fa06e343cc2 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-012 | 1.0 Pre-Construction | GP1.2 - Management Plans submitted and approved as per PMP | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-012
cl:cd8e4393-0349-44c2-b395-3fa06e343cc2 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-012 | 1.0 Pre-Construction | GP1.3 - Inspection Test Plan (ITP) submitted and approved | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-012
cl:cd8e4393-0349-44c2-b395-3fa06e343cc2 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-012 | 1.0 Pre-Construction | GP1.4 - Lot Register/ WBS submitted and approved | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-012
cl:cd8e4393-0349-44c2-b395-3fa06e343cc2 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-012 | 1.0 Pre-Construction | GP1.5 - Pavement material compliance testing | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-012
cl:cd8e4393-0349-44c2-b395-3fa06e343cc2 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-012 | 1.0 Pre-Construction | GP1.6 - Stockpile locations | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-012
cl:cd8e4393-0349-44c2-b395-3fa06e343cc2 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-012 | 1.0 Pre-Construction | GP1.7 - Underlying lot & ITP signed off and conforming | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-012
cl:cd8e4393-0349-44c2-b395-3fa06e343cc2 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-012 | 2.0 Construction | GP2.8 - Subgrade preparation under pavements | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-012
cl:cd8e4393-0349-44c2-b395-3fa06e343cc2 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-012 | 2.0 Construction | EC2.9 - Surface level check/ and survey pick-up | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-012
cl:cd8e4393-0349-44c2-b395-3fa06e343cc2 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-012 | 2.0 Construction | EC2.10 - Proof roll subgrade prior to placement of pavement materials | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-012
cl:cd8e4393-0349-44c2-b395-3fa06e343cc2 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-012 | 2.0 Construction | EC2.11 - Placement of pavement material layers | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-012
cl:cd8e4393-0349-44c2-b395-3fa06e343cc2 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-012 | 2.0 Construction | EC2.12 - Surface level check/ and survey pick-up | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-012
cl:cd8e4393-0349-44c2-b395-3fa06e343cc2 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-012 | 3.0 Post Construction | EC3.13 - Works completed and update ITP/ Lot Register/ MDR and close out of GDP | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-012
cl:782443f2-4ab3-4828-bbf1-0077f779e483 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-013 | 1.0 Pre-Construction | GP1.1 - Drawings supplied most current IFC | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-013
cl:782443f2-4ab3-4828-bbf1-0077f779e483 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-013 | 1.0 Pre-Construction | GP1.2 - Management Plans submitted and approved as per PMP | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-013
cl:782443f2-4ab3-4828-bbf1-0077f779e483 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-013 | 1.0 Pre-Construction | GP1.3 - Inspection Test Plan (ITP) submitted and approved | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-013
cl:782443f2-4ab3-4828-bbf1-0077f779e483 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-013 | 1.0 Pre-Construction | GP1.4 - Lot Register/ WBS submitted and approved | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-013
cl:782443f2-4ab3-4828-bbf1-0077f779e483 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-013 | 1.0 Pre-Construction | GP1.5 - Pavement material compliance testing | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-013
cl:782443f2-4ab3-4828-bbf1-0077f779e483 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-013 | 1.0 Pre-Construction | GP1.6 - Stockpile locations | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-013
cl:782443f2-4ab3-4828-bbf1-0077f779e483 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-013 | 1.0 Pre-Construction | GP1.7 - Underlying lot & ITP signed off and conforming | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-013
cl:782443f2-4ab3-4828-bbf1-0077f779e483 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-013 | 2.0 Construction | GP2.8 - Subgrade preparation under pavements | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-013
cl:782443f2-4ab3-4828-bbf1-0077f779e483 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-013 | 2.0 Construction | EC2.9 - Surface level check/ and survey pick-up | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-013
cl:782443f2-4ab3-4828-bbf1-0077f779e483 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-013 | 2.0 Construction | EC2.10 - Proof roll subgrade prior to placement of pavement materials | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-013
cl:782443f2-4ab3-4828-bbf1-0077f779e483 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-013 | 2.0 Construction | EC2.11 - Placement of pavement material layers | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-013
cl:782443f2-4ab3-4828-bbf1-0077f779e483 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-013 | 2.0 Construction | EC2.12 - Surface level check/ and survey pick-up | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-013
cl:782443f2-4ab3-4828-bbf1-0077f779e483 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-013 | 3.0 Post Construction | EC3.13 - Works completed and update ITP/ Lot Register/ MDR and close out of GDP | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-013
cl:799a734d-2a84-4459-bef2-728a6f1a1fd0 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-014 | 1.0 Pre-Construction | GP1.1 - Drawings supplied most current IFC | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-014
cl:799a734d-2a84-4459-bef2-728a6f1a1fd0 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-014 | 1.0 Pre-Construction | GP1.2 - Management Plans submitted and approved as per PMP | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-014
cl:799a734d-2a84-4459-bef2-728a6f1a1fd0 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-014 | 1.0 Pre-Construction | GP1.3 - Inspection Test Plan (ITP) submitted and approved | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-014
cl:799a734d-2a84-4459-bef2-728a6f1a1fd0 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-014 | 1.0 Pre-Construction | GP1.4 - Lot Register/ WBS submitted and approved | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-014
cl:799a734d-2a84-4459-bef2-728a6f1a1fd0 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-014 | 1.0 Pre-Construction | GP1.5 - Pavement material compliance testing | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-014
cl:799a734d-2a84-4459-bef2-728a6f1a1fd0 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-014 | 1.0 Pre-Construction | GP1.6 - Stockpile locations | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-014
cl:799a734d-2a84-4459-bef2-728a6f1a1fd0 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-014 | 1.0 Pre-Construction | GP1.7 - Underlying lot & ITP signed off and conforming | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-014
cl:799a734d-2a84-4459-bef2-728a6f1a1fd0 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-014 | 2.0 Construction | GP2.8 - Subgrade preparation under pavements | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-014
cl:799a734d-2a84-4459-bef2-728a6f1a1fd0 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-014 | 2.0 Construction | EC2.9 - Surface level check/ and survey pick-up | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-014
cl:799a734d-2a84-4459-bef2-728a6f1a1fd0 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-014 | 2.0 Construction | EC2.10 - Proof roll subgrade prior to placement of pavement materials | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-014
cl:799a734d-2a84-4459-bef2-728a6f1a1fd0 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-014 | 2.0 Construction | EC2.11 - Placement of pavement material layers | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-014
cl:799a734d-2a84-4459-bef2-728a6f1a1fd0 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-014 | 2.0 Construction | EC2.12 - Surface level check/ and survey pick-up | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-014
cl:799a734d-2a84-4459-bef2-728a6f1a1fd0 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-014 | 3.0 Post Construction | EC3.13 - Works completed and update ITP/ Lot Register/ MDR and close out of GDP | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-014
cl:102244ca-aa1f-4286-9f8d-e192b970b302 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-015 | 1.0 Pre-Construction | GP1.1 - Drawings supplied most current IFC | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-015
cl:102244ca-aa1f-4286-9f8d-e192b970b302 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-015 | 1.0 Pre-Construction | GP1.2 - Management Plans submitted and approved as per PMP | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-015
cl:102244ca-aa1f-4286-9f8d-e192b970b302 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-015 | 1.0 Pre-Construction | GP1.3 - Inspection Test Plan (ITP) submitted and approved | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-015
cl:102244ca-aa1f-4286-9f8d-e192b970b302 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-015 | 1.0 Pre-Construction | GP1.4 - Lot Register/ WBS submitted and approved | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-015
cl:102244ca-aa1f-4286-9f8d-e192b970b302 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-015 | 1.0 Pre-Construction | GP1.5 - Pavement material compliance testing | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-015
cl:102244ca-aa1f-4286-9f8d-e192b970b302 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-015 | 1.0 Pre-Construction | GP1.6 - Stockpile locations | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-015
cl:102244ca-aa1f-4286-9f8d-e192b970b302 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-015 | 1.0 Pre-Construction | GP1.7 - Underlying lot & ITP signed off and conforming | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-015
cl:102244ca-aa1f-4286-9f8d-e192b970b302 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-015 | 2.0 Construction | GP2.8 - Subgrade preparation under pavements | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-015
cl:102244ca-aa1f-4286-9f8d-e192b970b302 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-015 | 2.0 Construction | EC2.9 - Surface level check/ and survey pick-up | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-015
cl:102244ca-aa1f-4286-9f8d-e192b970b302 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-015 | 2.0 Construction | EC2.10 - Proof roll subgrade prior to placement of pavement materials | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-015
cl:102244ca-aa1f-4286-9f8d-e192b970b302 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-015 | 2.0 Construction | EC2.11 - Placement of pavement material layers | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-015
cl:102244ca-aa1f-4286-9f8d-e192b970b302 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-015 | 2.0 Construction | EC2.12 - Surface level check/ and survey pick-up | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-015
cl:102244ca-aa1f-4286-9f8d-e192b970b302 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-015 | 3.0 Post Construction | EC3.13 - Works completed and update ITP/ Lot Register/ MDR and close out of GDP | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-015
cl:2109d4a3-b736-4722-97b9-3f90f38d7a11 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-016 | 1.0 Pre-Construction | GP1.1 - Drawings supplied most current IFC | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-016
cl:2109d4a3-b736-4722-97b9-3f90f38d7a11 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-016 | 1.0 Pre-Construction | GP1.2 - Management Plans submitted and approved as per PMP | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-016
cl:2109d4a3-b736-4722-97b9-3f90f38d7a11 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-016 | 1.0 Pre-Construction | GP1.3 - Inspection Test Plan (ITP) submitted and approved | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-016
cl:2109d4a3-b736-4722-97b9-3f90f38d7a11 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-016 | 1.0 Pre-Construction | GP1.4 - Lot Register/ WBS submitted and approved | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-016
cl:2109d4a3-b736-4722-97b9-3f90f38d7a11 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-016 | 1.0 Pre-Construction | GP1.5 - Pavement material compliance testing | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-016
cl:2109d4a3-b736-4722-97b9-3f90f38d7a11 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-016 | 1.0 Pre-Construction | GP1.6 - Stockpile locations | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-016
cl:2109d4a3-b736-4722-97b9-3f90f38d7a11 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-016 | 1.0 Pre-Construction | GP1.7 - Underlying lot & ITP signed off and conforming | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-016
cl:2109d4a3-b736-4722-97b9-3f90f38d7a11 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-016 | 2.0 Construction | GP2.8 - Subgrade preparation under pavements | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-016
cl:2109d4a3-b736-4722-97b9-3f90f38d7a11 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-016 | 2.0 Construction | EC2.9 - Surface level check/ and survey pick-up | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-016
cl:2109d4a3-b736-4722-97b9-3f90f38d7a11 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-016 | 2.0 Construction | EC2.10 - Proof roll subgrade prior to placement of pavement materials | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-016
cl:2109d4a3-b736-4722-97b9-3f90f38d7a11 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-016 | 2.0 Construction | EC2.11 - Placement of pavement material layers | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-016
cl:2109d4a3-b736-4722-97b9-3f90f38d7a11 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-016 | 2.0 Construction | EC2.12 - Surface level check/ and survey pick-up | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-016
cl:2109d4a3-b736-4722-97b9-3f90f38d7a11 | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-016 | 3.0 Post Construction | EC3.13 - Works completed and update ITP/ Lot Register/ MDR and close out of GDP | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-016
cl:c791f107-4611-4016-950b-83138e3a4a0e | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-017 | 1.0 Pre-Construction | GP1.1 - Drawings supplied most current IFC | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-017
cl:c791f107-4611-4016-950b-83138e3a4a0e | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-017 | 1.0 Pre-Construction | GP1.2 - Management Plans submitted and approved as per PMP | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-017
cl:c791f107-4611-4016-950b-83138e3a4a0e | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-017 | 1.0 Pre-Construction | GP1.3 - Inspection Test Plan (ITP) submitted and approved | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-017
cl:c791f107-4611-4016-950b-83138e3a4a0e | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-017 | 1.0 Pre-Construction | GP1.4 - Lot Register/ WBS submitted and approved | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-017
cl:c791f107-4611-4016-950b-83138e3a4a0e | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-017 | 1.0 Pre-Construction | GP1.5 - Pavement material compliance testing | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-017
cl:c791f107-4611-4016-950b-83138e3a4a0e | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-017 | 1.0 Pre-Construction | GP1.6 - Stockpile locations | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-017
cl:c791f107-4611-4016-950b-83138e3a4a0e | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-017 | 1.0 Pre-Construction | GP1.7 - Underlying lot & ITP signed off and conforming | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-017
cl:c791f107-4611-4016-950b-83138e3a4a0e | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-017 | 2.0 Construction | GP2.8 - Subgrade preparation under pavements | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-017
cl:c791f107-4611-4016-950b-83138e3a4a0e | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-017 | 2.0 Construction | EC2.9 - Surface level check/ and survey pick-up | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-017
cl:c791f107-4611-4016-950b-83138e3a4a0e | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-017 | 2.0 Construction | EC2.10 - Proof roll subgrade prior to placement of pavement materials | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-017
cl:c791f107-4611-4016-950b-83138e3a4a0e | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-017 | 2.0 Construction | EC2.11 - Placement of pavement material layers | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-017
cl:c791f107-4611-4016-950b-83138e3a4a0e | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-017 | 2.0 Construction | EC2.12 - Surface level check/ and survey pick-up | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-017
cl:c791f107-4611-4016-950b-83138e3a4a0e | EVA Copper Mine Project | AWP-1A > Main Access Road (MAR) > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-017 | 3.0 Post Construction | EC3.13 - Works completed and update ITP/ Lot Register/ MDR and close out of GDP | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Main Access Road (MAR) | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-MAR-017
cl:ce5f8716-8a08-452a-83f4-ab67299b6b5f | EVA Copper Mine Project | AWP-1A > Village Access Road | ITP-000 Pre-construction-VAR | Pre-construction | PC1.2 - Lot Register/ WBS | Not started | Open | ITP-000 Pre-construction | AWP-1A | Village Access Road | ITP-000 Pre-construction-VAR
cl:ce5f8716-8a08-452a-83f4-ab67299b6b5f | EVA Copper Mine Project | AWP-1A > Village Access Road | ITP-000 Pre-construction-VAR | Pre-construction | PC1.3 - Construction procedures | Not started | Open | ITP-000 Pre-construction | AWP-1A | Village Access Road | ITP-000 Pre-construction-VAR
cl:ce5f8716-8a08-452a-83f4-ab67299b6b5f | EVA Copper Mine Project | AWP-1A > Village Access Road | ITP-000 Pre-construction-VAR | Pre-construction | PC1.4 - Excavation permit | Not started | Open | ITP-000 Pre-construction | AWP-1A | Village Access Road | ITP-000 Pre-construction-VAR
cl:ce5f8716-8a08-452a-83f4-ab67299b6b5f | EVA Copper Mine Project | AWP-1A > Village Access Road | ITP-000 Pre-construction-VAR | Pre-construction | PC1.5 - Dial before you dig check | Not started | Open | ITP-000 Pre-construction | AWP-1A | Village Access Road | ITP-000 Pre-construction-VAR
cl:ce5f8716-8a08-452a-83f4-ab67299b6b5f | EVA Copper Mine Project | AWP-1A > Village Access Road | ITP-000 Pre-construction-VAR | Pre-construction | PC1.6 - Traffic control plan | Not started | Open | ITP-000 Pre-construction | AWP-1A | Village Access Road | ITP-000 Pre-construction-VAR
cl:ce5f8716-8a08-452a-83f4-ab67299b6b5f | EVA Copper Mine Project | AWP-1A > Village Access Road | ITP-000 Pre-construction-VAR | Pre-construction | PC1.7 - Inspection Test Plan (ITP) submitted and approved | Not started | Open | ITP-000 Pre-construction | AWP-1A | Village Access Road | ITP-000 Pre-construction-VAR
cl:ce5f8716-8a08-452a-83f4-ab67299b6b5f | EVA Copper Mine Project | AWP-1A > Village Access Road | ITP-000 Pre-construction-VAR | Pre-construction | PC1.8 - IFC drawings | Not started | Open | ITP-000 Pre-construction | AWP-1A | Village Access Road | ITP-000 Pre-construction-VAR
cl:ce5f8716-8a08-452a-83f4-ab67299b6b5f | EVA Copper Mine Project | AWP-1A > Village Access Road | ITP-000 Pre-construction-VAR | Pre-construction | PC1.9 - Erosion and sediment control plan | Not started | Open | ITP-000 Pre-construction | AWP-1A | Village Access Road | ITP-000 Pre-construction-VAR
cl:ce5f8716-8a08-452a-83f4-ab67299b6b5f | EVA Copper Mine Project | AWP-1A > Village Access Road | ITP-000 Pre-construction-VAR | Pre-construction | PC1.10 - Approved stockpile locations | Not started | Open | ITP-000 Pre-construction | AWP-1A | Village Access Road | ITP-000 Pre-construction-VAR
cl:ce5f8716-8a08-452a-83f4-ab67299b6b5f | EVA Copper Mine Project | AWP-1A > Village Access Road | ITP-000 Pre-construction-VAR | Pre-construction | PC1.11 - Embankment fill materials | Not started | Open | ITP-000 Pre-construction | AWP-1A | Village Access Road | ITP-000 Pre-construction-VAR
cl:ce5f8716-8a08-452a-83f4-ab67299b6b5f | EVA Copper Mine Project | AWP-1A > Village Access Road | ITP-000 Pre-construction-VAR | Pre-construction | PC1.12 - QA close out | Not started | Open | ITP-000 Pre-construction | AWP-1A | Village Access Road | ITP-000 Pre-construction-VAR
cl:eec82efc-3ac4-44da-a09b-e7aa54d50a73 | EVA Copper Mine Project | AWP-1A > Village Access Road > ITP-001 Clear & Grub | ITP-001 Clear & Grub-VAR-001 | Clear & Grub | GC1.1 - Underlying lot & ITP signed off and conforming | Not started |  | ITP-001 Clear & Grub | AWP-1A | Village Access Road | ITP-001 Clear & Grub | ITP-001 Clear & Grub-VAR-001
cl:eec82efc-3ac4-44da-a09b-e7aa54d50a73 | EVA Copper Mine Project | AWP-1A > Village Access Road > ITP-001 Clear & Grub | ITP-001 Clear & Grub-VAR-001 | Clear & Grub | GC1.2 - Ground Disturbance Permit (GDP) | In progress | Open | ITP-001 Clear & Grub | AWP-1A | Village Access Road | ITP-001 Clear & Grub | ITP-001 Clear & Grub-VAR-001
cl:eec82efc-3ac4-44da-a09b-e7aa54d50a73 | EVA Copper Mine Project | AWP-1A > Village Access Road > ITP-001 Clear & Grub | ITP-001 Clear & Grub-VAR-001 | Clear & Grub | GC1.3 - Cultural Heritage(CH) Clearance Survey | In progress | Open | ITP-001 Clear & Grub | AWP-1A | Village Access Road | ITP-001 Clear & Grub | ITP-001 Clear & Grub-VAR-001
cl:eec82efc-3ac4-44da-a09b-e7aa54d50a73 | EVA Copper Mine Project | AWP-1A > Village Access Road > ITP-001 Clear & Grub | ITP-001 Clear & Grub-VAR-001 | Clear & Grub | GC1.4 - GDP survey set out | In progress | Open | ITP-001 Clear & Grub | AWP-1A | Village Access Road | ITP-001 Clear & Grub | ITP-001 Clear & Grub-VAR-001
cl:eec82efc-3ac4-44da-a09b-e7aa54d50a73 | EVA Copper Mine Project | AWP-1A > Village Access Road > ITP-001 Clear & Grub | ITP-001 Clear & Grub-VAR-001 | Clear & Grub | GC1.5 - Survey of pegs to confirm correct GDP survey set out | In progress | Open | ITP-001 Clear & Grub | AWP-1A | Village Access Road | ITP-001 Clear & Grub | ITP-001 Clear & Grub-VAR-001
cl:eec82efc-3ac4-44da-a09b-e7aa54d50a73 | EVA Copper Mine Project | AWP-1A > Village Access Road > ITP-001 Clear & Grub | ITP-001 Clear & Grub-VAR-001 | Clear & Grub | GC1.6 - Survey natural surface | In progress | Open | ITP-001 Clear & Grub | AWP-1A | Village Access Road | ITP-001 Clear & Grub | ITP-001 Clear & Grub-VAR-001
cl:eec82efc-3ac4-44da-a09b-e7aa54d50a73 | EVA Copper Mine Project | AWP-1A > Village Access Road > ITP-001 Clear & Grub | ITP-001 Clear & Grub-VAR-001 | Clear & Grub | GC1.7 - Fauna Spotter Catcher (FSC) Pre-Clearance Survey | In progress | Open | ITP-001 Clear & Grub | AWP-1A | Village Access Road | ITP-001 Clear & Grub | ITP-001 Clear & Grub-VAR-001
cl:eec82efc-3ac4-44da-a09b-e7aa54d50a73 | EVA Copper Mine Project | AWP-1A > Village Access Road > ITP-001 Clear & Grub | ITP-001 Clear & Grub-VAR-001 | Clear & Grub | GC1.8 - Mandatory GDP Pre-Clearing walk | In progress | Open | ITP-001 Clear & Grub | AWP-1A | Village Access Road | ITP-001 Clear & Grub | ITP-001 Clear & Grub-VAR-001
cl:eec82efc-3ac4-44da-a09b-e7aa54d50a73 | EVA Copper Mine Project | AWP-1A > Village Access Road > ITP-001 Clear & Grub | ITP-001 Clear & Grub-VAR-001 | Clear & Grub | GC1.9 - Clearing of vegetation | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Village Access Road | ITP-001 Clear & Grub | ITP-001 Clear & Grub-VAR-001
cl:eec82efc-3ac4-44da-a09b-e7aa54d50a73 | EVA Copper Mine Project | AWP-1A > Village Access Road > ITP-001 Clear & Grub | ITP-001 Clear & Grub-VAR-001 | Clear & Grub | GC1.10 - Stockpile Cleared Vegetation | In progress | Open | ITP-001 Clear & Grub | AWP-1A | Village Access Road | ITP-001 Clear & Grub | ITP-001 Clear & Grub-VAR-001
cl:eec82efc-3ac4-44da-a09b-e7aa54d50a73 | EVA Copper Mine Project | AWP-1A > Village Access Road > ITP-001 Clear & Grub | ITP-001 Clear & Grub-VAR-001 | Clear & Grub | GC1.11 - Erosion and sediment control | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Village Access Road | ITP-001 Clear & Grub | ITP-001 Clear & Grub-VAR-001
cl:eec82efc-3ac4-44da-a09b-e7aa54d50a73 | EVA Copper Mine Project | AWP-1A > Village Access Road > ITP-001 Clear & Grub | ITP-001 Clear & Grub-VAR-001 | Clear & Grub | GC1.12 - QA close out | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Village Access Road | ITP-001 Clear & Grub | ITP-001 Clear & Grub-VAR-001
cl:96088604-9e73-4737-92c8-b182ebea7e73 | EVA Copper Mine Project | AWP-1A > Village Access Road > ITP-001 Clear & Grub | ITP-001 Clear & Grub-VAR-002 | Clear & Grub | GC1.1 - Underlying lot & ITP signed off and conforming | Not started |  | ITP-001 Clear & Grub | AWP-1A | Village Access Road | ITP-001 Clear & Grub | ITP-001 Clear & Grub-VAR-002
cl:96088604-9e73-4737-92c8-b182ebea7e73 | EVA Copper Mine Project | AWP-1A > Village Access Road > ITP-001 Clear & Grub | ITP-001 Clear & Grub-VAR-002 | Clear & Grub | GC1.2 - Ground Disturbance Permit (GDP) | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Village Access Road | ITP-001 Clear & Grub | ITP-001 Clear & Grub-VAR-002
cl:96088604-9e73-4737-92c8-b182ebea7e73 | EVA Copper Mine Project | AWP-1A > Village Access Road > ITP-001 Clear & Grub | ITP-001 Clear & Grub-VAR-002 | Clear & Grub | GC1.3 - Cultural Heritage(CH) Clearance Survey | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Village Access Road | ITP-001 Clear & Grub | ITP-001 Clear & Grub-VAR-002
cl:96088604-9e73-4737-92c8-b182ebea7e73 | EVA Copper Mine Project | AWP-1A > Village Access Road > ITP-001 Clear & Grub | ITP-001 Clear & Grub-VAR-002 | Clear & Grub | GC1.4 - GDP survey set out | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Village Access Road | ITP-001 Clear & Grub | ITP-001 Clear & Grub-VAR-002
cl:96088604-9e73-4737-92c8-b182ebea7e73 | EVA Copper Mine Project | AWP-1A > Village Access Road > ITP-001 Clear & Grub | ITP-001 Clear & Grub-VAR-002 | Clear & Grub | GC1.5 - Survey of pegs to confirm correct GDP survey set out | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Village Access Road | ITP-001 Clear & Grub | ITP-001 Clear & Grub-VAR-002
cl:96088604-9e73-4737-92c8-b182ebea7e73 | EVA Copper Mine Project | AWP-1A > Village Access Road > ITP-001 Clear & Grub | ITP-001 Clear & Grub-VAR-002 | Clear & Grub | GC1.6 - Survey natural surface | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Village Access Road | ITP-001 Clear & Grub | ITP-001 Clear & Grub-VAR-002
cl:96088604-9e73-4737-92c8-b182ebea7e73 | EVA Copper Mine Project | AWP-1A > Village Access Road > ITP-001 Clear & Grub | ITP-001 Clear & Grub-VAR-002 | Clear & Grub | GC1.7 - Fauna Spotter Catcher (FSC) Pre-Clearance Survey | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Village Access Road | ITP-001 Clear & Grub | ITP-001 Clear & Grub-VAR-002
cl:96088604-9e73-4737-92c8-b182ebea7e73 | EVA Copper Mine Project | AWP-1A > Village Access Road > ITP-001 Clear & Grub | ITP-001 Clear & Grub-VAR-002 | Clear & Grub | GC1.8 - Mandatory GDP Pre-Clearing walk | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Village Access Road | ITP-001 Clear & Grub | ITP-001 Clear & Grub-VAR-002
cl:96088604-9e73-4737-92c8-b182ebea7e73 | EVA Copper Mine Project | AWP-1A > Village Access Road > ITP-001 Clear & Grub | ITP-001 Clear & Grub-VAR-002 | Clear & Grub | GC1.9 - Clearing of vegetation | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Village Access Road | ITP-001 Clear & Grub | ITP-001 Clear & Grub-VAR-002
cl:96088604-9e73-4737-92c8-b182ebea7e73 | EVA Copper Mine Project | AWP-1A > Village Access Road > ITP-001 Clear & Grub | ITP-001 Clear & Grub-VAR-002 | Clear & Grub | GC1.10 - Stockpile Cleared Vegetation | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Village Access Road | ITP-001 Clear & Grub | ITP-001 Clear & Grub-VAR-002
cl:96088604-9e73-4737-92c8-b182ebea7e73 | EVA Copper Mine Project | AWP-1A > Village Access Road > ITP-001 Clear & Grub | ITP-001 Clear & Grub-VAR-002 | Clear & Grub | GC1.11 - Erosion and sediment control | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Village Access Road | ITP-001 Clear & Grub | ITP-001 Clear & Grub-VAR-002
cl:96088604-9e73-4737-92c8-b182ebea7e73 | EVA Copper Mine Project | AWP-1A > Village Access Road > ITP-001 Clear & Grub | ITP-001 Clear & Grub-VAR-002 | Clear & Grub | GC1.12 - QA close out | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Village Access Road | ITP-001 Clear & Grub | ITP-001 Clear & Grub-VAR-002
cl:2f7f622b-dee3-40fa-b4d4-d11aff2d618f | EVA Copper Mine Project | AWP-1A > Village Access Road > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-VAR-001 | Topsoil Stripping | TS1.1 - Underlying lot & ITP signed off and conforming | Not started |  | ITP-002 Topsoil Stripping | AWP-1A | Village Access Road | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-VAR-001
cl:2f7f622b-dee3-40fa-b4d4-d11aff2d618f | EVA Copper Mine Project | AWP-1A > Village Access Road > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-VAR-001 | Topsoil Stripping | TS1.2 - Survey Set out | Not started | Open | ITP-002 Topsoil Stripping | AWP-1A | Village Access Road | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-VAR-001
cl:2f7f622b-dee3-40fa-b4d4-d11aff2d618f | EVA Copper Mine Project | AWP-1A > Village Access Road > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-VAR-001 | Topsoil Stripping | TS1.3 - Strip topsoil, load & haul to approved stockpile location | Not started | Open | ITP-002 Topsoil Stripping | AWP-1A | Village Access Road | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-VAR-001
cl:2f7f622b-dee3-40fa-b4d4-d11aff2d618f | EVA Copper Mine Project | AWP-1A > Village Access Road > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-VAR-001 | Topsoil Stripping | TS1.4 - Topsoil location, destination and quantity catalogued. | Not started | Open | ITP-002 Topsoil Stripping | AWP-1A | Village Access Road | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-VAR-001
cl:2f7f622b-dee3-40fa-b4d4-d11aff2d618f | EVA Copper Mine Project | AWP-1A > Village Access Road > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-VAR-001 | Topsoil Stripping | TS1.5 - Surface level check and survey pick-up | Not started | Open | ITP-002 Topsoil Stripping | AWP-1A | Village Access Road | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-VAR-001
cl:2f7f622b-dee3-40fa-b4d4-d11aff2d618f | EVA Copper Mine Project | AWP-1A > Village Access Road > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-VAR-001 | Topsoil Stripping | TS1.6 - QA close out | Not started | Open | ITP-002 Topsoil Stripping | AWP-1A | Village Access Road | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-VAR-001
cl:b06d0ba7-4979-4431-8a84-397bacc12308 | EVA Copper Mine Project | AWP-1A > Village Access Road > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-VAR-002 | Topsoil Stripping | TS1.1 - Underlying lot & ITP signed off and conforming | Not started |  | ITP-002 Topsoil Stripping | AWP-1A | Village Access Road | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-VAR-002
cl:b06d0ba7-4979-4431-8a84-397bacc12308 | EVA Copper Mine Project | AWP-1A > Village Access Road > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-VAR-002 | Topsoil Stripping | TS1.2 - Survey Set out | Not started | Open | ITP-002 Topsoil Stripping | AWP-1A | Village Access Road | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-VAR-002
cl:b06d0ba7-4979-4431-8a84-397bacc12308 | EVA Copper Mine Project | AWP-1A > Village Access Road > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-VAR-002 | Topsoil Stripping | TS1.3 - Strip topsoil, load & haul to approved stockpile location | Not started | Open | ITP-002 Topsoil Stripping | AWP-1A | Village Access Road | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-VAR-002
cl:b06d0ba7-4979-4431-8a84-397bacc12308 | EVA Copper Mine Project | AWP-1A > Village Access Road > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-VAR-002 | Topsoil Stripping | TS1.4 - Topsoil location, destination and quantity catalogued. | Not started | Open | ITP-002 Topsoil Stripping | AWP-1A | Village Access Road | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-VAR-002
cl:b06d0ba7-4979-4431-8a84-397bacc12308 | EVA Copper Mine Project | AWP-1A > Village Access Road > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-VAR-002 | Topsoil Stripping | TS1.5 - Surface level check and survey pick-up | Not started | Open | ITP-002 Topsoil Stripping | AWP-1A | Village Access Road | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-VAR-002
cl:b06d0ba7-4979-4431-8a84-397bacc12308 | EVA Copper Mine Project | AWP-1A > Village Access Road > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-VAR-002 | Topsoil Stripping | TS1.6 - QA close out | Not started | Open | ITP-002 Topsoil Stripping | AWP-1A | Village Access Road | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-VAR-002
cl:2addc368-ad46-4a60-8a50-f442ecc3a00c | EVA Copper Mine Project | AWP-1A > Village Access Road > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-VAR-001 | Subgrade/Foundation Preparation | SP.1.1 - Underlying lot & ITP signed off and conforming | N/A |  | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Village Access Road | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-VAR-001
cl:2addc368-ad46-4a60-8a50-f442ecc3a00c | EVA Copper Mine Project | AWP-1A > Village Access Road > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-VAR-001 | Subgrade/Foundation Preparation | SP.1.2 - Embankment fill material | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Village Access Road | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-VAR-001
cl:2addc368-ad46-4a60-8a50-f442ecc3a00c | EVA Copper Mine Project | AWP-1A > Village Access Road > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-VAR-001 | Subgrade/Foundation Preparation | SP.1.3 - Survey Set out | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Village Access Road | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-VAR-001
cl:2addc368-ad46-4a60-8a50-f442ecc3a00c | EVA Copper Mine Project | AWP-1A > Village Access Road > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-VAR-001 | Subgrade/Foundation Preparation | SP.1.4 - Removal and replacement of unsuitable material | Passed | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Village Access Road | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-VAR-001
cl:2addc368-ad46-4a60-8a50-f442ecc3a00c | EVA Copper Mine Project | AWP-1A > Village Access Road > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-VAR-001 | Subgrade/Foundation Preparation | SP.1.5 - Subgrade/Foundation preparation | Passed | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Village Access Road | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-VAR-001
cl:2addc368-ad46-4a60-8a50-f442ecc3a00c | EVA Copper Mine Project | AWP-1A > Village Access Road > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-VAR-001 | Subgrade/Foundation Preparation | SP.1.6 - Trim subgrade | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Village Access Road | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-VAR-001
cl:2addc368-ad46-4a60-8a50-f442ecc3a00c | EVA Copper Mine Project | AWP-1A > Village Access Road > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-VAR-001 | Subgrade/Foundation Preparation | SP.1.7 - Proof rolling | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Village Access Road | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-VAR-001
cl:2addc368-ad46-4a60-8a50-f442ecc3a00c | EVA Copper Mine Project | AWP-1A > Village Access Road > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-VAR-001 | Subgrade/Foundation Preparation | SP.1.8 - Surface level check and survey pick-up | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Village Access Road | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-VAR-001
cl:2addc368-ad46-4a60-8a50-f442ecc3a00c | EVA Copper Mine Project | AWP-1A > Village Access Road > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-VAR-001 | Subgrade/Foundation Preparation | SP.1.9 - QA close out | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Village Access Road | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-VAR-001
cl:8700bf87-789c-42c6-962c-8599ed772427 | EVA Copper Mine Project | AWP-1A > Village Access Road > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-VAR-002 | Subgrade/Foundation Preparation | SP.1.1 - Underlying lot & ITP signed off and conforming | Not started |  | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Village Access Road | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-VAR-002
cl:8700bf87-789c-42c6-962c-8599ed772427 | EVA Copper Mine Project | AWP-1A > Village Access Road > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-VAR-002 | Subgrade/Foundation Preparation | SP.1.2 - Embankment fill material | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Village Access Road | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-VAR-002
cl:8700bf87-789c-42c6-962c-8599ed772427 | EVA Copper Mine Project | AWP-1A > Village Access Road > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-VAR-002 | Subgrade/Foundation Preparation | SP.1.3 - Survey Set out | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Village Access Road | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-VAR-002
cl:8700bf87-789c-42c6-962c-8599ed772427 | EVA Copper Mine Project | AWP-1A > Village Access Road > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-VAR-002 | Subgrade/Foundation Preparation | SP.1.4 - Removal and replacement of unsuitable material | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Village Access Road | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-VAR-002
cl:8700bf87-789c-42c6-962c-8599ed772427 | EVA Copper Mine Project | AWP-1A > Village Access Road > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-VAR-002 | Subgrade/Foundation Preparation | SP.1.5 - Subgrade/Foundation preparation | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Village Access Road | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-VAR-002
cl:8700bf87-789c-42c6-962c-8599ed772427 | EVA Copper Mine Project | AWP-1A > Village Access Road > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-VAR-002 | Subgrade/Foundation Preparation | SP.1.6 - Trim subgrade | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Village Access Road | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-VAR-002
cl:8700bf87-789c-42c6-962c-8599ed772427 | EVA Copper Mine Project | AWP-1A > Village Access Road > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-VAR-002 | Subgrade/Foundation Preparation | SP.1.7 - Proof rolling | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Village Access Road | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-VAR-002
cl:8700bf87-789c-42c6-962c-8599ed772427 | EVA Copper Mine Project | AWP-1A > Village Access Road > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-VAR-002 | Subgrade/Foundation Preparation | SP.1.8 - Surface level check and survey pick-up | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Village Access Road | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-VAR-002
cl:8700bf87-789c-42c6-962c-8599ed772427 | EVA Copper Mine Project | AWP-1A > Village Access Road > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-VAR-002 | Subgrade/Foundation Preparation | SP.1.9 - QA close out | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Village Access Road | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-VAR-002
cl:8203d441-4a86-407c-bb91-4c1aab0c5def | EVA Copper Mine Project | AWP-1A > Village Access Road > ITP-004 RCP Installation | ITP-004 RCP Installation-VAR-001 | 1.0 Pre-Construction | RCP1.1 - Drawings supplied most current IFC | Not started | Open | ITP-004 RCP Installation | AWP-1A | Village Access Road | ITP-004 RCP Installation | ITP-004 RCP Installation-VAR-001
cl:8203d441-4a86-407c-bb91-4c1aab0c5def | EVA Copper Mine Project | AWP-1A > Village Access Road > ITP-004 RCP Installation | ITP-004 RCP Installation-VAR-001 | 1.0 Pre-Construction | RCP1.2 - Define RCP ID | Not started | Open | ITP-004 RCP Installation | AWP-1A | Village Access Road | ITP-004 RCP Installation | ITP-004 RCP Installation-VAR-001
cl:8203d441-4a86-407c-bb91-4c1aab0c5def | EVA Copper Mine Project | AWP-1A > Village Access Road > ITP-004 RCP Installation | ITP-004 RCP Installation-VAR-001 | 1.0 Pre-Construction | RCP1.3 - Lot Register/ WBS submitted and approved | Not started | Open | ITP-004 RCP Installation | AWP-1A | Village Access Road | ITP-004 RCP Installation | ITP-004 RCP Installation-VAR-001
cl:8203d441-4a86-407c-bb91-4c1aab0c5def | EVA Copper Mine Project | AWP-1A > Village Access Road > ITP-004 RCP Installation | ITP-004 RCP Installation-VAR-001 | 1.0 Pre-Construction | RCP1.4 - Underlying lot & ITP signed off and conforming | Not started | Open | ITP-004 RCP Installation | AWP-1A | Village Access Road | ITP-004 RCP Installation | ITP-004 RCP Installation-VAR-001
cl:8203d441-4a86-407c-bb91-4c1aab0c5def | EVA Copper Mine Project | AWP-1A > Village Access Road > ITP-004 RCP Installation | ITP-004 RCP Installation-VAR-001 | 1.0 Pre-Construction | RCP1.5 - Certificate of compliance for RCP Material | Not started | Open | ITP-004 RCP Installation | AWP-1A | Village Access Road | ITP-004 RCP Installation | ITP-004 RCP Installation-VAR-001
cl:8203d441-4a86-407c-bb91-4c1aab0c5def | EVA Copper Mine Project | AWP-1A > Village Access Road > ITP-004 RCP Installation | ITP-004 RCP Installation-VAR-001 | 1.0 Pre-Construction | RCP1.6 - Inspect reinforced pipe culverts for damage | Not started | Open | ITP-004 RCP Installation | AWP-1A | Village Access Road | ITP-004 RCP Installation | ITP-004 RCP Installation-VAR-001
cl:8203d441-4a86-407c-bb91-4c1aab0c5def | EVA Copper Mine Project | AWP-1A > Village Access Road > ITP-004 RCP Installation | ITP-004 RCP Installation-VAR-001 | 2.0 Construction | RCP2.7 - Trench Excavation | Not started | Open | ITP-004 RCP Installation | AWP-1A | Village Access Road | ITP-004 RCP Installation | ITP-004 RCP Installation-VAR-001
cl:8203d441-4a86-407c-bb91-4c1aab0c5def | EVA Copper Mine Project | AWP-1A > Village Access Road > ITP-004 RCP Installation | ITP-004 RCP Installation-VAR-001 | 2.0 Construction | RCP2.8 - Bedding | Not started | Open | ITP-004 RCP Installation | AWP-1A | Village Access Road | ITP-004 RCP Installation | ITP-004 RCP Installation-VAR-001
cl:8203d441-4a86-407c-bb91-4c1aab0c5def | EVA Copper Mine Project | AWP-1A > Village Access Road > ITP-004 RCP Installation | ITP-004 RCP Installation-VAR-001 | 2.0 Construction | RCP2.9 - RCP Installation | Not started | Open | ITP-004 RCP Installation | AWP-1A | Village Access Road | ITP-004 RCP Installation | ITP-004 RCP Installation-VAR-001
cl:8203d441-4a86-407c-bb91-4c1aab0c5def | EVA Copper Mine Project | AWP-1A > Village Access Road > ITP-004 RCP Installation | ITP-004 RCP Installation-VAR-001 | 2.0 Construction | RCP2.10 - Backfilling of culvert | Not started | Open | ITP-004 RCP Installation | AWP-1A | Village Access Road | ITP-004 RCP Installation | ITP-004 RCP Installation-VAR-001
cl:8203d441-4a86-407c-bb91-4c1aab0c5def | EVA Copper Mine Project | AWP-1A > Village Access Road > ITP-004 RCP Installation | ITP-004 RCP Installation-VAR-001 | 2.0 Construction | RCP2.11 - End Treatment – Headwall & Wingwalls (Reinforcement) | Not started | Open | ITP-004 RCP Installation | AWP-1A | Village Access Road | ITP-004 RCP Installation | ITP-004 RCP Installation-VAR-001
cl:8203d441-4a86-407c-bb91-4c1aab0c5def | EVA Copper Mine Project | AWP-1A > Village Access Road > ITP-004 RCP Installation | ITP-004 RCP Installation-VAR-001 | 2.0 Construction | RCP2.12 - End Treatment – Headwall & Wingwalls (Formwork) | Not started | Open | ITP-004 RCP Installation | AWP-1A | Village Access Road | ITP-004 RCP Installation | ITP-004 RCP Installation-VAR-001
cl:8203d441-4a86-407c-bb91-4c1aab0c5def | EVA Copper Mine Project | AWP-1A > Village Access Road > ITP-004 RCP Installation | ITP-004 RCP Installation-VAR-001 | 2.0 Construction | RCP2.13 - End Treatment – Headwall & Wingwalls (Concrete) | Not started | Open | ITP-004 RCP Installation | AWP-1A | Village Access Road | ITP-004 RCP Installation | ITP-004 RCP Installation-VAR-001
cl:8203d441-4a86-407c-bb91-4c1aab0c5def | EVA Copper Mine Project | AWP-1A > Village Access Road > ITP-004 RCP Installation | ITP-004 RCP Installation-VAR-001 | 2.0 Construction | RCP2.14 - Rock Protection | Not started | Open | ITP-004 RCP Installation | AWP-1A | Village Access Road | ITP-004 RCP Installation | ITP-004 RCP Installation-VAR-001
cl:8203d441-4a86-407c-bb91-4c1aab0c5def | EVA Copper Mine Project | AWP-1A > Village Access Road > ITP-004 RCP Installation | ITP-004 RCP Installation-VAR-001 | 3.0 Post Construction | RCP3.15 - Works completed and update ITP/ Lot Register/ MDR and close out of GDP | Not started | Open | ITP-004 RCP Installation | AWP-1A | Village Access Road | ITP-004 RCP Installation | ITP-004 RCP Installation-VAR-001
cl:9dd4ae65-c256-4d9b-a28e-98dfe0a92616 | EVA Copper Mine Project | AWP-1A > Village Access Road > ITP-004 RCP Installation | ITP-004 RCP Installation-VAR-002 | 1.0 Pre-Construction | RCP1.1 - Drawings supplied most current IFC | Not started | Open | ITP-004 RCP Installation | AWP-1A | Village Access Road | ITP-004 RCP Installation | ITP-004 RCP Installation-VAR-002
cl:9dd4ae65-c256-4d9b-a28e-98dfe0a92616 | EVA Copper Mine Project | AWP-1A > Village Access Road > ITP-004 RCP Installation | ITP-004 RCP Installation-VAR-002 | 1.0 Pre-Construction | RCP1.2 - Define RCP ID | Not started | Open | ITP-004 RCP Installation | AWP-1A | Village Access Road | ITP-004 RCP Installation | ITP-004 RCP Installation-VAR-002
cl:9dd4ae65-c256-4d9b-a28e-98dfe0a92616 | EVA Copper Mine Project | AWP-1A > Village Access Road > ITP-004 RCP Installation | ITP-004 RCP Installation-VAR-002 | 1.0 Pre-Construction | RCP1.3 - Lot Register/ WBS submitted and approved | Not started | Open | ITP-004 RCP Installation | AWP-1A | Village Access Road | ITP-004 RCP Installation | ITP-004 RCP Installation-VAR-002
cl:9dd4ae65-c256-4d9b-a28e-98dfe0a92616 | EVA Copper Mine Project | AWP-1A > Village Access Road > ITP-004 RCP Installation | ITP-004 RCP Installation-VAR-002 | 1.0 Pre-Construction | RCP1.4 - Underlying lot & ITP signed off and conforming | Not started | Open | ITP-004 RCP Installation | AWP-1A | Village Access Road | ITP-004 RCP Installation | ITP-004 RCP Installation-VAR-002
cl:9dd4ae65-c256-4d9b-a28e-98dfe0a92616 | EVA Copper Mine Project | AWP-1A > Village Access Road > ITP-004 RCP Installation | ITP-004 RCP Installation-VAR-002 | 1.0 Pre-Construction | RCP1.5 - Certificate of compliance for RCP Material | Not started | Open | ITP-004 RCP Installation | AWP-1A | Village Access Road | ITP-004 RCP Installation | ITP-004 RCP Installation-VAR-002
cl:9dd4ae65-c256-4d9b-a28e-98dfe0a92616 | EVA Copper Mine Project | AWP-1A > Village Access Road > ITP-004 RCP Installation | ITP-004 RCP Installation-VAR-002 | 1.0 Pre-Construction | RCP1.6 - Inspect reinforced pipe culverts for damage | Not started | Open | ITP-004 RCP Installation | AWP-1A | Village Access Road | ITP-004 RCP Installation | ITP-004 RCP Installation-VAR-002
cl:9dd4ae65-c256-4d9b-a28e-98dfe0a92616 | EVA Copper Mine Project | AWP-1A > Village Access Road > ITP-004 RCP Installation | ITP-004 RCP Installation-VAR-002 | 2.0 Construction | RCP2.7 - Trench Excavation | Not started | Open | ITP-004 RCP Installation | AWP-1A | Village Access Road | ITP-004 RCP Installation | ITP-004 RCP Installation-VAR-002
cl:9dd4ae65-c256-4d9b-a28e-98dfe0a92616 | EVA Copper Mine Project | AWP-1A > Village Access Road > ITP-004 RCP Installation | ITP-004 RCP Installation-VAR-002 | 2.0 Construction | RCP2.8 - Bedding | Not started | Open | ITP-004 RCP Installation | AWP-1A | Village Access Road | ITP-004 RCP Installation | ITP-004 RCP Installation-VAR-002
cl:9dd4ae65-c256-4d9b-a28e-98dfe0a92616 | EVA Copper Mine Project | AWP-1A > Village Access Road > ITP-004 RCP Installation | ITP-004 RCP Installation-VAR-002 | 2.0 Construction | RCP2.9 - RCP Installation | Not started | Open | ITP-004 RCP Installation | AWP-1A | Village Access Road | ITP-004 RCP Installation | ITP-004 RCP Installation-VAR-002
cl:9dd4ae65-c256-4d9b-a28e-98dfe0a92616 | EVA Copper Mine Project | AWP-1A > Village Access Road > ITP-004 RCP Installation | ITP-004 RCP Installation-VAR-002 | 2.0 Construction | RCP2.10 - Backfilling of culvert | Not started | Open | ITP-004 RCP Installation | AWP-1A | Village Access Road | ITP-004 RCP Installation | ITP-004 RCP Installation-VAR-002
cl:9dd4ae65-c256-4d9b-a28e-98dfe0a92616 | EVA Copper Mine Project | AWP-1A > Village Access Road > ITP-004 RCP Installation | ITP-004 RCP Installation-VAR-002 | 2.0 Construction | RCP2.11 - End Treatment – Headwall & Wingwalls (Reinforcement) | Not started | Open | ITP-004 RCP Installation | AWP-1A | Village Access Road | ITP-004 RCP Installation | ITP-004 RCP Installation-VAR-002
cl:9dd4ae65-c256-4d9b-a28e-98dfe0a92616 | EVA Copper Mine Project | AWP-1A > Village Access Road > ITP-004 RCP Installation | ITP-004 RCP Installation-VAR-002 | 2.0 Construction | RCP2.12 - End Treatment – Headwall & Wingwalls (Formwork) | Not started | Open | ITP-004 RCP Installation | AWP-1A | Village Access Road | ITP-004 RCP Installation | ITP-004 RCP Installation-VAR-002
cl:9dd4ae65-c256-4d9b-a28e-98dfe0a92616 | EVA Copper Mine Project | AWP-1A > Village Access Road > ITP-004 RCP Installation | ITP-004 RCP Installation-VAR-002 | 2.0 Construction | RCP2.13 - End Treatment – Headwall & Wingwalls (Concrete) | Not started | Open | ITP-004 RCP Installation | AWP-1A | Village Access Road | ITP-004 RCP Installation | ITP-004 RCP Installation-VAR-002
cl:9dd4ae65-c256-4d9b-a28e-98dfe0a92616 | EVA Copper Mine Project | AWP-1A > Village Access Road > ITP-004 RCP Installation | ITP-004 RCP Installation-VAR-002 | 2.0 Construction | RCP2.14 - Rock Protection | Not started | Open | ITP-004 RCP Installation | AWP-1A | Village Access Road | ITP-004 RCP Installation | ITP-004 RCP Installation-VAR-002
cl:9dd4ae65-c256-4d9b-a28e-98dfe0a92616 | EVA Copper Mine Project | AWP-1A > Village Access Road > ITP-004 RCP Installation | ITP-004 RCP Installation-VAR-002 | 3.0 Post Construction | RCP3.15 - Works completed and update ITP/ Lot Register/ MDR and close out of GDP | Not started | Open | ITP-004 RCP Installation | AWP-1A | Village Access Road | ITP-004 RCP Installation | ITP-004 RCP Installation-VAR-002
cl:d03a27b9-4791-498b-a7b0-88ddcb11e7f0 | EVA Copper Mine Project | AWP-1A > Village Access Road > ITP-008 Embankment Construction | ITP-008 Embankment Construction-VAR-001 | Embankment Construction | EC1.1 - Underlying lot & ITP signed off and conforming | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Village Access Road | ITP-008 Embankment Construction | ITP-008 Embankment Construction-VAR-001
cl:d03a27b9-4791-498b-a7b0-88ddcb11e7f0 | EVA Copper Mine Project | AWP-1A > Village Access Road > ITP-008 Embankment Construction | ITP-008 Embankment Construction-VAR-001 | Embankment Construction | EC1.2 - Embankment fill material | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Village Access Road | ITP-008 Embankment Construction | ITP-008 Embankment Construction-VAR-001
cl:d03a27b9-4791-498b-a7b0-88ddcb11e7f0 | EVA Copper Mine Project | AWP-1A > Village Access Road > ITP-008 Embankment Construction | ITP-008 Embankment Construction-VAR-001 | Embankment Construction | EC1.3 - Survey Set out | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Village Access Road | ITP-008 Embankment Construction | ITP-008 Embankment Construction-VAR-001
cl:d03a27b9-4791-498b-a7b0-88ddcb11e7f0 | EVA Copper Mine Project | AWP-1A > Village Access Road > ITP-008 Embankment Construction | ITP-008 Embankment Construction-VAR-001 | Embankment Construction | EC1.4 - Place, moisture condition & compact embankment fill | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Village Access Road | ITP-008 Embankment Construction | ITP-008 Embankment Construction-VAR-001
cl:d03a27b9-4791-498b-a7b0-88ddcb11e7f0 | EVA Copper Mine Project | AWP-1A > Village Access Road > ITP-008 Embankment Construction | ITP-008 Embankment Construction-VAR-001 | Embankment Construction | EC1.5 - Trim embankment | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Village Access Road | ITP-008 Embankment Construction | ITP-008 Embankment Construction-VAR-001
cl:d03a27b9-4791-498b-a7b0-88ddcb11e7f0 | EVA Copper Mine Project | AWP-1A > Village Access Road > ITP-008 Embankment Construction | ITP-008 Embankment Construction-VAR-001 | Embankment Construction | EC1.6 - Proof rolling | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Village Access Road | ITP-008 Embankment Construction | ITP-008 Embankment Construction-VAR-001
cl:d03a27b9-4791-498b-a7b0-88ddcb11e7f0 | EVA Copper Mine Project | AWP-1A > Village Access Road > ITP-008 Embankment Construction | ITP-008 Embankment Construction-VAR-001 | Embankment Construction | EC1.7 - Surface level check and survey pick-up | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Village Access Road | ITP-008 Embankment Construction | ITP-008 Embankment Construction-VAR-001
cl:d03a27b9-4791-498b-a7b0-88ddcb11e7f0 | EVA Copper Mine Project | AWP-1A > Village Access Road > ITP-008 Embankment Construction | ITP-008 Embankment Construction-VAR-001 | Embankment Construction | EC1.8 - QA close out | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Village Access Road | ITP-008 Embankment Construction | ITP-008 Embankment Construction-VAR-001
cl:08b4f1e7-d822-4d9f-88b2-748d2d979e83 | EVA Copper Mine Project | AWP-1A > Village Access Road > ITP-008 Embankment Construction | ITP-008 Embankment Construction-VAR-002 | Embankment Construction | EC1.1 - Underlying lot & ITP signed off and conforming | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Village Access Road | ITP-008 Embankment Construction | ITP-008 Embankment Construction-VAR-002
cl:08b4f1e7-d822-4d9f-88b2-748d2d979e83 | EVA Copper Mine Project | AWP-1A > Village Access Road > ITP-008 Embankment Construction | ITP-008 Embankment Construction-VAR-002 | Embankment Construction | EC1.2 - Embankment fill material | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Village Access Road | ITP-008 Embankment Construction | ITP-008 Embankment Construction-VAR-002
cl:08b4f1e7-d822-4d9f-88b2-748d2d979e83 | EVA Copper Mine Project | AWP-1A > Village Access Road > ITP-008 Embankment Construction | ITP-008 Embankment Construction-VAR-002 | Embankment Construction | EC1.3 - Survey Set out | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Village Access Road | ITP-008 Embankment Construction | ITP-008 Embankment Construction-VAR-002
cl:08b4f1e7-d822-4d9f-88b2-748d2d979e83 | EVA Copper Mine Project | AWP-1A > Village Access Road > ITP-008 Embankment Construction | ITP-008 Embankment Construction-VAR-002 | Embankment Construction | EC1.4 - Place, moisture condition & compact embankment fill | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Village Access Road | ITP-008 Embankment Construction | ITP-008 Embankment Construction-VAR-002
cl:08b4f1e7-d822-4d9f-88b2-748d2d979e83 | EVA Copper Mine Project | AWP-1A > Village Access Road > ITP-008 Embankment Construction | ITP-008 Embankment Construction-VAR-002 | Embankment Construction | EC1.5 - Trim embankment | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Village Access Road | ITP-008 Embankment Construction | ITP-008 Embankment Construction-VAR-002
cl:08b4f1e7-d822-4d9f-88b2-748d2d979e83 | EVA Copper Mine Project | AWP-1A > Village Access Road > ITP-008 Embankment Construction | ITP-008 Embankment Construction-VAR-002 | Embankment Construction | EC1.6 - Proof rolling | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Village Access Road | ITP-008 Embankment Construction | ITP-008 Embankment Construction-VAR-002
cl:08b4f1e7-d822-4d9f-88b2-748d2d979e83 | EVA Copper Mine Project | AWP-1A > Village Access Road > ITP-008 Embankment Construction | ITP-008 Embankment Construction-VAR-002 | Embankment Construction | EC1.7 - Surface level check and survey pick-up | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Village Access Road | ITP-008 Embankment Construction | ITP-008 Embankment Construction-VAR-002
cl:08b4f1e7-d822-4d9f-88b2-748d2d979e83 | EVA Copper Mine Project | AWP-1A > Village Access Road > ITP-008 Embankment Construction | ITP-008 Embankment Construction-VAR-002 | Embankment Construction | EC1.8 - QA close out | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Village Access Road | ITP-008 Embankment Construction | ITP-008 Embankment Construction-VAR-002
cl:eaa0e5ad-0014-4d40-91d4-2543189b840d | EVA Copper Mine Project | AWP-1A > Village Access Road > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-VAR-001 | 1.0 Pre-Construction | GP1.1 - Drawings supplied most current IFC | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Village Access Road | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-VAR-001
cl:eaa0e5ad-0014-4d40-91d4-2543189b840d | EVA Copper Mine Project | AWP-1A > Village Access Road > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-VAR-001 | 1.0 Pre-Construction | GP1.2 - Management Plans submitted and approved as per PMP | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Village Access Road | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-VAR-001
cl:eaa0e5ad-0014-4d40-91d4-2543189b840d | EVA Copper Mine Project | AWP-1A > Village Access Road > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-VAR-001 | 1.0 Pre-Construction | GP1.3 - Inspection Test Plan (ITP) submitted and approved | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Village Access Road | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-VAR-001
cl:eaa0e5ad-0014-4d40-91d4-2543189b840d | EVA Copper Mine Project | AWP-1A > Village Access Road > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-VAR-001 | 1.0 Pre-Construction | GP1.4 - Lot Register/ WBS submitted and approved | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Village Access Road | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-VAR-001
cl:eaa0e5ad-0014-4d40-91d4-2543189b840d | EVA Copper Mine Project | AWP-1A > Village Access Road > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-VAR-001 | 1.0 Pre-Construction | GP1.5 - Pavement material compliance testing | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Village Access Road | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-VAR-001
cl:eaa0e5ad-0014-4d40-91d4-2543189b840d | EVA Copper Mine Project | AWP-1A > Village Access Road > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-VAR-001 | 1.0 Pre-Construction | GP1.6 - Stockpile locations | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Village Access Road | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-VAR-001
cl:eaa0e5ad-0014-4d40-91d4-2543189b840d | EVA Copper Mine Project | AWP-1A > Village Access Road > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-VAR-001 | 1.0 Pre-Construction | GP1.7 - Underlying lot & ITP signed off and conforming | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Village Access Road | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-VAR-001
cl:eaa0e5ad-0014-4d40-91d4-2543189b840d | EVA Copper Mine Project | AWP-1A > Village Access Road > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-VAR-001 | 2.0 Construction | GP2.8 - Subgrade preparation under pavements | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Village Access Road | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-VAR-001
cl:eaa0e5ad-0014-4d40-91d4-2543189b840d | EVA Copper Mine Project | AWP-1A > Village Access Road > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-VAR-001 | 2.0 Construction | EC2.9 - Surface level check/ and survey pick-up | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Village Access Road | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-VAR-001
cl:eaa0e5ad-0014-4d40-91d4-2543189b840d | EVA Copper Mine Project | AWP-1A > Village Access Road > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-VAR-001 | 2.0 Construction | EC2.10 - Proof roll subgrade prior to placement of pavement materials | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Village Access Road | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-VAR-001
cl:eaa0e5ad-0014-4d40-91d4-2543189b840d | EVA Copper Mine Project | AWP-1A > Village Access Road > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-VAR-001 | 2.0 Construction | EC2.11 - Placement of pavement material layers | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Village Access Road | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-VAR-001
cl:eaa0e5ad-0014-4d40-91d4-2543189b840d | EVA Copper Mine Project | AWP-1A > Village Access Road > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-VAR-001 | 2.0 Construction | EC2.12 - Surface level check/ and survey pick-up | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Village Access Road | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-VAR-001
cl:eaa0e5ad-0014-4d40-91d4-2543189b840d | EVA Copper Mine Project | AWP-1A > Village Access Road > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-VAR-001 | 3.0 Post Construction | EC3.13 - Works completed and update ITP/ Lot Register/ MDR and close out of GDP | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Village Access Road | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-VAR-001
cl:12ac3408-6f63-41d1-9325-bd7fd5d5c990 | EVA Copper Mine Project | AWP-1A > Village Access Road > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-VAR-002 | 1.0 Pre-Construction | GP1.1 - Drawings supplied most current IFC | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Village Access Road | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-VAR-002
cl:12ac3408-6f63-41d1-9325-bd7fd5d5c990 | EVA Copper Mine Project | AWP-1A > Village Access Road > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-VAR-002 | 1.0 Pre-Construction | GP1.2 - Management Plans submitted and approved as per PMP | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Village Access Road | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-VAR-002
cl:12ac3408-6f63-41d1-9325-bd7fd5d5c990 | EVA Copper Mine Project | AWP-1A > Village Access Road > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-VAR-002 | 1.0 Pre-Construction | GP1.3 - Inspection Test Plan (ITP) submitted and approved | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Village Access Road | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-VAR-002
cl:12ac3408-6f63-41d1-9325-bd7fd5d5c990 | EVA Copper Mine Project | AWP-1A > Village Access Road > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-VAR-002 | 1.0 Pre-Construction | GP1.4 - Lot Register/ WBS submitted and approved | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Village Access Road | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-VAR-002
cl:12ac3408-6f63-41d1-9325-bd7fd5d5c990 | EVA Copper Mine Project | AWP-1A > Village Access Road > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-VAR-002 | 1.0 Pre-Construction | GP1.5 - Pavement material compliance testing | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Village Access Road | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-VAR-002
cl:12ac3408-6f63-41d1-9325-bd7fd5d5c990 | EVA Copper Mine Project | AWP-1A > Village Access Road > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-VAR-002 | 1.0 Pre-Construction | GP1.6 - Stockpile locations | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Village Access Road | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-VAR-002
cl:12ac3408-6f63-41d1-9325-bd7fd5d5c990 | EVA Copper Mine Project | AWP-1A > Village Access Road > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-VAR-002 | 1.0 Pre-Construction | GP1.7 - Underlying lot & ITP signed off and conforming | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Village Access Road | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-VAR-002
cl:12ac3408-6f63-41d1-9325-bd7fd5d5c990 | EVA Copper Mine Project | AWP-1A > Village Access Road > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-VAR-002 | 2.0 Construction | GP2.8 - Subgrade preparation under pavements | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Village Access Road | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-VAR-002
cl:12ac3408-6f63-41d1-9325-bd7fd5d5c990 | EVA Copper Mine Project | AWP-1A > Village Access Road > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-VAR-002 | 2.0 Construction | EC2.9 - Surface level check/ and survey pick-up | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Village Access Road | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-VAR-002
cl:12ac3408-6f63-41d1-9325-bd7fd5d5c990 | EVA Copper Mine Project | AWP-1A > Village Access Road > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-VAR-002 | 2.0 Construction | EC2.10 - Proof roll subgrade prior to placement of pavement materials | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Village Access Road | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-VAR-002
cl:12ac3408-6f63-41d1-9325-bd7fd5d5c990 | EVA Copper Mine Project | AWP-1A > Village Access Road > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-VAR-002 | 2.0 Construction | EC2.11 - Placement of pavement material layers | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Village Access Road | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-VAR-002
cl:12ac3408-6f63-41d1-9325-bd7fd5d5c990 | EVA Copper Mine Project | AWP-1A > Village Access Road > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-VAR-002 | 2.0 Construction | EC2.12 - Surface level check/ and survey pick-up | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Village Access Road | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-VAR-002
cl:12ac3408-6f63-41d1-9325-bd7fd5d5c990 | EVA Copper Mine Project | AWP-1A > Village Access Road > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-VAR-002 | 3.0 Post Construction | EC3.13 - Works completed and update ITP/ Lot Register/ MDR and close out of GDP | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Village Access Road | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-VAR-002
cl:863b5df0-70cf-44bb-81d8-1398c8f7ace6 | EVA Copper Mine Project | AWP-1A > Turkeys Nest | ITP-000 Pre-construction-TN | Pre-construction | PC1.2 - Lot Register/ WBS | Not started | Open | ITP-000 Pre-construction | AWP-1A | Turkeys Nest | ITP-000 Pre-construction-TN
cl:863b5df0-70cf-44bb-81d8-1398c8f7ace6 | EVA Copper Mine Project | AWP-1A > Turkeys Nest | ITP-000 Pre-construction-TN | Pre-construction | PC1.3 - Construction procedures | Not started | Open | ITP-000 Pre-construction | AWP-1A | Turkeys Nest | ITP-000 Pre-construction-TN
cl:863b5df0-70cf-44bb-81d8-1398c8f7ace6 | EVA Copper Mine Project | AWP-1A > Turkeys Nest | ITP-000 Pre-construction-TN | Pre-construction | PC1.4 - Excavation permit | Not started | Open | ITP-000 Pre-construction | AWP-1A | Turkeys Nest | ITP-000 Pre-construction-TN
cl:863b5df0-70cf-44bb-81d8-1398c8f7ace6 | EVA Copper Mine Project | AWP-1A > Turkeys Nest | ITP-000 Pre-construction-TN | Pre-construction | PC1.5 - Dial before you dig check | Not started | Open | ITP-000 Pre-construction | AWP-1A | Turkeys Nest | ITP-000 Pre-construction-TN
cl:863b5df0-70cf-44bb-81d8-1398c8f7ace6 | EVA Copper Mine Project | AWP-1A > Turkeys Nest | ITP-000 Pre-construction-TN | Pre-construction | PC1.6 - Traffic control plan | Not started | Open | ITP-000 Pre-construction | AWP-1A | Turkeys Nest | ITP-000 Pre-construction-TN
cl:863b5df0-70cf-44bb-81d8-1398c8f7ace6 | EVA Copper Mine Project | AWP-1A > Turkeys Nest | ITP-000 Pre-construction-TN | Pre-construction | PC1.7 - Inspection Test Plan (ITP) submitted and approved | Not started | Open | ITP-000 Pre-construction | AWP-1A | Turkeys Nest | ITP-000 Pre-construction-TN
cl:863b5df0-70cf-44bb-81d8-1398c8f7ace6 | EVA Copper Mine Project | AWP-1A > Turkeys Nest | ITP-000 Pre-construction-TN | Pre-construction | PC1.8 - IFC drawings | Not started | Open | ITP-000 Pre-construction | AWP-1A | Turkeys Nest | ITP-000 Pre-construction-TN
cl:863b5df0-70cf-44bb-81d8-1398c8f7ace6 | EVA Copper Mine Project | AWP-1A > Turkeys Nest | ITP-000 Pre-construction-TN | Pre-construction | PC1.9 - Erosion and sediment control plan | Not started | Open | ITP-000 Pre-construction | AWP-1A | Turkeys Nest | ITP-000 Pre-construction-TN
cl:863b5df0-70cf-44bb-81d8-1398c8f7ace6 | EVA Copper Mine Project | AWP-1A > Turkeys Nest | ITP-000 Pre-construction-TN | Pre-construction | PC1.10 - Approved stockpile locations | Not started | Open | ITP-000 Pre-construction | AWP-1A | Turkeys Nest | ITP-000 Pre-construction-TN
cl:863b5df0-70cf-44bb-81d8-1398c8f7ace6 | EVA Copper Mine Project | AWP-1A > Turkeys Nest | ITP-000 Pre-construction-TN | Pre-construction | PC1.11 - Embankment fill materials | Not started | Open | ITP-000 Pre-construction | AWP-1A | Turkeys Nest | ITP-000 Pre-construction-TN
cl:863b5df0-70cf-44bb-81d8-1398c8f7ace6 | EVA Copper Mine Project | AWP-1A > Turkeys Nest | ITP-000 Pre-construction-TN | Pre-construction | PC1.12 - QA close out | Not started | Open | ITP-000 Pre-construction | AWP-1A | Turkeys Nest | ITP-000 Pre-construction-TN
cl:9c1e0124-17e1-4f0d-9222-fb83608c0278 | EVA Copper Mine Project | AWP-1A > Turkeys Nest > ITP-001 Clear & Grub | ITP-001 Clear & Grub-TN-001 | Clear & Grub | GC1.1 - Underlying lot & ITP signed off and conforming | Not started |  | ITP-001 Clear & Grub | AWP-1A | Turkeys Nest | ITP-001 Clear & Grub | ITP-001 Clear & Grub-TN-001
cl:9c1e0124-17e1-4f0d-9222-fb83608c0278 | EVA Copper Mine Project | AWP-1A > Turkeys Nest > ITP-001 Clear & Grub | ITP-001 Clear & Grub-TN-001 | Clear & Grub | GC1.2 - Ground Disturbance Permit (GDP) | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Turkeys Nest | ITP-001 Clear & Grub | ITP-001 Clear & Grub-TN-001
cl:9c1e0124-17e1-4f0d-9222-fb83608c0278 | EVA Copper Mine Project | AWP-1A > Turkeys Nest > ITP-001 Clear & Grub | ITP-001 Clear & Grub-TN-001 | Clear & Grub | GC1.3 - Cultural Heritage(CH) Clearance Survey | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Turkeys Nest | ITP-001 Clear & Grub | ITP-001 Clear & Grub-TN-001
cl:9c1e0124-17e1-4f0d-9222-fb83608c0278 | EVA Copper Mine Project | AWP-1A > Turkeys Nest > ITP-001 Clear & Grub | ITP-001 Clear & Grub-TN-001 | Clear & Grub | GC1.4 - GDP survey set out | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Turkeys Nest | ITP-001 Clear & Grub | ITP-001 Clear & Grub-TN-001
cl:9c1e0124-17e1-4f0d-9222-fb83608c0278 | EVA Copper Mine Project | AWP-1A > Turkeys Nest > ITP-001 Clear & Grub | ITP-001 Clear & Grub-TN-001 | Clear & Grub | GC1.5 - Survey of pegs to confirm correct GDP survey set out | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Turkeys Nest | ITP-001 Clear & Grub | ITP-001 Clear & Grub-TN-001
cl:9c1e0124-17e1-4f0d-9222-fb83608c0278 | EVA Copper Mine Project | AWP-1A > Turkeys Nest > ITP-001 Clear & Grub | ITP-001 Clear & Grub-TN-001 | Clear & Grub | GC1.6 - Survey natural surface | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Turkeys Nest | ITP-001 Clear & Grub | ITP-001 Clear & Grub-TN-001
cl:9c1e0124-17e1-4f0d-9222-fb83608c0278 | EVA Copper Mine Project | AWP-1A > Turkeys Nest > ITP-001 Clear & Grub | ITP-001 Clear & Grub-TN-001 | Clear & Grub | GC1.7 - Fauna Spotter Catcher (FSC) Pre-Clearance Survey | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Turkeys Nest | ITP-001 Clear & Grub | ITP-001 Clear & Grub-TN-001
cl:9c1e0124-17e1-4f0d-9222-fb83608c0278 | EVA Copper Mine Project | AWP-1A > Turkeys Nest > ITP-001 Clear & Grub | ITP-001 Clear & Grub-TN-001 | Clear & Grub | GC1.8 - Mandatory GDP Pre-Clearing walk | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Turkeys Nest | ITP-001 Clear & Grub | ITP-001 Clear & Grub-TN-001
cl:9c1e0124-17e1-4f0d-9222-fb83608c0278 | EVA Copper Mine Project | AWP-1A > Turkeys Nest > ITP-001 Clear & Grub | ITP-001 Clear & Grub-TN-001 | Clear & Grub | GC1.9 - Clearing of vegetation | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Turkeys Nest | ITP-001 Clear & Grub | ITP-001 Clear & Grub-TN-001
cl:9c1e0124-17e1-4f0d-9222-fb83608c0278 | EVA Copper Mine Project | AWP-1A > Turkeys Nest > ITP-001 Clear & Grub | ITP-001 Clear & Grub-TN-001 | Clear & Grub | GC1.10 - Stockpile Cleared Vegetation | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Turkeys Nest | ITP-001 Clear & Grub | ITP-001 Clear & Grub-TN-001
cl:9c1e0124-17e1-4f0d-9222-fb83608c0278 | EVA Copper Mine Project | AWP-1A > Turkeys Nest > ITP-001 Clear & Grub | ITP-001 Clear & Grub-TN-001 | Clear & Grub | GC1.11 - Erosion and sediment control | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Turkeys Nest | ITP-001 Clear & Grub | ITP-001 Clear & Grub-TN-001
cl:9c1e0124-17e1-4f0d-9222-fb83608c0278 | EVA Copper Mine Project | AWP-1A > Turkeys Nest > ITP-001 Clear & Grub | ITP-001 Clear & Grub-TN-001 | Clear & Grub | GC1.12 - QA close out | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Turkeys Nest | ITP-001 Clear & Grub | ITP-001 Clear & Grub-TN-001
cl:c785cedb-987d-47ed-a39c-68580156cfef | EVA Copper Mine Project | AWP-1A > Turkeys Nest > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-TN-001 | Topsoil Stripping | TS1.1 - Underlying lot & ITP signed off and conforming | Not started |  | ITP-002 Topsoil Stripping | AWP-1A | Turkeys Nest | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-TN-001
cl:c785cedb-987d-47ed-a39c-68580156cfef | EVA Copper Mine Project | AWP-1A > Turkeys Nest > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-TN-001 | Topsoil Stripping | TS1.2 - Survey Set out | Not started | Open | ITP-002 Topsoil Stripping | AWP-1A | Turkeys Nest | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-TN-001
cl:c785cedb-987d-47ed-a39c-68580156cfef | EVA Copper Mine Project | AWP-1A > Turkeys Nest > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-TN-001 | Topsoil Stripping | TS1.3 - Strip topsoil, load & haul to approved stockpile location | Not started | Open | ITP-002 Topsoil Stripping | AWP-1A | Turkeys Nest | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-TN-001
cl:c785cedb-987d-47ed-a39c-68580156cfef | EVA Copper Mine Project | AWP-1A > Turkeys Nest > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-TN-001 | Topsoil Stripping | TS1.4 - Topsoil location, destination and quantity catalogued. | Not started | Open | ITP-002 Topsoil Stripping | AWP-1A | Turkeys Nest | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-TN-001
cl:c785cedb-987d-47ed-a39c-68580156cfef | EVA Copper Mine Project | AWP-1A > Turkeys Nest > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-TN-001 | Topsoil Stripping | TS1.5 - Surface level check and survey pick-up | Not started | Open | ITP-002 Topsoil Stripping | AWP-1A | Turkeys Nest | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-TN-001
cl:c785cedb-987d-47ed-a39c-68580156cfef | EVA Copper Mine Project | AWP-1A > Turkeys Nest > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-TN-001 | Topsoil Stripping | TS1.6 - QA close out | Not started | Open | ITP-002 Topsoil Stripping | AWP-1A | Turkeys Nest | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-TN-001
cl:a1d00da8-7c41-42d6-b580-d852ad6f4015 | EVA Copper Mine Project | AWP-1A > Turkeys Nest > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-TN-001 | Subgrade/Foundation Preparation | SP.1.1 - Underlying lot & ITP signed off and conforming | Not started |  | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Turkeys Nest | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-TN-001
cl:a1d00da8-7c41-42d6-b580-d852ad6f4015 | EVA Copper Mine Project | AWP-1A > Turkeys Nest > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-TN-001 | Subgrade/Foundation Preparation | SP.1.2 - Embankment fill material | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Turkeys Nest | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-TN-001
cl:a1d00da8-7c41-42d6-b580-d852ad6f4015 | EVA Copper Mine Project | AWP-1A > Turkeys Nest > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-TN-001 | Subgrade/Foundation Preparation | SP.1.3 - Survey Set out | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Turkeys Nest | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-TN-001
cl:a1d00da8-7c41-42d6-b580-d852ad6f4015 | EVA Copper Mine Project | AWP-1A > Turkeys Nest > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-TN-001 | Subgrade/Foundation Preparation | SP.1.4 - Removal and replacement of unsuitable material | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Turkeys Nest | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-TN-001
cl:a1d00da8-7c41-42d6-b580-d852ad6f4015 | EVA Copper Mine Project | AWP-1A > Turkeys Nest > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-TN-001 | Subgrade/Foundation Preparation | SP.1.5 - Subgrade/Foundation preparation | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Turkeys Nest | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-TN-001
cl:a1d00da8-7c41-42d6-b580-d852ad6f4015 | EVA Copper Mine Project | AWP-1A > Turkeys Nest > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-TN-001 | Subgrade/Foundation Preparation | SP.1.6 - Trim subgrade | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Turkeys Nest | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-TN-001
cl:a1d00da8-7c41-42d6-b580-d852ad6f4015 | EVA Copper Mine Project | AWP-1A > Turkeys Nest > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-TN-001 | Subgrade/Foundation Preparation | SP.1.7 - Proof rolling | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Turkeys Nest | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-TN-001
cl:a1d00da8-7c41-42d6-b580-d852ad6f4015 | EVA Copper Mine Project | AWP-1A > Turkeys Nest > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-TN-001 | Subgrade/Foundation Preparation | SP.1.8 - Surface level check and survey pick-up | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Turkeys Nest | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-TN-001
cl:a1d00da8-7c41-42d6-b580-d852ad6f4015 | EVA Copper Mine Project | AWP-1A > Turkeys Nest > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-TN-001 | Subgrade/Foundation Preparation | SP.1.9 - QA close out | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Turkeys Nest | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-TN-001
cl:a68f9673-a993-4460-aef7-eb828693691b | EVA Copper Mine Project | AWP-1A > Turkeys Nest > ITP-004 RCP Installation | ITP-004 RCP Installation-TN-001 | 1.0 Pre-Construction | RCP1.1 - Drawings supplied most current IFC | Not started | Open | ITP-004 RCP Installation | AWP-1A | Turkeys Nest | ITP-004 RCP Installation | ITP-004 RCP Installation-TN-001
cl:a68f9673-a993-4460-aef7-eb828693691b | EVA Copper Mine Project | AWP-1A > Turkeys Nest > ITP-004 RCP Installation | ITP-004 RCP Installation-TN-001 | 1.0 Pre-Construction | RCP1.2 - Define RCP ID | Not started | Open | ITP-004 RCP Installation | AWP-1A | Turkeys Nest | ITP-004 RCP Installation | ITP-004 RCP Installation-TN-001
cl:a68f9673-a993-4460-aef7-eb828693691b | EVA Copper Mine Project | AWP-1A > Turkeys Nest > ITP-004 RCP Installation | ITP-004 RCP Installation-TN-001 | 1.0 Pre-Construction | RCP1.3 - Lot Register/ WBS submitted and approved | Not started | Open | ITP-004 RCP Installation | AWP-1A | Turkeys Nest | ITP-004 RCP Installation | ITP-004 RCP Installation-TN-001
cl:a68f9673-a993-4460-aef7-eb828693691b | EVA Copper Mine Project | AWP-1A > Turkeys Nest > ITP-004 RCP Installation | ITP-004 RCP Installation-TN-001 | 1.0 Pre-Construction | RCP1.4 - Underlying lot & ITP signed off and conforming | Not started | Open | ITP-004 RCP Installation | AWP-1A | Turkeys Nest | ITP-004 RCP Installation | ITP-004 RCP Installation-TN-001
cl:a68f9673-a993-4460-aef7-eb828693691b | EVA Copper Mine Project | AWP-1A > Turkeys Nest > ITP-004 RCP Installation | ITP-004 RCP Installation-TN-001 | 1.0 Pre-Construction | RCP1.5 - Certificate of compliance for RCP Material | Not started | Open | ITP-004 RCP Installation | AWP-1A | Turkeys Nest | ITP-004 RCP Installation | ITP-004 RCP Installation-TN-001
cl:a68f9673-a993-4460-aef7-eb828693691b | EVA Copper Mine Project | AWP-1A > Turkeys Nest > ITP-004 RCP Installation | ITP-004 RCP Installation-TN-001 | 1.0 Pre-Construction | RCP1.6 - Inspect reinforced pipe culverts for damage | Not started | Open | ITP-004 RCP Installation | AWP-1A | Turkeys Nest | ITP-004 RCP Installation | ITP-004 RCP Installation-TN-001
cl:a68f9673-a993-4460-aef7-eb828693691b | EVA Copper Mine Project | AWP-1A > Turkeys Nest > ITP-004 RCP Installation | ITP-004 RCP Installation-TN-001 | 2.0 Construction | RCP2.7 - Trench Excavation | Not started | Open | ITP-004 RCP Installation | AWP-1A | Turkeys Nest | ITP-004 RCP Installation | ITP-004 RCP Installation-TN-001
cl:a68f9673-a993-4460-aef7-eb828693691b | EVA Copper Mine Project | AWP-1A > Turkeys Nest > ITP-004 RCP Installation | ITP-004 RCP Installation-TN-001 | 2.0 Construction | RCP2.8 - Bedding | Not started | Open | ITP-004 RCP Installation | AWP-1A | Turkeys Nest | ITP-004 RCP Installation | ITP-004 RCP Installation-TN-001
cl:a68f9673-a993-4460-aef7-eb828693691b | EVA Copper Mine Project | AWP-1A > Turkeys Nest > ITP-004 RCP Installation | ITP-004 RCP Installation-TN-001 | 2.0 Construction | RCP2.9 - RCP Installation | Not started | Open | ITP-004 RCP Installation | AWP-1A | Turkeys Nest | ITP-004 RCP Installation | ITP-004 RCP Installation-TN-001
cl:a68f9673-a993-4460-aef7-eb828693691b | EVA Copper Mine Project | AWP-1A > Turkeys Nest > ITP-004 RCP Installation | ITP-004 RCP Installation-TN-001 | 2.0 Construction | RCP2.10 - Backfilling of culvert | Not started | Open | ITP-004 RCP Installation | AWP-1A | Turkeys Nest | ITP-004 RCP Installation | ITP-004 RCP Installation-TN-001
cl:a68f9673-a993-4460-aef7-eb828693691b | EVA Copper Mine Project | AWP-1A > Turkeys Nest > ITP-004 RCP Installation | ITP-004 RCP Installation-TN-001 | 2.0 Construction | RCP2.11 - End Treatment – Headwall & Wingwalls (Reinforcement) | Not started | Open | ITP-004 RCP Installation | AWP-1A | Turkeys Nest | ITP-004 RCP Installation | ITP-004 RCP Installation-TN-001
cl:a68f9673-a993-4460-aef7-eb828693691b | EVA Copper Mine Project | AWP-1A > Turkeys Nest > ITP-004 RCP Installation | ITP-004 RCP Installation-TN-001 | 2.0 Construction | RCP2.12 - End Treatment – Headwall & Wingwalls (Formwork) | Not started | Open | ITP-004 RCP Installation | AWP-1A | Turkeys Nest | ITP-004 RCP Installation | ITP-004 RCP Installation-TN-001
cl:a68f9673-a993-4460-aef7-eb828693691b | EVA Copper Mine Project | AWP-1A > Turkeys Nest > ITP-004 RCP Installation | ITP-004 RCP Installation-TN-001 | 2.0 Construction | RCP2.13 - End Treatment – Headwall & Wingwalls (Concrete) | Not started | Open | ITP-004 RCP Installation | AWP-1A | Turkeys Nest | ITP-004 RCP Installation | ITP-004 RCP Installation-TN-001
cl:a68f9673-a993-4460-aef7-eb828693691b | EVA Copper Mine Project | AWP-1A > Turkeys Nest > ITP-004 RCP Installation | ITP-004 RCP Installation-TN-001 | 2.0 Construction | RCP2.14 - Rock Protection | Not started | Open | ITP-004 RCP Installation | AWP-1A | Turkeys Nest | ITP-004 RCP Installation | ITP-004 RCP Installation-TN-001
cl:a68f9673-a993-4460-aef7-eb828693691b | EVA Copper Mine Project | AWP-1A > Turkeys Nest > ITP-004 RCP Installation | ITP-004 RCP Installation-TN-001 | 3.0 Post Construction | RCP3.15 - Works completed and update ITP/ Lot Register/ MDR and close out of GDP | Not started | Open | ITP-004 RCP Installation | AWP-1A | Turkeys Nest | ITP-004 RCP Installation | ITP-004 RCP Installation-TN-001
cl:bf9e7e0d-5416-4121-9d39-cd434327914b | EVA Copper Mine Project | AWP-1A > Turkeys Nest > ITP-008 Embankment Construction | ITP-008 Embankment Construction-TN-001 | Embankment Construction | EC1.1 - Underlying lot & ITP signed off and conforming | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Turkeys Nest | ITP-008 Embankment Construction | ITP-008 Embankment Construction-TN-001
cl:bf9e7e0d-5416-4121-9d39-cd434327914b | EVA Copper Mine Project | AWP-1A > Turkeys Nest > ITP-008 Embankment Construction | ITP-008 Embankment Construction-TN-001 | Embankment Construction | EC1.2 - Embankment fill material | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Turkeys Nest | ITP-008 Embankment Construction | ITP-008 Embankment Construction-TN-001
cl:bf9e7e0d-5416-4121-9d39-cd434327914b | EVA Copper Mine Project | AWP-1A > Turkeys Nest > ITP-008 Embankment Construction | ITP-008 Embankment Construction-TN-001 | Embankment Construction | EC1.3 - Survey Set out | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Turkeys Nest | ITP-008 Embankment Construction | ITP-008 Embankment Construction-TN-001
cl:bf9e7e0d-5416-4121-9d39-cd434327914b | EVA Copper Mine Project | AWP-1A > Turkeys Nest > ITP-008 Embankment Construction | ITP-008 Embankment Construction-TN-001 | Embankment Construction | EC1.4 - Place, moisture condition & compact embankment fill | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Turkeys Nest | ITP-008 Embankment Construction | ITP-008 Embankment Construction-TN-001
cl:bf9e7e0d-5416-4121-9d39-cd434327914b | EVA Copper Mine Project | AWP-1A > Turkeys Nest > ITP-008 Embankment Construction | ITP-008 Embankment Construction-TN-001 | Embankment Construction | EC1.5 - Trim embankment | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Turkeys Nest | ITP-008 Embankment Construction | ITP-008 Embankment Construction-TN-001
cl:bf9e7e0d-5416-4121-9d39-cd434327914b | EVA Copper Mine Project | AWP-1A > Turkeys Nest > ITP-008 Embankment Construction | ITP-008 Embankment Construction-TN-001 | Embankment Construction | EC1.6 - Proof rolling | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Turkeys Nest | ITP-008 Embankment Construction | ITP-008 Embankment Construction-TN-001
cl:bf9e7e0d-5416-4121-9d39-cd434327914b | EVA Copper Mine Project | AWP-1A > Turkeys Nest > ITP-008 Embankment Construction | ITP-008 Embankment Construction-TN-001 | Embankment Construction | EC1.7 - Surface level check and survey pick-up | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Turkeys Nest | ITP-008 Embankment Construction | ITP-008 Embankment Construction-TN-001
cl:bf9e7e0d-5416-4121-9d39-cd434327914b | EVA Copper Mine Project | AWP-1A > Turkeys Nest > ITP-008 Embankment Construction | ITP-008 Embankment Construction-TN-001 | Embankment Construction | EC1.8 - QA close out | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Turkeys Nest | ITP-008 Embankment Construction | ITP-008 Embankment Construction-TN-001
cl:4c018e8a-b33e-468b-b03a-7a98da8469f8 | EVA Copper Mine Project | AWP-1A > Turkeys Nest > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-TN-001 | 1.0 Pre-Construction | GP1.1 - Drawings supplied most current IFC | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Turkeys Nest | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-TN-001
cl:4c018e8a-b33e-468b-b03a-7a98da8469f8 | EVA Copper Mine Project | AWP-1A > Turkeys Nest > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-TN-001 | 1.0 Pre-Construction | GP1.2 - Management Plans submitted and approved as per PMP | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Turkeys Nest | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-TN-001
cl:4c018e8a-b33e-468b-b03a-7a98da8469f8 | EVA Copper Mine Project | AWP-1A > Turkeys Nest > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-TN-001 | 1.0 Pre-Construction | GP1.3 - Inspection Test Plan (ITP) submitted and approved | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Turkeys Nest | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-TN-001
cl:4c018e8a-b33e-468b-b03a-7a98da8469f8 | EVA Copper Mine Project | AWP-1A > Turkeys Nest > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-TN-001 | 1.0 Pre-Construction | GP1.4 - Lot Register/ WBS submitted and approved | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Turkeys Nest | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-TN-001
cl:4c018e8a-b33e-468b-b03a-7a98da8469f8 | EVA Copper Mine Project | AWP-1A > Turkeys Nest > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-TN-001 | 1.0 Pre-Construction | GP1.5 - Pavement material compliance testing | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Turkeys Nest | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-TN-001
cl:4c018e8a-b33e-468b-b03a-7a98da8469f8 | EVA Copper Mine Project | AWP-1A > Turkeys Nest > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-TN-001 | 1.0 Pre-Construction | GP1.6 - Stockpile locations | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Turkeys Nest | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-TN-001
cl:4c018e8a-b33e-468b-b03a-7a98da8469f8 | EVA Copper Mine Project | AWP-1A > Turkeys Nest > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-TN-001 | 1.0 Pre-Construction | GP1.7 - Underlying lot & ITP signed off and conforming | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Turkeys Nest | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-TN-001
cl:4c018e8a-b33e-468b-b03a-7a98da8469f8 | EVA Copper Mine Project | AWP-1A > Turkeys Nest > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-TN-001 | 2.0 Construction | GP2.8 - Subgrade preparation under pavements | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Turkeys Nest | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-TN-001
cl:4c018e8a-b33e-468b-b03a-7a98da8469f8 | EVA Copper Mine Project | AWP-1A > Turkeys Nest > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-TN-001 | 2.0 Construction | EC2.9 - Surface level check/ and survey pick-up | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Turkeys Nest | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-TN-001
cl:4c018e8a-b33e-468b-b03a-7a98da8469f8 | EVA Copper Mine Project | AWP-1A > Turkeys Nest > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-TN-001 | 2.0 Construction | EC2.10 - Proof roll subgrade prior to placement of pavement materials | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Turkeys Nest | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-TN-001
cl:4c018e8a-b33e-468b-b03a-7a98da8469f8 | EVA Copper Mine Project | AWP-1A > Turkeys Nest > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-TN-001 | 2.0 Construction | EC2.11 - Placement of pavement material layers | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Turkeys Nest | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-TN-001
cl:4c018e8a-b33e-468b-b03a-7a98da8469f8 | EVA Copper Mine Project | AWP-1A > Turkeys Nest > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-TN-001 | 2.0 Construction | EC2.12 - Surface level check/ and survey pick-up | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Turkeys Nest | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-TN-001
cl:4c018e8a-b33e-468b-b03a-7a98da8469f8 | EVA Copper Mine Project | AWP-1A > Turkeys Nest > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-TN-001 | 3.0 Post Construction | EC3.13 - Works completed and update ITP/ Lot Register/ MDR and close out of GDP | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Turkeys Nest | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-TN-001
cl:a873b51e-ed65-44d2-a656-be824629281a | EVA Copper Mine Project | AWP-1A > Village Pad | ITP-000 Pre-construction-VP | Pre-construction | PC1.2 - Lot Register/ WBS | Passed | Open | ITP-000 Pre-construction | AWP-1A | Village Pad | ITP-000 Pre-construction-VP
cl:a873b51e-ed65-44d2-a656-be824629281a | EVA Copper Mine Project | AWP-1A > Village Pad | ITP-000 Pre-construction-VP | Pre-construction | PC1.3 - Construction procedures | Passed | Open | ITP-000 Pre-construction | AWP-1A | Village Pad | ITP-000 Pre-construction-VP
cl:a873b51e-ed65-44d2-a656-be824629281a | EVA Copper Mine Project | AWP-1A > Village Pad | ITP-000 Pre-construction-VP | Pre-construction | PC1.4 - Excavation permit | Not started | Open | ITP-000 Pre-construction | AWP-1A | Village Pad | ITP-000 Pre-construction-VP
cl:a873b51e-ed65-44d2-a656-be824629281a | EVA Copper Mine Project | AWP-1A > Village Pad | ITP-000 Pre-construction-VP | Pre-construction | PC1.5 - Dial before you dig check | Passed | Open | ITP-000 Pre-construction | AWP-1A | Village Pad | ITP-000 Pre-construction-VP
cl:a873b51e-ed65-44d2-a656-be824629281a | EVA Copper Mine Project | AWP-1A > Village Pad | ITP-000 Pre-construction-VP | Pre-construction | PC1.6 - Traffic control plan | Passed | Open | ITP-000 Pre-construction | AWP-1A | Village Pad | ITP-000 Pre-construction-VP
cl:a873b51e-ed65-44d2-a656-be824629281a | EVA Copper Mine Project | AWP-1A > Village Pad | ITP-000 Pre-construction-VP | Pre-construction | PC1.7 - Inspection Test Plan (ITP) submitted and approved | Passed | Open | ITP-000 Pre-construction | AWP-1A | Village Pad | ITP-000 Pre-construction-VP
cl:a873b51e-ed65-44d2-a656-be824629281a | EVA Copper Mine Project | AWP-1A > Village Pad | ITP-000 Pre-construction-VP | Pre-construction | PC1.8 - IFC drawings | Passed | Open | ITP-000 Pre-construction | AWP-1A | Village Pad | ITP-000 Pre-construction-VP
cl:a873b51e-ed65-44d2-a656-be824629281a | EVA Copper Mine Project | AWP-1A > Village Pad | ITP-000 Pre-construction-VP | Pre-construction | PC1.9 - Erosion and sediment control plan | Passed | Open | ITP-000 Pre-construction | AWP-1A | Village Pad | ITP-000 Pre-construction-VP
cl:a873b51e-ed65-44d2-a656-be824629281a | EVA Copper Mine Project | AWP-1A > Village Pad | ITP-000 Pre-construction-VP | Pre-construction | PC1.10 - Approved stockpile locations | In progress | Open | ITP-000 Pre-construction | AWP-1A | Village Pad | ITP-000 Pre-construction-VP
cl:a873b51e-ed65-44d2-a656-be824629281a | EVA Copper Mine Project | AWP-1A > Village Pad | ITP-000 Pre-construction-VP | Pre-construction | PC1.11 - Embankment fill materials | Not started | Open | ITP-000 Pre-construction | AWP-1A | Village Pad | ITP-000 Pre-construction-VP
cl:a873b51e-ed65-44d2-a656-be824629281a | EVA Copper Mine Project | AWP-1A > Village Pad | ITP-000 Pre-construction-VP | Pre-construction | PC1.12 - QA close out | Not started | Open | ITP-000 Pre-construction | AWP-1A | Village Pad | ITP-000 Pre-construction-VP
cl:dcd0b356-bcb7-492f-8bd8-1f03b6a49c33 | EVA Copper Mine Project | AWP-1A > Village Pad > ITP-001 Clear & Grub | ITP-001 Clear & Grub-VP-001 | Clear & Grub | GC1.1 - Underlying lot & ITP signed off and conforming | Not started |  | ITP-001 Clear & Grub | AWP-1A | Village Pad | ITP-001 Clear & Grub | ITP-001 Clear & Grub-VP-001
cl:dcd0b356-bcb7-492f-8bd8-1f03b6a49c33 | EVA Copper Mine Project | AWP-1A > Village Pad > ITP-001 Clear & Grub | ITP-001 Clear & Grub-VP-001 | Clear & Grub | GC1.2 - Ground Disturbance Permit (GDP) | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Village Pad | ITP-001 Clear & Grub | ITP-001 Clear & Grub-VP-001
cl:dcd0b356-bcb7-492f-8bd8-1f03b6a49c33 | EVA Copper Mine Project | AWP-1A > Village Pad > ITP-001 Clear & Grub | ITP-001 Clear & Grub-VP-001 | Clear & Grub | GC1.3 - Cultural Heritage(CH) Clearance Survey | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Village Pad | ITP-001 Clear & Grub | ITP-001 Clear & Grub-VP-001
cl:dcd0b356-bcb7-492f-8bd8-1f03b6a49c33 | EVA Copper Mine Project | AWP-1A > Village Pad > ITP-001 Clear & Grub | ITP-001 Clear & Grub-VP-001 | Clear & Grub | GC1.4 - GDP survey set out | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Village Pad | ITP-001 Clear & Grub | ITP-001 Clear & Grub-VP-001
cl:dcd0b356-bcb7-492f-8bd8-1f03b6a49c33 | EVA Copper Mine Project | AWP-1A > Village Pad > ITP-001 Clear & Grub | ITP-001 Clear & Grub-VP-001 | Clear & Grub | GC1.5 - Survey of pegs to confirm correct GDP survey set out | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Village Pad | ITP-001 Clear & Grub | ITP-001 Clear & Grub-VP-001
cl:dcd0b356-bcb7-492f-8bd8-1f03b6a49c33 | EVA Copper Mine Project | AWP-1A > Village Pad > ITP-001 Clear & Grub | ITP-001 Clear & Grub-VP-001 | Clear & Grub | GC1.6 - Survey natural surface | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Village Pad | ITP-001 Clear & Grub | ITP-001 Clear & Grub-VP-001
cl:dcd0b356-bcb7-492f-8bd8-1f03b6a49c33 | EVA Copper Mine Project | AWP-1A > Village Pad > ITP-001 Clear & Grub | ITP-001 Clear & Grub-VP-001 | Clear & Grub | GC1.7 - Fauna Spotter Catcher (FSC) Pre-Clearance Survey | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Village Pad | ITP-001 Clear & Grub | ITP-001 Clear & Grub-VP-001
cl:dcd0b356-bcb7-492f-8bd8-1f03b6a49c33 | EVA Copper Mine Project | AWP-1A > Village Pad > ITP-001 Clear & Grub | ITP-001 Clear & Grub-VP-001 | Clear & Grub | GC1.8 - Mandatory GDP Pre-Clearing walk | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Village Pad | ITP-001 Clear & Grub | ITP-001 Clear & Grub-VP-001
cl:dcd0b356-bcb7-492f-8bd8-1f03b6a49c33 | EVA Copper Mine Project | AWP-1A > Village Pad > ITP-001 Clear & Grub | ITP-001 Clear & Grub-VP-001 | Clear & Grub | GC1.9 - Clearing of vegetation | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Village Pad | ITP-001 Clear & Grub | ITP-001 Clear & Grub-VP-001
cl:dcd0b356-bcb7-492f-8bd8-1f03b6a49c33 | EVA Copper Mine Project | AWP-1A > Village Pad > ITP-001 Clear & Grub | ITP-001 Clear & Grub-VP-001 | Clear & Grub | GC1.10 - Stockpile Cleared Vegetation | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Village Pad | ITP-001 Clear & Grub | ITP-001 Clear & Grub-VP-001
cl:dcd0b356-bcb7-492f-8bd8-1f03b6a49c33 | EVA Copper Mine Project | AWP-1A > Village Pad > ITP-001 Clear & Grub | ITP-001 Clear & Grub-VP-001 | Clear & Grub | GC1.11 - Erosion and sediment control | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Village Pad | ITP-001 Clear & Grub | ITP-001 Clear & Grub-VP-001
cl:dcd0b356-bcb7-492f-8bd8-1f03b6a49c33 | EVA Copper Mine Project | AWP-1A > Village Pad > ITP-001 Clear & Grub | ITP-001 Clear & Grub-VP-001 | Clear & Grub | GC1.12 - QA close out | Not started | Open | ITP-001 Clear & Grub | AWP-1A | Village Pad | ITP-001 Clear & Grub | ITP-001 Clear & Grub-VP-001
cl:7b5ca7e4-80a1-4638-8249-e4f8e6871ba4 | EVA Copper Mine Project | AWP-1A > Village Pad > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-VP-001 | Topsoil Stripping | TS1.1 - Underlying lot & ITP signed off and conforming | Not started |  | ITP-002 Topsoil Stripping | AWP-1A | Village Pad | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-VP-001
cl:7b5ca7e4-80a1-4638-8249-e4f8e6871ba4 | EVA Copper Mine Project | AWP-1A > Village Pad > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-VP-001 | Topsoil Stripping | TS1.2 - Survey Set out | Not started | Open | ITP-002 Topsoil Stripping | AWP-1A | Village Pad | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-VP-001
cl:7b5ca7e4-80a1-4638-8249-e4f8e6871ba4 | EVA Copper Mine Project | AWP-1A > Village Pad > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-VP-001 | Topsoil Stripping | TS1.3 - Strip topsoil, load & haul to approved stockpile location | Not started | Open | ITP-002 Topsoil Stripping | AWP-1A | Village Pad | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-VP-001
cl:7b5ca7e4-80a1-4638-8249-e4f8e6871ba4 | EVA Copper Mine Project | AWP-1A > Village Pad > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-VP-001 | Topsoil Stripping | TS1.4 - Topsoil location, destination and quantity catalogued. | Not started | Open | ITP-002 Topsoil Stripping | AWP-1A | Village Pad | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-VP-001
cl:7b5ca7e4-80a1-4638-8249-e4f8e6871ba4 | EVA Copper Mine Project | AWP-1A > Village Pad > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-VP-001 | Topsoil Stripping | TS1.5 - Surface level check and survey pick-up | Not started | Open | ITP-002 Topsoil Stripping | AWP-1A | Village Pad | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-VP-001
cl:7b5ca7e4-80a1-4638-8249-e4f8e6871ba4 | EVA Copper Mine Project | AWP-1A > Village Pad > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-VP-001 | Topsoil Stripping | TS1.6 - QA close out | Not started | Open | ITP-002 Topsoil Stripping | AWP-1A | Village Pad | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-VP-001
cl:b49cbe14-4567-4781-bde0-d751a945ad52 | EVA Copper Mine Project | AWP-1A > Village Pad > ITP-003 Foundation Preparation-VP | ITP-003 Foundation Preparation-VP002.003.010.011.014.015_FP1 | Subgrade/Foundation Preparation | SP.1.1 - Underlying lot & ITP signed off and conforming | Not started |  | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Village Pad | ITP-003 Foundation Preparation-VP | ITP-003 Foundation Preparation-VP002.003.010.011.014.015_FP1
cl:b49cbe14-4567-4781-bde0-d751a945ad52 | EVA Copper Mine Project | AWP-1A > Village Pad > ITP-003 Foundation Preparation-VP | ITP-003 Foundation Preparation-VP002.003.010.011.014.015_FP1 | Subgrade/Foundation Preparation | SP.1.2 - Embankment fill material | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Village Pad | ITP-003 Foundation Preparation-VP | ITP-003 Foundation Preparation-VP002.003.010.011.014.015_FP1
cl:b49cbe14-4567-4781-bde0-d751a945ad52 | EVA Copper Mine Project | AWP-1A > Village Pad > ITP-003 Foundation Preparation-VP | ITP-003 Foundation Preparation-VP002.003.010.011.014.015_FP1 | Subgrade/Foundation Preparation | SP.1.3 - Survey Set out | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Village Pad | ITP-003 Foundation Preparation-VP | ITP-003 Foundation Preparation-VP002.003.010.011.014.015_FP1
cl:b49cbe14-4567-4781-bde0-d751a945ad52 | EVA Copper Mine Project | AWP-1A > Village Pad > ITP-003 Foundation Preparation-VP | ITP-003 Foundation Preparation-VP002.003.010.011.014.015_FP1 | Subgrade/Foundation Preparation | SP.1.4 - Removal and replacement of unsuitable material | N/A | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Village Pad | ITP-003 Foundation Preparation-VP | ITP-003 Foundation Preparation-VP002.003.010.011.014.015_FP1
cl:b49cbe14-4567-4781-bde0-d751a945ad52 | EVA Copper Mine Project | AWP-1A > Village Pad > ITP-003 Foundation Preparation-VP | ITP-003 Foundation Preparation-VP002.003.010.011.014.015_FP1 | Subgrade/Foundation Preparation | SP.1.5 - Subgrade/Foundation preparation | In progress | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Village Pad | ITP-003 Foundation Preparation-VP | ITP-003 Foundation Preparation-VP002.003.010.011.014.015_FP1
cl:b49cbe14-4567-4781-bde0-d751a945ad52 | EVA Copper Mine Project | AWP-1A > Village Pad > ITP-003 Foundation Preparation-VP | ITP-003 Foundation Preparation-VP002.003.010.011.014.015_FP1 | Subgrade/Foundation Preparation | SP.1.6 - Trim subgrade | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Village Pad | ITP-003 Foundation Preparation-VP | ITP-003 Foundation Preparation-VP002.003.010.011.014.015_FP1
cl:b49cbe14-4567-4781-bde0-d751a945ad52 | EVA Copper Mine Project | AWP-1A > Village Pad > ITP-003 Foundation Preparation-VP | ITP-003 Foundation Preparation-VP002.003.010.011.014.015_FP1 | Subgrade/Foundation Preparation | SP.1.7 - Proof rolling | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Village Pad | ITP-003 Foundation Preparation-VP | ITP-003 Foundation Preparation-VP002.003.010.011.014.015_FP1
cl:b49cbe14-4567-4781-bde0-d751a945ad52 | EVA Copper Mine Project | AWP-1A > Village Pad > ITP-003 Foundation Preparation-VP | ITP-003 Foundation Preparation-VP002.003.010.011.014.015_FP1 | Subgrade/Foundation Preparation | SP.1.8 - Surface level check and survey pick-up | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Village Pad | ITP-003 Foundation Preparation-VP | ITP-003 Foundation Preparation-VP002.003.010.011.014.015_FP1
cl:b49cbe14-4567-4781-bde0-d751a945ad52 | EVA Copper Mine Project | AWP-1A > Village Pad > ITP-003 Foundation Preparation-VP | ITP-003 Foundation Preparation-VP002.003.010.011.014.015_FP1 | Subgrade/Foundation Preparation | SP.1.9 - QA close out | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Village Pad | ITP-003 Foundation Preparation-VP | ITP-003 Foundation Preparation-VP002.003.010.011.014.015_FP1
cl:190640f7-fe77-42dd-9dcf-f0dc4cc8569f | EVA Copper Mine Project | AWP-1A > Village Pad > ITP-003 Foundation Preparation-VP | ITP-003 Foundation Preparation-VP004.005.006.007.008.017.018_FP2 | Subgrade/Foundation Preparation | SP.1.1 - Underlying lot & ITP signed off and conforming | Not started |  | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Village Pad | ITP-003 Foundation Preparation-VP | ITP-003 Foundation Preparation-VP004.005.006.007.008.017.018_FP2
cl:190640f7-fe77-42dd-9dcf-f0dc4cc8569f | EVA Copper Mine Project | AWP-1A > Village Pad > ITP-003 Foundation Preparation-VP | ITP-003 Foundation Preparation-VP004.005.006.007.008.017.018_FP2 | Subgrade/Foundation Preparation | SP.1.2 - Embankment fill material | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Village Pad | ITP-003 Foundation Preparation-VP | ITP-003 Foundation Preparation-VP004.005.006.007.008.017.018_FP2
cl:190640f7-fe77-42dd-9dcf-f0dc4cc8569f | EVA Copper Mine Project | AWP-1A > Village Pad > ITP-003 Foundation Preparation-VP | ITP-003 Foundation Preparation-VP004.005.006.007.008.017.018_FP2 | Subgrade/Foundation Preparation | SP.1.3 - Survey Set out | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Village Pad | ITP-003 Foundation Preparation-VP | ITP-003 Foundation Preparation-VP004.005.006.007.008.017.018_FP2
cl:190640f7-fe77-42dd-9dcf-f0dc4cc8569f | EVA Copper Mine Project | AWP-1A > Village Pad > ITP-003 Foundation Preparation-VP | ITP-003 Foundation Preparation-VP004.005.006.007.008.017.018_FP2 | Subgrade/Foundation Preparation | SP.1.4 - Removal and replacement of unsuitable material | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Village Pad | ITP-003 Foundation Preparation-VP | ITP-003 Foundation Preparation-VP004.005.006.007.008.017.018_FP2
cl:190640f7-fe77-42dd-9dcf-f0dc4cc8569f | EVA Copper Mine Project | AWP-1A > Village Pad > ITP-003 Foundation Preparation-VP | ITP-003 Foundation Preparation-VP004.005.006.007.008.017.018_FP2 | Subgrade/Foundation Preparation | SP.1.5 - Subgrade/Foundation preparation | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Village Pad | ITP-003 Foundation Preparation-VP | ITP-003 Foundation Preparation-VP004.005.006.007.008.017.018_FP2
cl:190640f7-fe77-42dd-9dcf-f0dc4cc8569f | EVA Copper Mine Project | AWP-1A > Village Pad > ITP-003 Foundation Preparation-VP | ITP-003 Foundation Preparation-VP004.005.006.007.008.017.018_FP2 | Subgrade/Foundation Preparation | SP.1.6 - Trim subgrade | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Village Pad | ITP-003 Foundation Preparation-VP | ITP-003 Foundation Preparation-VP004.005.006.007.008.017.018_FP2
cl:190640f7-fe77-42dd-9dcf-f0dc4cc8569f | EVA Copper Mine Project | AWP-1A > Village Pad > ITP-003 Foundation Preparation-VP | ITP-003 Foundation Preparation-VP004.005.006.007.008.017.018_FP2 | Subgrade/Foundation Preparation | SP.1.7 - Proof rolling | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Village Pad | ITP-003 Foundation Preparation-VP | ITP-003 Foundation Preparation-VP004.005.006.007.008.017.018_FP2
cl:190640f7-fe77-42dd-9dcf-f0dc4cc8569f | EVA Copper Mine Project | AWP-1A > Village Pad > ITP-003 Foundation Preparation-VP | ITP-003 Foundation Preparation-VP004.005.006.007.008.017.018_FP2 | Subgrade/Foundation Preparation | SP.1.8 - Surface level check and survey pick-up | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Village Pad | ITP-003 Foundation Preparation-VP | ITP-003 Foundation Preparation-VP004.005.006.007.008.017.018_FP2
cl:190640f7-fe77-42dd-9dcf-f0dc4cc8569f | EVA Copper Mine Project | AWP-1A > Village Pad > ITP-003 Foundation Preparation-VP | ITP-003 Foundation Preparation-VP004.005.006.007.008.017.018_FP2 | Subgrade/Foundation Preparation | SP.1.9 - QA close out | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Village Pad | ITP-003 Foundation Preparation-VP | ITP-003 Foundation Preparation-VP004.005.006.007.008.017.018_FP2
cl:8fe28aa9-4762-4573-ad1f-c93fd32862a6 | EVA Copper Mine Project | AWP-1A > Village Pad > ITP-003 Foundation Preparation-VP | ITP-003 Foundation Preparation-VP001.012.013_FP3 | Subgrade/Foundation Preparation | SP.1.1 - Underlying lot & ITP signed off and conforming | Not started |  | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Village Pad | ITP-003 Foundation Preparation-VP | ITP-003 Foundation Preparation-VP001.012.013_FP3
cl:8fe28aa9-4762-4573-ad1f-c93fd32862a6 | EVA Copper Mine Project | AWP-1A > Village Pad > ITP-003 Foundation Preparation-VP | ITP-003 Foundation Preparation-VP001.012.013_FP3 | Subgrade/Foundation Preparation | SP.1.2 - Embankment fill material | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Village Pad | ITP-003 Foundation Preparation-VP | ITP-003 Foundation Preparation-VP001.012.013_FP3
cl:8fe28aa9-4762-4573-ad1f-c93fd32862a6 | EVA Copper Mine Project | AWP-1A > Village Pad > ITP-003 Foundation Preparation-VP | ITP-003 Foundation Preparation-VP001.012.013_FP3 | Subgrade/Foundation Preparation | SP.1.3 - Survey Set out | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Village Pad | ITP-003 Foundation Preparation-VP | ITP-003 Foundation Preparation-VP001.012.013_FP3
cl:8fe28aa9-4762-4573-ad1f-c93fd32862a6 | EVA Copper Mine Project | AWP-1A > Village Pad > ITP-003 Foundation Preparation-VP | ITP-003 Foundation Preparation-VP001.012.013_FP3 | Subgrade/Foundation Preparation | SP.1.4 - Removal and replacement of unsuitable material | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Village Pad | ITP-003 Foundation Preparation-VP | ITP-003 Foundation Preparation-VP001.012.013_FP3
cl:8fe28aa9-4762-4573-ad1f-c93fd32862a6 | EVA Copper Mine Project | AWP-1A > Village Pad > ITP-003 Foundation Preparation-VP | ITP-003 Foundation Preparation-VP001.012.013_FP3 | Subgrade/Foundation Preparation | SP.1.5 - Subgrade/Foundation preparation | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Village Pad | ITP-003 Foundation Preparation-VP | ITP-003 Foundation Preparation-VP001.012.013_FP3
cl:8fe28aa9-4762-4573-ad1f-c93fd32862a6 | EVA Copper Mine Project | AWP-1A > Village Pad > ITP-003 Foundation Preparation-VP | ITP-003 Foundation Preparation-VP001.012.013_FP3 | Subgrade/Foundation Preparation | SP.1.6 - Trim subgrade | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Village Pad | ITP-003 Foundation Preparation-VP | ITP-003 Foundation Preparation-VP001.012.013_FP3
cl:8fe28aa9-4762-4573-ad1f-c93fd32862a6 | EVA Copper Mine Project | AWP-1A > Village Pad > ITP-003 Foundation Preparation-VP | ITP-003 Foundation Preparation-VP001.012.013_FP3 | Subgrade/Foundation Preparation | SP.1.7 - Proof rolling | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Village Pad | ITP-003 Foundation Preparation-VP | ITP-003 Foundation Preparation-VP001.012.013_FP3
cl:8fe28aa9-4762-4573-ad1f-c93fd32862a6 | EVA Copper Mine Project | AWP-1A > Village Pad > ITP-003 Foundation Preparation-VP | ITP-003 Foundation Preparation-VP001.012.013_FP3 | Subgrade/Foundation Preparation | SP.1.8 - Surface level check and survey pick-up | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Village Pad | ITP-003 Foundation Preparation-VP | ITP-003 Foundation Preparation-VP001.012.013_FP3
cl:8fe28aa9-4762-4573-ad1f-c93fd32862a6 | EVA Copper Mine Project | AWP-1A > Village Pad > ITP-003 Foundation Preparation-VP | ITP-003 Foundation Preparation-VP001.012.013_FP3 | Subgrade/Foundation Preparation | SP.1.9 - QA close out | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Village Pad | ITP-003 Foundation Preparation-VP | ITP-003 Foundation Preparation-VP001.012.013_FP3
cl:cda7526f-5945-417c-a387-8dae7b459a1f | EVA Copper Mine Project | AWP-1A > Village Pad > ITP-004 RCP Installation | ITP-004 RCP Installation-VP-001 | 1.0 Pre-Construction | RCP1.1 - Drawings supplied most current IFC | Not started | Open | ITP-004 RCP Installation | AWP-1A | Village Pad | ITP-004 RCP Installation | ITP-004 RCP Installation-VP-001
cl:cda7526f-5945-417c-a387-8dae7b459a1f | EVA Copper Mine Project | AWP-1A > Village Pad > ITP-004 RCP Installation | ITP-004 RCP Installation-VP-001 | 1.0 Pre-Construction | RCP1.2 - Define RCP ID | Not started | Open | ITP-004 RCP Installation | AWP-1A | Village Pad | ITP-004 RCP Installation | ITP-004 RCP Installation-VP-001
cl:cda7526f-5945-417c-a387-8dae7b459a1f | EVA Copper Mine Project | AWP-1A > Village Pad > ITP-004 RCP Installation | ITP-004 RCP Installation-VP-001 | 1.0 Pre-Construction | RCP1.3 - Lot Register/ WBS submitted and approved | Not started | Open | ITP-004 RCP Installation | AWP-1A | Village Pad | ITP-004 RCP Installation | ITP-004 RCP Installation-VP-001
cl:cda7526f-5945-417c-a387-8dae7b459a1f | EVA Copper Mine Project | AWP-1A > Village Pad > ITP-004 RCP Installation | ITP-004 RCP Installation-VP-001 | 1.0 Pre-Construction | RCP1.4 - Underlying lot & ITP signed off and conforming | Not started | Open | ITP-004 RCP Installation | AWP-1A | Village Pad | ITP-004 RCP Installation | ITP-004 RCP Installation-VP-001
cl:cda7526f-5945-417c-a387-8dae7b459a1f | EVA Copper Mine Project | AWP-1A > Village Pad > ITP-004 RCP Installation | ITP-004 RCP Installation-VP-001 | 1.0 Pre-Construction | RCP1.5 - Certificate of compliance for RCP Material | Not started | Open | ITP-004 RCP Installation | AWP-1A | Village Pad | ITP-004 RCP Installation | ITP-004 RCP Installation-VP-001
cl:cda7526f-5945-417c-a387-8dae7b459a1f | EVA Copper Mine Project | AWP-1A > Village Pad > ITP-004 RCP Installation | ITP-004 RCP Installation-VP-001 | 1.0 Pre-Construction | RCP1.6 - Inspect reinforced pipe culverts for damage | Not started | Open | ITP-004 RCP Installation | AWP-1A | Village Pad | ITP-004 RCP Installation | ITP-004 RCP Installation-VP-001
cl:cda7526f-5945-417c-a387-8dae7b459a1f | EVA Copper Mine Project | AWP-1A > Village Pad > ITP-004 RCP Installation | ITP-004 RCP Installation-VP-001 | 2.0 Construction | RCP2.7 - Trench Excavation | Not started | Open | ITP-004 RCP Installation | AWP-1A | Village Pad | ITP-004 RCP Installation | ITP-004 RCP Installation-VP-001
cl:cda7526f-5945-417c-a387-8dae7b459a1f | EVA Copper Mine Project | AWP-1A > Village Pad > ITP-004 RCP Installation | ITP-004 RCP Installation-VP-001 | 2.0 Construction | RCP2.8 - Bedding | Not started | Open | ITP-004 RCP Installation | AWP-1A | Village Pad | ITP-004 RCP Installation | ITP-004 RCP Installation-VP-001
cl:cda7526f-5945-417c-a387-8dae7b459a1f | EVA Copper Mine Project | AWP-1A > Village Pad > ITP-004 RCP Installation | ITP-004 RCP Installation-VP-001 | 2.0 Construction | RCP2.9 - RCP Installation | Not started | Open | ITP-004 RCP Installation | AWP-1A | Village Pad | ITP-004 RCP Installation | ITP-004 RCP Installation-VP-001
cl:cda7526f-5945-417c-a387-8dae7b459a1f | EVA Copper Mine Project | AWP-1A > Village Pad > ITP-004 RCP Installation | ITP-004 RCP Installation-VP-001 | 2.0 Construction | RCP2.10 - Backfilling of culvert | Not started | Open | ITP-004 RCP Installation | AWP-1A | Village Pad | ITP-004 RCP Installation | ITP-004 RCP Installation-VP-001
cl:cda7526f-5945-417c-a387-8dae7b459a1f | EVA Copper Mine Project | AWP-1A > Village Pad > ITP-004 RCP Installation | ITP-004 RCP Installation-VP-001 | 2.0 Construction | RCP2.11 - End Treatment – Headwall & Wingwalls (Reinforcement) | Not started | Open | ITP-004 RCP Installation | AWP-1A | Village Pad | ITP-004 RCP Installation | ITP-004 RCP Installation-VP-001
cl:cda7526f-5945-417c-a387-8dae7b459a1f | EVA Copper Mine Project | AWP-1A > Village Pad > ITP-004 RCP Installation | ITP-004 RCP Installation-VP-001 | 2.0 Construction | RCP2.12 - End Treatment – Headwall & Wingwalls (Formwork) | Not started | Open | ITP-004 RCP Installation | AWP-1A | Village Pad | ITP-004 RCP Installation | ITP-004 RCP Installation-VP-001
cl:cda7526f-5945-417c-a387-8dae7b459a1f | EVA Copper Mine Project | AWP-1A > Village Pad > ITP-004 RCP Installation | ITP-004 RCP Installation-VP-001 | 2.0 Construction | RCP2.13 - End Treatment – Headwall & Wingwalls (Concrete) | Not started | Open | ITP-004 RCP Installation | AWP-1A | Village Pad | ITP-004 RCP Installation | ITP-004 RCP Installation-VP-001
cl:cda7526f-5945-417c-a387-8dae7b459a1f | EVA Copper Mine Project | AWP-1A > Village Pad > ITP-004 RCP Installation | ITP-004 RCP Installation-VP-001 | 2.0 Construction | RCP2.14 - Rock Protection | Not started | Open | ITP-004 RCP Installation | AWP-1A | Village Pad | ITP-004 RCP Installation | ITP-004 RCP Installation-VP-001
cl:cda7526f-5945-417c-a387-8dae7b459a1f | EVA Copper Mine Project | AWP-1A > Village Pad > ITP-004 RCP Installation | ITP-004 RCP Installation-VP-001 | 3.0 Post Construction | RCP3.15 - Works completed and update ITP/ Lot Register/ MDR and close out of GDP | Not started | Open | ITP-004 RCP Installation | AWP-1A | Village Pad | ITP-004 RCP Installation | ITP-004 RCP Installation-VP-001
cl:b212dd87-d68c-47b0-a5e5-6bdbcc3b5473 | EVA Copper Mine Project | AWP-1A > Village Pad > ITP-008 Embankment Construction | ITP-008 Embankment Construction-VP-001 | Embankment Construction | EC1.1 - Underlying lot & ITP signed off and conforming | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Village Pad | ITP-008 Embankment Construction | ITP-008 Embankment Construction-VP-001
cl:b212dd87-d68c-47b0-a5e5-6bdbcc3b5473 | EVA Copper Mine Project | AWP-1A > Village Pad > ITP-008 Embankment Construction | ITP-008 Embankment Construction-VP-001 | Embankment Construction | EC1.2 - Embankment fill material | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Village Pad | ITP-008 Embankment Construction | ITP-008 Embankment Construction-VP-001
cl:b212dd87-d68c-47b0-a5e5-6bdbcc3b5473 | EVA Copper Mine Project | AWP-1A > Village Pad > ITP-008 Embankment Construction | ITP-008 Embankment Construction-VP-001 | Embankment Construction | EC1.3 - Survey Set out | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Village Pad | ITP-008 Embankment Construction | ITP-008 Embankment Construction-VP-001
cl:b212dd87-d68c-47b0-a5e5-6bdbcc3b5473 | EVA Copper Mine Project | AWP-1A > Village Pad > ITP-008 Embankment Construction | ITP-008 Embankment Construction-VP-001 | Embankment Construction | EC1.4 - Place, moisture condition & compact embankment fill | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Village Pad | ITP-008 Embankment Construction | ITP-008 Embankment Construction-VP-001
cl:b212dd87-d68c-47b0-a5e5-6bdbcc3b5473 | EVA Copper Mine Project | AWP-1A > Village Pad > ITP-008 Embankment Construction | ITP-008 Embankment Construction-VP-001 | Embankment Construction | EC1.5 - Trim embankment | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Village Pad | ITP-008 Embankment Construction | ITP-008 Embankment Construction-VP-001
cl:b212dd87-d68c-47b0-a5e5-6bdbcc3b5473 | EVA Copper Mine Project | AWP-1A > Village Pad > ITP-008 Embankment Construction | ITP-008 Embankment Construction-VP-001 | Embankment Construction | EC1.6 - Proof rolling | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Village Pad | ITP-008 Embankment Construction | ITP-008 Embankment Construction-VP-001
cl:b212dd87-d68c-47b0-a5e5-6bdbcc3b5473 | EVA Copper Mine Project | AWP-1A > Village Pad > ITP-008 Embankment Construction | ITP-008 Embankment Construction-VP-001 | Embankment Construction | EC1.7 - Surface level check and survey pick-up | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Village Pad | ITP-008 Embankment Construction | ITP-008 Embankment Construction-VP-001
cl:b212dd87-d68c-47b0-a5e5-6bdbcc3b5473 | EVA Copper Mine Project | AWP-1A > Village Pad > ITP-008 Embankment Construction | ITP-008 Embankment Construction-VP-001 | Embankment Construction | EC1.8 - QA close out | Not started | Open | ITP-008 Embankment Construction | AWP-1A | Village Pad | ITP-008 Embankment Construction | ITP-008 Embankment Construction-VP-001
cl:3fe0627c-caaf-4216-b936-e959750e1735 | EVA Copper Mine Project | AWP-1A > Village Pad > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-VP-001 | 1.0 Pre-Construction | GP1.1 - Drawings supplied most current IFC | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Village Pad | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-VP-001
cl:3fe0627c-caaf-4216-b936-e959750e1735 | EVA Copper Mine Project | AWP-1A > Village Pad > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-VP-001 | 1.0 Pre-Construction | GP1.2 - Management Plans submitted and approved as per PMP | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Village Pad | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-VP-001
cl:3fe0627c-caaf-4216-b936-e959750e1735 | EVA Copper Mine Project | AWP-1A > Village Pad > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-VP-001 | 1.0 Pre-Construction | GP1.3 - Inspection Test Plan (ITP) submitted and approved | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Village Pad | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-VP-001
cl:3fe0627c-caaf-4216-b936-e959750e1735 | EVA Copper Mine Project | AWP-1A > Village Pad > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-VP-001 | 1.0 Pre-Construction | GP1.4 - Lot Register/ WBS submitted and approved | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Village Pad | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-VP-001
cl:3fe0627c-caaf-4216-b936-e959750e1735 | EVA Copper Mine Project | AWP-1A > Village Pad > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-VP-001 | 1.0 Pre-Construction | GP1.5 - Pavement material compliance testing | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Village Pad | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-VP-001
cl:3fe0627c-caaf-4216-b936-e959750e1735 | EVA Copper Mine Project | AWP-1A > Village Pad > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-VP-001 | 1.0 Pre-Construction | GP1.6 - Stockpile locations | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Village Pad | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-VP-001
cl:3fe0627c-caaf-4216-b936-e959750e1735 | EVA Copper Mine Project | AWP-1A > Village Pad > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-VP-001 | 1.0 Pre-Construction | GP1.7 - Underlying lot & ITP signed off and conforming | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Village Pad | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-VP-001
cl:3fe0627c-caaf-4216-b936-e959750e1735 | EVA Copper Mine Project | AWP-1A > Village Pad > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-VP-001 | 2.0 Construction | GP2.8 - Subgrade preparation under pavements | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Village Pad | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-VP-001
cl:3fe0627c-caaf-4216-b936-e959750e1735 | EVA Copper Mine Project | AWP-1A > Village Pad > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-VP-001 | 2.0 Construction | EC2.9 - Surface level check/ and survey pick-up | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Village Pad | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-VP-001
cl:3fe0627c-caaf-4216-b936-e959750e1735 | EVA Copper Mine Project | AWP-1A > Village Pad > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-VP-001 | 2.0 Construction | EC2.10 - Proof roll subgrade prior to placement of pavement materials | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Village Pad | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-VP-001
cl:3fe0627c-caaf-4216-b936-e959750e1735 | EVA Copper Mine Project | AWP-1A > Village Pad > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-VP-001 | 2.0 Construction | EC2.11 - Placement of pavement material layers | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Village Pad | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-VP-001
cl:3fe0627c-caaf-4216-b936-e959750e1735 | EVA Copper Mine Project | AWP-1A > Village Pad > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-VP-001 | 2.0 Construction | EC2.12 - Surface level check/ and survey pick-up | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Village Pad | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-VP-001
cl:3fe0627c-caaf-4216-b936-e959750e1735 | EVA Copper Mine Project | AWP-1A > Village Pad > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-VP-001 | 3.0 Post Construction | EC3.13 - Works completed and update ITP/ Lot Register/ MDR and close out of GDP | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1A | Village Pad | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-VP-001
cl:bcfe35ca-d308-438a-9c66-9112a48dc484 | EVA Copper Mine Project | AWP-1A > Village Pad > ITP-009 Unbound Gravel Pavements | ITP-003 Subgrade/Foundation Preparation-VP-008 - 008/017_FP5,FP7 | Subgrade/Foundation Preparation | SP.1.1 - Underlying lot & ITP signed off and conforming | Not started |  | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Village Pad | ITP-009 Unbound Gravel Pavements | ITP-003 Subgrade/Foundation Preparation-VP-008 - 008/017_FP5,FP7
cl:bcfe35ca-d308-438a-9c66-9112a48dc484 | EVA Copper Mine Project | AWP-1A > Village Pad > ITP-009 Unbound Gravel Pavements | ITP-003 Subgrade/Foundation Preparation-VP-008 - 008/017_FP5,FP7 | Subgrade/Foundation Preparation | SP.1.2 - Embankment fill material | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Village Pad | ITP-009 Unbound Gravel Pavements | ITP-003 Subgrade/Foundation Preparation-VP-008 - 008/017_FP5,FP7
cl:bcfe35ca-d308-438a-9c66-9112a48dc484 | EVA Copper Mine Project | AWP-1A > Village Pad > ITP-009 Unbound Gravel Pavements | ITP-003 Subgrade/Foundation Preparation-VP-008 - 008/017_FP5,FP7 | Subgrade/Foundation Preparation | SP.1.3 - Survey Set out | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Village Pad | ITP-009 Unbound Gravel Pavements | ITP-003 Subgrade/Foundation Preparation-VP-008 - 008/017_FP5,FP7
cl:bcfe35ca-d308-438a-9c66-9112a48dc484 | EVA Copper Mine Project | AWP-1A > Village Pad > ITP-009 Unbound Gravel Pavements | ITP-003 Subgrade/Foundation Preparation-VP-008 - 008/017_FP5,FP7 | Subgrade/Foundation Preparation | SP.1.4 - Removal and replacement of unsuitable material | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Village Pad | ITP-009 Unbound Gravel Pavements | ITP-003 Subgrade/Foundation Preparation-VP-008 - 008/017_FP5,FP7
cl:bcfe35ca-d308-438a-9c66-9112a48dc484 | EVA Copper Mine Project | AWP-1A > Village Pad > ITP-009 Unbound Gravel Pavements | ITP-003 Subgrade/Foundation Preparation-VP-008 - 008/017_FP5,FP7 | Subgrade/Foundation Preparation | SP.1.5 - Subgrade/Foundation preparation | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Village Pad | ITP-009 Unbound Gravel Pavements | ITP-003 Subgrade/Foundation Preparation-VP-008 - 008/017_FP5,FP7
cl:bcfe35ca-d308-438a-9c66-9112a48dc484 | EVA Copper Mine Project | AWP-1A > Village Pad > ITP-009 Unbound Gravel Pavements | ITP-003 Subgrade/Foundation Preparation-VP-008 - 008/017_FP5,FP7 | Subgrade/Foundation Preparation | SP.1.6 - Trim subgrade | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Village Pad | ITP-009 Unbound Gravel Pavements | ITP-003 Subgrade/Foundation Preparation-VP-008 - 008/017_FP5,FP7
cl:bcfe35ca-d308-438a-9c66-9112a48dc484 | EVA Copper Mine Project | AWP-1A > Village Pad > ITP-009 Unbound Gravel Pavements | ITP-003 Subgrade/Foundation Preparation-VP-008 - 008/017_FP5,FP7 | Subgrade/Foundation Preparation | SP.1.7 - Proof rolling | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Village Pad | ITP-009 Unbound Gravel Pavements | ITP-003 Subgrade/Foundation Preparation-VP-008 - 008/017_FP5,FP7
cl:bcfe35ca-d308-438a-9c66-9112a48dc484 | EVA Copper Mine Project | AWP-1A > Village Pad > ITP-009 Unbound Gravel Pavements | ITP-003 Subgrade/Foundation Preparation-VP-008 - 008/017_FP5,FP7 | Subgrade/Foundation Preparation | SP.1.8 - Surface level check and survey pick-up | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Village Pad | ITP-009 Unbound Gravel Pavements | ITP-003 Subgrade/Foundation Preparation-VP-008 - 008/017_FP5,FP7
cl:bcfe35ca-d308-438a-9c66-9112a48dc484 | EVA Copper Mine Project | AWP-1A > Village Pad > ITP-009 Unbound Gravel Pavements | ITP-003 Subgrade/Foundation Preparation-VP-008 - 008/017_FP5,FP7 | Subgrade/Foundation Preparation | SP.1.9 - QA close out | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1A | Village Pad | ITP-009 Unbound Gravel Pavements | ITP-003 Subgrade/Foundation Preparation-VP-008 - 008/017_FP5,FP7
cl:ce5f8716-8a08-452a-83f4-ab67299b6b5f | EVA Copper Mine Project | Village Access Road | ITP-000 Pre-construction-VAR | Pre-construction | PC1.2 - Lot Register/ WBS | Not started | Open | ITP-000 Pre-construction | Village Access Road | ITP-000 Pre-construction-VAR
cl:ce5f8716-8a08-452a-83f4-ab67299b6b5f | EVA Copper Mine Project | Village Access Road | ITP-000 Pre-construction-VAR | Pre-construction | PC1.3 - Construction procedures | Not started | Open | ITP-000 Pre-construction | Village Access Road | ITP-000 Pre-construction-VAR
cl:ce5f8716-8a08-452a-83f4-ab67299b6b5f | EVA Copper Mine Project | Village Access Road | ITP-000 Pre-construction-VAR | Pre-construction | PC1.4 - Excavation permit | Not started | Open | ITP-000 Pre-construction | Village Access Road | ITP-000 Pre-construction-VAR
cl:ce5f8716-8a08-452a-83f4-ab67299b6b5f | EVA Copper Mine Project | Village Access Road | ITP-000 Pre-construction-VAR | Pre-construction | PC1.5 - Dial before you dig check | Not started | Open | ITP-000 Pre-construction | Village Access Road | ITP-000 Pre-construction-VAR
cl:ce5f8716-8a08-452a-83f4-ab67299b6b5f | EVA Copper Mine Project | Village Access Road | ITP-000 Pre-construction-VAR | Pre-construction | PC1.6 - Traffic control plan | Not started | Open | ITP-000 Pre-construction | Village Access Road | ITP-000 Pre-construction-VAR
cl:ce5f8716-8a08-452a-83f4-ab67299b6b5f | EVA Copper Mine Project | Village Access Road | ITP-000 Pre-construction-VAR | Pre-construction | PC1.7 - Inspection Test Plan (ITP) submitted and approved | Not started | Open | ITP-000 Pre-construction | Village Access Road | ITP-000 Pre-construction-VAR
cl:ce5f8716-8a08-452a-83f4-ab67299b6b5f | EVA Copper Mine Project | Village Access Road | ITP-000 Pre-construction-VAR | Pre-construction | PC1.8 - IFC drawings | Not started | Open | ITP-000 Pre-construction | Village Access Road | ITP-000 Pre-construction-VAR
cl:ce5f8716-8a08-452a-83f4-ab67299b6b5f | EVA Copper Mine Project | Village Access Road | ITP-000 Pre-construction-VAR | Pre-construction | PC1.9 - Erosion and sediment control plan | Not started | Open | ITP-000 Pre-construction | Village Access Road | ITP-000 Pre-construction-VAR
cl:ce5f8716-8a08-452a-83f4-ab67299b6b5f | EVA Copper Mine Project | Village Access Road | ITP-000 Pre-construction-VAR | Pre-construction | PC1.10 - Approved stockpile locations | Not started | Open | ITP-000 Pre-construction | Village Access Road | ITP-000 Pre-construction-VAR
cl:ce5f8716-8a08-452a-83f4-ab67299b6b5f | EVA Copper Mine Project | Village Access Road | ITP-000 Pre-construction-VAR | Pre-construction | PC1.11 - Embankment fill materials | Not started | Open | ITP-000 Pre-construction | Village Access Road | ITP-000 Pre-construction-VAR
cl:ce5f8716-8a08-452a-83f4-ab67299b6b5f | EVA Copper Mine Project | Village Access Road | ITP-000 Pre-construction-VAR | Pre-construction | PC1.12 - QA close out | Not started | Open | ITP-000 Pre-construction | Village Access Road | ITP-000 Pre-construction-VAR
cl:eec82efc-3ac4-44da-a09b-e7aa54d50a73 | EVA Copper Mine Project | Village Access Road > ITP-001 Clear & Grub | ITP-001 Clear & Grub-VAR-001 | Clear & Grub | GC1.1 - Underlying lot & ITP signed off and conforming | Not started |  | ITP-001 Clear & Grub | Village Access Road | ITP-001 Clear & Grub | ITP-001 Clear & Grub-VAR-001
cl:eec82efc-3ac4-44da-a09b-e7aa54d50a73 | EVA Copper Mine Project | Village Access Road > ITP-001 Clear & Grub | ITP-001 Clear & Grub-VAR-001 | Clear & Grub | GC1.2 - Ground Disturbance Permit (GDP) | In progress | Open | ITP-001 Clear & Grub | Village Access Road | ITP-001 Clear & Grub | ITP-001 Clear & Grub-VAR-001
cl:eec82efc-3ac4-44da-a09b-e7aa54d50a73 | EVA Copper Mine Project | Village Access Road > ITP-001 Clear & Grub | ITP-001 Clear & Grub-VAR-001 | Clear & Grub | GC1.3 - Cultural Heritage(CH) Clearance Survey | In progress | Open | ITP-001 Clear & Grub | Village Access Road | ITP-001 Clear & Grub | ITP-001 Clear & Grub-VAR-001
cl:eec82efc-3ac4-44da-a09b-e7aa54d50a73 | EVA Copper Mine Project | Village Access Road > ITP-001 Clear & Grub | ITP-001 Clear & Grub-VAR-001 | Clear & Grub | GC1.4 - GDP survey set out | In progress | Open | ITP-001 Clear & Grub | Village Access Road | ITP-001 Clear & Grub | ITP-001 Clear & Grub-VAR-001
cl:eec82efc-3ac4-44da-a09b-e7aa54d50a73 | EVA Copper Mine Project | Village Access Road > ITP-001 Clear & Grub | ITP-001 Clear & Grub-VAR-001 | Clear & Grub | GC1.5 - Survey of pegs to confirm correct GDP survey set out | In progress | Open | ITP-001 Clear & Grub | Village Access Road | ITP-001 Clear & Grub | ITP-001 Clear & Grub-VAR-001
cl:eec82efc-3ac4-44da-a09b-e7aa54d50a73 | EVA Copper Mine Project | Village Access Road > ITP-001 Clear & Grub | ITP-001 Clear & Grub-VAR-001 | Clear & Grub | GC1.6 - Survey natural surface | In progress | Open | ITP-001 Clear & Grub | Village Access Road | ITP-001 Clear & Grub | ITP-001 Clear & Grub-VAR-001
cl:eec82efc-3ac4-44da-a09b-e7aa54d50a73 | EVA Copper Mine Project | Village Access Road > ITP-001 Clear & Grub | ITP-001 Clear & Grub-VAR-001 | Clear & Grub | GC1.7 - Fauna Spotter Catcher (FSC) Pre-Clearance Survey | In progress | Open | ITP-001 Clear & Grub | Village Access Road | ITP-001 Clear & Grub | ITP-001 Clear & Grub-VAR-001
cl:eec82efc-3ac4-44da-a09b-e7aa54d50a73 | EVA Copper Mine Project | Village Access Road > ITP-001 Clear & Grub | ITP-001 Clear & Grub-VAR-001 | Clear & Grub | GC1.8 - Mandatory GDP Pre-Clearing walk | In progress | Open | ITP-001 Clear & Grub | Village Access Road | ITP-001 Clear & Grub | ITP-001 Clear & Grub-VAR-001
cl:eec82efc-3ac4-44da-a09b-e7aa54d50a73 | EVA Copper Mine Project | Village Access Road > ITP-001 Clear & Grub | ITP-001 Clear & Grub-VAR-001 | Clear & Grub | GC1.9 - Clearing of vegetation | Not started | Open | ITP-001 Clear & Grub | Village Access Road | ITP-001 Clear & Grub | ITP-001 Clear & Grub-VAR-001
cl:eec82efc-3ac4-44da-a09b-e7aa54d50a73 | EVA Copper Mine Project | Village Access Road > ITP-001 Clear & Grub | ITP-001 Clear & Grub-VAR-001 | Clear & Grub | GC1.10 - Stockpile Cleared Vegetation | In progress | Open | ITP-001 Clear & Grub | Village Access Road | ITP-001 Clear & Grub | ITP-001 Clear & Grub-VAR-001
cl:eec82efc-3ac4-44da-a09b-e7aa54d50a73 | EVA Copper Mine Project | Village Access Road > ITP-001 Clear & Grub | ITP-001 Clear & Grub-VAR-001 | Clear & Grub | GC1.11 - Erosion and sediment control | Not started | Open | ITP-001 Clear & Grub | Village Access Road | ITP-001 Clear & Grub | ITP-001 Clear & Grub-VAR-001
cl:eec82efc-3ac4-44da-a09b-e7aa54d50a73 | EVA Copper Mine Project | Village Access Road > ITP-001 Clear & Grub | ITP-001 Clear & Grub-VAR-001 | Clear & Grub | GC1.12 - QA close out | Not started | Open | ITP-001 Clear & Grub | Village Access Road | ITP-001 Clear & Grub | ITP-001 Clear & Grub-VAR-001
cl:96088604-9e73-4737-92c8-b182ebea7e73 | EVA Copper Mine Project | Village Access Road > ITP-001 Clear & Grub | ITP-001 Clear & Grub-VAR-002 | Clear & Grub | GC1.1 - Underlying lot & ITP signed off and conforming | Not started |  | ITP-001 Clear & Grub | Village Access Road | ITP-001 Clear & Grub | ITP-001 Clear & Grub-VAR-002
cl:96088604-9e73-4737-92c8-b182ebea7e73 | EVA Copper Mine Project | Village Access Road > ITP-001 Clear & Grub | ITP-001 Clear & Grub-VAR-002 | Clear & Grub | GC1.2 - Ground Disturbance Permit (GDP) | Not started | Open | ITP-001 Clear & Grub | Village Access Road | ITP-001 Clear & Grub | ITP-001 Clear & Grub-VAR-002
cl:96088604-9e73-4737-92c8-b182ebea7e73 | EVA Copper Mine Project | Village Access Road > ITP-001 Clear & Grub | ITP-001 Clear & Grub-VAR-002 | Clear & Grub | GC1.3 - Cultural Heritage(CH) Clearance Survey | Not started | Open | ITP-001 Clear & Grub | Village Access Road | ITP-001 Clear & Grub | ITP-001 Clear & Grub-VAR-002
cl:96088604-9e73-4737-92c8-b182ebea7e73 | EVA Copper Mine Project | Village Access Road > ITP-001 Clear & Grub | ITP-001 Clear & Grub-VAR-002 | Clear & Grub | GC1.4 - GDP survey set out | Not started | Open | ITP-001 Clear & Grub | Village Access Road | ITP-001 Clear & Grub | ITP-001 Clear & Grub-VAR-002
cl:96088604-9e73-4737-92c8-b182ebea7e73 | EVA Copper Mine Project | Village Access Road > ITP-001 Clear & Grub | ITP-001 Clear & Grub-VAR-002 | Clear & Grub | GC1.5 - Survey of pegs to confirm correct GDP survey set out | Not started | Open | ITP-001 Clear & Grub | Village Access Road | ITP-001 Clear & Grub | ITP-001 Clear & Grub-VAR-002
cl:96088604-9e73-4737-92c8-b182ebea7e73 | EVA Copper Mine Project | Village Access Road > ITP-001 Clear & Grub | ITP-001 Clear & Grub-VAR-002 | Clear & Grub | GC1.6 - Survey natural surface | Not started | Open | ITP-001 Clear & Grub | Village Access Road | ITP-001 Clear & Grub | ITP-001 Clear & Grub-VAR-002
cl:96088604-9e73-4737-92c8-b182ebea7e73 | EVA Copper Mine Project | Village Access Road > ITP-001 Clear & Grub | ITP-001 Clear & Grub-VAR-002 | Clear & Grub | GC1.7 - Fauna Spotter Catcher (FSC) Pre-Clearance Survey | Not started | Open | ITP-001 Clear & Grub | Village Access Road | ITP-001 Clear & Grub | ITP-001 Clear & Grub-VAR-002
cl:96088604-9e73-4737-92c8-b182ebea7e73 | EVA Copper Mine Project | Village Access Road > ITP-001 Clear & Grub | ITP-001 Clear & Grub-VAR-002 | Clear & Grub | GC1.8 - Mandatory GDP Pre-Clearing walk | Not started | Open | ITP-001 Clear & Grub | Village Access Road | ITP-001 Clear & Grub | ITP-001 Clear & Grub-VAR-002
cl:96088604-9e73-4737-92c8-b182ebea7e73 | EVA Copper Mine Project | Village Access Road > ITP-001 Clear & Grub | ITP-001 Clear & Grub-VAR-002 | Clear & Grub | GC1.9 - Clearing of vegetation | Not started | Open | ITP-001 Clear & Grub | Village Access Road | ITP-001 Clear & Grub | ITP-001 Clear & Grub-VAR-002
cl:96088604-9e73-4737-92c8-b182ebea7e73 | EVA Copper Mine Project | Village Access Road > ITP-001 Clear & Grub | ITP-001 Clear & Grub-VAR-002 | Clear & Grub | GC1.10 - Stockpile Cleared Vegetation | Not started | Open | ITP-001 Clear & Grub | Village Access Road | ITP-001 Clear & Grub | ITP-001 Clear & Grub-VAR-002
cl:96088604-9e73-4737-92c8-b182ebea7e73 | EVA Copper Mine Project | Village Access Road > ITP-001 Clear & Grub | ITP-001 Clear & Grub-VAR-002 | Clear & Grub | GC1.11 - Erosion and sediment control | Not started | Open | ITP-001 Clear & Grub | Village Access Road | ITP-001 Clear & Grub | ITP-001 Clear & Grub-VAR-002
cl:96088604-9e73-4737-92c8-b182ebea7e73 | EVA Copper Mine Project | Village Access Road > ITP-001 Clear & Grub | ITP-001 Clear & Grub-VAR-002 | Clear & Grub | GC1.12 - QA close out | Not started | Open | ITP-001 Clear & Grub | Village Access Road | ITP-001 Clear & Grub | ITP-001 Clear & Grub-VAR-002
cl:2f7f622b-dee3-40fa-b4d4-d11aff2d618f | EVA Copper Mine Project | Village Access Road > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-VAR-001 | Topsoil Stripping | TS1.1 - Underlying lot & ITP signed off and conforming | Not started |  | ITP-002 Topsoil Stripping | Village Access Road | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-VAR-001
cl:2f7f622b-dee3-40fa-b4d4-d11aff2d618f | EVA Copper Mine Project | Village Access Road > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-VAR-001 | Topsoil Stripping | TS1.2 - Survey Set out | Not started | Open | ITP-002 Topsoil Stripping | Village Access Road | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-VAR-001
cl:2f7f622b-dee3-40fa-b4d4-d11aff2d618f | EVA Copper Mine Project | Village Access Road > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-VAR-001 | Topsoil Stripping | TS1.3 - Strip topsoil, load & haul to approved stockpile location | Not started | Open | ITP-002 Topsoil Stripping | Village Access Road | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-VAR-001
cl:2f7f622b-dee3-40fa-b4d4-d11aff2d618f | EVA Copper Mine Project | Village Access Road > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-VAR-001 | Topsoil Stripping | TS1.4 - Topsoil location, destination and quantity catalogued. | Not started | Open | ITP-002 Topsoil Stripping | Village Access Road | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-VAR-001
cl:2f7f622b-dee3-40fa-b4d4-d11aff2d618f | EVA Copper Mine Project | Village Access Road > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-VAR-001 | Topsoil Stripping | TS1.5 - Surface level check and survey pick-up | Not started | Open | ITP-002 Topsoil Stripping | Village Access Road | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-VAR-001
cl:2f7f622b-dee3-40fa-b4d4-d11aff2d618f | EVA Copper Mine Project | Village Access Road > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-VAR-001 | Topsoil Stripping | TS1.6 - QA close out | Not started | Open | ITP-002 Topsoil Stripping | Village Access Road | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-VAR-001
cl:b06d0ba7-4979-4431-8a84-397bacc12308 | EVA Copper Mine Project | Village Access Road > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-VAR-002 | Topsoil Stripping | TS1.1 - Underlying lot & ITP signed off and conforming | Not started |  | ITP-002 Topsoil Stripping | Village Access Road | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-VAR-002
cl:b06d0ba7-4979-4431-8a84-397bacc12308 | EVA Copper Mine Project | Village Access Road > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-VAR-002 | Topsoil Stripping | TS1.2 - Survey Set out | Not started | Open | ITP-002 Topsoil Stripping | Village Access Road | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-VAR-002
cl:b06d0ba7-4979-4431-8a84-397bacc12308 | EVA Copper Mine Project | Village Access Road > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-VAR-002 | Topsoil Stripping | TS1.3 - Strip topsoil, load & haul to approved stockpile location | Not started | Open | ITP-002 Topsoil Stripping | Village Access Road | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-VAR-002
cl:b06d0ba7-4979-4431-8a84-397bacc12308 | EVA Copper Mine Project | Village Access Road > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-VAR-002 | Topsoil Stripping | TS1.4 - Topsoil location, destination and quantity catalogued. | Not started | Open | ITP-002 Topsoil Stripping | Village Access Road | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-VAR-002
cl:b06d0ba7-4979-4431-8a84-397bacc12308 | EVA Copper Mine Project | Village Access Road > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-VAR-002 | Topsoil Stripping | TS1.5 - Surface level check and survey pick-up | Not started | Open | ITP-002 Topsoil Stripping | Village Access Road | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-VAR-002
cl:b06d0ba7-4979-4431-8a84-397bacc12308 | EVA Copper Mine Project | Village Access Road > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-VAR-002 | Topsoil Stripping | TS1.6 - QA close out | Not started | Open | ITP-002 Topsoil Stripping | Village Access Road | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-VAR-002
cl:2addc368-ad46-4a60-8a50-f442ecc3a00c | EVA Copper Mine Project | Village Access Road > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-VAR-001 | Subgrade/Foundation Preparation | SP.1.1 - Underlying lot & ITP signed off and conforming | N/A |  | ITP-003 Subgrade/Foundation Preparation | Village Access Road | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-VAR-001
cl:2addc368-ad46-4a60-8a50-f442ecc3a00c | EVA Copper Mine Project | Village Access Road > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-VAR-001 | Subgrade/Foundation Preparation | SP.1.2 - Embankment fill material | Not started | Open | ITP-003 Subgrade/Foundation Preparation | Village Access Road | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-VAR-001
cl:2addc368-ad46-4a60-8a50-f442ecc3a00c | EVA Copper Mine Project | Village Access Road > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-VAR-001 | Subgrade/Foundation Preparation | SP.1.3 - Survey Set out | Not started | Open | ITP-003 Subgrade/Foundation Preparation | Village Access Road | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-VAR-001
cl:2addc368-ad46-4a60-8a50-f442ecc3a00c | EVA Copper Mine Project | Village Access Road > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-VAR-001 | Subgrade/Foundation Preparation | SP.1.4 - Removal and replacement of unsuitable material | Passed | Open | ITP-003 Subgrade/Foundation Preparation | Village Access Road | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-VAR-001
cl:2addc368-ad46-4a60-8a50-f442ecc3a00c | EVA Copper Mine Project | Village Access Road > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-VAR-001 | Subgrade/Foundation Preparation | SP.1.5 - Subgrade/Foundation preparation | Passed | Open | ITP-003 Subgrade/Foundation Preparation | Village Access Road | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-VAR-001
cl:2addc368-ad46-4a60-8a50-f442ecc3a00c | EVA Copper Mine Project | Village Access Road > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-VAR-001 | Subgrade/Foundation Preparation | SP.1.6 - Trim subgrade | Not started | Open | ITP-003 Subgrade/Foundation Preparation | Village Access Road | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-VAR-001
cl:2addc368-ad46-4a60-8a50-f442ecc3a00c | EVA Copper Mine Project | Village Access Road > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-VAR-001 | Subgrade/Foundation Preparation | SP.1.7 - Proof rolling | Not started | Open | ITP-003 Subgrade/Foundation Preparation | Village Access Road | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-VAR-001
cl:2addc368-ad46-4a60-8a50-f442ecc3a00c | EVA Copper Mine Project | Village Access Road > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-VAR-001 | Subgrade/Foundation Preparation | SP.1.8 - Surface level check and survey pick-up | Not started | Open | ITP-003 Subgrade/Foundation Preparation | Village Access Road | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-VAR-001
cl:2addc368-ad46-4a60-8a50-f442ecc3a00c | EVA Copper Mine Project | Village Access Road > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-VAR-001 | Subgrade/Foundation Preparation | SP.1.9 - QA close out | Not started | Open | ITP-003 Subgrade/Foundation Preparation | Village Access Road | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-VAR-001
cl:8700bf87-789c-42c6-962c-8599ed772427 | EVA Copper Mine Project | Village Access Road > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-VAR-002 | Subgrade/Foundation Preparation | SP.1.1 - Underlying lot & ITP signed off and conforming | Not started |  | ITP-003 Subgrade/Foundation Preparation | Village Access Road | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-VAR-002
cl:8700bf87-789c-42c6-962c-8599ed772427 | EVA Copper Mine Project | Village Access Road > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-VAR-002 | Subgrade/Foundation Preparation | SP.1.2 - Embankment fill material | Not started | Open | ITP-003 Subgrade/Foundation Preparation | Village Access Road | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-VAR-002
cl:8700bf87-789c-42c6-962c-8599ed772427 | EVA Copper Mine Project | Village Access Road > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-VAR-002 | Subgrade/Foundation Preparation | SP.1.3 - Survey Set out | Not started | Open | ITP-003 Subgrade/Foundation Preparation | Village Access Road | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-VAR-002
cl:8700bf87-789c-42c6-962c-8599ed772427 | EVA Copper Mine Project | Village Access Road > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-VAR-002 | Subgrade/Foundation Preparation | SP.1.4 - Removal and replacement of unsuitable material | Not started | Open | ITP-003 Subgrade/Foundation Preparation | Village Access Road | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-VAR-002
cl:8700bf87-789c-42c6-962c-8599ed772427 | EVA Copper Mine Project | Village Access Road > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-VAR-002 | Subgrade/Foundation Preparation | SP.1.5 - Subgrade/Foundation preparation | Not started | Open | ITP-003 Subgrade/Foundation Preparation | Village Access Road | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-VAR-002
cl:8700bf87-789c-42c6-962c-8599ed772427 | EVA Copper Mine Project | Village Access Road > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-VAR-002 | Subgrade/Foundation Preparation | SP.1.6 - Trim subgrade | Not started | Open | ITP-003 Subgrade/Foundation Preparation | Village Access Road | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-VAR-002
cl:8700bf87-789c-42c6-962c-8599ed772427 | EVA Copper Mine Project | Village Access Road > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-VAR-002 | Subgrade/Foundation Preparation | SP.1.7 - Proof rolling | Not started | Open | ITP-003 Subgrade/Foundation Preparation | Village Access Road | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-VAR-002
cl:8700bf87-789c-42c6-962c-8599ed772427 | EVA Copper Mine Project | Village Access Road > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-VAR-002 | Subgrade/Foundation Preparation | SP.1.8 - Surface level check and survey pick-up | Not started | Open | ITP-003 Subgrade/Foundation Preparation | Village Access Road | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-VAR-002
cl:8700bf87-789c-42c6-962c-8599ed772427 | EVA Copper Mine Project | Village Access Road > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-VAR-002 | Subgrade/Foundation Preparation | SP.1.9 - QA close out | Not started | Open | ITP-003 Subgrade/Foundation Preparation | Village Access Road | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-VAR-002
cl:8203d441-4a86-407c-bb91-4c1aab0c5def | EVA Copper Mine Project | Village Access Road > ITP-004 RCP Installation | ITP-004 RCP Installation-VAR-001 | 1.0 Pre-Construction | RCP1.1 - Drawings supplied most current IFC | Not started | Open | ITP-004 RCP Installation | Village Access Road | ITP-004 RCP Installation | ITP-004 RCP Installation-VAR-001
cl:8203d441-4a86-407c-bb91-4c1aab0c5def | EVA Copper Mine Project | Village Access Road > ITP-004 RCP Installation | ITP-004 RCP Installation-VAR-001 | 1.0 Pre-Construction | RCP1.2 - Define RCP ID | Not started | Open | ITP-004 RCP Installation | Village Access Road | ITP-004 RCP Installation | ITP-004 RCP Installation-VAR-001
cl:8203d441-4a86-407c-bb91-4c1aab0c5def | EVA Copper Mine Project | Village Access Road > ITP-004 RCP Installation | ITP-004 RCP Installation-VAR-001 | 1.0 Pre-Construction | RCP1.3 - Lot Register/ WBS submitted and approved | Not started | Open | ITP-004 RCP Installation | Village Access Road | ITP-004 RCP Installation | ITP-004 RCP Installation-VAR-001
cl:8203d441-4a86-407c-bb91-4c1aab0c5def | EVA Copper Mine Project | Village Access Road > ITP-004 RCP Installation | ITP-004 RCP Installation-VAR-001 | 1.0 Pre-Construction | RCP1.4 - Underlying lot & ITP signed off and conforming | Not started | Open | ITP-004 RCP Installation | Village Access Road | ITP-004 RCP Installation | ITP-004 RCP Installation-VAR-001
cl:8203d441-4a86-407c-bb91-4c1aab0c5def | EVA Copper Mine Project | Village Access Road > ITP-004 RCP Installation | ITP-004 RCP Installation-VAR-001 | 1.0 Pre-Construction | RCP1.5 - Certificate of compliance for RCP Material | Not started | Open | ITP-004 RCP Installation | Village Access Road | ITP-004 RCP Installation | ITP-004 RCP Installation-VAR-001
cl:8203d441-4a86-407c-bb91-4c1aab0c5def | EVA Copper Mine Project | Village Access Road > ITP-004 RCP Installation | ITP-004 RCP Installation-VAR-001 | 1.0 Pre-Construction | RCP1.6 - Inspect reinforced pipe culverts for damage | Not started | Open | ITP-004 RCP Installation | Village Access Road | ITP-004 RCP Installation | ITP-004 RCP Installation-VAR-001
cl:8203d441-4a86-407c-bb91-4c1aab0c5def | EVA Copper Mine Project | Village Access Road > ITP-004 RCP Installation | ITP-004 RCP Installation-VAR-001 | 2.0 Construction | RCP2.7 - Trench Excavation | Not started | Open | ITP-004 RCP Installation | Village Access Road | ITP-004 RCP Installation | ITP-004 RCP Installation-VAR-001
cl:8203d441-4a86-407c-bb91-4c1aab0c5def | EVA Copper Mine Project | Village Access Road > ITP-004 RCP Installation | ITP-004 RCP Installation-VAR-001 | 2.0 Construction | RCP2.8 - Bedding | Not started | Open | ITP-004 RCP Installation | Village Access Road | ITP-004 RCP Installation | ITP-004 RCP Installation-VAR-001
cl:8203d441-4a86-407c-bb91-4c1aab0c5def | EVA Copper Mine Project | Village Access Road > ITP-004 RCP Installation | ITP-004 RCP Installation-VAR-001 | 2.0 Construction | RCP2.9 - RCP Installation | Not started | Open | ITP-004 RCP Installation | Village Access Road | ITP-004 RCP Installation | ITP-004 RCP Installation-VAR-001
cl:8203d441-4a86-407c-bb91-4c1aab0c5def | EVA Copper Mine Project | Village Access Road > ITP-004 RCP Installation | ITP-004 RCP Installation-VAR-001 | 2.0 Construction | RCP2.10 - Backfilling of culvert | Not started | Open | ITP-004 RCP Installation | Village Access Road | ITP-004 RCP Installation | ITP-004 RCP Installation-VAR-001
cl:8203d441-4a86-407c-bb91-4c1aab0c5def | EVA Copper Mine Project | Village Access Road > ITP-004 RCP Installation | ITP-004 RCP Installation-VAR-001 | 2.0 Construction | RCP2.11 - End Treatment – Headwall & Wingwalls (Reinforcement) | Not started | Open | ITP-004 RCP Installation | Village Access Road | ITP-004 RCP Installation | ITP-004 RCP Installation-VAR-001
cl:8203d441-4a86-407c-bb91-4c1aab0c5def | EVA Copper Mine Project | Village Access Road > ITP-004 RCP Installation | ITP-004 RCP Installation-VAR-001 | 2.0 Construction | RCP2.12 - End Treatment – Headwall & Wingwalls (Formwork) | Not started | Open | ITP-004 RCP Installation | Village Access Road | ITP-004 RCP Installation | ITP-004 RCP Installation-VAR-001
cl:8203d441-4a86-407c-bb91-4c1aab0c5def | EVA Copper Mine Project | Village Access Road > ITP-004 RCP Installation | ITP-004 RCP Installation-VAR-001 | 2.0 Construction | RCP2.13 - End Treatment – Headwall & Wingwalls (Concrete) | Not started | Open | ITP-004 RCP Installation | Village Access Road | ITP-004 RCP Installation | ITP-004 RCP Installation-VAR-001
cl:8203d441-4a86-407c-bb91-4c1aab0c5def | EVA Copper Mine Project | Village Access Road > ITP-004 RCP Installation | ITP-004 RCP Installation-VAR-001 | 2.0 Construction | RCP2.14 - Rock Protection | Not started | Open | ITP-004 RCP Installation | Village Access Road | ITP-004 RCP Installation | ITP-004 RCP Installation-VAR-001
cl:8203d441-4a86-407c-bb91-4c1aab0c5def | EVA Copper Mine Project | Village Access Road > ITP-004 RCP Installation | ITP-004 RCP Installation-VAR-001 | 3.0 Post Construction | RCP3.15 - Works completed and update ITP/ Lot Register/ MDR and close out of GDP | Not started | Open | ITP-004 RCP Installation | Village Access Road | ITP-004 RCP Installation | ITP-004 RCP Installation-VAR-001
cl:9dd4ae65-c256-4d9b-a28e-98dfe0a92616 | EVA Copper Mine Project | Village Access Road > ITP-004 RCP Installation | ITP-004 RCP Installation-VAR-002 | 1.0 Pre-Construction | RCP1.1 - Drawings supplied most current IFC | Not started | Open | ITP-004 RCP Installation | Village Access Road | ITP-004 RCP Installation | ITP-004 RCP Installation-VAR-002
cl:9dd4ae65-c256-4d9b-a28e-98dfe0a92616 | EVA Copper Mine Project | Village Access Road > ITP-004 RCP Installation | ITP-004 RCP Installation-VAR-002 | 1.0 Pre-Construction | RCP1.2 - Define RCP ID | Not started | Open | ITP-004 RCP Installation | Village Access Road | ITP-004 RCP Installation | ITP-004 RCP Installation-VAR-002
cl:9dd4ae65-c256-4d9b-a28e-98dfe0a92616 | EVA Copper Mine Project | Village Access Road > ITP-004 RCP Installation | ITP-004 RCP Installation-VAR-002 | 1.0 Pre-Construction | RCP1.3 - Lot Register/ WBS submitted and approved | Not started | Open | ITP-004 RCP Installation | Village Access Road | ITP-004 RCP Installation | ITP-004 RCP Installation-VAR-002
cl:9dd4ae65-c256-4d9b-a28e-98dfe0a92616 | EVA Copper Mine Project | Village Access Road > ITP-004 RCP Installation | ITP-004 RCP Installation-VAR-002 | 1.0 Pre-Construction | RCP1.4 - Underlying lot & ITP signed off and conforming | Not started | Open | ITP-004 RCP Installation | Village Access Road | ITP-004 RCP Installation | ITP-004 RCP Installation-VAR-002
cl:9dd4ae65-c256-4d9b-a28e-98dfe0a92616 | EVA Copper Mine Project | Village Access Road > ITP-004 RCP Installation | ITP-004 RCP Installation-VAR-002 | 1.0 Pre-Construction | RCP1.5 - Certificate of compliance for RCP Material | Not started | Open | ITP-004 RCP Installation | Village Access Road | ITP-004 RCP Installation | ITP-004 RCP Installation-VAR-002
cl:9dd4ae65-c256-4d9b-a28e-98dfe0a92616 | EVA Copper Mine Project | Village Access Road > ITP-004 RCP Installation | ITP-004 RCP Installation-VAR-002 | 1.0 Pre-Construction | RCP1.6 - Inspect reinforced pipe culverts for damage | Not started | Open | ITP-004 RCP Installation | Village Access Road | ITP-004 RCP Installation | ITP-004 RCP Installation-VAR-002
cl:9dd4ae65-c256-4d9b-a28e-98dfe0a92616 | EVA Copper Mine Project | Village Access Road > ITP-004 RCP Installation | ITP-004 RCP Installation-VAR-002 | 2.0 Construction | RCP2.7 - Trench Excavation | Not started | Open | ITP-004 RCP Installation | Village Access Road | ITP-004 RCP Installation | ITP-004 RCP Installation-VAR-002
cl:9dd4ae65-c256-4d9b-a28e-98dfe0a92616 | EVA Copper Mine Project | Village Access Road > ITP-004 RCP Installation | ITP-004 RCP Installation-VAR-002 | 2.0 Construction | RCP2.8 - Bedding | Not started | Open | ITP-004 RCP Installation | Village Access Road | ITP-004 RCP Installation | ITP-004 RCP Installation-VAR-002
cl:9dd4ae65-c256-4d9b-a28e-98dfe0a92616 | EVA Copper Mine Project | Village Access Road > ITP-004 RCP Installation | ITP-004 RCP Installation-VAR-002 | 2.0 Construction | RCP2.9 - RCP Installation | Not started | Open | ITP-004 RCP Installation | Village Access Road | ITP-004 RCP Installation | ITP-004 RCP Installation-VAR-002
cl:9dd4ae65-c256-4d9b-a28e-98dfe0a92616 | EVA Copper Mine Project | Village Access Road > ITP-004 RCP Installation | ITP-004 RCP Installation-VAR-002 | 2.0 Construction | RCP2.10 - Backfilling of culvert | Not started | Open | ITP-004 RCP Installation | Village Access Road | ITP-004 RCP Installation | ITP-004 RCP Installation-VAR-002
cl:9dd4ae65-c256-4d9b-a28e-98dfe0a92616 | EVA Copper Mine Project | Village Access Road > ITP-004 RCP Installation | ITP-004 RCP Installation-VAR-002 | 2.0 Construction | RCP2.11 - End Treatment – Headwall & Wingwalls (Reinforcement) | Not started | Open | ITP-004 RCP Installation | Village Access Road | ITP-004 RCP Installation | ITP-004 RCP Installation-VAR-002
cl:9dd4ae65-c256-4d9b-a28e-98dfe0a92616 | EVA Copper Mine Project | Village Access Road > ITP-004 RCP Installation | ITP-004 RCP Installation-VAR-002 | 2.0 Construction | RCP2.12 - End Treatment – Headwall & Wingwalls (Formwork) | Not started | Open | ITP-004 RCP Installation | Village Access Road | ITP-004 RCP Installation | ITP-004 RCP Installation-VAR-002
cl:9dd4ae65-c256-4d9b-a28e-98dfe0a92616 | EVA Copper Mine Project | Village Access Road > ITP-004 RCP Installation | ITP-004 RCP Installation-VAR-002 | 2.0 Construction | RCP2.13 - End Treatment – Headwall & Wingwalls (Concrete) | Not started | Open | ITP-004 RCP Installation | Village Access Road | ITP-004 RCP Installation | ITP-004 RCP Installation-VAR-002
cl:9dd4ae65-c256-4d9b-a28e-98dfe0a92616 | EVA Copper Mine Project | Village Access Road > ITP-004 RCP Installation | ITP-004 RCP Installation-VAR-002 | 2.0 Construction | RCP2.14 - Rock Protection | Not started | Open | ITP-004 RCP Installation | Village Access Road | ITP-004 RCP Installation | ITP-004 RCP Installation-VAR-002
cl:9dd4ae65-c256-4d9b-a28e-98dfe0a92616 | EVA Copper Mine Project | Village Access Road > ITP-004 RCP Installation | ITP-004 RCP Installation-VAR-002 | 3.0 Post Construction | RCP3.15 - Works completed and update ITP/ Lot Register/ MDR and close out of GDP | Not started | Open | ITP-004 RCP Installation | Village Access Road | ITP-004 RCP Installation | ITP-004 RCP Installation-VAR-002
cl:d03a27b9-4791-498b-a7b0-88ddcb11e7f0 | EVA Copper Mine Project | Village Access Road > ITP-008 Embankment Construction | ITP-008 Embankment Construction-VAR-001 | Embankment Construction | EC1.1 - Underlying lot & ITP signed off and conforming | Not started | Open | ITP-008 Embankment Construction | Village Access Road | ITP-008 Embankment Construction | ITP-008 Embankment Construction-VAR-001
cl:d03a27b9-4791-498b-a7b0-88ddcb11e7f0 | EVA Copper Mine Project | Village Access Road > ITP-008 Embankment Construction | ITP-008 Embankment Construction-VAR-001 | Embankment Construction | EC1.2 - Embankment fill material | Not started | Open | ITP-008 Embankment Construction | Village Access Road | ITP-008 Embankment Construction | ITP-008 Embankment Construction-VAR-001
cl:d03a27b9-4791-498b-a7b0-88ddcb11e7f0 | EVA Copper Mine Project | Village Access Road > ITP-008 Embankment Construction | ITP-008 Embankment Construction-VAR-001 | Embankment Construction | EC1.3 - Survey Set out | Not started | Open | ITP-008 Embankment Construction | Village Access Road | ITP-008 Embankment Construction | ITP-008 Embankment Construction-VAR-001
cl:d03a27b9-4791-498b-a7b0-88ddcb11e7f0 | EVA Copper Mine Project | Village Access Road > ITP-008 Embankment Construction | ITP-008 Embankment Construction-VAR-001 | Embankment Construction | EC1.4 - Place, moisture condition & compact embankment fill | Not started | Open | ITP-008 Embankment Construction | Village Access Road | ITP-008 Embankment Construction | ITP-008 Embankment Construction-VAR-001
cl:d03a27b9-4791-498b-a7b0-88ddcb11e7f0 | EVA Copper Mine Project | Village Access Road > ITP-008 Embankment Construction | ITP-008 Embankment Construction-VAR-001 | Embankment Construction | EC1.5 - Trim embankment | Not started | Open | ITP-008 Embankment Construction | Village Access Road | ITP-008 Embankment Construction | ITP-008 Embankment Construction-VAR-001
cl:d03a27b9-4791-498b-a7b0-88ddcb11e7f0 | EVA Copper Mine Project | Village Access Road > ITP-008 Embankment Construction | ITP-008 Embankment Construction-VAR-001 | Embankment Construction | EC1.6 - Proof rolling | Not started | Open | ITP-008 Embankment Construction | Village Access Road | ITP-008 Embankment Construction | ITP-008 Embankment Construction-VAR-001
cl:d03a27b9-4791-498b-a7b0-88ddcb11e7f0 | EVA Copper Mine Project | Village Access Road > ITP-008 Embankment Construction | ITP-008 Embankment Construction-VAR-001 | Embankment Construction | EC1.7 - Surface level check and survey pick-up | Not started | Open | ITP-008 Embankment Construction | Village Access Road | ITP-008 Embankment Construction | ITP-008 Embankment Construction-VAR-001
cl:d03a27b9-4791-498b-a7b0-88ddcb11e7f0 | EVA Copper Mine Project | Village Access Road > ITP-008 Embankment Construction | ITP-008 Embankment Construction-VAR-001 | Embankment Construction | EC1.8 - QA close out | Not started | Open | ITP-008 Embankment Construction | Village Access Road | ITP-008 Embankment Construction | ITP-008 Embankment Construction-VAR-001
cl:08b4f1e7-d822-4d9f-88b2-748d2d979e83 | EVA Copper Mine Project | Village Access Road > ITP-008 Embankment Construction | ITP-008 Embankment Construction-VAR-002 | Embankment Construction | EC1.1 - Underlying lot & ITP signed off and conforming | Not started | Open | ITP-008 Embankment Construction | Village Access Road | ITP-008 Embankment Construction | ITP-008 Embankment Construction-VAR-002
cl:08b4f1e7-d822-4d9f-88b2-748d2d979e83 | EVA Copper Mine Project | Village Access Road > ITP-008 Embankment Construction | ITP-008 Embankment Construction-VAR-002 | Embankment Construction | EC1.2 - Embankment fill material | Not started | Open | ITP-008 Embankment Construction | Village Access Road | ITP-008 Embankment Construction | ITP-008 Embankment Construction-VAR-002
cl:08b4f1e7-d822-4d9f-88b2-748d2d979e83 | EVA Copper Mine Project | Village Access Road > ITP-008 Embankment Construction | ITP-008 Embankment Construction-VAR-002 | Embankment Construction | EC1.3 - Survey Set out | Not started | Open | ITP-008 Embankment Construction | Village Access Road | ITP-008 Embankment Construction | ITP-008 Embankment Construction-VAR-002
cl:08b4f1e7-d822-4d9f-88b2-748d2d979e83 | EVA Copper Mine Project | Village Access Road > ITP-008 Embankment Construction | ITP-008 Embankment Construction-VAR-002 | Embankment Construction | EC1.4 - Place, moisture condition & compact embankment fill | Not started | Open | ITP-008 Embankment Construction | Village Access Road | ITP-008 Embankment Construction | ITP-008 Embankment Construction-VAR-002
cl:08b4f1e7-d822-4d9f-88b2-748d2d979e83 | EVA Copper Mine Project | Village Access Road > ITP-008 Embankment Construction | ITP-008 Embankment Construction-VAR-002 | Embankment Construction | EC1.5 - Trim embankment | Not started | Open | ITP-008 Embankment Construction | Village Access Road | ITP-008 Embankment Construction | ITP-008 Embankment Construction-VAR-002
cl:08b4f1e7-d822-4d9f-88b2-748d2d979e83 | EVA Copper Mine Project | Village Access Road > ITP-008 Embankment Construction | ITP-008 Embankment Construction-VAR-002 | Embankment Construction | EC1.6 - Proof rolling | Not started | Open | ITP-008 Embankment Construction | Village Access Road | ITP-008 Embankment Construction | ITP-008 Embankment Construction-VAR-002
cl:08b4f1e7-d822-4d9f-88b2-748d2d979e83 | EVA Copper Mine Project | Village Access Road > ITP-008 Embankment Construction | ITP-008 Embankment Construction-VAR-002 | Embankment Construction | EC1.7 - Surface level check and survey pick-up | Not started | Open | ITP-008 Embankment Construction | Village Access Road | ITP-008 Embankment Construction | ITP-008 Embankment Construction-VAR-002
cl:08b4f1e7-d822-4d9f-88b2-748d2d979e83 | EVA Copper Mine Project | Village Access Road > ITP-008 Embankment Construction | ITP-008 Embankment Construction-VAR-002 | Embankment Construction | EC1.8 - QA close out | Not started | Open | ITP-008 Embankment Construction | Village Access Road | ITP-008 Embankment Construction | ITP-008 Embankment Construction-VAR-002
cl:eaa0e5ad-0014-4d40-91d4-2543189b840d | EVA Copper Mine Project | Village Access Road > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-VAR-001 | 1.0 Pre-Construction | GP1.1 - Drawings supplied most current IFC | Not started | Open | ITP-009 Unbound Gravel Pavements | Village Access Road | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-VAR-001
cl:eaa0e5ad-0014-4d40-91d4-2543189b840d | EVA Copper Mine Project | Village Access Road > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-VAR-001 | 1.0 Pre-Construction | GP1.2 - Management Plans submitted and approved as per PMP | Not started | Open | ITP-009 Unbound Gravel Pavements | Village Access Road | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-VAR-001
cl:eaa0e5ad-0014-4d40-91d4-2543189b840d | EVA Copper Mine Project | Village Access Road > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-VAR-001 | 1.0 Pre-Construction | GP1.3 - Inspection Test Plan (ITP) submitted and approved | Not started | Open | ITP-009 Unbound Gravel Pavements | Village Access Road | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-VAR-001
cl:eaa0e5ad-0014-4d40-91d4-2543189b840d | EVA Copper Mine Project | Village Access Road > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-VAR-001 | 1.0 Pre-Construction | GP1.4 - Lot Register/ WBS submitted and approved | Not started | Open | ITP-009 Unbound Gravel Pavements | Village Access Road | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-VAR-001
cl:eaa0e5ad-0014-4d40-91d4-2543189b840d | EVA Copper Mine Project | Village Access Road > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-VAR-001 | 1.0 Pre-Construction | GP1.5 - Pavement material compliance testing | Not started | Open | ITP-009 Unbound Gravel Pavements | Village Access Road | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-VAR-001
cl:eaa0e5ad-0014-4d40-91d4-2543189b840d | EVA Copper Mine Project | Village Access Road > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-VAR-001 | 1.0 Pre-Construction | GP1.6 - Stockpile locations | Not started | Open | ITP-009 Unbound Gravel Pavements | Village Access Road | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-VAR-001
cl:eaa0e5ad-0014-4d40-91d4-2543189b840d | EVA Copper Mine Project | Village Access Road > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-VAR-001 | 1.0 Pre-Construction | GP1.7 - Underlying lot & ITP signed off and conforming | Not started | Open | ITP-009 Unbound Gravel Pavements | Village Access Road | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-VAR-001
cl:eaa0e5ad-0014-4d40-91d4-2543189b840d | EVA Copper Mine Project | Village Access Road > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-VAR-001 | 2.0 Construction | GP2.8 - Subgrade preparation under pavements | Not started | Open | ITP-009 Unbound Gravel Pavements | Village Access Road | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-VAR-001
cl:eaa0e5ad-0014-4d40-91d4-2543189b840d | EVA Copper Mine Project | Village Access Road > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-VAR-001 | 2.0 Construction | EC2.9 - Surface level check/ and survey pick-up | Not started | Open | ITP-009 Unbound Gravel Pavements | Village Access Road | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-VAR-001
cl:eaa0e5ad-0014-4d40-91d4-2543189b840d | EVA Copper Mine Project | Village Access Road > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-VAR-001 | 2.0 Construction | EC2.10 - Proof roll subgrade prior to placement of pavement materials | Not started | Open | ITP-009 Unbound Gravel Pavements | Village Access Road | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-VAR-001
cl:eaa0e5ad-0014-4d40-91d4-2543189b840d | EVA Copper Mine Project | Village Access Road > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-VAR-001 | 2.0 Construction | EC2.11 - Placement of pavement material layers | Not started | Open | ITP-009 Unbound Gravel Pavements | Village Access Road | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-VAR-001
cl:eaa0e5ad-0014-4d40-91d4-2543189b840d | EVA Copper Mine Project | Village Access Road > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-VAR-001 | 2.0 Construction | EC2.12 - Surface level check/ and survey pick-up | Not started | Open | ITP-009 Unbound Gravel Pavements | Village Access Road | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-VAR-001
cl:eaa0e5ad-0014-4d40-91d4-2543189b840d | EVA Copper Mine Project | Village Access Road > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-VAR-001 | 3.0 Post Construction | EC3.13 - Works completed and update ITP/ Lot Register/ MDR and close out of GDP | Not started | Open | ITP-009 Unbound Gravel Pavements | Village Access Road | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-VAR-001
cl:12ac3408-6f63-41d1-9325-bd7fd5d5c990 | EVA Copper Mine Project | Village Access Road > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-VAR-002 | 1.0 Pre-Construction | GP1.1 - Drawings supplied most current IFC | Not started | Open | ITP-009 Unbound Gravel Pavements | Village Access Road | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-VAR-002
cl:12ac3408-6f63-41d1-9325-bd7fd5d5c990 | EVA Copper Mine Project | Village Access Road > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-VAR-002 | 1.0 Pre-Construction | GP1.2 - Management Plans submitted and approved as per PMP | Not started | Open | ITP-009 Unbound Gravel Pavements | Village Access Road | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-VAR-002
cl:12ac3408-6f63-41d1-9325-bd7fd5d5c990 | EVA Copper Mine Project | Village Access Road > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-VAR-002 | 1.0 Pre-Construction | GP1.3 - Inspection Test Plan (ITP) submitted and approved | Not started | Open | ITP-009 Unbound Gravel Pavements | Village Access Road | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-VAR-002
cl:12ac3408-6f63-41d1-9325-bd7fd5d5c990 | EVA Copper Mine Project | Village Access Road > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-VAR-002 | 1.0 Pre-Construction | GP1.4 - Lot Register/ WBS submitted and approved | Not started | Open | ITP-009 Unbound Gravel Pavements | Village Access Road | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-VAR-002
cl:12ac3408-6f63-41d1-9325-bd7fd5d5c990 | EVA Copper Mine Project | Village Access Road > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-VAR-002 | 1.0 Pre-Construction | GP1.5 - Pavement material compliance testing | Not started | Open | ITP-009 Unbound Gravel Pavements | Village Access Road | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-VAR-002
cl:12ac3408-6f63-41d1-9325-bd7fd5d5c990 | EVA Copper Mine Project | Village Access Road > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-VAR-002 | 1.0 Pre-Construction | GP1.6 - Stockpile locations | Not started | Open | ITP-009 Unbound Gravel Pavements | Village Access Road | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-VAR-002
cl:12ac3408-6f63-41d1-9325-bd7fd5d5c990 | EVA Copper Mine Project | Village Access Road > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-VAR-002 | 1.0 Pre-Construction | GP1.7 - Underlying lot & ITP signed off and conforming | Not started | Open | ITP-009 Unbound Gravel Pavements | Village Access Road | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-VAR-002
cl:12ac3408-6f63-41d1-9325-bd7fd5d5c990 | EVA Copper Mine Project | Village Access Road > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-VAR-002 | 2.0 Construction | GP2.8 - Subgrade preparation under pavements | Not started | Open | ITP-009 Unbound Gravel Pavements | Village Access Road | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-VAR-002
cl:12ac3408-6f63-41d1-9325-bd7fd5d5c990 | EVA Copper Mine Project | Village Access Road > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-VAR-002 | 2.0 Construction | EC2.9 - Surface level check/ and survey pick-up | Not started | Open | ITP-009 Unbound Gravel Pavements | Village Access Road | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-VAR-002
cl:12ac3408-6f63-41d1-9325-bd7fd5d5c990 | EVA Copper Mine Project | Village Access Road > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-VAR-002 | 2.0 Construction | EC2.10 - Proof roll subgrade prior to placement of pavement materials | Not started | Open | ITP-009 Unbound Gravel Pavements | Village Access Road | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-VAR-002
cl:12ac3408-6f63-41d1-9325-bd7fd5d5c990 | EVA Copper Mine Project | Village Access Road > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-VAR-002 | 2.0 Construction | EC2.11 - Placement of pavement material layers | Not started | Open | ITP-009 Unbound Gravel Pavements | Village Access Road | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-VAR-002
cl:12ac3408-6f63-41d1-9325-bd7fd5d5c990 | EVA Copper Mine Project | Village Access Road > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-VAR-002 | 2.0 Construction | EC2.12 - Surface level check/ and survey pick-up | Not started | Open | ITP-009 Unbound Gravel Pavements | Village Access Road | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-VAR-002
cl:12ac3408-6f63-41d1-9325-bd7fd5d5c990 | EVA Copper Mine Project | Village Access Road > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-VAR-002 | 3.0 Post Construction | EC3.13 - Works completed and update ITP/ Lot Register/ MDR and close out of GDP | Not started | Open | ITP-009 Unbound Gravel Pavements | Village Access Road | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-VAR-002
cl:dbbb96c4-cbaf-4489-9dc8-5cca11326792 | EVA Copper Mine Project | AWP-1B > Process Plant | ITP-000 Pre-construction-PP | Pre-construction | PC1.2 - Lot Register/ WBS | Not started | Open | ITP-000 Pre-construction | AWP-1B | Process Plant | ITP-000 Pre-construction-PP
cl:dbbb96c4-cbaf-4489-9dc8-5cca11326792 | EVA Copper Mine Project | AWP-1B > Process Plant | ITP-000 Pre-construction-PP | Pre-construction | PC1.3 - Construction procedures | Not started | Open | ITP-000 Pre-construction | AWP-1B | Process Plant | ITP-000 Pre-construction-PP
cl:dbbb96c4-cbaf-4489-9dc8-5cca11326792 | EVA Copper Mine Project | AWP-1B > Process Plant | ITP-000 Pre-construction-PP | Pre-construction | PC1.4 - Excavation permit | Not started | Open | ITP-000 Pre-construction | AWP-1B | Process Plant | ITP-000 Pre-construction-PP
cl:dbbb96c4-cbaf-4489-9dc8-5cca11326792 | EVA Copper Mine Project | AWP-1B > Process Plant | ITP-000 Pre-construction-PP | Pre-construction | PC1.5 - Dial before you dig check | Not started | Open | ITP-000 Pre-construction | AWP-1B | Process Plant | ITP-000 Pre-construction-PP
cl:dbbb96c4-cbaf-4489-9dc8-5cca11326792 | EVA Copper Mine Project | AWP-1B > Process Plant | ITP-000 Pre-construction-PP | Pre-construction | PC1.6 - Traffic control plan | Not started | Open | ITP-000 Pre-construction | AWP-1B | Process Plant | ITP-000 Pre-construction-PP
cl:dbbb96c4-cbaf-4489-9dc8-5cca11326792 | EVA Copper Mine Project | AWP-1B > Process Plant | ITP-000 Pre-construction-PP | Pre-construction | PC1.7 - Inspection Test Plan (ITP) submitted and approved | Not started | Open | ITP-000 Pre-construction | AWP-1B | Process Plant | ITP-000 Pre-construction-PP
cl:dbbb96c4-cbaf-4489-9dc8-5cca11326792 | EVA Copper Mine Project | AWP-1B > Process Plant | ITP-000 Pre-construction-PP | Pre-construction | PC1.8 - IFC drawings | Not started | Open | ITP-000 Pre-construction | AWP-1B | Process Plant | ITP-000 Pre-construction-PP
cl:dbbb96c4-cbaf-4489-9dc8-5cca11326792 | EVA Copper Mine Project | AWP-1B > Process Plant | ITP-000 Pre-construction-PP | Pre-construction | PC1.9 - Erosion and sediment control plan | Not started | Open | ITP-000 Pre-construction | AWP-1B | Process Plant | ITP-000 Pre-construction-PP
cl:dbbb96c4-cbaf-4489-9dc8-5cca11326792 | EVA Copper Mine Project | AWP-1B > Process Plant | ITP-000 Pre-construction-PP | Pre-construction | PC1.10 - Approved stockpile locations | Not started | Open | ITP-000 Pre-construction | AWP-1B | Process Plant | ITP-000 Pre-construction-PP
cl:dbbb96c4-cbaf-4489-9dc8-5cca11326792 | EVA Copper Mine Project | AWP-1B > Process Plant | ITP-000 Pre-construction-PP | Pre-construction | PC1.11 - Embankment fill materials | Not started | Open | ITP-000 Pre-construction | AWP-1B | Process Plant | ITP-000 Pre-construction-PP
cl:dbbb96c4-cbaf-4489-9dc8-5cca11326792 | EVA Copper Mine Project | AWP-1B > Process Plant | ITP-000 Pre-construction-PP | Pre-construction | PC1.12 - QA close out | Not started | Open | ITP-000 Pre-construction | AWP-1B | Process Plant | ITP-000 Pre-construction-PP
cl:9b3084a9-2ff3-4c55-a4cf-1ef6945702b5 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-001 | Clear & Grub | GC1.1 - Underlying lot & ITP signed off and conforming | Not started |  | ITP-001 Clear & Grub | AWP-1B | Process Plant | ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-001
cl:9b3084a9-2ff3-4c55-a4cf-1ef6945702b5 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-001 | Clear & Grub | GC1.2 - Ground Disturbance Permit (GDP) | Not started | Open | ITP-001 Clear & Grub | AWP-1B | Process Plant | ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-001
cl:9b3084a9-2ff3-4c55-a4cf-1ef6945702b5 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-001 | Clear & Grub | GC1.3 - Cultural Heritage(CH) Clearance Survey | Not started | Open | ITP-001 Clear & Grub | AWP-1B | Process Plant | ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-001
cl:9b3084a9-2ff3-4c55-a4cf-1ef6945702b5 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-001 | Clear & Grub | GC1.4 - GDP survey set out | Not started | Open | ITP-001 Clear & Grub | AWP-1B | Process Plant | ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-001
cl:9b3084a9-2ff3-4c55-a4cf-1ef6945702b5 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-001 | Clear & Grub | GC1.5 - Survey of pegs to confirm correct GDP survey set out | Not started | Open | ITP-001 Clear & Grub | AWP-1B | Process Plant | ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-001
cl:9b3084a9-2ff3-4c55-a4cf-1ef6945702b5 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-001 | Clear & Grub | GC1.6 - Survey natural surface | Not started | Open | ITP-001 Clear & Grub | AWP-1B | Process Plant | ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-001
cl:9b3084a9-2ff3-4c55-a4cf-1ef6945702b5 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-001 | Clear & Grub | GC1.7 - Fauna Spotter Catcher (FSC) Pre-Clearance Survey | Not started | Open | ITP-001 Clear & Grub | AWP-1B | Process Plant | ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-001
cl:9b3084a9-2ff3-4c55-a4cf-1ef6945702b5 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-001 | Clear & Grub | GC1.8 - Mandatory GDP Pre-Clearing walk | Not started | Open | ITP-001 Clear & Grub | AWP-1B | Process Plant | ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-001
cl:9b3084a9-2ff3-4c55-a4cf-1ef6945702b5 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-001 | Clear & Grub | GC1.9 - Clearing of vegetation | Not started | Open | ITP-001 Clear & Grub | AWP-1B | Process Plant | ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-001
cl:9b3084a9-2ff3-4c55-a4cf-1ef6945702b5 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-001 | Clear & Grub | GC1.10 - Stockpile Cleared Vegetation | Not started | Open | ITP-001 Clear & Grub | AWP-1B | Process Plant | ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-001
cl:9b3084a9-2ff3-4c55-a4cf-1ef6945702b5 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-001 | Clear & Grub | GC1.11 - Erosion and sediment control | Not started | Open | ITP-001 Clear & Grub | AWP-1B | Process Plant | ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-001
cl:9b3084a9-2ff3-4c55-a4cf-1ef6945702b5 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-001 | Clear & Grub | GC1.12 - QA close out | Not started | Open | ITP-001 Clear & Grub | AWP-1B | Process Plant | ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-001
cl:263d5a5c-0e10-4f86-b4d7-e052179fb61d | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-002 | Clear & Grub | GC1.1 - Underlying lot & ITP signed off and conforming | Not started |  | ITP-001 Clear & Grub | AWP-1B | Process Plant | ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-002
cl:263d5a5c-0e10-4f86-b4d7-e052179fb61d | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-002 | Clear & Grub | GC1.2 - Ground Disturbance Permit (GDP) | Not started | Open | ITP-001 Clear & Grub | AWP-1B | Process Plant | ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-002
cl:263d5a5c-0e10-4f86-b4d7-e052179fb61d | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-002 | Clear & Grub | GC1.3 - Cultural Heritage(CH) Clearance Survey | Not started | Open | ITP-001 Clear & Grub | AWP-1B | Process Plant | ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-002
cl:263d5a5c-0e10-4f86-b4d7-e052179fb61d | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-002 | Clear & Grub | GC1.4 - GDP survey set out | Not started | Open | ITP-001 Clear & Grub | AWP-1B | Process Plant | ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-002
cl:263d5a5c-0e10-4f86-b4d7-e052179fb61d | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-002 | Clear & Grub | GC1.5 - Survey of pegs to confirm correct GDP survey set out | Not started | Open | ITP-001 Clear & Grub | AWP-1B | Process Plant | ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-002
cl:263d5a5c-0e10-4f86-b4d7-e052179fb61d | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-002 | Clear & Grub | GC1.6 - Survey natural surface | Not started | Open | ITP-001 Clear & Grub | AWP-1B | Process Plant | ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-002
cl:263d5a5c-0e10-4f86-b4d7-e052179fb61d | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-002 | Clear & Grub | GC1.7 - Fauna Spotter Catcher (FSC) Pre-Clearance Survey | Not started | Open | ITP-001 Clear & Grub | AWP-1B | Process Plant | ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-002
cl:263d5a5c-0e10-4f86-b4d7-e052179fb61d | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-002 | Clear & Grub | GC1.8 - Mandatory GDP Pre-Clearing walk | Not started | Open | ITP-001 Clear & Grub | AWP-1B | Process Plant | ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-002
cl:263d5a5c-0e10-4f86-b4d7-e052179fb61d | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-002 | Clear & Grub | GC1.9 - Clearing of vegetation | Not started | Open | ITP-001 Clear & Grub | AWP-1B | Process Plant | ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-002
cl:263d5a5c-0e10-4f86-b4d7-e052179fb61d | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-002 | Clear & Grub | GC1.10 - Stockpile Cleared Vegetation | Not started | Open | ITP-001 Clear & Grub | AWP-1B | Process Plant | ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-002
cl:263d5a5c-0e10-4f86-b4d7-e052179fb61d | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-002 | Clear & Grub | GC1.11 - Erosion and sediment control | Not started | Open | ITP-001 Clear & Grub | AWP-1B | Process Plant | ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-002
cl:263d5a5c-0e10-4f86-b4d7-e052179fb61d | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-002 | Clear & Grub | GC1.12 - QA close out | Not started | Open | ITP-001 Clear & Grub | AWP-1B | Process Plant | ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-002
cl:45cb3de9-b82e-4bcd-b795-eb8fc7c59f10 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-003 | Clear & Grub | GC1.1 - Underlying lot & ITP signed off and conforming | Not started |  | ITP-001 Clear & Grub | AWP-1B | Process Plant | ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-003
cl:45cb3de9-b82e-4bcd-b795-eb8fc7c59f10 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-003 | Clear & Grub | GC1.2 - Ground Disturbance Permit (GDP) | Not started | Open | ITP-001 Clear & Grub | AWP-1B | Process Plant | ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-003
cl:45cb3de9-b82e-4bcd-b795-eb8fc7c59f10 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-003 | Clear & Grub | GC1.3 - Cultural Heritage(CH) Clearance Survey | Not started | Open | ITP-001 Clear & Grub | AWP-1B | Process Plant | ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-003
cl:45cb3de9-b82e-4bcd-b795-eb8fc7c59f10 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-003 | Clear & Grub | GC1.4 - GDP survey set out | Not started | Open | ITP-001 Clear & Grub | AWP-1B | Process Plant | ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-003
cl:45cb3de9-b82e-4bcd-b795-eb8fc7c59f10 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-003 | Clear & Grub | GC1.5 - Survey of pegs to confirm correct GDP survey set out | Not started | Open | ITP-001 Clear & Grub | AWP-1B | Process Plant | ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-003
cl:45cb3de9-b82e-4bcd-b795-eb8fc7c59f10 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-003 | Clear & Grub | GC1.6 - Survey natural surface | Not started | Open | ITP-001 Clear & Grub | AWP-1B | Process Plant | ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-003
cl:45cb3de9-b82e-4bcd-b795-eb8fc7c59f10 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-003 | Clear & Grub | GC1.7 - Fauna Spotter Catcher (FSC) Pre-Clearance Survey | Not started | Open | ITP-001 Clear & Grub | AWP-1B | Process Plant | ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-003
cl:45cb3de9-b82e-4bcd-b795-eb8fc7c59f10 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-003 | Clear & Grub | GC1.8 - Mandatory GDP Pre-Clearing walk | Not started | Open | ITP-001 Clear & Grub | AWP-1B | Process Plant | ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-003
cl:45cb3de9-b82e-4bcd-b795-eb8fc7c59f10 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-003 | Clear & Grub | GC1.9 - Clearing of vegetation | Not started | Open | ITP-001 Clear & Grub | AWP-1B | Process Plant | ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-003
cl:45cb3de9-b82e-4bcd-b795-eb8fc7c59f10 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-003 | Clear & Grub | GC1.10 - Stockpile Cleared Vegetation | Not started | Open | ITP-001 Clear & Grub | AWP-1B | Process Plant | ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-003
cl:45cb3de9-b82e-4bcd-b795-eb8fc7c59f10 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-003 | Clear & Grub | GC1.11 - Erosion and sediment control | Not started | Open | ITP-001 Clear & Grub | AWP-1B | Process Plant | ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-003
cl:45cb3de9-b82e-4bcd-b795-eb8fc7c59f10 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-003 | Clear & Grub | GC1.12 - QA close out | Not started | Open | ITP-001 Clear & Grub | AWP-1B | Process Plant | ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-003
cl:4941b796-b809-4e6d-bbb0-cdb857d5144e | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-004 | Clear & Grub | GC1.1 - Underlying lot & ITP signed off and conforming | Not started |  | ITP-001 Clear & Grub | AWP-1B | Process Plant | ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-004
cl:4941b796-b809-4e6d-bbb0-cdb857d5144e | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-004 | Clear & Grub | GC1.2 - Ground Disturbance Permit (GDP) | Not started | Open | ITP-001 Clear & Grub | AWP-1B | Process Plant | ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-004
cl:4941b796-b809-4e6d-bbb0-cdb857d5144e | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-004 | Clear & Grub | GC1.3 - Cultural Heritage(CH) Clearance Survey | Not started | Open | ITP-001 Clear & Grub | AWP-1B | Process Plant | ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-004
cl:4941b796-b809-4e6d-bbb0-cdb857d5144e | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-004 | Clear & Grub | GC1.4 - GDP survey set out | Not started | Open | ITP-001 Clear & Grub | AWP-1B | Process Plant | ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-004
cl:4941b796-b809-4e6d-bbb0-cdb857d5144e | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-004 | Clear & Grub | GC1.5 - Survey of pegs to confirm correct GDP survey set out | Not started | Open | ITP-001 Clear & Grub | AWP-1B | Process Plant | ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-004
cl:4941b796-b809-4e6d-bbb0-cdb857d5144e | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-004 | Clear & Grub | GC1.6 - Survey natural surface | Not started | Open | ITP-001 Clear & Grub | AWP-1B | Process Plant | ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-004
cl:4941b796-b809-4e6d-bbb0-cdb857d5144e | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-004 | Clear & Grub | GC1.7 - Fauna Spotter Catcher (FSC) Pre-Clearance Survey | Not started | Open | ITP-001 Clear & Grub | AWP-1B | Process Plant | ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-004
cl:4941b796-b809-4e6d-bbb0-cdb857d5144e | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-004 | Clear & Grub | GC1.8 - Mandatory GDP Pre-Clearing walk | Not started | Open | ITP-001 Clear & Grub | AWP-1B | Process Plant | ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-004
cl:4941b796-b809-4e6d-bbb0-cdb857d5144e | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-004 | Clear & Grub | GC1.9 - Clearing of vegetation | Not started | Open | ITP-001 Clear & Grub | AWP-1B | Process Plant | ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-004
cl:4941b796-b809-4e6d-bbb0-cdb857d5144e | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-004 | Clear & Grub | GC1.10 - Stockpile Cleared Vegetation | Not started | Open | ITP-001 Clear & Grub | AWP-1B | Process Plant | ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-004
cl:4941b796-b809-4e6d-bbb0-cdb857d5144e | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-004 | Clear & Grub | GC1.11 - Erosion and sediment control | Not started | Open | ITP-001 Clear & Grub | AWP-1B | Process Plant | ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-004
cl:4941b796-b809-4e6d-bbb0-cdb857d5144e | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-004 | Clear & Grub | GC1.12 - QA close out | Not started | Open | ITP-001 Clear & Grub | AWP-1B | Process Plant | ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-004
cl:e94c4960-c452-405f-956e-1f03cd758a70 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-005 | Clear & Grub | GC1.1 - Underlying lot & ITP signed off and conforming | Not started |  | ITP-001 Clear & Grub | AWP-1B | Process Plant | ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-005
cl:e94c4960-c452-405f-956e-1f03cd758a70 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-005 | Clear & Grub | GC1.2 - Ground Disturbance Permit (GDP) | Not started | Open | ITP-001 Clear & Grub | AWP-1B | Process Plant | ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-005
cl:e94c4960-c452-405f-956e-1f03cd758a70 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-005 | Clear & Grub | GC1.3 - Cultural Heritage(CH) Clearance Survey | Not started | Open | ITP-001 Clear & Grub | AWP-1B | Process Plant | ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-005
cl:e94c4960-c452-405f-956e-1f03cd758a70 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-005 | Clear & Grub | GC1.4 - GDP survey set out | Not started | Open | ITP-001 Clear & Grub | AWP-1B | Process Plant | ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-005
cl:e94c4960-c452-405f-956e-1f03cd758a70 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-005 | Clear & Grub | GC1.5 - Survey of pegs to confirm correct GDP survey set out | Not started | Open | ITP-001 Clear & Grub | AWP-1B | Process Plant | ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-005
cl:e94c4960-c452-405f-956e-1f03cd758a70 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-005 | Clear & Grub | GC1.6 - Survey natural surface | Not started | Open | ITP-001 Clear & Grub | AWP-1B | Process Plant | ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-005
cl:e94c4960-c452-405f-956e-1f03cd758a70 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-005 | Clear & Grub | GC1.7 - Fauna Spotter Catcher (FSC) Pre-Clearance Survey | Not started | Open | ITP-001 Clear & Grub | AWP-1B | Process Plant | ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-005
cl:e94c4960-c452-405f-956e-1f03cd758a70 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-005 | Clear & Grub | GC1.8 - Mandatory GDP Pre-Clearing walk | Not started | Open | ITP-001 Clear & Grub | AWP-1B | Process Plant | ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-005
cl:e94c4960-c452-405f-956e-1f03cd758a70 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-005 | Clear & Grub | GC1.9 - Clearing of vegetation | Not started | Open | ITP-001 Clear & Grub | AWP-1B | Process Plant | ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-005
cl:e94c4960-c452-405f-956e-1f03cd758a70 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-005 | Clear & Grub | GC1.10 - Stockpile Cleared Vegetation | Not started | Open | ITP-001 Clear & Grub | AWP-1B | Process Plant | ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-005
cl:e94c4960-c452-405f-956e-1f03cd758a70 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-005 | Clear & Grub | GC1.11 - Erosion and sediment control | Not started | Open | ITP-001 Clear & Grub | AWP-1B | Process Plant | ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-005
cl:e94c4960-c452-405f-956e-1f03cd758a70 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-005 | Clear & Grub | GC1.12 - QA close out | Not started | Open | ITP-001 Clear & Grub | AWP-1B | Process Plant | ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-005
cl:79d2a2d6-46cf-4299-9604-afcd416acd33 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-006 | Clear & Grub | GC1.1 - Underlying lot & ITP signed off and conforming | Not started |  | ITP-001 Clear & Grub | AWP-1B | Process Plant | ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-006
cl:79d2a2d6-46cf-4299-9604-afcd416acd33 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-006 | Clear & Grub | GC1.2 - Ground Disturbance Permit (GDP) | Not started | Open | ITP-001 Clear & Grub | AWP-1B | Process Plant | ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-006
cl:79d2a2d6-46cf-4299-9604-afcd416acd33 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-006 | Clear & Grub | GC1.3 - Cultural Heritage(CH) Clearance Survey | Not started | Open | ITP-001 Clear & Grub | AWP-1B | Process Plant | ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-006
cl:79d2a2d6-46cf-4299-9604-afcd416acd33 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-006 | Clear & Grub | GC1.4 - GDP survey set out | Not started | Open | ITP-001 Clear & Grub | AWP-1B | Process Plant | ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-006
cl:79d2a2d6-46cf-4299-9604-afcd416acd33 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-006 | Clear & Grub | GC1.5 - Survey of pegs to confirm correct GDP survey set out | Not started | Open | ITP-001 Clear & Grub | AWP-1B | Process Plant | ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-006
cl:79d2a2d6-46cf-4299-9604-afcd416acd33 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-006 | Clear & Grub | GC1.6 - Survey natural surface | Not started | Open | ITP-001 Clear & Grub | AWP-1B | Process Plant | ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-006
cl:79d2a2d6-46cf-4299-9604-afcd416acd33 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-006 | Clear & Grub | GC1.7 - Fauna Spotter Catcher (FSC) Pre-Clearance Survey | Not started | Open | ITP-001 Clear & Grub | AWP-1B | Process Plant | ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-006
cl:79d2a2d6-46cf-4299-9604-afcd416acd33 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-006 | Clear & Grub | GC1.8 - Mandatory GDP Pre-Clearing walk | Not started | Open | ITP-001 Clear & Grub | AWP-1B | Process Plant | ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-006
cl:79d2a2d6-46cf-4299-9604-afcd416acd33 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-006 | Clear & Grub | GC1.9 - Clearing of vegetation | Not started | Open | ITP-001 Clear & Grub | AWP-1B | Process Plant | ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-006
cl:79d2a2d6-46cf-4299-9604-afcd416acd33 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-006 | Clear & Grub | GC1.10 - Stockpile Cleared Vegetation | Not started | Open | ITP-001 Clear & Grub | AWP-1B | Process Plant | ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-006
cl:79d2a2d6-46cf-4299-9604-afcd416acd33 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-006 | Clear & Grub | GC1.11 - Erosion and sediment control | Not started | Open | ITP-001 Clear & Grub | AWP-1B | Process Plant | ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-006
cl:79d2a2d6-46cf-4299-9604-afcd416acd33 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-006 | Clear & Grub | GC1.12 - QA close out | Not started | Open | ITP-001 Clear & Grub | AWP-1B | Process Plant | ITP-001 Clear & Grub | ITP-001 Clear & Grub-PP-006
cl:87d789b1-653f-43e1-b6a0-1fc2c40e8973 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-PP-001 | Topsoil Stripping | TS1.1 - Underlying lot & ITP signed off and conforming | Not started |  | ITP-002 Topsoil Stripping | AWP-1B | Process Plant | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-PP-001
cl:87d789b1-653f-43e1-b6a0-1fc2c40e8973 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-PP-001 | Topsoil Stripping | TS1.2 - Survey Set out | Not started | Open | ITP-002 Topsoil Stripping | AWP-1B | Process Plant | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-PP-001
cl:87d789b1-653f-43e1-b6a0-1fc2c40e8973 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-PP-001 | Topsoil Stripping | TS1.3 - Strip topsoil, load & haul to approved stockpile location | Not started | Open | ITP-002 Topsoil Stripping | AWP-1B | Process Plant | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-PP-001
cl:87d789b1-653f-43e1-b6a0-1fc2c40e8973 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-PP-001 | Topsoil Stripping | TS1.4 - Topsoil location, destination and quantity catalogued. | Not started | Open | ITP-002 Topsoil Stripping | AWP-1B | Process Plant | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-PP-001
cl:87d789b1-653f-43e1-b6a0-1fc2c40e8973 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-PP-001 | Topsoil Stripping | TS1.5 - Surface level check and survey pick-up | Not started | Open | ITP-002 Topsoil Stripping | AWP-1B | Process Plant | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-PP-001
cl:87d789b1-653f-43e1-b6a0-1fc2c40e8973 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-PP-001 | Topsoil Stripping | TS1.6 - QA close out | Not started | Open | ITP-002 Topsoil Stripping | AWP-1B | Process Plant | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-PP-001
cl:112ff002-8ffb-443f-b91d-8cda3058e037 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-PP-002 | Topsoil Stripping | TS1.1 - Underlying lot & ITP signed off and conforming | Not started |  | ITP-002 Topsoil Stripping | AWP-1B | Process Plant | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-PP-002
cl:112ff002-8ffb-443f-b91d-8cda3058e037 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-PP-002 | Topsoil Stripping | TS1.2 - Survey Set out | Not started | Open | ITP-002 Topsoil Stripping | AWP-1B | Process Plant | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-PP-002
cl:112ff002-8ffb-443f-b91d-8cda3058e037 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-PP-002 | Topsoil Stripping | TS1.3 - Strip topsoil, load & haul to approved stockpile location | Not started | Open | ITP-002 Topsoil Stripping | AWP-1B | Process Plant | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-PP-002
cl:112ff002-8ffb-443f-b91d-8cda3058e037 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-PP-002 | Topsoil Stripping | TS1.4 - Topsoil location, destination and quantity catalogued. | Not started | Open | ITP-002 Topsoil Stripping | AWP-1B | Process Plant | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-PP-002
cl:112ff002-8ffb-443f-b91d-8cda3058e037 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-PP-002 | Topsoil Stripping | TS1.5 - Surface level check and survey pick-up | Not started | Open | ITP-002 Topsoil Stripping | AWP-1B | Process Plant | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-PP-002
cl:112ff002-8ffb-443f-b91d-8cda3058e037 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-PP-002 | Topsoil Stripping | TS1.6 - QA close out | Not started | Open | ITP-002 Topsoil Stripping | AWP-1B | Process Plant | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-PP-002
cl:d98da602-4a75-4ac3-9326-9818772e906c | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-PP-003 | Topsoil Stripping | TS1.1 - Underlying lot & ITP signed off and conforming | Not started |  | ITP-002 Topsoil Stripping | AWP-1B | Process Plant | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-PP-003
cl:d98da602-4a75-4ac3-9326-9818772e906c | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-PP-003 | Topsoil Stripping | TS1.2 - Survey Set out | Not started | Open | ITP-002 Topsoil Stripping | AWP-1B | Process Plant | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-PP-003
cl:d98da602-4a75-4ac3-9326-9818772e906c | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-PP-003 | Topsoil Stripping | TS1.3 - Strip topsoil, load & haul to approved stockpile location | Not started | Open | ITP-002 Topsoil Stripping | AWP-1B | Process Plant | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-PP-003
cl:d98da602-4a75-4ac3-9326-9818772e906c | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-PP-003 | Topsoil Stripping | TS1.4 - Topsoil location, destination and quantity catalogued. | Not started | Open | ITP-002 Topsoil Stripping | AWP-1B | Process Plant | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-PP-003
cl:d98da602-4a75-4ac3-9326-9818772e906c | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-PP-003 | Topsoil Stripping | TS1.5 - Surface level check and survey pick-up | Not started | Open | ITP-002 Topsoil Stripping | AWP-1B | Process Plant | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-PP-003
cl:d98da602-4a75-4ac3-9326-9818772e906c | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-PP-003 | Topsoil Stripping | TS1.6 - QA close out | Not started | Open | ITP-002 Topsoil Stripping | AWP-1B | Process Plant | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-PP-003
cl:ab80b72a-3510-4f6a-bca7-c488e1578588 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-PP-004 | Topsoil Stripping | TS1.1 - Underlying lot & ITP signed off and conforming | Not started |  | ITP-002 Topsoil Stripping | AWP-1B | Process Plant | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-PP-004
cl:ab80b72a-3510-4f6a-bca7-c488e1578588 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-PP-004 | Topsoil Stripping | TS1.2 - Survey Set out | Not started | Open | ITP-002 Topsoil Stripping | AWP-1B | Process Plant | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-PP-004
cl:ab80b72a-3510-4f6a-bca7-c488e1578588 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-PP-004 | Topsoil Stripping | TS1.3 - Strip topsoil, load & haul to approved stockpile location | Not started | Open | ITP-002 Topsoil Stripping | AWP-1B | Process Plant | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-PP-004
cl:ab80b72a-3510-4f6a-bca7-c488e1578588 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-PP-004 | Topsoil Stripping | TS1.4 - Topsoil location, destination and quantity catalogued. | Not started | Open | ITP-002 Topsoil Stripping | AWP-1B | Process Plant | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-PP-004
cl:ab80b72a-3510-4f6a-bca7-c488e1578588 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-PP-004 | Topsoil Stripping | TS1.5 - Surface level check and survey pick-up | Not started | Open | ITP-002 Topsoil Stripping | AWP-1B | Process Plant | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-PP-004
cl:ab80b72a-3510-4f6a-bca7-c488e1578588 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-PP-004 | Topsoil Stripping | TS1.6 - QA close out | Not started | Open | ITP-002 Topsoil Stripping | AWP-1B | Process Plant | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-PP-004
cl:b995c116-cc00-483d-a290-50f2c7deeb2c | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-PP-005 | Topsoil Stripping | TS1.1 - Underlying lot & ITP signed off and conforming | Not started |  | ITP-002 Topsoil Stripping | AWP-1B | Process Plant | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-PP-005
cl:b995c116-cc00-483d-a290-50f2c7deeb2c | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-PP-005 | Topsoil Stripping | TS1.2 - Survey Set out | Not started | Open | ITP-002 Topsoil Stripping | AWP-1B | Process Plant | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-PP-005
cl:b995c116-cc00-483d-a290-50f2c7deeb2c | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-PP-005 | Topsoil Stripping | TS1.3 - Strip topsoil, load & haul to approved stockpile location | Not started | Open | ITP-002 Topsoil Stripping | AWP-1B | Process Plant | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-PP-005
cl:b995c116-cc00-483d-a290-50f2c7deeb2c | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-PP-005 | Topsoil Stripping | TS1.4 - Topsoil location, destination and quantity catalogued. | Not started | Open | ITP-002 Topsoil Stripping | AWP-1B | Process Plant | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-PP-005
cl:b995c116-cc00-483d-a290-50f2c7deeb2c | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-PP-005 | Topsoil Stripping | TS1.5 - Surface level check and survey pick-up | Not started | Open | ITP-002 Topsoil Stripping | AWP-1B | Process Plant | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-PP-005
cl:b995c116-cc00-483d-a290-50f2c7deeb2c | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-PP-005 | Topsoil Stripping | TS1.6 - QA close out | Not started | Open | ITP-002 Topsoil Stripping | AWP-1B | Process Plant | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-PP-005
cl:bce65fde-c703-4ac8-9b3b-17e5b4eeb76a | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-PP-006 | Topsoil Stripping | TS1.1 - Underlying lot & ITP signed off and conforming | Not started |  | ITP-002 Topsoil Stripping | AWP-1B | Process Plant | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-PP-006
cl:bce65fde-c703-4ac8-9b3b-17e5b4eeb76a | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-PP-006 | Topsoil Stripping | TS1.2 - Survey Set out | Not started | Open | ITP-002 Topsoil Stripping | AWP-1B | Process Plant | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-PP-006
cl:bce65fde-c703-4ac8-9b3b-17e5b4eeb76a | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-PP-006 | Topsoil Stripping | TS1.3 - Strip topsoil, load & haul to approved stockpile location | Not started | Open | ITP-002 Topsoil Stripping | AWP-1B | Process Plant | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-PP-006
cl:bce65fde-c703-4ac8-9b3b-17e5b4eeb76a | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-PP-006 | Topsoil Stripping | TS1.4 - Topsoil location, destination and quantity catalogued. | Not started | Open | ITP-002 Topsoil Stripping | AWP-1B | Process Plant | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-PP-006
cl:bce65fde-c703-4ac8-9b3b-17e5b4eeb76a | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-PP-006 | Topsoil Stripping | TS1.5 - Surface level check and survey pick-up | Not started | Open | ITP-002 Topsoil Stripping | AWP-1B | Process Plant | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-PP-006
cl:bce65fde-c703-4ac8-9b3b-17e5b4eeb76a | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-PP-006 | Topsoil Stripping | TS1.6 - QA close out | Not started | Open | ITP-002 Topsoil Stripping | AWP-1B | Process Plant | ITP-002 Topsoil Stripping | ITP-002 Topsoil Stripping-PP-006
cl:7d2202b9-930d-41a4-a326-190917c09d4f | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-PP-001 | Subgrade/Foundation Preparation | SP.1.1 - Underlying lot & ITP signed off and conforming | Not started |  | ITP-003 Subgrade/Foundation Preparation | AWP-1B | Process Plant | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-PP-001
cl:7d2202b9-930d-41a4-a326-190917c09d4f | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-PP-001 | Subgrade/Foundation Preparation | SP.1.2 - Embankment fill material | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1B | Process Plant | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-PP-001
cl:7d2202b9-930d-41a4-a326-190917c09d4f | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-PP-001 | Subgrade/Foundation Preparation | SP.1.3 - Survey Set out | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1B | Process Plant | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-PP-001
cl:7d2202b9-930d-41a4-a326-190917c09d4f | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-PP-001 | Subgrade/Foundation Preparation | SP.1.4 - Removal and replacement of unsuitable material | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1B | Process Plant | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-PP-001
cl:7d2202b9-930d-41a4-a326-190917c09d4f | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-PP-001 | Subgrade/Foundation Preparation | SP.1.5 - Subgrade/Foundation preparation | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1B | Process Plant | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-PP-001
cl:7d2202b9-930d-41a4-a326-190917c09d4f | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-PP-001 | Subgrade/Foundation Preparation | SP.1.6 - Trim subgrade | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1B | Process Plant | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-PP-001
cl:7d2202b9-930d-41a4-a326-190917c09d4f | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-PP-001 | Subgrade/Foundation Preparation | SP.1.7 - Proof rolling | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1B | Process Plant | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-PP-001
cl:7d2202b9-930d-41a4-a326-190917c09d4f | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-PP-001 | Subgrade/Foundation Preparation | SP.1.8 - Surface level check and survey pick-up | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1B | Process Plant | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-PP-001
cl:7d2202b9-930d-41a4-a326-190917c09d4f | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-PP-001 | Subgrade/Foundation Preparation | SP.1.9 - QA close out | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1B | Process Plant | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-PP-001
cl:1d16e40f-dbc0-4e18-9127-6c88e225c757 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-PP-002 | Subgrade/Foundation Preparation | SP.1.1 - Underlying lot & ITP signed off and conforming | Not started |  | ITP-003 Subgrade/Foundation Preparation | AWP-1B | Process Plant | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-PP-002
cl:1d16e40f-dbc0-4e18-9127-6c88e225c757 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-PP-002 | Subgrade/Foundation Preparation | SP.1.2 - Embankment fill material | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1B | Process Plant | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-PP-002
cl:1d16e40f-dbc0-4e18-9127-6c88e225c757 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-PP-002 | Subgrade/Foundation Preparation | SP.1.3 - Survey Set out | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1B | Process Plant | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-PP-002
cl:1d16e40f-dbc0-4e18-9127-6c88e225c757 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-PP-002 | Subgrade/Foundation Preparation | SP.1.4 - Removal and replacement of unsuitable material | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1B | Process Plant | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-PP-002
cl:1d16e40f-dbc0-4e18-9127-6c88e225c757 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-PP-002 | Subgrade/Foundation Preparation | SP.1.5 - Subgrade/Foundation preparation | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1B | Process Plant | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-PP-002
cl:1d16e40f-dbc0-4e18-9127-6c88e225c757 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-PP-002 | Subgrade/Foundation Preparation | SP.1.6 - Trim subgrade | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1B | Process Plant | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-PP-002
cl:1d16e40f-dbc0-4e18-9127-6c88e225c757 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-PP-002 | Subgrade/Foundation Preparation | SP.1.7 - Proof rolling | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1B | Process Plant | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-PP-002
cl:1d16e40f-dbc0-4e18-9127-6c88e225c757 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-PP-002 | Subgrade/Foundation Preparation | SP.1.8 - Surface level check and survey pick-up | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1B | Process Plant | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-PP-002
cl:1d16e40f-dbc0-4e18-9127-6c88e225c757 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-PP-002 | Subgrade/Foundation Preparation | SP.1.9 - QA close out | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1B | Process Plant | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-PP-002
cl:8647b7b5-ffd1-4566-8a6d-f4ebbd94e6ac | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-PP-003 | Subgrade/Foundation Preparation | SP.1.1 - Underlying lot & ITP signed off and conforming | Not started |  | ITP-003 Subgrade/Foundation Preparation | AWP-1B | Process Plant | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-PP-003
cl:8647b7b5-ffd1-4566-8a6d-f4ebbd94e6ac | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-PP-003 | Subgrade/Foundation Preparation | SP.1.2 - Embankment fill material | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1B | Process Plant | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-PP-003
cl:8647b7b5-ffd1-4566-8a6d-f4ebbd94e6ac | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-PP-003 | Subgrade/Foundation Preparation | SP.1.3 - Survey Set out | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1B | Process Plant | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-PP-003
cl:8647b7b5-ffd1-4566-8a6d-f4ebbd94e6ac | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-PP-003 | Subgrade/Foundation Preparation | SP.1.4 - Removal and replacement of unsuitable material | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1B | Process Plant | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-PP-003
cl:8647b7b5-ffd1-4566-8a6d-f4ebbd94e6ac | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-PP-003 | Subgrade/Foundation Preparation | SP.1.5 - Subgrade/Foundation preparation | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1B | Process Plant | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-PP-003
cl:8647b7b5-ffd1-4566-8a6d-f4ebbd94e6ac | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-PP-003 | Subgrade/Foundation Preparation | SP.1.6 - Trim subgrade | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1B | Process Plant | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-PP-003
cl:8647b7b5-ffd1-4566-8a6d-f4ebbd94e6ac | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-PP-003 | Subgrade/Foundation Preparation | SP.1.7 - Proof rolling | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1B | Process Plant | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-PP-003
cl:8647b7b5-ffd1-4566-8a6d-f4ebbd94e6ac | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-PP-003 | Subgrade/Foundation Preparation | SP.1.8 - Surface level check and survey pick-up | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1B | Process Plant | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-PP-003
cl:8647b7b5-ffd1-4566-8a6d-f4ebbd94e6ac | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-PP-003 | Subgrade/Foundation Preparation | SP.1.9 - QA close out | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1B | Process Plant | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-PP-003
cl:559c6287-adee-4dfa-8ec7-b979dad2fb7c | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-PP-004 | Subgrade/Foundation Preparation | SP.1.1 - Underlying lot & ITP signed off and conforming | Not started |  | ITP-003 Subgrade/Foundation Preparation | AWP-1B | Process Plant | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-PP-004
cl:559c6287-adee-4dfa-8ec7-b979dad2fb7c | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-PP-004 | Subgrade/Foundation Preparation | SP.1.2 - Embankment fill material | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1B | Process Plant | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-PP-004
cl:559c6287-adee-4dfa-8ec7-b979dad2fb7c | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-PP-004 | Subgrade/Foundation Preparation | SP.1.3 - Survey Set out | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1B | Process Plant | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-PP-004
cl:559c6287-adee-4dfa-8ec7-b979dad2fb7c | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-PP-004 | Subgrade/Foundation Preparation | SP.1.4 - Removal and replacement of unsuitable material | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1B | Process Plant | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-PP-004
cl:559c6287-adee-4dfa-8ec7-b979dad2fb7c | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-PP-004 | Subgrade/Foundation Preparation | SP.1.5 - Subgrade/Foundation preparation | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1B | Process Plant | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-PP-004
cl:559c6287-adee-4dfa-8ec7-b979dad2fb7c | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-PP-004 | Subgrade/Foundation Preparation | SP.1.6 - Trim subgrade | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1B | Process Plant | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-PP-004
cl:559c6287-adee-4dfa-8ec7-b979dad2fb7c | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-PP-004 | Subgrade/Foundation Preparation | SP.1.7 - Proof rolling | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1B | Process Plant | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-PP-004
cl:559c6287-adee-4dfa-8ec7-b979dad2fb7c | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-PP-004 | Subgrade/Foundation Preparation | SP.1.8 - Surface level check and survey pick-up | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1B | Process Plant | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-PP-004
cl:559c6287-adee-4dfa-8ec7-b979dad2fb7c | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-PP-004 | Subgrade/Foundation Preparation | SP.1.9 - QA close out | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1B | Process Plant | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-PP-004
cl:0065894c-41ff-4c17-8285-413a35f383ae | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-PP-005 | Subgrade/Foundation Preparation | SP.1.1 - Underlying lot & ITP signed off and conforming | Not started |  | ITP-003 Subgrade/Foundation Preparation | AWP-1B | Process Plant | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-PP-005
cl:0065894c-41ff-4c17-8285-413a35f383ae | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-PP-005 | Subgrade/Foundation Preparation | SP.1.2 - Embankment fill material | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1B | Process Plant | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-PP-005
cl:0065894c-41ff-4c17-8285-413a35f383ae | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-PP-005 | Subgrade/Foundation Preparation | SP.1.3 - Survey Set out | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1B | Process Plant | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-PP-005
cl:0065894c-41ff-4c17-8285-413a35f383ae | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-PP-005 | Subgrade/Foundation Preparation | SP.1.4 - Removal and replacement of unsuitable material | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1B | Process Plant | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-PP-005
cl:0065894c-41ff-4c17-8285-413a35f383ae | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-PP-005 | Subgrade/Foundation Preparation | SP.1.5 - Subgrade/Foundation preparation | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1B | Process Plant | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-PP-005
cl:0065894c-41ff-4c17-8285-413a35f383ae | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-PP-005 | Subgrade/Foundation Preparation | SP.1.6 - Trim subgrade | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1B | Process Plant | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-PP-005
cl:0065894c-41ff-4c17-8285-413a35f383ae | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-PP-005 | Subgrade/Foundation Preparation | SP.1.7 - Proof rolling | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1B | Process Plant | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-PP-005
cl:0065894c-41ff-4c17-8285-413a35f383ae | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-PP-005 | Subgrade/Foundation Preparation | SP.1.8 - Surface level check and survey pick-up | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1B | Process Plant | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-PP-005
cl:0065894c-41ff-4c17-8285-413a35f383ae | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-PP-005 | Subgrade/Foundation Preparation | SP.1.9 - QA close out | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1B | Process Plant | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-PP-005
cl:cf3526a3-39c6-4ed8-b27a-160122a63181 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-PP-006 | Subgrade/Foundation Preparation | SP.1.1 - Underlying lot & ITP signed off and conforming | Not started |  | ITP-003 Subgrade/Foundation Preparation | AWP-1B | Process Plant | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-PP-006
cl:cf3526a3-39c6-4ed8-b27a-160122a63181 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-PP-006 | Subgrade/Foundation Preparation | SP.1.2 - Embankment fill material | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1B | Process Plant | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-PP-006
cl:cf3526a3-39c6-4ed8-b27a-160122a63181 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-PP-006 | Subgrade/Foundation Preparation | SP.1.3 - Survey Set out | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1B | Process Plant | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-PP-006
cl:cf3526a3-39c6-4ed8-b27a-160122a63181 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-PP-006 | Subgrade/Foundation Preparation | SP.1.4 - Removal and replacement of unsuitable material | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1B | Process Plant | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-PP-006
cl:cf3526a3-39c6-4ed8-b27a-160122a63181 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-PP-006 | Subgrade/Foundation Preparation | SP.1.5 - Subgrade/Foundation preparation | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1B | Process Plant | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-PP-006
cl:cf3526a3-39c6-4ed8-b27a-160122a63181 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-PP-006 | Subgrade/Foundation Preparation | SP.1.6 - Trim subgrade | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1B | Process Plant | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-PP-006
cl:cf3526a3-39c6-4ed8-b27a-160122a63181 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-PP-006 | Subgrade/Foundation Preparation | SP.1.7 - Proof rolling | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1B | Process Plant | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-PP-006
cl:cf3526a3-39c6-4ed8-b27a-160122a63181 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-PP-006 | Subgrade/Foundation Preparation | SP.1.8 - Surface level check and survey pick-up | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1B | Process Plant | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-PP-006
cl:cf3526a3-39c6-4ed8-b27a-160122a63181 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-PP-006 | Subgrade/Foundation Preparation | SP.1.9 - QA close out | Not started | Open | ITP-003 Subgrade/Foundation Preparation | AWP-1B | Process Plant | ITP-003 Subgrade/Foundation Preparation | ITP-003 Subgrade/Foundation Preparation-PP-006
cl:327686f6-4cfc-42c5-bb1a-33d56d1d6b82 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-004 RCP Installation | ITP-004 RCP Installation-PP-001 | 1.0 Pre-Construction | RCP1.1 - Drawings supplied most current IFC | Not started | Open | ITP-004 RCP Installation | AWP-1B | Process Plant | ITP-004 RCP Installation | ITP-004 RCP Installation-PP-001
cl:327686f6-4cfc-42c5-bb1a-33d56d1d6b82 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-004 RCP Installation | ITP-004 RCP Installation-PP-001 | 1.0 Pre-Construction | RCP1.2 - Define RCP ID | Not started | Open | ITP-004 RCP Installation | AWP-1B | Process Plant | ITP-004 RCP Installation | ITP-004 RCP Installation-PP-001
cl:327686f6-4cfc-42c5-bb1a-33d56d1d6b82 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-004 RCP Installation | ITP-004 RCP Installation-PP-001 | 1.0 Pre-Construction | RCP1.3 - Lot Register/ WBS submitted and approved | Not started | Open | ITP-004 RCP Installation | AWP-1B | Process Plant | ITP-004 RCP Installation | ITP-004 RCP Installation-PP-001
cl:327686f6-4cfc-42c5-bb1a-33d56d1d6b82 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-004 RCP Installation | ITP-004 RCP Installation-PP-001 | 1.0 Pre-Construction | RCP1.4 - Underlying lot & ITP signed off and conforming | Not started | Open | ITP-004 RCP Installation | AWP-1B | Process Plant | ITP-004 RCP Installation | ITP-004 RCP Installation-PP-001
cl:327686f6-4cfc-42c5-bb1a-33d56d1d6b82 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-004 RCP Installation | ITP-004 RCP Installation-PP-001 | 1.0 Pre-Construction | RCP1.5 - Certificate of compliance for RCP Material | Not started | Open | ITP-004 RCP Installation | AWP-1B | Process Plant | ITP-004 RCP Installation | ITP-004 RCP Installation-PP-001
cl:327686f6-4cfc-42c5-bb1a-33d56d1d6b82 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-004 RCP Installation | ITP-004 RCP Installation-PP-001 | 1.0 Pre-Construction | RCP1.6 - Inspect reinforced pipe culverts for damage | Not started | Open | ITP-004 RCP Installation | AWP-1B | Process Plant | ITP-004 RCP Installation | ITP-004 RCP Installation-PP-001
cl:327686f6-4cfc-42c5-bb1a-33d56d1d6b82 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-004 RCP Installation | ITP-004 RCP Installation-PP-001 | 2.0 Construction | RCP2.7 - Trench Excavation | Not started | Open | ITP-004 RCP Installation | AWP-1B | Process Plant | ITP-004 RCP Installation | ITP-004 RCP Installation-PP-001
cl:327686f6-4cfc-42c5-bb1a-33d56d1d6b82 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-004 RCP Installation | ITP-004 RCP Installation-PP-001 | 2.0 Construction | RCP2.8 - Bedding | Not started | Open | ITP-004 RCP Installation | AWP-1B | Process Plant | ITP-004 RCP Installation | ITP-004 RCP Installation-PP-001
cl:327686f6-4cfc-42c5-bb1a-33d56d1d6b82 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-004 RCP Installation | ITP-004 RCP Installation-PP-001 | 2.0 Construction | RCP2.9 - RCP Installation | Not started | Open | ITP-004 RCP Installation | AWP-1B | Process Plant | ITP-004 RCP Installation | ITP-004 RCP Installation-PP-001
cl:327686f6-4cfc-42c5-bb1a-33d56d1d6b82 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-004 RCP Installation | ITP-004 RCP Installation-PP-001 | 2.0 Construction | RCP2.10 - Backfilling of culvert | Not started | Open | ITP-004 RCP Installation | AWP-1B | Process Plant | ITP-004 RCP Installation | ITP-004 RCP Installation-PP-001
cl:327686f6-4cfc-42c5-bb1a-33d56d1d6b82 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-004 RCP Installation | ITP-004 RCP Installation-PP-001 | 2.0 Construction | RCP2.11 - End Treatment – Headwall & Wingwalls (Reinforcement) | Not started | Open | ITP-004 RCP Installation | AWP-1B | Process Plant | ITP-004 RCP Installation | ITP-004 RCP Installation-PP-001
cl:327686f6-4cfc-42c5-bb1a-33d56d1d6b82 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-004 RCP Installation | ITP-004 RCP Installation-PP-001 | 2.0 Construction | RCP2.12 - End Treatment – Headwall & Wingwalls (Formwork) | Not started | Open | ITP-004 RCP Installation | AWP-1B | Process Plant | ITP-004 RCP Installation | ITP-004 RCP Installation-PP-001
cl:327686f6-4cfc-42c5-bb1a-33d56d1d6b82 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-004 RCP Installation | ITP-004 RCP Installation-PP-001 | 2.0 Construction | RCP2.13 - End Treatment – Headwall & Wingwalls (Concrete) | Not started | Open | ITP-004 RCP Installation | AWP-1B | Process Plant | ITP-004 RCP Installation | ITP-004 RCP Installation-PP-001
cl:327686f6-4cfc-42c5-bb1a-33d56d1d6b82 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-004 RCP Installation | ITP-004 RCP Installation-PP-001 | 2.0 Construction | RCP2.14 - Rock Protection | Not started | Open | ITP-004 RCP Installation | AWP-1B | Process Plant | ITP-004 RCP Installation | ITP-004 RCP Installation-PP-001
cl:327686f6-4cfc-42c5-bb1a-33d56d1d6b82 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-004 RCP Installation | ITP-004 RCP Installation-PP-001 | 3.0 Post Construction | RCP3.15 - Works completed and update ITP/ Lot Register/ MDR and close out of GDP | Not started | Open | ITP-004 RCP Installation | AWP-1B | Process Plant | ITP-004 RCP Installation | ITP-004 RCP Installation-PP-001
cl:78c12252-ccdc-44f0-8ec8-a1e7a7add732 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-004 RCP Installation | ITP-004 RCP Installation-PP-002 | 1.0 Pre-Construction | RCP1.1 - Drawings supplied most current IFC | Not started | Open | ITP-004 RCP Installation | AWP-1B | Process Plant | ITP-004 RCP Installation | ITP-004 RCP Installation-PP-002
cl:78c12252-ccdc-44f0-8ec8-a1e7a7add732 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-004 RCP Installation | ITP-004 RCP Installation-PP-002 | 1.0 Pre-Construction | RCP1.2 - Define RCP ID | Not started | Open | ITP-004 RCP Installation | AWP-1B | Process Plant | ITP-004 RCP Installation | ITP-004 RCP Installation-PP-002
cl:78c12252-ccdc-44f0-8ec8-a1e7a7add732 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-004 RCP Installation | ITP-004 RCP Installation-PP-002 | 1.0 Pre-Construction | RCP1.3 - Lot Register/ WBS submitted and approved | Not started | Open | ITP-004 RCP Installation | AWP-1B | Process Plant | ITP-004 RCP Installation | ITP-004 RCP Installation-PP-002
cl:78c12252-ccdc-44f0-8ec8-a1e7a7add732 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-004 RCP Installation | ITP-004 RCP Installation-PP-002 | 1.0 Pre-Construction | RCP1.4 - Underlying lot & ITP signed off and conforming | Not started | Open | ITP-004 RCP Installation | AWP-1B | Process Plant | ITP-004 RCP Installation | ITP-004 RCP Installation-PP-002
cl:78c12252-ccdc-44f0-8ec8-a1e7a7add732 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-004 RCP Installation | ITP-004 RCP Installation-PP-002 | 1.0 Pre-Construction | RCP1.5 - Certificate of compliance for RCP Material | Not started | Open | ITP-004 RCP Installation | AWP-1B | Process Plant | ITP-004 RCP Installation | ITP-004 RCP Installation-PP-002
cl:78c12252-ccdc-44f0-8ec8-a1e7a7add732 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-004 RCP Installation | ITP-004 RCP Installation-PP-002 | 1.0 Pre-Construction | RCP1.6 - Inspect reinforced pipe culverts for damage | Not started | Open | ITP-004 RCP Installation | AWP-1B | Process Plant | ITP-004 RCP Installation | ITP-004 RCP Installation-PP-002
cl:78c12252-ccdc-44f0-8ec8-a1e7a7add732 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-004 RCP Installation | ITP-004 RCP Installation-PP-002 | 2.0 Construction | RCP2.7 - Trench Excavation | Not started | Open | ITP-004 RCP Installation | AWP-1B | Process Plant | ITP-004 RCP Installation | ITP-004 RCP Installation-PP-002
cl:78c12252-ccdc-44f0-8ec8-a1e7a7add732 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-004 RCP Installation | ITP-004 RCP Installation-PP-002 | 2.0 Construction | RCP2.8 - Bedding | Not started | Open | ITP-004 RCP Installation | AWP-1B | Process Plant | ITP-004 RCP Installation | ITP-004 RCP Installation-PP-002
cl:78c12252-ccdc-44f0-8ec8-a1e7a7add732 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-004 RCP Installation | ITP-004 RCP Installation-PP-002 | 2.0 Construction | RCP2.9 - RCP Installation | Not started | Open | ITP-004 RCP Installation | AWP-1B | Process Plant | ITP-004 RCP Installation | ITP-004 RCP Installation-PP-002
cl:78c12252-ccdc-44f0-8ec8-a1e7a7add732 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-004 RCP Installation | ITP-004 RCP Installation-PP-002 | 2.0 Construction | RCP2.10 - Backfilling of culvert | Not started | Open | ITP-004 RCP Installation | AWP-1B | Process Plant | ITP-004 RCP Installation | ITP-004 RCP Installation-PP-002
cl:78c12252-ccdc-44f0-8ec8-a1e7a7add732 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-004 RCP Installation | ITP-004 RCP Installation-PP-002 | 2.0 Construction | RCP2.11 - End Treatment – Headwall & Wingwalls (Reinforcement) | Not started | Open | ITP-004 RCP Installation | AWP-1B | Process Plant | ITP-004 RCP Installation | ITP-004 RCP Installation-PP-002
cl:78c12252-ccdc-44f0-8ec8-a1e7a7add732 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-004 RCP Installation | ITP-004 RCP Installation-PP-002 | 2.0 Construction | RCP2.12 - End Treatment – Headwall & Wingwalls (Formwork) | Not started | Open | ITP-004 RCP Installation | AWP-1B | Process Plant | ITP-004 RCP Installation | ITP-004 RCP Installation-PP-002
cl:78c12252-ccdc-44f0-8ec8-a1e7a7add732 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-004 RCP Installation | ITP-004 RCP Installation-PP-002 | 2.0 Construction | RCP2.13 - End Treatment – Headwall & Wingwalls (Concrete) | Not started | Open | ITP-004 RCP Installation | AWP-1B | Process Plant | ITP-004 RCP Installation | ITP-004 RCP Installation-PP-002
cl:78c12252-ccdc-44f0-8ec8-a1e7a7add732 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-004 RCP Installation | ITP-004 RCP Installation-PP-002 | 2.0 Construction | RCP2.14 - Rock Protection | Not started | Open | ITP-004 RCP Installation | AWP-1B | Process Plant | ITP-004 RCP Installation | ITP-004 RCP Installation-PP-002
cl:78c12252-ccdc-44f0-8ec8-a1e7a7add732 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-004 RCP Installation | ITP-004 RCP Installation-PP-002 | 3.0 Post Construction | RCP3.15 - Works completed and update ITP/ Lot Register/ MDR and close out of GDP | Not started | Open | ITP-004 RCP Installation | AWP-1B | Process Plant | ITP-004 RCP Installation | ITP-004 RCP Installation-PP-002
cl:ea5712bd-2726-4f90-aef1-88828567cfab | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-004 RCP Installation | ITP-004 RCP Installation-PP-003 | 1.0 Pre-Construction | RCP1.1 - Drawings supplied most current IFC | Not started | Open | ITP-004 RCP Installation | AWP-1B | Process Plant | ITP-004 RCP Installation | ITP-004 RCP Installation-PP-003
cl:ea5712bd-2726-4f90-aef1-88828567cfab | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-004 RCP Installation | ITP-004 RCP Installation-PP-003 | 1.0 Pre-Construction | RCP1.2 - Define RCP ID | Not started | Open | ITP-004 RCP Installation | AWP-1B | Process Plant | ITP-004 RCP Installation | ITP-004 RCP Installation-PP-003
cl:ea5712bd-2726-4f90-aef1-88828567cfab | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-004 RCP Installation | ITP-004 RCP Installation-PP-003 | 1.0 Pre-Construction | RCP1.3 - Lot Register/ WBS submitted and approved | Not started | Open | ITP-004 RCP Installation | AWP-1B | Process Plant | ITP-004 RCP Installation | ITP-004 RCP Installation-PP-003
cl:ea5712bd-2726-4f90-aef1-88828567cfab | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-004 RCP Installation | ITP-004 RCP Installation-PP-003 | 1.0 Pre-Construction | RCP1.4 - Underlying lot & ITP signed off and conforming | Not started | Open | ITP-004 RCP Installation | AWP-1B | Process Plant | ITP-004 RCP Installation | ITP-004 RCP Installation-PP-003
cl:ea5712bd-2726-4f90-aef1-88828567cfab | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-004 RCP Installation | ITP-004 RCP Installation-PP-003 | 1.0 Pre-Construction | RCP1.5 - Certificate of compliance for RCP Material | Not started | Open | ITP-004 RCP Installation | AWP-1B | Process Plant | ITP-004 RCP Installation | ITP-004 RCP Installation-PP-003
cl:ea5712bd-2726-4f90-aef1-88828567cfab | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-004 RCP Installation | ITP-004 RCP Installation-PP-003 | 1.0 Pre-Construction | RCP1.6 - Inspect reinforced pipe culverts for damage | Not started | Open | ITP-004 RCP Installation | AWP-1B | Process Plant | ITP-004 RCP Installation | ITP-004 RCP Installation-PP-003
cl:ea5712bd-2726-4f90-aef1-88828567cfab | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-004 RCP Installation | ITP-004 RCP Installation-PP-003 | 2.0 Construction | RCP2.7 - Trench Excavation | Not started | Open | ITP-004 RCP Installation | AWP-1B | Process Plant | ITP-004 RCP Installation | ITP-004 RCP Installation-PP-003
cl:ea5712bd-2726-4f90-aef1-88828567cfab | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-004 RCP Installation | ITP-004 RCP Installation-PP-003 | 2.0 Construction | RCP2.8 - Bedding | Not started | Open | ITP-004 RCP Installation | AWP-1B | Process Plant | ITP-004 RCP Installation | ITP-004 RCP Installation-PP-003
cl:ea5712bd-2726-4f90-aef1-88828567cfab | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-004 RCP Installation | ITP-004 RCP Installation-PP-003 | 2.0 Construction | RCP2.9 - RCP Installation | Not started | Open | ITP-004 RCP Installation | AWP-1B | Process Plant | ITP-004 RCP Installation | ITP-004 RCP Installation-PP-003
cl:ea5712bd-2726-4f90-aef1-88828567cfab | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-004 RCP Installation | ITP-004 RCP Installation-PP-003 | 2.0 Construction | RCP2.10 - Backfilling of culvert | Not started | Open | ITP-004 RCP Installation | AWP-1B | Process Plant | ITP-004 RCP Installation | ITP-004 RCP Installation-PP-003
cl:ea5712bd-2726-4f90-aef1-88828567cfab | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-004 RCP Installation | ITP-004 RCP Installation-PP-003 | 2.0 Construction | RCP2.11 - End Treatment – Headwall & Wingwalls (Reinforcement) | Not started | Open | ITP-004 RCP Installation | AWP-1B | Process Plant | ITP-004 RCP Installation | ITP-004 RCP Installation-PP-003
cl:ea5712bd-2726-4f90-aef1-88828567cfab | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-004 RCP Installation | ITP-004 RCP Installation-PP-003 | 2.0 Construction | RCP2.12 - End Treatment – Headwall & Wingwalls (Formwork) | Not started | Open | ITP-004 RCP Installation | AWP-1B | Process Plant | ITP-004 RCP Installation | ITP-004 RCP Installation-PP-003
cl:ea5712bd-2726-4f90-aef1-88828567cfab | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-004 RCP Installation | ITP-004 RCP Installation-PP-003 | 2.0 Construction | RCP2.13 - End Treatment – Headwall & Wingwalls (Concrete) | Not started | Open | ITP-004 RCP Installation | AWP-1B | Process Plant | ITP-004 RCP Installation | ITP-004 RCP Installation-PP-003
cl:ea5712bd-2726-4f90-aef1-88828567cfab | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-004 RCP Installation | ITP-004 RCP Installation-PP-003 | 2.0 Construction | RCP2.14 - Rock Protection | Not started | Open | ITP-004 RCP Installation | AWP-1B | Process Plant | ITP-004 RCP Installation | ITP-004 RCP Installation-PP-003
cl:ea5712bd-2726-4f90-aef1-88828567cfab | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-004 RCP Installation | ITP-004 RCP Installation-PP-003 | 3.0 Post Construction | RCP3.15 - Works completed and update ITP/ Lot Register/ MDR and close out of GDP | Not started | Open | ITP-004 RCP Installation | AWP-1B | Process Plant | ITP-004 RCP Installation | ITP-004 RCP Installation-PP-003
cl:b3da67de-d5f8-4307-9505-6854525fd8b5 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-004 RCP Installation | ITP-004 RCP Installation-PP-004 | 1.0 Pre-Construction | RCP1.1 - Drawings supplied most current IFC | Not started | Open | ITP-004 RCP Installation | AWP-1B | Process Plant | ITP-004 RCP Installation | ITP-004 RCP Installation-PP-004
cl:b3da67de-d5f8-4307-9505-6854525fd8b5 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-004 RCP Installation | ITP-004 RCP Installation-PP-004 | 1.0 Pre-Construction | RCP1.2 - Define RCP ID | Not started | Open | ITP-004 RCP Installation | AWP-1B | Process Plant | ITP-004 RCP Installation | ITP-004 RCP Installation-PP-004
cl:b3da67de-d5f8-4307-9505-6854525fd8b5 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-004 RCP Installation | ITP-004 RCP Installation-PP-004 | 1.0 Pre-Construction | RCP1.3 - Lot Register/ WBS submitted and approved | Not started | Open | ITP-004 RCP Installation | AWP-1B | Process Plant | ITP-004 RCP Installation | ITP-004 RCP Installation-PP-004
cl:b3da67de-d5f8-4307-9505-6854525fd8b5 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-004 RCP Installation | ITP-004 RCP Installation-PP-004 | 1.0 Pre-Construction | RCP1.4 - Underlying lot & ITP signed off and conforming | Not started | Open | ITP-004 RCP Installation | AWP-1B | Process Plant | ITP-004 RCP Installation | ITP-004 RCP Installation-PP-004
cl:b3da67de-d5f8-4307-9505-6854525fd8b5 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-004 RCP Installation | ITP-004 RCP Installation-PP-004 | 1.0 Pre-Construction | RCP1.5 - Certificate of compliance for RCP Material | Not started | Open | ITP-004 RCP Installation | AWP-1B | Process Plant | ITP-004 RCP Installation | ITP-004 RCP Installation-PP-004
cl:b3da67de-d5f8-4307-9505-6854525fd8b5 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-004 RCP Installation | ITP-004 RCP Installation-PP-004 | 1.0 Pre-Construction | RCP1.6 - Inspect reinforced pipe culverts for damage | Not started | Open | ITP-004 RCP Installation | AWP-1B | Process Plant | ITP-004 RCP Installation | ITP-004 RCP Installation-PP-004
cl:b3da67de-d5f8-4307-9505-6854525fd8b5 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-004 RCP Installation | ITP-004 RCP Installation-PP-004 | 2.0 Construction | RCP2.7 - Trench Excavation | Not started | Open | ITP-004 RCP Installation | AWP-1B | Process Plant | ITP-004 RCP Installation | ITP-004 RCP Installation-PP-004
cl:b3da67de-d5f8-4307-9505-6854525fd8b5 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-004 RCP Installation | ITP-004 RCP Installation-PP-004 | 2.0 Construction | RCP2.8 - Bedding | Not started | Open | ITP-004 RCP Installation | AWP-1B | Process Plant | ITP-004 RCP Installation | ITP-004 RCP Installation-PP-004
cl:b3da67de-d5f8-4307-9505-6854525fd8b5 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-004 RCP Installation | ITP-004 RCP Installation-PP-004 | 2.0 Construction | RCP2.9 - RCP Installation | Not started | Open | ITP-004 RCP Installation | AWP-1B | Process Plant | ITP-004 RCP Installation | ITP-004 RCP Installation-PP-004
cl:b3da67de-d5f8-4307-9505-6854525fd8b5 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-004 RCP Installation | ITP-004 RCP Installation-PP-004 | 2.0 Construction | RCP2.10 - Backfilling of culvert | Not started | Open | ITP-004 RCP Installation | AWP-1B | Process Plant | ITP-004 RCP Installation | ITP-004 RCP Installation-PP-004
cl:b3da67de-d5f8-4307-9505-6854525fd8b5 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-004 RCP Installation | ITP-004 RCP Installation-PP-004 | 2.0 Construction | RCP2.11 - End Treatment – Headwall & Wingwalls (Reinforcement) | Not started | Open | ITP-004 RCP Installation | AWP-1B | Process Plant | ITP-004 RCP Installation | ITP-004 RCP Installation-PP-004
cl:b3da67de-d5f8-4307-9505-6854525fd8b5 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-004 RCP Installation | ITP-004 RCP Installation-PP-004 | 2.0 Construction | RCP2.12 - End Treatment – Headwall & Wingwalls (Formwork) | Not started | Open | ITP-004 RCP Installation | AWP-1B | Process Plant | ITP-004 RCP Installation | ITP-004 RCP Installation-PP-004
cl:b3da67de-d5f8-4307-9505-6854525fd8b5 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-004 RCP Installation | ITP-004 RCP Installation-PP-004 | 2.0 Construction | RCP2.13 - End Treatment – Headwall & Wingwalls (Concrete) | Not started | Open | ITP-004 RCP Installation | AWP-1B | Process Plant | ITP-004 RCP Installation | ITP-004 RCP Installation-PP-004
cl:b3da67de-d5f8-4307-9505-6854525fd8b5 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-004 RCP Installation | ITP-004 RCP Installation-PP-004 | 2.0 Construction | RCP2.14 - Rock Protection | Not started | Open | ITP-004 RCP Installation | AWP-1B | Process Plant | ITP-004 RCP Installation | ITP-004 RCP Installation-PP-004
cl:b3da67de-d5f8-4307-9505-6854525fd8b5 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-004 RCP Installation | ITP-004 RCP Installation-PP-004 | 3.0 Post Construction | RCP3.15 - Works completed and update ITP/ Lot Register/ MDR and close out of GDP | Not started | Open | ITP-004 RCP Installation | AWP-1B | Process Plant | ITP-004 RCP Installation | ITP-004 RCP Installation-PP-004
cl:716ed9c9-4c7b-482b-a67d-0b6da1f448f3 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-004 RCP Installation | ITP-004 RCP Installation-PP-005 | 1.0 Pre-Construction | RCP1.1 - Drawings supplied most current IFC | Not started | Open | ITP-004 RCP Installation | AWP-1B | Process Plant | ITP-004 RCP Installation | ITP-004 RCP Installation-PP-005
cl:716ed9c9-4c7b-482b-a67d-0b6da1f448f3 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-004 RCP Installation | ITP-004 RCP Installation-PP-005 | 1.0 Pre-Construction | RCP1.2 - Define RCP ID | Not started | Open | ITP-004 RCP Installation | AWP-1B | Process Plant | ITP-004 RCP Installation | ITP-004 RCP Installation-PP-005
cl:716ed9c9-4c7b-482b-a67d-0b6da1f448f3 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-004 RCP Installation | ITP-004 RCP Installation-PP-005 | 1.0 Pre-Construction | RCP1.3 - Lot Register/ WBS submitted and approved | Not started | Open | ITP-004 RCP Installation | AWP-1B | Process Plant | ITP-004 RCP Installation | ITP-004 RCP Installation-PP-005
cl:716ed9c9-4c7b-482b-a67d-0b6da1f448f3 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-004 RCP Installation | ITP-004 RCP Installation-PP-005 | 1.0 Pre-Construction | RCP1.4 - Underlying lot & ITP signed off and conforming | Not started | Open | ITP-004 RCP Installation | AWP-1B | Process Plant | ITP-004 RCP Installation | ITP-004 RCP Installation-PP-005
cl:716ed9c9-4c7b-482b-a67d-0b6da1f448f3 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-004 RCP Installation | ITP-004 RCP Installation-PP-005 | 1.0 Pre-Construction | RCP1.5 - Certificate of compliance for RCP Material | Not started | Open | ITP-004 RCP Installation | AWP-1B | Process Plant | ITP-004 RCP Installation | ITP-004 RCP Installation-PP-005
cl:716ed9c9-4c7b-482b-a67d-0b6da1f448f3 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-004 RCP Installation | ITP-004 RCP Installation-PP-005 | 1.0 Pre-Construction | RCP1.6 - Inspect reinforced pipe culverts for damage | Not started | Open | ITP-004 RCP Installation | AWP-1B | Process Plant | ITP-004 RCP Installation | ITP-004 RCP Installation-PP-005
cl:716ed9c9-4c7b-482b-a67d-0b6da1f448f3 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-004 RCP Installation | ITP-004 RCP Installation-PP-005 | 2.0 Construction | RCP2.7 - Trench Excavation | Not started | Open | ITP-004 RCP Installation | AWP-1B | Process Plant | ITP-004 RCP Installation | ITP-004 RCP Installation-PP-005
cl:716ed9c9-4c7b-482b-a67d-0b6da1f448f3 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-004 RCP Installation | ITP-004 RCP Installation-PP-005 | 2.0 Construction | RCP2.8 - Bedding | Not started | Open | ITP-004 RCP Installation | AWP-1B | Process Plant | ITP-004 RCP Installation | ITP-004 RCP Installation-PP-005
cl:716ed9c9-4c7b-482b-a67d-0b6da1f448f3 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-004 RCP Installation | ITP-004 RCP Installation-PP-005 | 2.0 Construction | RCP2.9 - RCP Installation | Not started | Open | ITP-004 RCP Installation | AWP-1B | Process Plant | ITP-004 RCP Installation | ITP-004 RCP Installation-PP-005
cl:716ed9c9-4c7b-482b-a67d-0b6da1f448f3 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-004 RCP Installation | ITP-004 RCP Installation-PP-005 | 2.0 Construction | RCP2.10 - Backfilling of culvert | Not started | Open | ITP-004 RCP Installation | AWP-1B | Process Plant | ITP-004 RCP Installation | ITP-004 RCP Installation-PP-005
cl:716ed9c9-4c7b-482b-a67d-0b6da1f448f3 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-004 RCP Installation | ITP-004 RCP Installation-PP-005 | 2.0 Construction | RCP2.11 - End Treatment – Headwall & Wingwalls (Reinforcement) | Not started | Open | ITP-004 RCP Installation | AWP-1B | Process Plant | ITP-004 RCP Installation | ITP-004 RCP Installation-PP-005
cl:716ed9c9-4c7b-482b-a67d-0b6da1f448f3 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-004 RCP Installation | ITP-004 RCP Installation-PP-005 | 2.0 Construction | RCP2.12 - End Treatment – Headwall & Wingwalls (Formwork) | Not started | Open | ITP-004 RCP Installation | AWP-1B | Process Plant | ITP-004 RCP Installation | ITP-004 RCP Installation-PP-005
cl:716ed9c9-4c7b-482b-a67d-0b6da1f448f3 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-004 RCP Installation | ITP-004 RCP Installation-PP-005 | 2.0 Construction | RCP2.13 - End Treatment – Headwall & Wingwalls (Concrete) | Not started | Open | ITP-004 RCP Installation | AWP-1B | Process Plant | ITP-004 RCP Installation | ITP-004 RCP Installation-PP-005
cl:716ed9c9-4c7b-482b-a67d-0b6da1f448f3 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-004 RCP Installation | ITP-004 RCP Installation-PP-005 | 2.0 Construction | RCP2.14 - Rock Protection | Not started | Open | ITP-004 RCP Installation | AWP-1B | Process Plant | ITP-004 RCP Installation | ITP-004 RCP Installation-PP-005
cl:716ed9c9-4c7b-482b-a67d-0b6da1f448f3 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-004 RCP Installation | ITP-004 RCP Installation-PP-005 | 3.0 Post Construction | RCP3.15 - Works completed and update ITP/ Lot Register/ MDR and close out of GDP | Not started | Open | ITP-004 RCP Installation | AWP-1B | Process Plant | ITP-004 RCP Installation | ITP-004 RCP Installation-PP-005
cl:0ec6dbf8-4c10-4c45-998d-72abcbf29ad6 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-004 RCP Installation | ITP-004 RCP Installation-PP-006 | 1.0 Pre-Construction | RCP1.1 - Drawings supplied most current IFC | Not started | Open | ITP-004 RCP Installation | AWP-1B | Process Plant | ITP-004 RCP Installation | ITP-004 RCP Installation-PP-006
cl:0ec6dbf8-4c10-4c45-998d-72abcbf29ad6 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-004 RCP Installation | ITP-004 RCP Installation-PP-006 | 1.0 Pre-Construction | RCP1.2 - Define RCP ID | Not started | Open | ITP-004 RCP Installation | AWP-1B | Process Plant | ITP-004 RCP Installation | ITP-004 RCP Installation-PP-006
cl:0ec6dbf8-4c10-4c45-998d-72abcbf29ad6 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-004 RCP Installation | ITP-004 RCP Installation-PP-006 | 1.0 Pre-Construction | RCP1.3 - Lot Register/ WBS submitted and approved | Not started | Open | ITP-004 RCP Installation | AWP-1B | Process Plant | ITP-004 RCP Installation | ITP-004 RCP Installation-PP-006
cl:0ec6dbf8-4c10-4c45-998d-72abcbf29ad6 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-004 RCP Installation | ITP-004 RCP Installation-PP-006 | 1.0 Pre-Construction | RCP1.4 - Underlying lot & ITP signed off and conforming | Not started | Open | ITP-004 RCP Installation | AWP-1B | Process Plant | ITP-004 RCP Installation | ITP-004 RCP Installation-PP-006
cl:0ec6dbf8-4c10-4c45-998d-72abcbf29ad6 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-004 RCP Installation | ITP-004 RCP Installation-PP-006 | 1.0 Pre-Construction | RCP1.5 - Certificate of compliance for RCP Material | Not started | Open | ITP-004 RCP Installation | AWP-1B | Process Plant | ITP-004 RCP Installation | ITP-004 RCP Installation-PP-006
cl:0ec6dbf8-4c10-4c45-998d-72abcbf29ad6 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-004 RCP Installation | ITP-004 RCP Installation-PP-006 | 1.0 Pre-Construction | RCP1.6 - Inspect reinforced pipe culverts for damage | Not started | Open | ITP-004 RCP Installation | AWP-1B | Process Plant | ITP-004 RCP Installation | ITP-004 RCP Installation-PP-006
cl:0ec6dbf8-4c10-4c45-998d-72abcbf29ad6 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-004 RCP Installation | ITP-004 RCP Installation-PP-006 | 2.0 Construction | RCP2.7 - Trench Excavation | Not started | Open | ITP-004 RCP Installation | AWP-1B | Process Plant | ITP-004 RCP Installation | ITP-004 RCP Installation-PP-006
cl:0ec6dbf8-4c10-4c45-998d-72abcbf29ad6 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-004 RCP Installation | ITP-004 RCP Installation-PP-006 | 2.0 Construction | RCP2.8 - Bedding | Not started | Open | ITP-004 RCP Installation | AWP-1B | Process Plant | ITP-004 RCP Installation | ITP-004 RCP Installation-PP-006
cl:0ec6dbf8-4c10-4c45-998d-72abcbf29ad6 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-004 RCP Installation | ITP-004 RCP Installation-PP-006 | 2.0 Construction | RCP2.9 - RCP Installation | Not started | Open | ITP-004 RCP Installation | AWP-1B | Process Plant | ITP-004 RCP Installation | ITP-004 RCP Installation-PP-006
cl:0ec6dbf8-4c10-4c45-998d-72abcbf29ad6 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-004 RCP Installation | ITP-004 RCP Installation-PP-006 | 2.0 Construction | RCP2.10 - Backfilling of culvert | Not started | Open | ITP-004 RCP Installation | AWP-1B | Process Plant | ITP-004 RCP Installation | ITP-004 RCP Installation-PP-006
cl:0ec6dbf8-4c10-4c45-998d-72abcbf29ad6 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-004 RCP Installation | ITP-004 RCP Installation-PP-006 | 2.0 Construction | RCP2.11 - End Treatment – Headwall & Wingwalls (Reinforcement) | Not started | Open | ITP-004 RCP Installation | AWP-1B | Process Plant | ITP-004 RCP Installation | ITP-004 RCP Installation-PP-006
cl:0ec6dbf8-4c10-4c45-998d-72abcbf29ad6 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-004 RCP Installation | ITP-004 RCP Installation-PP-006 | 2.0 Construction | RCP2.12 - End Treatment – Headwall & Wingwalls (Formwork) | Not started | Open | ITP-004 RCP Installation | AWP-1B | Process Plant | ITP-004 RCP Installation | ITP-004 RCP Installation-PP-006
cl:0ec6dbf8-4c10-4c45-998d-72abcbf29ad6 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-004 RCP Installation | ITP-004 RCP Installation-PP-006 | 2.0 Construction | RCP2.13 - End Treatment – Headwall & Wingwalls (Concrete) | Not started | Open | ITP-004 RCP Installation | AWP-1B | Process Plant | ITP-004 RCP Installation | ITP-004 RCP Installation-PP-006
cl:0ec6dbf8-4c10-4c45-998d-72abcbf29ad6 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-004 RCP Installation | ITP-004 RCP Installation-PP-006 | 2.0 Construction | RCP2.14 - Rock Protection | Not started | Open | ITP-004 RCP Installation | AWP-1B | Process Plant | ITP-004 RCP Installation | ITP-004 RCP Installation-PP-006
cl:0ec6dbf8-4c10-4c45-998d-72abcbf29ad6 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-004 RCP Installation | ITP-004 RCP Installation-PP-006 | 3.0 Post Construction | RCP3.15 - Works completed and update ITP/ Lot Register/ MDR and close out of GDP | Not started | Open | ITP-004 RCP Installation | AWP-1B | Process Plant | ITP-004 RCP Installation | ITP-004 RCP Installation-PP-006
cl:34a0f8ef-207f-4f96-9919-9e5c4749c252 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-008 Embankment Construction | ITP-008 Embankment Construction-PP-001 | Embankment Construction | EC1.1 - Underlying lot & ITP signed off and conforming | Not started | Open | ITP-008 Embankment Construction | AWP-1B | Process Plant | ITP-008 Embankment Construction | ITP-008 Embankment Construction-PP-001
cl:34a0f8ef-207f-4f96-9919-9e5c4749c252 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-008 Embankment Construction | ITP-008 Embankment Construction-PP-001 | Embankment Construction | EC1.2 - Embankment fill material | Not started | Open | ITP-008 Embankment Construction | AWP-1B | Process Plant | ITP-008 Embankment Construction | ITP-008 Embankment Construction-PP-001
cl:34a0f8ef-207f-4f96-9919-9e5c4749c252 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-008 Embankment Construction | ITP-008 Embankment Construction-PP-001 | Embankment Construction | EC1.3 - Survey Set out | Not started | Open | ITP-008 Embankment Construction | AWP-1B | Process Plant | ITP-008 Embankment Construction | ITP-008 Embankment Construction-PP-001
cl:34a0f8ef-207f-4f96-9919-9e5c4749c252 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-008 Embankment Construction | ITP-008 Embankment Construction-PP-001 | Embankment Construction | EC1.4 - Place, moisture condition & compact embankment fill | Not started | Open | ITP-008 Embankment Construction | AWP-1B | Process Plant | ITP-008 Embankment Construction | ITP-008 Embankment Construction-PP-001
cl:34a0f8ef-207f-4f96-9919-9e5c4749c252 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-008 Embankment Construction | ITP-008 Embankment Construction-PP-001 | Embankment Construction | EC1.5 - Trim embankment | Not started | Open | ITP-008 Embankment Construction | AWP-1B | Process Plant | ITP-008 Embankment Construction | ITP-008 Embankment Construction-PP-001
cl:34a0f8ef-207f-4f96-9919-9e5c4749c252 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-008 Embankment Construction | ITP-008 Embankment Construction-PP-001 | Embankment Construction | EC1.6 - Proof rolling | Not started | Open | ITP-008 Embankment Construction | AWP-1B | Process Plant | ITP-008 Embankment Construction | ITP-008 Embankment Construction-PP-001
cl:34a0f8ef-207f-4f96-9919-9e5c4749c252 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-008 Embankment Construction | ITP-008 Embankment Construction-PP-001 | Embankment Construction | EC1.7 - Surface level check and survey pick-up | Not started | Open | ITP-008 Embankment Construction | AWP-1B | Process Plant | ITP-008 Embankment Construction | ITP-008 Embankment Construction-PP-001
cl:34a0f8ef-207f-4f96-9919-9e5c4749c252 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-008 Embankment Construction | ITP-008 Embankment Construction-PP-001 | Embankment Construction | EC1.8 - QA close out | Not started | Open | ITP-008 Embankment Construction | AWP-1B | Process Plant | ITP-008 Embankment Construction | ITP-008 Embankment Construction-PP-001
cl:9386c9cd-c572-49f2-b0db-9a4e30c5081e | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-008 Embankment Construction | ITP-008 Embankment Construction-PP-002 | Embankment Construction | EC1.1 - Underlying lot & ITP signed off and conforming | Not started | Open | ITP-008 Embankment Construction | AWP-1B | Process Plant | ITP-008 Embankment Construction | ITP-008 Embankment Construction-PP-002
cl:9386c9cd-c572-49f2-b0db-9a4e30c5081e | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-008 Embankment Construction | ITP-008 Embankment Construction-PP-002 | Embankment Construction | EC1.2 - Embankment fill material | Not started | Open | ITP-008 Embankment Construction | AWP-1B | Process Plant | ITP-008 Embankment Construction | ITP-008 Embankment Construction-PP-002
cl:9386c9cd-c572-49f2-b0db-9a4e30c5081e | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-008 Embankment Construction | ITP-008 Embankment Construction-PP-002 | Embankment Construction | EC1.3 - Survey Set out | Not started | Open | ITP-008 Embankment Construction | AWP-1B | Process Plant | ITP-008 Embankment Construction | ITP-008 Embankment Construction-PP-002
cl:9386c9cd-c572-49f2-b0db-9a4e30c5081e | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-008 Embankment Construction | ITP-008 Embankment Construction-PP-002 | Embankment Construction | EC1.4 - Place, moisture condition & compact embankment fill | Not started | Open | ITP-008 Embankment Construction | AWP-1B | Process Plant | ITP-008 Embankment Construction | ITP-008 Embankment Construction-PP-002
cl:9386c9cd-c572-49f2-b0db-9a4e30c5081e | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-008 Embankment Construction | ITP-008 Embankment Construction-PP-002 | Embankment Construction | EC1.5 - Trim embankment | Not started | Open | ITP-008 Embankment Construction | AWP-1B | Process Plant | ITP-008 Embankment Construction | ITP-008 Embankment Construction-PP-002
cl:9386c9cd-c572-49f2-b0db-9a4e30c5081e | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-008 Embankment Construction | ITP-008 Embankment Construction-PP-002 | Embankment Construction | EC1.6 - Proof rolling | Not started | Open | ITP-008 Embankment Construction | AWP-1B | Process Plant | ITP-008 Embankment Construction | ITP-008 Embankment Construction-PP-002
cl:9386c9cd-c572-49f2-b0db-9a4e30c5081e | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-008 Embankment Construction | ITP-008 Embankment Construction-PP-002 | Embankment Construction | EC1.7 - Surface level check and survey pick-up | Not started | Open | ITP-008 Embankment Construction | AWP-1B | Process Plant | ITP-008 Embankment Construction | ITP-008 Embankment Construction-PP-002
cl:9386c9cd-c572-49f2-b0db-9a4e30c5081e | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-008 Embankment Construction | ITP-008 Embankment Construction-PP-002 | Embankment Construction | EC1.8 - QA close out | Not started | Open | ITP-008 Embankment Construction | AWP-1B | Process Plant | ITP-008 Embankment Construction | ITP-008 Embankment Construction-PP-002
cl:35a4ec69-97d7-430c-90f4-cfab9eeccef8 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-008 Embankment Construction | ITP-008 Embankment Construction-PP-003 | Embankment Construction | EC1.1 - Underlying lot & ITP signed off and conforming | Not started | Open | ITP-008 Embankment Construction | AWP-1B | Process Plant | ITP-008 Embankment Construction | ITP-008 Embankment Construction-PP-003
cl:35a4ec69-97d7-430c-90f4-cfab9eeccef8 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-008 Embankment Construction | ITP-008 Embankment Construction-PP-003 | Embankment Construction | EC1.2 - Embankment fill material | Not started | Open | ITP-008 Embankment Construction | AWP-1B | Process Plant | ITP-008 Embankment Construction | ITP-008 Embankment Construction-PP-003
cl:35a4ec69-97d7-430c-90f4-cfab9eeccef8 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-008 Embankment Construction | ITP-008 Embankment Construction-PP-003 | Embankment Construction | EC1.3 - Survey Set out | Not started | Open | ITP-008 Embankment Construction | AWP-1B | Process Plant | ITP-008 Embankment Construction | ITP-008 Embankment Construction-PP-003
cl:35a4ec69-97d7-430c-90f4-cfab9eeccef8 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-008 Embankment Construction | ITP-008 Embankment Construction-PP-003 | Embankment Construction | EC1.4 - Place, moisture condition & compact embankment fill | Not started | Open | ITP-008 Embankment Construction | AWP-1B | Process Plant | ITP-008 Embankment Construction | ITP-008 Embankment Construction-PP-003
cl:35a4ec69-97d7-430c-90f4-cfab9eeccef8 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-008 Embankment Construction | ITP-008 Embankment Construction-PP-003 | Embankment Construction | EC1.5 - Trim embankment | Not started | Open | ITP-008 Embankment Construction | AWP-1B | Process Plant | ITP-008 Embankment Construction | ITP-008 Embankment Construction-PP-003
cl:35a4ec69-97d7-430c-90f4-cfab9eeccef8 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-008 Embankment Construction | ITP-008 Embankment Construction-PP-003 | Embankment Construction | EC1.6 - Proof rolling | Not started | Open | ITP-008 Embankment Construction | AWP-1B | Process Plant | ITP-008 Embankment Construction | ITP-008 Embankment Construction-PP-003
cl:35a4ec69-97d7-430c-90f4-cfab9eeccef8 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-008 Embankment Construction | ITP-008 Embankment Construction-PP-003 | Embankment Construction | EC1.7 - Surface level check and survey pick-up | Not started | Open | ITP-008 Embankment Construction | AWP-1B | Process Plant | ITP-008 Embankment Construction | ITP-008 Embankment Construction-PP-003
cl:35a4ec69-97d7-430c-90f4-cfab9eeccef8 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-008 Embankment Construction | ITP-008 Embankment Construction-PP-003 | Embankment Construction | EC1.8 - QA close out | Not started | Open | ITP-008 Embankment Construction | AWP-1B | Process Plant | ITP-008 Embankment Construction | ITP-008 Embankment Construction-PP-003
cl:62bc3b8f-7bba-4d2a-9590-a2eacee51cfc | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-008 Embankment Construction | ITP-008 Embankment Construction-PP-004 | Embankment Construction | EC1.1 - Underlying lot & ITP signed off and conforming | Not started | Open | ITP-008 Embankment Construction | AWP-1B | Process Plant | ITP-008 Embankment Construction | ITP-008 Embankment Construction-PP-004
cl:62bc3b8f-7bba-4d2a-9590-a2eacee51cfc | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-008 Embankment Construction | ITP-008 Embankment Construction-PP-004 | Embankment Construction | EC1.2 - Embankment fill material | Not started | Open | ITP-008 Embankment Construction | AWP-1B | Process Plant | ITP-008 Embankment Construction | ITP-008 Embankment Construction-PP-004
cl:62bc3b8f-7bba-4d2a-9590-a2eacee51cfc | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-008 Embankment Construction | ITP-008 Embankment Construction-PP-004 | Embankment Construction | EC1.3 - Survey Set out | Not started | Open | ITP-008 Embankment Construction | AWP-1B | Process Plant | ITP-008 Embankment Construction | ITP-008 Embankment Construction-PP-004
cl:62bc3b8f-7bba-4d2a-9590-a2eacee51cfc | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-008 Embankment Construction | ITP-008 Embankment Construction-PP-004 | Embankment Construction | EC1.4 - Place, moisture condition & compact embankment fill | Not started | Open | ITP-008 Embankment Construction | AWP-1B | Process Plant | ITP-008 Embankment Construction | ITP-008 Embankment Construction-PP-004
cl:62bc3b8f-7bba-4d2a-9590-a2eacee51cfc | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-008 Embankment Construction | ITP-008 Embankment Construction-PP-004 | Embankment Construction | EC1.5 - Trim embankment | Not started | Open | ITP-008 Embankment Construction | AWP-1B | Process Plant | ITP-008 Embankment Construction | ITP-008 Embankment Construction-PP-004
cl:62bc3b8f-7bba-4d2a-9590-a2eacee51cfc | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-008 Embankment Construction | ITP-008 Embankment Construction-PP-004 | Embankment Construction | EC1.6 - Proof rolling | Not started | Open | ITP-008 Embankment Construction | AWP-1B | Process Plant | ITP-008 Embankment Construction | ITP-008 Embankment Construction-PP-004
cl:62bc3b8f-7bba-4d2a-9590-a2eacee51cfc | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-008 Embankment Construction | ITP-008 Embankment Construction-PP-004 | Embankment Construction | EC1.7 - Surface level check and survey pick-up | Not started | Open | ITP-008 Embankment Construction | AWP-1B | Process Plant | ITP-008 Embankment Construction | ITP-008 Embankment Construction-PP-004
cl:62bc3b8f-7bba-4d2a-9590-a2eacee51cfc | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-008 Embankment Construction | ITP-008 Embankment Construction-PP-004 | Embankment Construction | EC1.8 - QA close out | Not started | Open | ITP-008 Embankment Construction | AWP-1B | Process Plant | ITP-008 Embankment Construction | ITP-008 Embankment Construction-PP-004
cl:6d7cd6c4-190a-4308-89f3-2f5727f1a541 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-008 Embankment Construction | ITP-008 Embankment Construction-PP-005 | Embankment Construction | EC1.1 - Underlying lot & ITP signed off and conforming | Not started | Open | ITP-008 Embankment Construction | AWP-1B | Process Plant | ITP-008 Embankment Construction | ITP-008 Embankment Construction-PP-005
cl:6d7cd6c4-190a-4308-89f3-2f5727f1a541 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-008 Embankment Construction | ITP-008 Embankment Construction-PP-005 | Embankment Construction | EC1.2 - Embankment fill material | Not started | Open | ITP-008 Embankment Construction | AWP-1B | Process Plant | ITP-008 Embankment Construction | ITP-008 Embankment Construction-PP-005
cl:6d7cd6c4-190a-4308-89f3-2f5727f1a541 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-008 Embankment Construction | ITP-008 Embankment Construction-PP-005 | Embankment Construction | EC1.3 - Survey Set out | Not started | Open | ITP-008 Embankment Construction | AWP-1B | Process Plant | ITP-008 Embankment Construction | ITP-008 Embankment Construction-PP-005
cl:6d7cd6c4-190a-4308-89f3-2f5727f1a541 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-008 Embankment Construction | ITP-008 Embankment Construction-PP-005 | Embankment Construction | EC1.4 - Place, moisture condition & compact embankment fill | Not started | Open | ITP-008 Embankment Construction | AWP-1B | Process Plant | ITP-008 Embankment Construction | ITP-008 Embankment Construction-PP-005
cl:6d7cd6c4-190a-4308-89f3-2f5727f1a541 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-008 Embankment Construction | ITP-008 Embankment Construction-PP-005 | Embankment Construction | EC1.5 - Trim embankment | Not started | Open | ITP-008 Embankment Construction | AWP-1B | Process Plant | ITP-008 Embankment Construction | ITP-008 Embankment Construction-PP-005
cl:6d7cd6c4-190a-4308-89f3-2f5727f1a541 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-008 Embankment Construction | ITP-008 Embankment Construction-PP-005 | Embankment Construction | EC1.6 - Proof rolling | Not started | Open | ITP-008 Embankment Construction | AWP-1B | Process Plant | ITP-008 Embankment Construction | ITP-008 Embankment Construction-PP-005
cl:6d7cd6c4-190a-4308-89f3-2f5727f1a541 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-008 Embankment Construction | ITP-008 Embankment Construction-PP-005 | Embankment Construction | EC1.7 - Surface level check and survey pick-up | Not started | Open | ITP-008 Embankment Construction | AWP-1B | Process Plant | ITP-008 Embankment Construction | ITP-008 Embankment Construction-PP-005
cl:6d7cd6c4-190a-4308-89f3-2f5727f1a541 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-008 Embankment Construction | ITP-008 Embankment Construction-PP-005 | Embankment Construction | EC1.8 - QA close out | Not started | Open | ITP-008 Embankment Construction | AWP-1B | Process Plant | ITP-008 Embankment Construction | ITP-008 Embankment Construction-PP-005
cl:36c50743-d7f9-4c31-9411-9c7dfd700e26 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-008 Embankment Construction | ITP-008 Embankment Construction-PP-006 | Embankment Construction | EC1.1 - Underlying lot & ITP signed off and conforming | Not started | Open | ITP-008 Embankment Construction | AWP-1B | Process Plant | ITP-008 Embankment Construction | ITP-008 Embankment Construction-PP-006
cl:36c50743-d7f9-4c31-9411-9c7dfd700e26 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-008 Embankment Construction | ITP-008 Embankment Construction-PP-006 | Embankment Construction | EC1.2 - Embankment fill material | Not started | Open | ITP-008 Embankment Construction | AWP-1B | Process Plant | ITP-008 Embankment Construction | ITP-008 Embankment Construction-PP-006
cl:36c50743-d7f9-4c31-9411-9c7dfd700e26 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-008 Embankment Construction | ITP-008 Embankment Construction-PP-006 | Embankment Construction | EC1.3 - Survey Set out | Not started | Open | ITP-008 Embankment Construction | AWP-1B | Process Plant | ITP-008 Embankment Construction | ITP-008 Embankment Construction-PP-006
cl:36c50743-d7f9-4c31-9411-9c7dfd700e26 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-008 Embankment Construction | ITP-008 Embankment Construction-PP-006 | Embankment Construction | EC1.4 - Place, moisture condition & compact embankment fill | Not started | Open | ITP-008 Embankment Construction | AWP-1B | Process Plant | ITP-008 Embankment Construction | ITP-008 Embankment Construction-PP-006
cl:36c50743-d7f9-4c31-9411-9c7dfd700e26 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-008 Embankment Construction | ITP-008 Embankment Construction-PP-006 | Embankment Construction | EC1.5 - Trim embankment | Not started | Open | ITP-008 Embankment Construction | AWP-1B | Process Plant | ITP-008 Embankment Construction | ITP-008 Embankment Construction-PP-006
cl:36c50743-d7f9-4c31-9411-9c7dfd700e26 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-008 Embankment Construction | ITP-008 Embankment Construction-PP-006 | Embankment Construction | EC1.6 - Proof rolling | Not started | Open | ITP-008 Embankment Construction | AWP-1B | Process Plant | ITP-008 Embankment Construction | ITP-008 Embankment Construction-PP-006
cl:36c50743-d7f9-4c31-9411-9c7dfd700e26 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-008 Embankment Construction | ITP-008 Embankment Construction-PP-006 | Embankment Construction | EC1.7 - Surface level check and survey pick-up | Not started | Open | ITP-008 Embankment Construction | AWP-1B | Process Plant | ITP-008 Embankment Construction | ITP-008 Embankment Construction-PP-006
cl:36c50743-d7f9-4c31-9411-9c7dfd700e26 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-008 Embankment Construction | ITP-008 Embankment Construction-PP-006 | Embankment Construction | EC1.8 - QA close out | Not started | Open | ITP-008 Embankment Construction | AWP-1B | Process Plant | ITP-008 Embankment Construction | ITP-008 Embankment Construction-PP-006
cl:e5240338-56e4-487c-b409-020c3bff2d7e | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-001 | 1.0 Pre-Construction | GP1.1 - Drawings supplied most current IFC | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1B | Process Plant | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-001
cl:e5240338-56e4-487c-b409-020c3bff2d7e | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-001 | 1.0 Pre-Construction | GP1.2 - Management Plans submitted and approved as per PMP | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1B | Process Plant | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-001
cl:e5240338-56e4-487c-b409-020c3bff2d7e | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-001 | 1.0 Pre-Construction | GP1.3 - Inspection Test Plan (ITP) submitted and approved | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1B | Process Plant | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-001
cl:e5240338-56e4-487c-b409-020c3bff2d7e | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-001 | 1.0 Pre-Construction | GP1.4 - Lot Register/ WBS submitted and approved | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1B | Process Plant | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-001
cl:e5240338-56e4-487c-b409-020c3bff2d7e | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-001 | 1.0 Pre-Construction | GP1.5 - Pavement material compliance testing | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1B | Process Plant | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-001
cl:e5240338-56e4-487c-b409-020c3bff2d7e | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-001 | 1.0 Pre-Construction | GP1.6 - Stockpile locations | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1B | Process Plant | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-001
cl:e5240338-56e4-487c-b409-020c3bff2d7e | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-001 | 1.0 Pre-Construction | GP1.7 - Underlying lot & ITP signed off and conforming | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1B | Process Plant | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-001
cl:e5240338-56e4-487c-b409-020c3bff2d7e | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-001 | 2.0 Construction | GP2.8 - Subgrade preparation under pavements | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1B | Process Plant | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-001
cl:e5240338-56e4-487c-b409-020c3bff2d7e | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-001 | 2.0 Construction | EC2.9 - Surface level check/ and survey pick-up | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1B | Process Plant | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-001
cl:e5240338-56e4-487c-b409-020c3bff2d7e | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-001 | 2.0 Construction | EC2.10 - Proof roll subgrade prior to placement of pavement materials | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1B | Process Plant | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-001
cl:e5240338-56e4-487c-b409-020c3bff2d7e | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-001 | 2.0 Construction | EC2.11 - Placement of pavement material layers | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1B | Process Plant | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-001
cl:e5240338-56e4-487c-b409-020c3bff2d7e | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-001 | 2.0 Construction | EC2.12 - Surface level check/ and survey pick-up | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1B | Process Plant | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-001
cl:e5240338-56e4-487c-b409-020c3bff2d7e | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-001 | 3.0 Post Construction | EC3.13 - Works completed and update ITP/ Lot Register/ MDR and close out of GDP | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1B | Process Plant | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-001
cl:1413e480-0f68-49b0-a36b-fd35f6e91974 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-002 | 1.0 Pre-Construction | GP1.1 - Drawings supplied most current IFC | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1B | Process Plant | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-002
cl:1413e480-0f68-49b0-a36b-fd35f6e91974 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-002 | 1.0 Pre-Construction | GP1.2 - Management Plans submitted and approved as per PMP | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1B | Process Plant | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-002
cl:1413e480-0f68-49b0-a36b-fd35f6e91974 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-002 | 1.0 Pre-Construction | GP1.3 - Inspection Test Plan (ITP) submitted and approved | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1B | Process Plant | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-002
cl:1413e480-0f68-49b0-a36b-fd35f6e91974 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-002 | 1.0 Pre-Construction | GP1.4 - Lot Register/ WBS submitted and approved | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1B | Process Plant | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-002
cl:1413e480-0f68-49b0-a36b-fd35f6e91974 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-002 | 1.0 Pre-Construction | GP1.5 - Pavement material compliance testing | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1B | Process Plant | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-002
cl:1413e480-0f68-49b0-a36b-fd35f6e91974 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-002 | 1.0 Pre-Construction | GP1.6 - Stockpile locations | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1B | Process Plant | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-002
cl:1413e480-0f68-49b0-a36b-fd35f6e91974 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-002 | 1.0 Pre-Construction | GP1.7 - Underlying lot & ITP signed off and conforming | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1B | Process Plant | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-002
cl:1413e480-0f68-49b0-a36b-fd35f6e91974 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-002 | 2.0 Construction | GP2.8 - Subgrade preparation under pavements | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1B | Process Plant | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-002
cl:1413e480-0f68-49b0-a36b-fd35f6e91974 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-002 | 2.0 Construction | EC2.9 - Surface level check/ and survey pick-up | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1B | Process Plant | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-002
cl:1413e480-0f68-49b0-a36b-fd35f6e91974 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-002 | 2.0 Construction | EC2.10 - Proof roll subgrade prior to placement of pavement materials | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1B | Process Plant | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-002
cl:1413e480-0f68-49b0-a36b-fd35f6e91974 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-002 | 2.0 Construction | EC2.11 - Placement of pavement material layers | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1B | Process Plant | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-002
cl:1413e480-0f68-49b0-a36b-fd35f6e91974 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-002 | 2.0 Construction | EC2.12 - Surface level check/ and survey pick-up | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1B | Process Plant | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-002
cl:1413e480-0f68-49b0-a36b-fd35f6e91974 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-002 | 3.0 Post Construction | EC3.13 - Works completed and update ITP/ Lot Register/ MDR and close out of GDP | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1B | Process Plant | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-002
cl:189e3c23-6d1e-4997-a42a-ccab401c7352 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-003 | 1.0 Pre-Construction | GP1.1 - Drawings supplied most current IFC | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1B | Process Plant | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-003
cl:189e3c23-6d1e-4997-a42a-ccab401c7352 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-003 | 1.0 Pre-Construction | GP1.2 - Management Plans submitted and approved as per PMP | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1B | Process Plant | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-003
cl:189e3c23-6d1e-4997-a42a-ccab401c7352 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-003 | 1.0 Pre-Construction | GP1.3 - Inspection Test Plan (ITP) submitted and approved | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1B | Process Plant | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-003
cl:189e3c23-6d1e-4997-a42a-ccab401c7352 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-003 | 1.0 Pre-Construction | GP1.4 - Lot Register/ WBS submitted and approved | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1B | Process Plant | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-003
cl:189e3c23-6d1e-4997-a42a-ccab401c7352 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-003 | 1.0 Pre-Construction | GP1.5 - Pavement material compliance testing | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1B | Process Plant | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-003
cl:189e3c23-6d1e-4997-a42a-ccab401c7352 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-003 | 1.0 Pre-Construction | GP1.6 - Stockpile locations | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1B | Process Plant | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-003
cl:189e3c23-6d1e-4997-a42a-ccab401c7352 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-003 | 1.0 Pre-Construction | GP1.7 - Underlying lot & ITP signed off and conforming | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1B | Process Plant | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-003
cl:189e3c23-6d1e-4997-a42a-ccab401c7352 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-003 | 2.0 Construction | GP2.8 - Subgrade preparation under pavements | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1B | Process Plant | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-003
cl:189e3c23-6d1e-4997-a42a-ccab401c7352 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-003 | 2.0 Construction | EC2.9 - Surface level check/ and survey pick-up | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1B | Process Plant | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-003
cl:189e3c23-6d1e-4997-a42a-ccab401c7352 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-003 | 2.0 Construction | EC2.10 - Proof roll subgrade prior to placement of pavement materials | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1B | Process Plant | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-003
cl:189e3c23-6d1e-4997-a42a-ccab401c7352 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-003 | 2.0 Construction | EC2.11 - Placement of pavement material layers | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1B | Process Plant | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-003
cl:189e3c23-6d1e-4997-a42a-ccab401c7352 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-003 | 2.0 Construction | EC2.12 - Surface level check/ and survey pick-up | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1B | Process Plant | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-003
cl:189e3c23-6d1e-4997-a42a-ccab401c7352 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-003 | 3.0 Post Construction | EC3.13 - Works completed and update ITP/ Lot Register/ MDR and close out of GDP | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1B | Process Plant | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-003
cl:8c7ea01e-ab45-4fcd-8e50-1b5d4302be9c | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-004 | 1.0 Pre-Construction | GP1.1 - Drawings supplied most current IFC | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1B | Process Plant | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-004
cl:8c7ea01e-ab45-4fcd-8e50-1b5d4302be9c | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-004 | 1.0 Pre-Construction | GP1.2 - Management Plans submitted and approved as per PMP | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1B | Process Plant | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-004
cl:8c7ea01e-ab45-4fcd-8e50-1b5d4302be9c | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-004 | 1.0 Pre-Construction | GP1.3 - Inspection Test Plan (ITP) submitted and approved | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1B | Process Plant | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-004
cl:8c7ea01e-ab45-4fcd-8e50-1b5d4302be9c | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-004 | 1.0 Pre-Construction | GP1.4 - Lot Register/ WBS submitted and approved | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1B | Process Plant | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-004
cl:8c7ea01e-ab45-4fcd-8e50-1b5d4302be9c | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-004 | 1.0 Pre-Construction | GP1.5 - Pavement material compliance testing | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1B | Process Plant | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-004
cl:8c7ea01e-ab45-4fcd-8e50-1b5d4302be9c | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-004 | 1.0 Pre-Construction | GP1.6 - Stockpile locations | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1B | Process Plant | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-004
cl:8c7ea01e-ab45-4fcd-8e50-1b5d4302be9c | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-004 | 1.0 Pre-Construction | GP1.7 - Underlying lot & ITP signed off and conforming | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1B | Process Plant | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-004
cl:8c7ea01e-ab45-4fcd-8e50-1b5d4302be9c | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-004 | 2.0 Construction | GP2.8 - Subgrade preparation under pavements | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1B | Process Plant | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-004
cl:8c7ea01e-ab45-4fcd-8e50-1b5d4302be9c | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-004 | 2.0 Construction | EC2.9 - Surface level check/ and survey pick-up | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1B | Process Plant | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-004
cl:8c7ea01e-ab45-4fcd-8e50-1b5d4302be9c | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-004 | 2.0 Construction | EC2.10 - Proof roll subgrade prior to placement of pavement materials | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1B | Process Plant | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-004
cl:8c7ea01e-ab45-4fcd-8e50-1b5d4302be9c | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-004 | 2.0 Construction | EC2.11 - Placement of pavement material layers | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1B | Process Plant | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-004
cl:8c7ea01e-ab45-4fcd-8e50-1b5d4302be9c | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-004 | 2.0 Construction | EC2.12 - Surface level check/ and survey pick-up | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1B | Process Plant | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-004
cl:8c7ea01e-ab45-4fcd-8e50-1b5d4302be9c | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-004 | 3.0 Post Construction | EC3.13 - Works completed and update ITP/ Lot Register/ MDR and close out of GDP | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1B | Process Plant | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-004
cl:769af0f8-c942-4998-9524-7e8b1acf89a8 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-005 | 1.0 Pre-Construction | GP1.1 - Drawings supplied most current IFC | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1B | Process Plant | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-005
cl:769af0f8-c942-4998-9524-7e8b1acf89a8 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-005 | 1.0 Pre-Construction | GP1.2 - Management Plans submitted and approved as per PMP | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1B | Process Plant | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-005
cl:769af0f8-c942-4998-9524-7e8b1acf89a8 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-005 | 1.0 Pre-Construction | GP1.3 - Inspection Test Plan (ITP) submitted and approved | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1B | Process Plant | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-005
cl:769af0f8-c942-4998-9524-7e8b1acf89a8 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-005 | 1.0 Pre-Construction | GP1.4 - Lot Register/ WBS submitted and approved | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1B | Process Plant | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-005
cl:769af0f8-c942-4998-9524-7e8b1acf89a8 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-005 | 1.0 Pre-Construction | GP1.5 - Pavement material compliance testing | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1B | Process Plant | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-005
cl:769af0f8-c942-4998-9524-7e8b1acf89a8 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-005 | 1.0 Pre-Construction | GP1.6 - Stockpile locations | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1B | Process Plant | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-005
cl:769af0f8-c942-4998-9524-7e8b1acf89a8 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-005 | 1.0 Pre-Construction | GP1.7 - Underlying lot & ITP signed off and conforming | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1B | Process Plant | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-005
cl:769af0f8-c942-4998-9524-7e8b1acf89a8 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-005 | 2.0 Construction | GP2.8 - Subgrade preparation under pavements | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1B | Process Plant | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-005
cl:769af0f8-c942-4998-9524-7e8b1acf89a8 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-005 | 2.0 Construction | EC2.9 - Surface level check/ and survey pick-up | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1B | Process Plant | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-005
cl:769af0f8-c942-4998-9524-7e8b1acf89a8 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-005 | 2.0 Construction | EC2.10 - Proof roll subgrade prior to placement of pavement materials | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1B | Process Plant | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-005
cl:769af0f8-c942-4998-9524-7e8b1acf89a8 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-005 | 2.0 Construction | EC2.11 - Placement of pavement material layers | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1B | Process Plant | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-005
cl:769af0f8-c942-4998-9524-7e8b1acf89a8 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-005 | 2.0 Construction | EC2.12 - Surface level check/ and survey pick-up | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1B | Process Plant | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-005
cl:769af0f8-c942-4998-9524-7e8b1acf89a8 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-005 | 3.0 Post Construction | EC3.13 - Works completed and update ITP/ Lot Register/ MDR and close out of GDP | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1B | Process Plant | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-005
cl:f1f0156b-a60c-48c3-b0ee-4780306e1fa8 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-006 | 1.0 Pre-Construction | GP1.1 - Drawings supplied most current IFC | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1B | Process Plant | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-006
cl:f1f0156b-a60c-48c3-b0ee-4780306e1fa8 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-006 | 1.0 Pre-Construction | GP1.2 - Management Plans submitted and approved as per PMP | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1B | Process Plant | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-006
cl:f1f0156b-a60c-48c3-b0ee-4780306e1fa8 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-006 | 1.0 Pre-Construction | GP1.3 - Inspection Test Plan (ITP) submitted and approved | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1B | Process Plant | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-006
cl:f1f0156b-a60c-48c3-b0ee-4780306e1fa8 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-006 | 1.0 Pre-Construction | GP1.4 - Lot Register/ WBS submitted and approved | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1B | Process Plant | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-006
cl:f1f0156b-a60c-48c3-b0ee-4780306e1fa8 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-006 | 1.0 Pre-Construction | GP1.5 - Pavement material compliance testing | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1B | Process Plant | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-006
cl:f1f0156b-a60c-48c3-b0ee-4780306e1fa8 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-006 | 1.0 Pre-Construction | GP1.6 - Stockpile locations | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1B | Process Plant | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-006
cl:f1f0156b-a60c-48c3-b0ee-4780306e1fa8 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-006 | 1.0 Pre-Construction | GP1.7 - Underlying lot & ITP signed off and conforming | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1B | Process Plant | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-006
cl:f1f0156b-a60c-48c3-b0ee-4780306e1fa8 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-006 | 2.0 Construction | GP2.8 - Subgrade preparation under pavements | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1B | Process Plant | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-006
cl:f1f0156b-a60c-48c3-b0ee-4780306e1fa8 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-006 | 2.0 Construction | EC2.9 - Surface level check/ and survey pick-up | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1B | Process Plant | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-006
cl:f1f0156b-a60c-48c3-b0ee-4780306e1fa8 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-006 | 2.0 Construction | EC2.10 - Proof roll subgrade prior to placement of pavement materials | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1B | Process Plant | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-006
cl:f1f0156b-a60c-48c3-b0ee-4780306e1fa8 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-006 | 2.0 Construction | EC2.11 - Placement of pavement material layers | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1B | Process Plant | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-006
cl:f1f0156b-a60c-48c3-b0ee-4780306e1fa8 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-006 | 2.0 Construction | EC2.12 - Surface level check/ and survey pick-up | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1B | Process Plant | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-006
cl:f1f0156b-a60c-48c3-b0ee-4780306e1fa8 | EVA Copper Mine Project | AWP-1B > Process Plant > ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-006 | 3.0 Post Construction | EC3.13 - Works completed and update ITP/ Lot Register/ MDR and close out of GDP | Not started | Open | ITP-009 Unbound Gravel Pavements | AWP-1B | Process Plant | ITP-009 Unbound Gravel Pavements | ITP-009 Unbound Gravel Pavements-PP-006

## Master List Checklist Templates
Id | Type | Name | Values | Prompting Name | Usage Count | Resource Id
db980d36-b393-4cae-96a5-5d92d16fdff9/2 | checklist | EVAMP001-THS-QA-ITP-0003 - Subgrade Preparation | itp | EVAMP001-THS-QA-ITP-0003 - Subgrade Preparation | 0 | 09842f60-92c0-417e-b8ba-800a4115612a
a3728f01-7949-462b-a069-9f4a9c5708f7 | section | 1 - Pre-Construction
e956ccaa-3b5c-4b88-b1bd-0c5a9fb602ad | checkpoint | Lot Map
ec7d65fc-9244-48e8-969f-84a7bea75889 | checkpoint | Test Results
64407864-774c-4fa9-b98f-dcc227a852b5 | section | 2 - Construction
919c395d-1f97-4282-9f28-f63691b5c18b | checkpoint | 6 - Underlying lot & ITP signed off and conforming
68624404-36f1-583e-92db-a98ff217b5e7 | note | Responsibility - ENG
03f189a1-adc1-537f-acb6-e78d1c74de16 | note | Method - Visual
cc753c97-023f-564e-908e-020a68ea60b2 | note | Conformance Criteria - Topsoil stripping ITP signed off
79d299d0-42b7-5176-8211-2afb0d143cd0 | note | Specification Clause - Approved QMP
e6c2d882-e1e0-5419-ab31-7243ae5fe949 | note | Frequency - Prior to works
83724454-bc64-504e-ba2e-48e89fc6209a | note | Verification: THIESS (Initial) - HP
a77f0315-4624-5ae3-bbe8-c5b952bd749f | note | Verification: Client (Initial) - W
762ece96-d03b-45c5-8a54-66dbae60b72c | signoff | WITNESS POINT
8e9dbe40-a5cf-4f64-9c0f-facab2d71738 | checkpoint | 7 - Removal and replacement of unsuitable material
f73d3e12-a1cd-5a8b-a064-b4fb73ba4089 | note | Responsibility - SV
03956dbd-a0ab-5499-858d-a9f37f12e7b3 | note | Method - Visual
914e75d9-b106-5473-a8e0-b45a58fbc487 | note | Conformance Criteria - Determination of unsuitable material by the Level 1 GITA or Principal is required prior to the removal of any unsuitable material.
81aa9528-8ffa-57bc-9d44-2191dcf68cf5 | note | ○ Unsuitable material shall be disposed as directed by the company or in areas specified in the annexure.
13f2b256-8293-54a0-9f89-0b99823a6f85 | note | Specification Clause - EVAMP001-THS- CV-SPE-0001
a43a01a3-b6b0-5a25-b85a-3ebdf20f7bb7 | note | Frequency - As required
b8c135cb-a494-5646-8ec8-e00b1b4757b9 | note | Verification: THIESS (Initial) - HP
5e9ef728-55b9-574b-8268-717bfa4b589f | note | Verification: Client (Initial) - W
00b55881-f2e3-4133-82eb-3496308d2180 | signoff | WITNESS POINT
00d679e7-d09d-429c-9998-09e7552b433a | checkpoint | 8 - Subgrade preparation – 200mm depth
e2eebd06-a2fc-5579-ad58-e628b49acc06 | note | Responsibility - SV
badfeb2f-8642-5752-acab-116aae4aa317 | note | Method - Visual
faa735b0-fdf1-5a15-98ba-85386707f954 | note | Conformance Criteria - Area to be ripped and conditioned to suit a minimum CBR value of 10.
1f4a78f8-82da-5928-a6cc-fff806c2495c | note | Specification Clause - C10 and C14 107501-EB-00000-27280-001 Rev A
233ea6ef-885c-5e8a-a670-e19478844992 | note | — EVAMP001-THS- CV-SPE-0001 clause 4.16
552ce3b6-ff77-560b-9257-72d3ae5ecd08 | note | Frequency - As required
2d46c621-efa4-5491-941f-985568789c8a | note | Verification: THIESS (Initial) - HP
e88c16c1-f089-5b5f-accc-88eb9c45a907 | note | Verification: Client (Initial) - HP
97ef884e-5d14-4529-a0da-cdb0fcd944bc | signoff | HOLD POINT
942e2cc5-650c-4b58-8b69-c00cb79a6050 | checkpoint | 9 - Proof-roll subgrade surface prior to placement of embankment fill
c7af55be-697b-5153-b670-3e84c2e96e63 | note | Responsibility - SV
09c73cf9-a7a2-5d82-8d4b-2c0bd829eb50 | note | Method - Field Test
36d3a400-5525-5bcb-b248-924fd46371fe | note | Conformance Criteria - All subgrades and foundations shall be proof rolled under a standard 8 tonne axle load to confirm that, in the principal’s opinion, deflections are negligible.
3d52e9d4-81c0-5505-af79-f9833db3ce7e | note | Specification Clause - EVAMP001-THS- CV-SPE-0001 clause 4.16
0a025c1b-81d5-5d4c-b1b7-523781061e80 | note | Frequency - As required
7a05aeab-7603-5bf5-8472-c2602289a658 | note | Verification: THIESS (Initial) - HP
d865f730-a19a-5340-a948-151678a800e0 | note | Verification: Client (Initial) - W
f75d0c6d-2faf-4078-b6a1-e197e60122be | signoff | WITNESS POINT
b6b366a3-5408-4251-8269-ce84604dde79 | checkpoint | 10 - Surface level check/ and survey pick-up
962c3e74-d737-5ce0-aa66-e97c533f2d08 | note | Responsibility - Surv
2155f7cb-ccf2-5077-adac-13a031e94003 | note | Method - Survey/ Field test
e3f84197-67d4-57fb-90e3-c12e9678be99 | note | Conformance Criteria - Surface level as per Table 10 C15
ad0ea4a5-91eb-5858-a6cf-7efcc1366f74 | note | ○ DXF file submitted to Company
13dd35fc-3a74-5da7-b24c-105cb34a9596 | note | Specification Clause - EVAMP001-THS- CV-SPE-0001 clause 4.16
42e75c73-ace3-5dc9-953d-589af7caf2c5 | note | Frequency - As required
7458c5d8-daac-50ef-8dce-e0ff8ba33721 | note | Verification: THIESS (Initial) - HP
61c52c2e-2aa1-5e4f-974b-f34672327276 | note | Verification: Client (Initial) - HP
443a13dc-9996-4492-b97e-0432ab2d6f51 | signoff | HOLD POINT
84f84b57-1479-4568-b984-83e8bc7c55ec | section | 3 - Post Construction
04029cd9-69f4-4343-bf5c-2685ca58e6be | checkpoint | 11 - Works completed and update ITP/ Lot Register/ MDR and close out of GDP
065e6724-8a6a-5899-aa74-4cfe5a626dee | note | Responsibility - ENG
fa3f9f99-31b4-526e-aa91-af724b07b376 | note | Method - Visual
c5ab272c-f0b4-51dc-a0d0-01597e939177 | note | Conformance Criteria - GDP permits closed.
a70d4651-6e27-52f3-bf91-c2fb5fe09beb | note | ○ ITP closed. Approved MDR
0ee368aa-f400-5806-bebb-44dde7021f20 | note | Specification Clause - EVAMP001- EVA-EN-PLA- 0001
e9788671-4d00-5a6e-a6ca-310b519c8e94 | note | — EVA PMP
8d16f1ec-84e6-5542-a08f-e7c15a3f7514 | note | Frequency - As required
4d529521-5b2c-5920-893f-4ec9baa2e25d | note | Verification: THIESS (Initial) - HP
d425ee3f-4815-5fa3-9fb0-cc42717f415f | note | Verification: Client (Initial) - HP
d2eddce9-014b-45d7-b02b-6fefccb5fc00 | signoff | HOLD POINT
16793a3e-90a6-495c-ab04-025bd238e148 | checkpoint | Final Inspection
bbf8c7f5-f960-5383-a263-b3f517e4a3d8 | tickbox | Conformance to Specification
33d3b783-7aad-53c2-a189-ae4041f36e8a | tickbox | Requires Re-Work:
e82b2fdf-244f-5c92-b0c4-b3d031f56bd4 | textbox | (Provide Details):
734a7b6b-d3bb-5845-b791-f3dc9c14a0f4 | tickbox | Non-Conformance
c2c5b5da-56ec-5488-84f9-980dea82d593 | textbox | NCR No:
c6ba9168-1177-4b63-846f-fac64b35ef93 | signoff | Approved by THIESS QA Representative / THIESS Project Manager / Client

## Project Checklist Templates
Id | Type | Name | Values | Prompting Name | Usage Count | Resource Id
AWP-1A
|  | ITP-000 Pre-Construction-PKG-Construction Management Plan | DELETE
Responsibility - ENG
Test Method - Visual
Conformance Criteria - Lot register saved in Construction Team Sharepoint and detailed in register
Frequency - Prior to works
Thiess HP/WP Check - WP
Inspector HP/WP Sign Off - WP
39eaf1a6-ee0d-4100-9bf0-c837b429ac24/3 | checklist | ITP-000 Pre-construction | itp | ITP-000 Pre-construction | 7 | 57bc4505-9df8-4695-bace-1effe5755910
51535b1a-ac26-4769-bc85-1f7ba1beade1 | section | Pre-construction
| checkpoint | PC1.1 Pre-Construction-PKG-Construction Management Plan | ADD
Responsibility - ENG
Test Method - Visual
Conformance Criteria - Approved Construction Management Plan saved in Construction Team Sharepoint and detailed in register
Frequency - Prior to works
Thiess HP/WP Check - WP
Inspector HP/WP Sign Off - WP
dccbd29c-6e53-42a4-aa77-56d5a2245e5c | checkpoint | PC1.2 - Lot Register/ WBS
731f8e63-9c21-51d9-8e55-9d9b575b5560 | note | Responsibility - ENG
5067a1db-2194-5c58-9d4a-8e6cb1f8cf52 | note | Test Method - Visual
ea6fa4bd-af40-557b-a1b1-ef2c1fe6b6cf | note | Conformance Criteria - Lot register saved in Construction Team Sharepoint and detailed in register
94588b25-c4ac-5621-ae43-e8a1da908b68 | note | Frequency - Prior to works
a6e495d4-a85e-5c8b-9e94-d0483d48b40e | note | Thiess HP/WP Check - WP
147f889c-d6d7-50b8-b9a2-f8c4d49faaf0 | note | Inspector HP/WP Sign Off - WP
4fcac2b7-4adc-4364-b8a4-7412fb080e6a | signoff | WITNESS POINT
f72a1074-063a-4d47-a7f1-0395bd9eb44b | checkpoint | PC1.3 - Construction procedures
51a8cb8d-2c61-53cb-99e3-e639f64c30c6 | note | Responsibility - ENG
933726ca-6948-5c00-90d7-15d6999cd3de | note | Test Method - Visual
93830690-3c17-57f0-ba13-a8310246c567 | note | Conformance Criteria - Construction procedures saved in Construction Team Sharepoint and detailed in register
6d6147dd-ff23-59a0-90f0-99695566b1f5 | note | Frequency - Prior to works
bbc2999f-f76d-515c-8153-7442c2461dbd | note | Thiess HP/WP Check - HP
7797c642-0f5a-5b06-af1d-9511c315b41f | note | Inspector HP/WP Sign Off - WP
9a028711-23bb-4193-9607-8ddc0bae556b | signoff | WITNESS POINT
9798f2ba-d8c2-48f2-a4f5-d710b962012a | checkpoint | PC1.4 - Excavation permit
95d3c806-8063-5e27-9668-d0b242086300 | note | Responsibility - ENG
8916aac1-51a6-5ce0-8291-cb123c58ade7 | note | Test Method - Visual
f265cb18-d913-5d79-a643-61a578d8f806 | note | Conformance Criteria - Approved Excavation Permit saved in Construction Team Sharepoint and detailed in register
7f93843b-9275-5f5c-8251-435da3789f4b | note | Frequency - Prior to works
8e60b629-9f32-500e-add6-a101551735db | note | Thiess HP/WP Check - HP
0f1e7ca5-4178-5015-bfab-f0176438b559 | note | Inspector HP/WP Sign Off - WP
0793db85-0e32-4baa-a740-27bcc77097e7 | signoff | WITNESS POINT
e25f76c5-b49e-4616-8bf9-5aa7766491c5 | checkpoint | PC1.5 - Dial before you dig check
57a4f0a8-3f8d-5d0e-93ec-6e1a94d3278c | note | Responsibility - ENG
c23a4f48-c772-5fa4-9fcd-b9218b736d35 | note | Test Method - Visual
6363e9c4-d829-5d6c-afdb-b270d7ea490f | note | Conformance Criteria - In date DBYD certificate saved in Construction Team Sharepoint and detailed in register
8c0a1cb2-a6f1-5dd6-901f-16f0e1910bc4 | note | Frequency - Prior to works
81f1fe66-23c8-5d52-9a8f-401f164b4895 | note | Thiess HP/WP Check - HP
62029c75-459c-56b7-9133-1ccc3d7189c2 | note | Inspector HP/WP Sign Off - WP
f89bc0d0-c7d9-4e30-a447-98e5649ba193 | signoff | WITNESS POINT
1afaa620-9ec9-4f52-aefc-23b6fce4cf53 | checkpoint | PC1.6 - Traffic control plan
96b6c5da-dcdf-5ade-bda1-2dd57041593b | note | Responsibility - ENG
756c5fce-de98-5311-8a4b-0df638afd89a | note | Test Method - Visual
3a87cab9-fbc4-5d6a-9ce5-102913bdc911 | note | Conformance Criteria - Traffic control plansaved in Construction Team Sharepoint and detailed in register
10d26ef2-b36a-5071-bd09-c1f8a4c5e39c | note | Frequency - Prior to works
b7f85538-7ac7-5097-8cc0-77faceb9d107 | note | Thiess HP/WP Check - HP
cacb7889-fac6-52a0-bdd7-4b5e86efaec6 | note | Inspector HP/WP Sign Off - WP
c70f264d-517d-40d2-86a2-61ad62419bd1 | signoff | WITNESS POINT
8f7e8f93-0c5e-4834-ba08-0c7b3abcfb02 | checkpoint | PC1.7 - Inspection Test Plan (ITP) submitted and approved
4363e8b0-8dcd-5c88-b25a-db546e0f5a1f | note | Responsibility - ENG
5e97c6ee-75bb-5768-b9e7-ba49656e6d63 | note | Test Method - Visual
4d52017a-5463-5b85-b8a2-3490bd5784db | note | Conformance Criteria - Approved ITPs relevant to the works saved in Construction Team Sharepoint and detailed in register
d2440ea8-6546-56a1-8021-c92d68f9da8d | note | Frequency - Prior to works
7976b1a3-9bf9-5c3a-a4e8-fcf344a5ee9b | note | Thiess HP/WP Check - HP
23bd4684-ca52-5fd9-a24c-746a633febbc | note | Inspector HP/WP Sign Off - WP
89fc55c4-d4a5-4806-9cb7-b5fdd80d1182 | signoff | WITNESS POINT
92b8e7de-0df5-4bd4-84f2-ed1d9583bda8 | checkpoint | PC1.8 - IFC drawings
dc75979a-20a0-5198-8f40-76724f87d807 | note | Responsibility - ENG
5e63740a-41ee-5679-ae88-2d7a1934463a | note | Test Method - Visual
ac97cf8d-b749-5685-bf0b-1e8b850118fb | note | Conformance Criteria - IFC drawings and revisions transmitted from theThiess Technical Services team and detailed in register
4eef36e5-3799-5ded-867a-de41840304f3 | note | Frequency - Prior to works
338676cc-0a7f-5cc4-b981-b7d3d80cc0ee | note | Thiess HP/WP Check - HP
e7452242-72fe-5ea2-b8a8-5a1113f5edf5 | note | Inspector HP/WP Sign Off - WP
d8b918de-ee98-4b11-9e9b-7f7d3f6b19b1 | signoff | WITNESS POINT
d052d567-770d-41f4-afa2-c174d6f29b37 | checkpoint | PC1.9 - Erosion and sediment control plan
0a1d5052-5415-595f-8bed-9139b638007a | note | Responsibility - ENV ENG
9533c9b2-6961-53e0-87af-23d55c41ba75 | note | Test Method - Visual
0f432034-d55b-593b-ac9f-fda7d25cf71a | note | Conformance Criteria - Approved Erosion and Sediment Control Plan saved in Construction Team Sharepoint and detailed in register
0a6a815d-69fe-515d-9c35-c2add07f9b11 | note | Frequency - Prior to works
2559b787-9a4c-5975-a49f-033d91a8272b | note | Thiess HP/WP Check - HP
281a1ef7-5a88-5fc5-ad2c-eae8a63115b1 | note | Inspector HP/WP Sign Off - HP
ad97dae8-4823-426a-ac7e-5254da201e9e | signoff | HOLD POINT
0dddaa81-7464-47f7-90d2-0d5115acd6d1 | checkpoint | PC1.10 - Approved stockpile locations
06dc5854-4fd1-599c-8ef9-94764f959249 | note | Responsibility - ENG
33273c30-deca-50be-93e6-e195869ffbd7 | note | Test Method - Visual
1b9e3f79-a398-5254-9d11-bcfa22c56fbe | note | Conformance Criteria - All stockpile locations to be nominated and approved prior to commencement of activity.
c6d4ccea-a004-51f0-ad47-d7bc6d8aae81 | note | ○ Topsoil register to be maintained with information on topsoil volumes and stockpile locations.
e17e1457-fbe9-54d1-be3f-e7a481ff5179 | note | Frequency - Prior to works
1e774b75-714f-5165-a028-87be80be1650 | note | Thiess HP/WP Check - HP
599e6b3d-22bf-5c13-8c36-8fdf7f17f781 | note | Inspector HP/WP Sign Off - HP
474b6e42-eabe-40f3-bbd3-43605e9adf8a | signoff | HOLD POINT
95d44b0d-a0ff-4806-8aae-b5928f44fc01 | checkpoint | PC1.11 - Embankment fill materials
fdb76142-99c9-55c7-8098-97b80702bf80 | note | Responsibility - ENG
7ccde0eb-d330-5eb3-b587-f42d4c1dd53c | note | Test Method - Visual
f7c7398e-42e6-5c31-941a-f186e2b66f19 | note | Conformance Criteria - Embankment fill materials have been approved for use and in accordance with the requirements in the specification.
19f448f4-3314-5630-99f5-74a35dde96f6 | note | ○ General fill material as per Table A3-1 Cut/fill material properties in the specification:
40acf6ee-7928-5d79-90bc-c98badb4606c | note | ○ Less than 30% passing 0.075mm sieve
57c7c285-386d-5bc9-8fae-e6450218c790 | note | ○ Liquid limit 20% to 60% Soaked CBR = or >3% (STD compaction @ OMC)
ead91126-8b1c-5b92-aae2-945b752557a7 | note | ○ 1 test per 5,000 m3
9193395c-6e53-549e-b314-3ef8a4544b39 | note | ○ Subgrade replacement material CBR10.
4a1f5779-21c3-55d4-85f7-6eaafb7b52ef | note | ○ Select Fill as per the details in Table A3-2 Select fill material properties & Table A3-3 Select fill grading envelope.
eabb899f-69c7-5124-96f4-33e7fbce683c | note | Frequency - Prior to works
64d2f340-b7fd-5a5a-9b03-ae4d09f98563 | note | Thiess HP/WP Check - HP
89ebe463-c0f5-56bd-a9d4-f58461278a09 | note | Inspector HP/WP Sign Off - WP
e97f3805-6609-4c7a-847e-469d22f8c748 | signoff | WITNESS POINT
07aecab2-8e27-4719-bd19-1c267e693f81 | checkpoint | PC1.12 - QA close out
e1e833cd-7a61-51eb-9747-58e7ce7a1842 | note | Responsibility - ENG
be630aec-8448-550b-9b22-0ad6f23eb76d | note | Test Method - Visual
b1ce9316-1d43-56d0-8f25-dcfa9c5697e2 | note | Conformance Criteria - Works completed and update ITP/Lot register/MDR and close out of GDP
0fda6c46-7778-5ac7-8a3e-e4554528dc37 | note | Frequency - As required
4f7f58c0-5220-5a52-ac2b-a5fcf91bacee | note | Thiess HP/WP Check - HP
8b1a8832-b0d6-5ba8-b862-009772c75ad2 | note | Inspector HP/WP Sign Off - HP
14d0655d-3699-4033-bf1d-d54efd28e116 | signoff | HOLD POINT
6796a4b7-50fd-4c6d-82a5-85be75cf9074/1 | checklist | ITP-001 Clear & Grub | itp | ITP-001 Clear & Grub | 46 | 09146b29-0bbc-45fa-b79f-41f151a9fd72
65c63129-50bb-463f-92ee-20d59b94b854 | section | Clear & Grub
489aefec-c9f3-4977-a3a2-44421446c676 | checkpoint | GC1.1 - Underlying lot & ITP signed off and conforming
98434abf-234a-51f2-b704-be1a9de86c51 | note | Responsibility - ENG
a024fe55-4ba9-5fc2-90b0-30f84dcbf2ab | note | Test Method - Visual
c07fbf52-8dec-534f-86e3-08b175a65330 | note | Conformance Criteria - Pre-construction lots closed out
e1d80108-10e4-512a-8cc8-0f00f2bac03b | note | Frequency - As required
f9e55d9e-59ba-5f88-bb29-b5db805daafa | note | Link to ITP - PC1.19 | Link to ITP - PC1.18
| checkpoint | GC1.2 Survey of Natural Surface | insert
responsibility - Survey
Conformance Criteria - Check survey pick up of work area and digital file saved in Construction Team Sharepoint and detailed in register. Surface area shape file created and uploaded to Qfield
fca88b3e-0751-4e64-9fb1-95b6b63e64e1 | checkpoint | GC1.2 - Ground Disturbance Permit (GDP) | Delete
978d432b-1bf4-5a25-966a-0242c9412fc0 | note | Responsibility - ENV ENG | Delete
27d61d67-c12f-5e77-8a4c-768e9625f3ae | note | Test Method - Visual | Delete
be5d205a-b9ff-54d1-b330-aa333b7d1c1d | note | Conformance Criteria - Approved GDP saved in Construction Team Sharepoint and detailed in register | Delete
7633d20b-f11f-5995-86cf-aed4deaa66cb | note | Frequency - Prior to works (Check if this has already been completed at ITP Pre-construction stage) | Delete
745df801-8762-5343-9bc5-24556ea12758 | note | Link to ITP - PC1.15 | Delete
cb5ab8ae-d69c-5ee2-91ca-0800fc89d36b | note | Thiess HP/WP Check - HP | Delete
8a408bda-3df9-5830-9111-e26350854a3f | note | Inspector HP/WP Sign Off - HP | Delete
cfb9396b-4caa-4b96-929a-0a16ccc834e0 | signoff | HOLD POINT | Delete
266269d8-b950-43e5-8543-c2b3eab8d43e | checkpoint | GC1.3 - Cultural Heritage(CH) Clearance Survey | Delete
b8f79f88-33e3-5a43-b05c-403c36639c7b | note | Responsibility - CH | Delete
0e203685-3016-5af6-ae94-1d263da12700 | note | Test Method - Visual | Delete
a4a19328-b1b2-510d-9b2e-07f9784576c8 | note | Conformance Criteria - Approved CH Clearance Survey saved in Construction Team Sharepoint and detailed in register | Delete
c93283a8-55f9-53e7-8163-c2de509c1163 | note | ○ Areas of CH clearly demarcated | Delete
f57d0f4b-5423-5a20-8558-e37664f08df1 | note | Frequency - Prior to works (Check if this has already been completed at ITP Pre-construction stage) | Delete
5f20b016-d0b5-55d5-9184-cb86e8b0f012 | note | Link to ITP - PC1.14 | Delete
3896cd71-e6fa-58cb-bd16-2acb3c739ffd | note | Thiess HP/WP Check - HP | Delete
3ca3b303-baf1-52c4-9ef1-cdd42acdb33e | note | Inspector HP/WP Sign Off - HP | Delete
8a8883cc-c2ec-4e86-ba9b-57c2adc9e3ee | signoff | HOLD POINT | Delete
119b407c-9217-4c0c-9ca3-9c66f881bd0d | checkpoint | GC1.4 - GDP survey set out | Delete
dce5e84f-f9f2-540a-b62f-aa2e935083b3 | note | Responsibility - SURV | Delete
92afeb73-849d-514d-8ef0-6bddcb23b669 | note | Test Method - Field | Delete
0b6a5774-e8fd-55f9-a4a9-84135097e415 | note | Conformance Criteria - Area of works pegged and clearly defined to GDP. | Delete
6c7911b2-c9c9-5950-b9f3-592c22486d25 | note | ○ Clearing pegs installed at nominal intervals to ensure no over-clearing. | Delete
19446839-e2f6-53e7-82b8-ec70f940c706 | note | Frequency - Prior to works (Check if this has already been completed at ITP Pre-construction stage) | Delete
d1727a01-d642-5cc9-8818-87157736286c | note | Link to ITP - PC1.16 | Delete
52904e09-81dc-5864-859a-f401f642031c | note | Thiess HP/WP Check - HP | Delete
ee42d4d2-bc79-57b9-b00e-e5f7974afa85 | note | Inspector HP/WP Sign Off - WP | Delete
13e9538e-221b-4fc7-ae63-d227ec979ef1 | signoff | WITNESS POINT | Delete
6055ae09-38c0-4d75-8692-5490848b29c6 | checkpoint | GC1.5 - Survey of pegs to confirm correct GDP survey set out | Delete
451f8ff7-04fc-5756-a7c9-a1f2fef60040 | note | Responsibility - ENV | Delete
27c69dcb-afc4-5a17-8f63-f9fccc4fff1e | note | Test Method - Visual | Delete
6b68dcd0-e127-5bed-87ab-be08f8b3bdcf | note | Conformance Criteria - Pegs to be surveyed and sent back to the engineer. This is then to be confirmed by the environmental team | Delete
979643f1-6d72-55b7-b267-312537028d54 | note | Frequency - Prior to works (Check if this has already been completed at ITP Pre-construction stage) | Delete
47065cb1-ead6-58cf-b42e-7491e23ea648 | note | Link to ITP - PC1.17 | Delete
85315615-bbb5-5426-849c-3c10a3947590 | note | Thiess HP/WP Check - HP | Delete
1d4cb4c3-398d-5b5c-bc2f-2ad264f00d6b | note | Inspector HP/WP Sign Off - WP | Delete
a7e84b21-dcff-49c6-b00b-58e21ae71760 | signoff | WITNESS POINT | Delete
3964e4a0-038f-4c0c-8288-e14042cae2a0 | checkpoint | GC1.6 - Survey natural surface | Delete
5888dfc7-fbf2-59fb-968c-3a9227538bd5 | note | Responsibility - SURV | Delete
31390e86-a343-59bf-89eb-e1b35e6b183d | note | Test Method - Field | Delete
5ec29348-8393-5210-a775-b08b034326fc | note | Conformance Criteria - Check survey pick up of work area and digital file saved in Construction Team Sharepoint and detailed in register. | Delete
b54d678d-e8cf-58fe-aea6-cc2cd8c4e7e8 | note | ○ Surface area shape file created and uploaded to Qfield | Delete
c56aca32-35c2-53f2-a49c-e32d9049ce9f | note | Frequency - Prior to works (Check if this has already been completed at ITP Pre-construction stage) | Delete
7b985af9-5568-5ffd-8af8-403e5eb641de | note | Link to ITP - PC1.9 | Delete
494a4c99-c566-5b31-bad5-c426312d71b2 | note | Thiess HP/WP Check - HP | Delete
46aa4abd-5343-5354-818e-cedd5ce47aef | note | Inspector HP/WP Sign Off - HP | Delete
70bca751-c0f6-4cff-adff-6dbb5d00d58a | signoff | HOLD POINT | Delete
63f12227-eb41-494e-838a-7d5b664e38ff | checkpoint | GC1.7 - Fauna Spotter Catcher (FSC) Pre-Clearance Survey | Delete
405c2945-db79-5dbd-be91-2f679f7767e4 | note | Responsibility - ENG | Delete
1422c724-163c-5156-bca5-5d837c6a6a6e | note | Test Method - Visual | Delete
172902e2-5637-5499-bdef-8ca418fbe155 | note | Conformance Criteria - FSC pre-clearance survey completed within 2 weeks of construction. | Delete
50912c86-e7d6-51e0-ab93-5c320d6e4154 | note | ○ Habitat vegetation, threatened species demarcated. | Delete
17ce7cd5-86f2-591e-8dd4-3d61d8a0d7a3 | note | Frequency - Prior to works (Check if this has already been completed at ITP Pre-construction stage) | Delete
984fb003-8603-5061-b15b-3893a5445bcf | note | Link to ITP - PC1.13 | Delete
bb372c82-2c7e-5055-89b3-098f9b6d897b | note | Thiess HP/WP Check - HP | Delete
e866b3f2-05be-5635-b01c-137d88a97720 | note | Inspector HP/WP Sign Off - HP | Delete
7d15fd4b-0569-4ef4-9355-92f207ac998e | signoff | HOLD POINT | Delete
b9a47c3d-acaa-46a8-a5f1-c6f2a00bd24a | checkpoint | GC1.8 - Mandatory GDP Pre-Clearing walk | Delete
d6720244-96ce-5b56-b3f0-c10db1cc3706 | note | Responsibility - SUP OP ENG ENV | Delete
5d409e5b-dc2a-56a0-8272-3865a72fa972 | note | Test Method - Field | Delete
1a74e138-0dca-584f-9941-1b0680245e5d | note | Conformance Criteria - Walkthrough with FSC, Supervisor, Surveyor, PM or Senior Engineer, operations that will be undertaking the clearing | Delete
261187f5-9219-5bb8-9157-20435b52d7f2 | note | Frequency - Prior to works (Check if this has already been completed at ITP Pre-construction stage) | Delete
d4ec68cf-6bc8-58d4-b816-c05ae99b3ea9 | note | Link to ITP - PC1.18 | Delete
84c1612e-a9e7-53ee-a41e-7f6105eec780 | note | Thiess HP/WP Check - HP | Delete
f5cd13cb-fc71-5e52-a9a5-133ebe733e51 | note | Inspector HP/WP Sign Off - WP | Delete
770649e0-e1bd-44b7-92f3-f827029b4c07 | signoff | WITNESS POINT | Delete
96356e00-b597-41a7-be38-ca41842ab0df | checkpoint | GC1.9 - Clearing of vegetation | GC1.3
4ad76604-a732-5f00-9202-8b479ba6a09f | note | Responsibility - SUP
160b8fc7-a7f6-5d83-b268-e1aaa26d4321 | note | Test Method - Visual
afd40b38-8546-5d46-b008-32e8c6f6d1f4 | note | Conformance Criteria - FSC individual on site at works during clearing operations.
b0a60139-c641-5810-8191-a3b4d22dfebe | note | ○ Habitat vegetation, threatened species and cultural heritage areas demarcated
b69d176b-96b4-5d45-9aa2-af9173cac2d2 | note | Frequency - As required
b596ec02-f4aa-5645-a935-4d7777f98606 | note | Thiess HP/WP Check - HP
d24f16aa-677d-5eb7-b1c3-48d78cc9f8c4 | note | Inspector HP/WP Sign Off - WP
a7af8165-3a25-45f7-b0f4-c5c6827e3060 | signoff | WITNESS POINT
2ffd8602-4159-4631-b51f-fb50d097b50f | checkpoint | GC1.10 - Stockpile Cleared Vegetation | GC1.4
6ee3953f-8735-54f5-89e5-f208aec95df3 | note | Responsibility - SUP
dd7b1d88-2f7f-5ad0-9131-e4a6399a168c | note | Test Method - Visual
92ca0ab2-2216-5ca8-a440-49b9a542ab8f | note | Conformance Criteria - Cleared vegetation loaded and hauled to approved stockpile location
3387fd36-cd13-5095-87ff-d7937b609226 | note | Frequency - As required
3563f903-fe3e-5750-9c03-7bb8024f8ce7 | note | Link to ITP - PC1.11 | Delete
8ad94a31-975a-5c99-8ca0-6636fb57e981 | note | Thiess HP/WP Check - HP
10a24508-4e40-532b-9d55-58c51ec51adc | note | Inspector HP/WP Sign Off - WP
aaf1e0b1-b8f8-426f-bf9f-6bb0df391867 | signoff | WITNESS POINT
668916bf-b68c-4a79-a23e-e790bbe46f1c | checkpoint | GC1.11 - Erosion and sediment control | GC1.5
be16683f-6acc-519f-8e55-b4bc294ff9f9 | note | Responsibility - SUP
46dfae90-06f8-5f4e-857b-bfd837333e53 | note | Test Method - Visual
c6dd806e-baa9-5e10-a07e-51f568dd4282 | note | Conformance Criteria - Erosion and sediment control measures to be implemented whereever possible after clearing has been completed.
27238811-fa23-5cb2-b8af-a292a3025dce | note | Frequency - After clearing
62509e03-b70a-5049-a275-c2aacb3714ae | note | Link to ITP - PC1.10
3c1a6503-66f6-5eb7-be27-47b33e6a9cfb | note | Thiess HP/WP Check - HP
65e4534a-f135-5b93-bd94-cb77a4b83a92 | note | Inspector HP/WP Sign Off - HP
fa877d86-55e1-456c-9e59-c94fd9b13286 | signoff | HOLD POINT
15100512-873e-4694-b8bb-6ae6e682538e | checkpoint | GC1.12 - QA close out | GC1.6
2123b05c-fda5-5cef-ba89-eb0e7e09d771 | note | Responsibility - ENG
7cbe0163-db58-5298-a5ce-55e4205257e2 | note | Test Method - Visual
e3dfd798-8daa-5d94-a78e-aefcba19b2f1 | note | Conformance Criteria - Works completed and update ITP/Lot register/MDR and close out of GDP
c975079d-ffaa-54ef-8b9d-b3003d95f4a0 | note | Frequency - As required
da06f814-8fbd-5785-9bc4-6286327f6abb | note | Thiess HP/WP Check - HP
aac6fe69-eb96-56eb-87d9-32d99c7afd4c | note | Inspector HP/WP Sign Off - HP
12b79af7-f40a-4688-b33d-60e2db049043 | signoff | HOLD POINT
b86ac2fb-a936-4959-bc2c-0b212ce6cb6a/1 | checklist | ITP-002 Topsoil Stripping | itp | ITP-002 Topsoil Stripping | 46 | 1ad683bf-34bc-41ff-b5dd-224cfd3bdf1d
8749f0ea-dcaf-40a1-a9fb-38172bde624a | section | Topsoil Stripping
916380c8-3601-4c5d-aaec-d8f5ce265520 | checkpoint | TS1.1 - Underlying lot & ITP signed off and conforming
ae37fa4e-a8c8-5621-99d3-c3093ffbd813 | note | Responsibility - ENG
eaa1749a-e2ec-5b85-8edd-42ddd734d8a2 | note | Test Method - Visual
dae7b959-a92f-50a9-80f0-f8e4f50ef610 | note | Conformance Criteria - Clear & Grubbing ITP closed out
eeadea39-f306-52fc-83e8-4c96215d2126 | note | Frequency - Prior to works
b23b17a7-7376-533d-9afe-1423f0cb849c | note | Link to ITP - GC1.12 | Link to ITP - GC1.6
6c621a60-d7a2-4f30-86cf-79266b7cfff1 | checkpoint | TS1.2 - Survey Set out
a04a85f3-030f-5947-93a2-83065c379130 | note | Responsibility - Surv
b0740eeb-b1e8-565d-b6bb-e79334e3c6b7 | note | Test Method - Field
8795b855-e66e-55e4-ae20-2c067a367fa7 | note | Conformance Criteria - Areas of work to be set out by surveyor and/or models in plant
c707d4ab-6d68-5bb7-aa60-78dc74f21831 | note | Frequency - As required
225fa33d-4b6f-5408-b2e1-861b17ce1c7b | note | Thiess HP/WP Check - HP
c0fab7ed-3a57-510c-99ca-1308ec25b414 | note | Inspector HP/WP Sign Off - WP
92c3d114-4ca0-4687-9ab6-1be8c3bbaf48 | signoff | WITNESS POINT
ef0f707e-77c6-47e0-b7b6-f00e62939a07 | checkpoint | TS1.3 - Strip topsoil, load & haul to approved stockpile location
944babb1-ca24-540f-903e-b2314fa26865 | note | Responsibility - ENG
a591edf9-2637-5776-97cf-4ac30f68fd7f | note | Test Method - Visual
93eddc67-b978-54f9-8611-85f084d83259 | note | Conformance Criteria - Provisional depth of topsoil strip shall be 100 mm unless shown otherwise on the drawings.
8e938ca4-1f2e-543e-b9b6-75e0ac18fd76 | note | ○ Stripped topsoil loaded and hauled to approved stockpile location.
e13284e2-f46f-585b-bcd5-00fe9807e382 | note | ○ Stockpile locations located minimum 40m from watercourses and not exceed 2m in height.
48714638-6934-566f-8a20-7f697f7d162d | note | ○ Native seeding of topsoil stockpiles as agreed with Company.
e05858cc-a4bd-5b6a-9caf-8cde8db7aa22 | note | Frequency - As required
9463ad6a-351e-5eee-973e-cc0598eb1f1c | note | Link to ITP - PC1.11 | Link to ITP - PC1.10
10901a46-aadc-5279-b7e6-6b0eef29320f | note | Thiess HP/WP Check - HP
cabcfed7-1ef9-558c-b8c6-22527fc21bc5 | note | Inspector HP/WP Sign Off - WP
d2bc2732-0651-43bb-8cb4-971bf9e1c4ff | signoff | WITNESS POINT
071da937-196f-4dbf-ac54-4880807d9d2f | checkpoint | TS1.4 - Topsoil location, destination and quantity catalogued.
2f69d885-0944-5510-bc4d-b099d07f8d6e | note | Responsibility - ENG
76b50feb-f81f-5024-9cc6-1a08b9096a8d | note | Test Method - Visual
cfd53ca6-93ea-522e-990b-36f528577392 | note | Conformance Criteria - Topsoil register to be maintained with information on topsoil volumes and stockpile locations
9fef3602-e591-50a2-8b1e-b28b30b00301 | note | Frequency - As required
de9b897a-7bf0-558d-a79a-ab5d0a872b6e | note | Link to ITP - PC1.11 | Link to ITP - PC1.10
4278a0ee-23c0-5b19-8a90-69a59d37c005 | note | Thiess HP/WP Check - HP
d7122674-faca-594e-887a-749570912de2 | note | Inspector HP/WP Sign Off - HP
05dccf20-f68b-4781-954e-06157df5e77b | signoff | HOLD POINT
c6e48c99-ba54-4abd-bc57-c3bcd1e665fd | checkpoint | TS1.5 - Surface level check and survey pick-up
765c1ef7-26db-5fcb-81b9-462bb14fbba4 | note | Responsibility - SURV
6503a485-f9c8-558d-811b-469336ece816 | note | Test Method - Survey / Field Test
64c8342e-8aae-5f7c-a4e3-df39e8aecf3b | note | Conformance Criteria - Stripped surface level picked up as per Table 10 C15 (DXF file format, volume calculated and filr saved in Construction Team Sharepoint and detailed in register
162e926d-aa9c-5849-b1af-ef6f44f75ea6 | note | Frequency - As required
2ed18220-a06f-52d7-9f65-00887d5aad21 | note | Thiess HP/WP Check - HP
9e188d56-9fad-5d14-b173-8c642a6c6397 | note | Inspector HP/WP Sign Off - HP
af4ae563-b4e9-47a2-a180-1d478211e8ec | signoff | HOLD POINT
ae6c69bd-ecc2-454a-9bff-6080c8c1c94a | checkpoint | TS1.6 - QA close out
8efc1984-16d2-53ba-a057-5431c08fd38b | note | Responsibility - ENG
0e4486bc-38e8-544f-ac30-fb17669c1687 | note | Test Method - Visual
c7e83a05-827a-55ab-a626-c824caa8593d | note | Conformance Criteria - GDP permits closed. ITP closed. Approved MDR.
d228505a-fca4-59be-b984-2e29b12b43a9 | note | Frequency - As required
e910bce3-f30b-59aa-b87d-43474fc1cf31 | note | Thiess HP/WP Check - HP
ef4ec3ef-ada0-5aae-b30f-6405d1fe60ab | note | Inspector HP/WP Sign Off - HP
5e2f8d5f-e7ee-48e0-844a-1e4cf9f054a9 | signoff | HOLD POINT
1e0915ac-c4f2-4889-bc14-8ff55ed38f8d/1 | checklist | ITP-003 Subgrade/Foundation Preparation | itp | ITP-003 Subgrade/Foundation Preparation | 49 | 82469385-fe81-434a-891a-69a60d614f18
3888cb15-c6e9-4774-94f4-ef0136a8d2b8 | section | Subgrade/Foundation Preparation
ac475546-f2ce-4c02-a316-d1bc173edfa8 | checkpoint | SP.1.1 - Underlying lot & ITP signed off and conforming
0ba38702-7e4a-5305-999e-9d0c380b72b1 | note | Responsibility - ENG
cd2dc35a-9502-5741-8b68-f7ea4a27f70c | note | Test Method - Visual
cdae2c66-de7c-5ca1-aaa5-1dcaadf88613 | note | Conformance Criteria - Topsoil ITP closed out
39fb73af-ee7e-5cfb-a384-6dabf3434961 | note | Frequency - Prior to Works
8ee4a552-2995-58d0-9e48-752e910a3518 | note | Link to ITP - TS1.6
2897bed4-d43c-43af-aa95-e7d21d62accd | checkpoint | SP.1.2 - Embankment fill material
6698839b-9391-5658-8be4-54b8641f1d75 | note | Responsibility - ENG
afc74dae-bdf5-5e03-929d-edad53d7c4be | note | Test Method - Visual
e98679c2-b70a-536b-9a9c-bef3a3d5405e | note | Conformance Criteria - Ensure CBR10 subgrade replacement materials have been approved for use and within specification
6171a00d-a560-5761-b6c3-27e3f1536543 | note | Frequency - Prior to works (Check if this has already been completed at ITP Pre-construction stage)
cd5ca6cd-ecd1-5805-9164-3664d4d56063 | note | Link to ITP - PC1.12 | Link to ITP - PC1.11
8ebc67a8-3f8e-5cfc-aa2c-2ab9989333fa | note | Thiess HP/WP Check - HP
c22e0b29-ee08-5f77-a31c-95c7a96e983a | note | Inspector HP/WP Sign Off - WP
e6f51fb7-6c5b-4f3e-b073-2d76ec83af4c | signoff | WITNESS POINT
f18384a0-36b1-404a-ba16-b643c5ba2214 | checkpoint | SP.1.3 - Survey Set out
4b25c72b-e94d-529d-aa6b-3835cde661fb | note | Responsibility - Surv
6db7605f-6648-5850-b3e9-c41e7f2cfe70 | note | Test Method - Field
d0b3b03b-7fa3-511c-b9b7-9c1db665c392 | note | Conformance Criteria - Areas of work to be set out by surveyor and/or models in plant
662d8646-ee30-5fd1-9ce4-7ccc7f1318a9 | note | Frequency - As required
57f8ebaa-8d19-5e99-8c43-2d16b8aff760 | note | Thiess HP/WP Check - HP
45364d23-92d3-5007-895d-5930c2185259 | note | Inspector HP/WP Sign Off - WP
4d57dd0c-68ce-48ab-bd54-2cee86b3fca9 | signoff | WITNESS POINT
dbba825e-74ac-4f55-a21f-fc1ed370c529 | checkpoint | SP.1.4 - Removal and replacement of unsuitable material
747e0dbf-fcba-5695-b1a3-01b9361dabf7 | note | Responsibility - SUP
30352755-f0c8-5be8-bb2c-b08aec36a9b4 | note | Test Method - Field
21dbc2ce-af3d-5371-a91b-5b924c2fdfbc | note | Conformance Criteria - Determination of unsuitable material by the Level 1 GITA or Inspector (Sedgman) is required prior to the removal of any unsuitable material. Unsuitable material criteria is in the specification.
e4d39c20-3fe5-5de7-bc69-b4f7f854c5fd | note | Frequency - As required
153058c6-af8e-59bf-ba0a-0d361dab80d0 | note | Link to ITP - PC1.12 | delete
c84d290d-5958-537c-9c8e-48a52d608cc3 | note | Thiess HP/WP Check - HP
47ac2868-dfa4-5963-aa63-9fdf4d28309a | note | Inspector HP/WP Sign Off - HP
abc7c254-a1c2-4d1e-a2cc-9dda06113411 | signoff | HOLD POINT
bf2a450e-c73d-4e58-b6c5-f8d0ad38ec50 | checkpoint | SP.1.7 - Proof rolling | SP.1.5 Proof rolling and soft spots
6ac50545-6961-5f6e-9358-6a0ee1fb360f | note | Responsibility - SUP
c709b948-1ca6-56d0-9cf6-aefd7aedbedc | note | Test Method - Field
c378f6ef-6f7b-516a-8e9d-004032c7b05c | note | Conformance Criteria - Proof-roll subgrade/foundation surface prior to placement of embankment fill. Proof roll under a standard 8 tonne axle load or 10,000L water cart or heavy self propellled smooth drum roller dynapac 620D or equivalent to confirm that, in the Inspector (Sedgman) s opinion, deflections are negligible | Proof-roll subgrade/foundation surface prior to placement of embankment fill. Proof roll under a standard 8 tonne axle load or 10,000L water cart or heavy self propellled smooth drum roller dynapac 620D or equivalent to confirm that, in the Inspector (Sedgman) s opinion, deflections are negligible. Any soft spots identified shall be scarified, aerated and recompacted with moisture near optimum.
3a550ce8-816b-5397-a561-01745103d955 | note | Frequency - As required
ffbdbde8-4eed-59a2-a503-187d9143d7f6 | note | Thiess HP/WP Check - HP
118fb4dc-b6f4-5712-8aa5-f3abc584a348 | note | Inspector HP/WP Sign Off - HP
6e4cdf2a-ea9e-4e8c-aef7-9e25439a1400 | signoff | HOLD POINT
4fd12e0e-f712-429a-8540-2f342f7bb820 | checkpoint | SP.1.5 - Subgrade/Foundation preparation | SP.1.6
53ba4411-a5de-531c-961b-c446ae05e42d | note | Responsibility - SUP
d0ce048c-197d-5912-80e4-60df6073967c | note | Test Method - Field
36fa4a64-d46f-5f5c-ba5f-c800dda0a565 | note | Conformance Criteria - Foundations for embankments to be ripped 200m deep, moisture conditioned then compacted. Density requirements: < 300mm from finished level under roads & structures minimum RDD 97%, all other areas and depths RDD 95%, moisture content -1% to +2%, normal level of testing 1 test per 500m3, reduced level of testing 1 test per 1,000m3. | Conformance Criteria - Lightly tyne the subgrade/foundation immediately prior to placing embankment fill.
aa96d8ee-81e4-5cf0-9311-27c35702a144 | note | ○ All material exposed in cuttings at subgrade level minimum CBR 3 or DCP 150kpa. If CBR2: Remove & replace with CBR10 select fill 150mm deep. If CBR1: Remove & replace with CBR10 select fill 250mm deep | All material exposed in cuttings at subgrade level minimum CBR 3 or DCP 150kpa. If CBR2: Remove & replace with CBR10 select fill 150mm deep. If CBR1: Remove & replace with CBR10 select fill 250mm deep.
0d516928-6b59-57fe-b7ca-1ee4b1414d64 | note | Frequency - As required
7ad79ff9-eae9-5987-9e5b-82402f192491 | note | Link to ITP - PC1.12 | delete
ed5e1566-2280-51c3-be8e-1eb5461ee755 | note | Thiess HP/WP Check - HP
0e74b08d-944f-5d4f-a1a0-598735ce57d8 | note | Inspector HP/WP Sign Off - HP
c760cec8-8ceb-4a0d-a985-5324d40c2be8 | signoff | HOLD POINT
187efc59-29ad-49ed-8390-8b60becf1967 | checkpoint | SP.1.6 - Trim subgrade | SP.1.7 Trim subgrade in cuttings
b3913e7c-bebc-5d12-9a25-bb41ac3c832f | note | Responsibility - SUP / SURV
ae93ba34-1d60-5116-972f-c6a9676fd814 | note | Test Method - Field
a76edf78-b419-5b0e-8f24-353676836a66 | note | Conformance Criteria - Trim all subgrade to the lines and levels shown on the drawings in accordance with the following tolerances: Top of bulk earthworks +/-50mm; Road subgrades & under buildings & structures +0mm to -25mm.
549c5914-07e3-55e7-bad0-0bbf1fce3fab | note | Frequency - As required
ffcc823b-be30-5129-a036-a226605a90d8 | note | Thiess HP/WP Check - HP
f45a1c01-4b58-5b13-93cd-bdb9bab52ee2 | note | Inspector HP/WP Sign Off - HP
f23b4a57-60f2-4a1f-bbca-c06f05da3796 | signoff | HOLD POINT
71594be2-04a9-4642-8c27-46fc02041e66 | checkpoint | SP.1.8 - Surface level check and survey pick-up
ae3e3dc0-bbb7-5161-ab48-8f3e93da7c89 | note | Responsibility - SURV
0233e3da-d7b0-57cb-a28f-791670b10318 | note | Test Method - Survey / Field Test
181a65b6-888f-5718-abc5-1c5ea421f1f5 | note | Conformance Criteria - Surface level picked up as per Table 10 C15 (DXF file format, volume calculated and filr saved in Construction Team Sharepoint and detailed in register
8205adaf-59f9-5e9c-94e0-2407ce8f2386 | note | Frequency - As required
816da858-ab98-54c1-b51c-3cfa04e1791f | note | Thiess HP/WP Check - HP
8fd83ed0-b72c-5af0-9b4a-dc40044dbcee | note | Inspector HP/WP Sign Off - HP
4bcc759d-350a-4250-8f6b-244794b056e2 | signoff | HOLD POINT
cf8c9bf4-266f-4abf-8026-2827cb980a71 | checkpoint | SP.1.9 - QA close out
f480ed2e-dad9-5d6f-bd96-060b4d89131c | note | Responsibility - ENG
1a40051b-4408-5dcb-b87a-220c77689e1a | note | Test Method - Visual
f5308beb-802e-5f5c-af91-fc47fbd956cb | note | Conformance Criteria - GDP permits closed. ITP closed. Approved MDR.
5dd34aff-46bd-5dab-b2af-b6da8a1c725f | note | Frequency - As required
348d3807-5f57-5b32-ba96-d3d360a60099 | note | Thiess HP/WP Check - HP
b9692b12-b245-507c-a77b-b367d15bbc3d | note | Inspector HP/WP Sign Off - HP
fe791962-27f7-473b-bde7-91e7f40b4125 | signoff | HOLD POINT
010e0c6d-951b-4ef9-941a-9ea0f881fde8/1 | checklist | ITP-004 RCP Installation | itp | ITP-004 RCP Installation | 48 | b601106e-1666-4571-92e8-00c48736fbfd
bcd810f0-bd1c-493c-a0f7-4aa16e546710 | section | 1.0 Pre-Construction
1b3a1513-b678-4b99-b6d3-43cc70619a41 | checkpoint | RCP1.1 - Drawings supplied most current IFC | DELETE
a4aacebf-171b-5589-81ef-e7db3359c74e | note | Responsibility - ENG | DELETE
df665c3b-ed53-581f-a541-00db45ac308e | note | Test Method - Visual | DELETE
8a2663ba-3a19-5fbd-a510-b4447a77b6af | note | Conformance Criteria - Reviewed drawing register | DELETE
e1fc5ac9-094e-5c3f-b9b8-6a1cad559c19 | note | Frequency - Prior to works | DELETE
dc6fe15c-1fb7-58ab-bd9c-70e33c087ca7 | note | HP/WP - HP | DELETE
78a3b4cb-df5e-4259-bd01-0d06330e8e78 | signoff | HOLD POINT | DELETE
a3ff5f79-821c-4bbc-8a0d-c574a2deea4b | checkpoint | RCP1.2 - Define RCP ID | DELETE
bd3ab7df-c91e-50ed-9c41-b6c6b564eeb1 | note | Responsibility - ENG | DELETE
f2cd55c9-a1ad-5d00-8b04-cfdea5a6ddcc | note | Test Method - Visual | DELETE
7a92402f-d212-5ba3-932f-a049223bbf1a | note | Conformance Criteria - Inspection Register. Allocate ID for reinforced concrete pipe, define work area | DELETE
3eabb13e-a5fc-55d1-9e5e-0c2304fa3e88 | note | Frequency - Prior to works | DELETE
01fa1a7c-777c-5326-96dd-c13febbaac90 | note | HP/WP - HP | DELETE
9b40fdda-d960-4284-a862-8dfb98171065 | signoff | HOLD POINT | DELETE
e2eaff84-907c-4e99-a499-7f1652a18357 | checkpoint | RCP1.3 - Lot Register/ WBS submitted and approved | DELETE
9d4aa403-6f6a-56b3-9372-ec231ffee1e7 | note | Responsibility - ENG | DELETE
64c2a9f9-6b2b-5b57-8a32-fb3bd9d4174e | note | Test Method - Visual | DELETE
ba7ba610-14b2-5188-a1e6-92386ddc6c3c | note | Conformance Criteria - Approved WBS | DELETE
17885f00-406b-5763-9247-ed7adbacc4bf | note | Frequency - Prior to works | DELETE
5adf77d9-fa43-553f-82e4-d6e8eb9048d2 | note | HP/WP - WP | DELETE
ca05ac74-ea8b-45d4-83f9-bab5020bb454 | signoff | WITNESS POINT | DELETE
eee4d041-394d-4bdc-9161-bd3ffe86de15 | checkpoint | RCP1.4 - Underlying lot & ITP signed off and conforming | DELETE
7e277ac4-11ad-5e40-9244-52e7e58a8071 | note | Responsibility - ENG | DELETE
0c8f7f10-d540-5ed9-a151-284222351156 | note | Test Method - Visual | DELETE
f0367775-9636-538b-b3e2-cfee1452cc27 | note | Conformance Criteria - Subgrade prep ITP Signed | DELETE
4627fa70-eb8e-5276-a9f6-2e41cf56ff42 | note | Frequency - Prior to works | DELETE
b5bb2635-6b24-5837-88d6-392ed9200951 | note | HP/WP - HP | DELETE
6ae1236e-00fd-41d0-adcb-7fe315b39cb5 | signoff | HOLD POINT | DELETE
9fd03587-637a-44af-9e2e-3403e67262d6 | checkpoint | RCP1.5 - Certificate of compliance for RCP Material | DELETE
8ba8d961-bcba-575b-a70c-8221d691db4a | note | Responsibility - ENG | DELETE
fb518153-c4c9-599d-9784-df1212063dd3 | note | Test Method - Written | DELETE
5fa30fd3-a30c-5c0d-b147-18f8f133a4fc | note | Conformance Criteria - Supplier to provide certificates indicating manufacturing processes, materials, thicknesses, classes, and diameters (Only culverts with materials & dimensions complying with the culvert schedule & specification to be used). | DELETE
8cf8f6f2-49a8-5b2f-8d01-435496f6c210 | note | Frequency - Per pipe | DELETE
dadf5e5f-dbe9-5839-8f7c-dce6dde67535 | note | HP/WP - HP | DELETE
b344cfc7-f523-4fa2-80a8-9b815274c179 | signoff | HOLD POINT | DELETE
21e2741c-a798-4e5a-98ea-a31953dcc9a3 | checkpoint | RCP1.6 - Inspect reinforced pipe culverts for damage | DELETE
510ea7b2-1f35-5a8c-be2d-a617092ba77b | note | Responsibility - ENG/SV | DELETE
3307ff91-9395-5339-ae22-fed4c21b27b9 | note | Test Method - Visual | DELETE
c605fc15-0b95-5237-bf71-4fad6d6f87ef | note | Conformance Criteria - Prior to installation, Pipes are checked for damages and accepted/rejected and documented on Incoming Goods Inspection form | DELETE
b707dbed-6891-5e5f-996b-f590d76e0587 | note | Frequency - Per pipe | DELETE
fc05bda0-7cfd-566c-b319-df86a9634428 | note | HP/WP - HP | DELETE
17ecaae1-e8c3-400e-ae7e-b91084f51cfa | signoff | HOLD POINT | DELETE
da327277-4581-4fec-9efc-c9ce2dfc1626 | section | 2.0 Construction | DELETE
5f99f083-bd7a-4240-bb56-a6513b0ad898 | checkpoint | RCP2.7 - Trench Excavation | DELETE
c62dd798-30d9-55b6-9719-cb98ed9e671c | note | Responsibility - SV/SC | DELETE
1c623934-6d2d-5d7b-8e83-f6226c870251 | note | Test Method - Visual | DELETE
192f5475-7e7a-55bf-b802-3502072f98b0 | note | Conformance Criteria - Trenches should be excavated to the required width and grade indicated on the IFC Drawings, with allowance made for benching for excavations greater than 1.5 meters. | DELETE
4d99e440-ce89-5b56-b3d4-0f2fde0da81f | note | ○ Excavations must be kept free from water until work below ground level us adequately set or protected | DELETE
26e33e4b-e8e6-54aa-87e7-3c1a0727a43a | note | Frequency - As required | DELETE
28ba21a3-654e-513b-8455-8a42b0612b39 | note | HP/WP - HP | DELETE
84dd3f76-d9bd-4de2-aefd-c9b56cc67b8c | signoff | HOLD POINT | DELETE
9abc2cf3-3ebd-40c3-a008-5c8afe13ab60 | checkpoint | RCP2.8 - Bedding | DELETE
7a995bcf-015e-5546-9827-de648a94a4d1 | note | Responsibility - SV/SC | DELETE
76ab9dd0-7895-5420-8f1c-ed2586e46a53 | note | Test Method - Visual | DELETE
2711b593-0da7-5a67-b619-3ef4e4329c9b | note | Conformance Criteria - Culverts shall be bedded as detailed on the Drawings. Proposed | DELETE
957c6294-5252-5c6b-ad8f-c46338a51a43 | note | Frequency - As required | DELETE
40873e2e-581a-55ae-85e2-45f5188c79e7 | note | HP/WP - HP | DELETE
0094bca9-f5e9-444c-b170-f3eaa36d3310 | signoff | HOLD POINT | DELETE
980cb612-3b1f-4948-be4f-ea2d97c5ad43 | checkpoint | RCP2.9 - RCP Installation | DELETE
f986d57c-aa74-5859-b681-d4d43425e32a | note | Responsibility - SV/SC | DELETE
ec0fb102-ee15-58c8-a28a-cff8bc7e8645 | note | Test Method - Written/survey | DELETE
0959b8c6-7d24-5417-ab64-96e0a95e728d | note | Conformance Criteria - Culverts are to be installed to the line, level, and grade shown on the IFC Drawings. Inlet and outlet invert levels shall be as shown in the Drawings plus or minus 10mm. Inverts shall be smooth and of uniform gradient throughout each culvert length. | DELETE
b0760e81-3fb9-5f87-8386-e4352f120eb0 | note | Tolerances: | DELETE
e0408b1f-90d2-5e4d-8940-1ce733429e5d | note | ○ Vertical level: ± 10mm | DELETE
f980cab6-dba3-5de1-a198-55d97da85384 | note | ○ Horizontal Alignment: ± 25mm | DELETE
5c5c42b8-59fa-5640-97ce-c7cf3a315b86 | note | Frequency - As required | DELETE
9bd65722-6507-5be8-84ba-d465c52382ff | note | HP/WP - HP | DELETE
f0cf5b45-b952-4de6-b5c3-522098197da4 | signoff | HOLD POINT | DELETE
6744fe45-cbe1-42fc-9e07-36442691798f | checkpoint | RCP2.10 - Backfilling of culvert | DELETE
f6a2f34f-0089-5d78-b186-01c03bdb80df | note | Responsibility - ENG/SV | DELETE
5ac2048e-d459-5ceb-954d-56ca75cfcf62 | note | Test Method - Visual | DELETE
95968821-c489-5dc4-b025-745a8334401b | note | Conformance Criteria - Backfilling and compaction shall be carried out in horizontal layers of uniform thickness not exceeding 200 mm of uncompacted selected fill material for 300 mm all around the pipe or culvert. Compaction in this zone shall generally be by hand tampers to a minimum density of 95% of the standard maximum dry density at +/- 2% optimum moisture content. Compaction of backfill in the remainder of the trench to subgrade level shall be to a minimum 98% modified MDD at +/-2% OMC shall be advised | DELETE
92f38c01-2aa7-5ebe-af6c-1d0ded24edd0 | note | Frequency - As required | DELETE
d884d3c9-653e-56ae-9678-7a54f64f3c21 | note | HP/WP - HP | DELETE
0e7e983c-c392-42ac-810c-7028e1deca5f | signoff | HOLD POINT | DELETE
969947be-626a-40d1-bc13-819f2e7cc7b3 | checkpoint | RCP2.11 - End Treatment – Headwall & Wingwalls (Reinforcement) | DELETE
7d724690-d36d-53cd-a673-65d07ed5cc12 | note | Responsibility - ENG/SV | DELETE
086fbb4c-5b7a-5a48-9d37-3b7e13829cf4 | note | Test Method - Visual | DELETE
5114ec53-3c27-58ea-be63-b51987298736 | note | Conformance Criteria - Reinforcement installed as per IFC design drawings | DELETE
087035a4-ead7-5a9e-817e-c939b19c4ad2 | note | Frequency - V | DELETE
cfdd3212-9157-50b6-ba02-12ecf47edf45 | note | HP/WP - HP | DELETE
9d7f81c7-2bd0-44da-8a2e-2a2081fc04ab | signoff | HOLD POINT | DELETE
d182e6b8-e74b-4565-8218-4bed820fd55c | checkpoint | RCP2.12 - End Treatment – Headwall & Wingwalls (Formwork) | DELETE
7cdb1916-fc65-590d-a4eb-fa79d6946c8c | note | Responsibility - ENG/SV | DELETE
f85ccf81-f09f-5dff-9f20-137a1b59c880 | note | Test Method - Visual/Field Survey | DELETE
04c00cb2-0e94-5702-b4b1-b892e31f337f | note | Conformance Criteria - Formwork installed as per IFC design drawings. | DELETE
6474c17e-0a90-50e2-bac3-18a3ce994be3 | note | Tolerances: | DELETE
5fe57c4b-dda0-5203-9bd7-63206b00d494 | note | ○ Variation in cross-sectional Dimensions: + 5mm | DELETE
d6ea1f61-ea27-5460-8ed7-0106e259c934 | note | ○ Variation in overall dimensions: + 10mm | DELETE
9e8f26a3-2dee-5221-adaf-f9a929d50c7e | note | ○ Variation in surface level: + 5mm | DELETE
4894c764-4eed-5101-a19c-37e50b168ace | note | Frequency - Each inlet/outlet | DELETE
7525f319-694c-51ff-ad26-e50f5e7d21f6 | note | HP/WP - HP | DELETE
51f2810b-9de3-4564-85e9-1784f4711ae2 | signoff | HOLD POINT | DELETE
dbd762d8-b5af-4b90-bb78-eb60a39c9f5a | checkpoint | RCP2.13 - End Treatment – Headwall & Wingwalls (Concrete) | DELETE
237b4e5c-5984-53e2-90af-25bfa6b49276 | note | Responsibility - SC/SV | DELETE
6e4694ab-2d41-5ee1-b575-390eb90dc7a7 | note | Test Method - Visual | DELETE
b794ad17-dbc8-5670-8315-71a072c71eaf | note | Conformance Criteria - Concrete placed and compacted to specified strength (N40) and slump (max100mm). | DELETE
0fbaa609-c1f4-513e-84c0-9e0c811c0ca9 | note | Frequency - Each inlet/outlet | DELETE
2239c767-8b55-5af5-a9ed-18f41f9a517f | note | HP/WP - HP | DELETE
fe6cada3-8994-4551-8fa6-65904ce0e6d7 | signoff | HOLD POINT | DELETE
7cb7c32d-7d51-439b-bca5-bdba7c65b1eb | checkpoint | RCP2.14 - Rock Protection | DELETE
1aca3833-d4ee-5f5b-95b6-a3e81fe9907c | note | Responsibility - SC/SV | DELETE
21d2ef86-da78-5e3f-b1f6-465e6dc1d09c | note | Test Method - Visual | DELETE
6e7ec58d-8826-5eab-8eb3-008e9894cd23 | note | Conformance Criteria - Dimensions and class of rock protection shall be as specified in the Culvert Schedule and supplied IFC Drawings. | DELETE
74276163-6b6b-58a5-9c83-d5bfe438ecd8 | note | Frequency - Each inlet/outlet | DELETE
cb9f8697-2a81-50d5-bad7-6053d541410b | note | HP/WP - HP | DELETE
299c20d8-e330-4fd8-bd71-87bb5629e5c2 | signoff | HOLD POINT | DELETE
a3293d54-d437-40ba-832e-fa3f5b592ca3 | section | 3.0 Post Construction | DELETE
511e13d7-a7ba-4110-af10-f7d0a9723274 | checkpoint | RCP3.15 - Works completed and update ITP/ Lot Register/ MDR and close out of GDP | DELETE
cc4c4d61-91aa-5702-bb71-30191f88ba22 | note | Responsibility - ENG | DELETE
04968476-c886-53ef-8b56-116cf3dcb036 | note | Test Method - Visual | DELETE
8e2e92e8-66da-5e87-834e-c0f6429d05c6 | note | Conformance Criteria - GDP permits closed. | DELETE
81bfe09f-ab3a-5f27-a301-6fbe6e38a7cc | note | ○ ITP closed. | DELETE
5954fb59-df58-5672-81a1-47f1247e9cf9 | note | ○ Approved MDR | DELETE
f6c3fe36-be45-5f35-b78f-ca66fec32398 | note | Frequency - As required | DELETE
71bcd464-bfc3-5a88-94ec-5e66074455df | note | HP/WP - HP | DELETE
0985de39-1d78-45e8-833f-3a49b66440df | signoff | HOLD POINT | DELETE
DELETE
e75b191c-dd7a-40a2-a54d-7b0af1535acf/1 | checklist | ITP-008 Embankment Construction | itp | ITP-008 Embankment Construction | 46 | 23c8d112-2a14-4c85-bd32-9fe7f0eb04de
e8558513-7ab6-48d1-98de-433944eb476e | section | Embankment Construction
4a614c52-e477-4c8c-b9e8-f9f66f963fae | checkpoint | EC1.1 - Underlying lot & ITP signed off and conforming
635d023a-43cc-507d-b6a4-24cad7028583 | note | Responsibility - ENG
7a8f9240-8a69-5c27-80fb-9d3502e0f1b1 | note | Test Method - Visual
783de080-e185-55a5-b451-0ac7c73b29a8 | note | Conformance Criteria - Subgrade/Foundation Preparation ITP signed off
ba80dbfd-0503-5808-bd81-935e41563a00 | note | Frequency - Prior to works
e20c78d0-1941-5154-ac0b-ffc993dea396 | note | Link to ITP - SP.1.9
3f344af9-d08a-5865-81ef-d9da96d5e264 | note | Thiess HP/WP Check - HP
7db41919-c6e1-5e66-90ec-00c0aa29a5c9 | note | Inspector HP/WP Sign Off - WP
51d9a739-4898-4980-a216-4b966f532089 | signoff | WITNESS POINT
492095ef-bc3f-4c0b-b398-01ff56260bd6 | checkpoint | EC1.2 - Embankment fill material
98a574b1-314a-575b-aca7-fe9482091f7c | note | Responsibility - ENG
627647d6-75a4-5752-8fb3-d2056f51c319 | note | Test Method - Visual
723a775a-1db8-5bf8-8f2a-c909a29ed3c3 | note | Conformance Criteria - Ensure embankment fill materials have been approved for use and within specification
8bd82068-6705-521e-814f-145754eb5f73 | note | Frequency - Prior to works (Check if this has already been completed at ITP Pre-construction stage)
a780ca05-c85c-5f5f-85c1-2b0adbf240d3 | note | Link to ITP - PC1.12 | Link to ITP - PC1.17
9a67a0a0-915a-56ff-b4f5-9cb31fe49ffc | note | Thiess HP/WP Check - HP
2b09a7b7-e569-5fd1-aea6-8705fa41ac77 | note | Inspector HP/WP Sign Off - WP
a8f80374-068c-4565-8062-7727b7ea763c | signoff | WITNESS POINT
6493e315-0ff4-4f7a-9623-6ef291088e0c | checkpoint | EC1.3 - Survey Set out
2c32f299-db28-5f0d-9219-dad69aa702da | note | Responsibility - Surv
b538f08c-0104-5524-b035-0648db232fbd | note | Test Method - Field
4f98f1fa-6f4a-54b5-9861-396450f47579 | note | Conformance Criteria - Areas of work to be set out by surveyor and/or models in plant
7fd90e11-4239-5ae5-b1f6-d92dd61588ac | note | Frequency - As required
cea1e636-bbb1-5c17-b1d7-a6c6b4e0e266 | note | Thiess HP/WP Check - HP
e6df3954-8c47-523e-9c9a-036c5c7a7d0d | note | Inspector HP/WP Sign Off - WP
78e12c6e-590d-4b8c-8cee-4a2451ccdfef | signoff | WITNESS POINT
ccdc3a9c-ac5e-4033-8c3b-ff3b1cb8c838 | checkpoint | EC1.4 - Place, moisture condition & compact embankment fill
cac8963c-7cf9-5eff-8b81-1bef0d83b70e | note | Responsibility - SUP/GeoTech
3617b082-f963-5109-83e7-e68d12666756 | note | Test Method - Field Test
5503e2c0-6737-5ccf-91b7-cf28d197e969 | note | Conformance Criteria - Layer thickness minimum 150mm maximum 300mm.
45b6b68f-e933-5ad8-83b0-7eb3946a126c | note | ○ Density requirements: < 300mm from finished level under roads & structures minimum RDD 97%, all other areas and depths RDD 95%, moisture content -1% to +2%, normal level of testing 1 test per 500m3, reduced level of testing 1 test per 1,000m3. | Lightly tyne the subgrade/foundation immediately prior to placing embankment fill. Layer thickness minimum 150mm maximum 300mm. Density requirements: < 300mm from finished level under roads & structures minimum RDD 97%, all other areas and depths RDD 95%, moisture content -1% to +2%, normal level of testing 1 test per 500m3, reduced level of testing 1 test per 1,000m3. Subject to client approval oversized material up to 500mm can be used in general fill at the following depths: 600mm or greater in depth below subgrade for stockpiles, road surfaces and embankments, or 2m or greater in depth below the footprints of structures. Rock fill may be used >600mm below subgrade level. Material containing a high proportion of large particles may be used in embankments using the Mechanical interlock method of construction.Maximum layer thickness 500mm.
466bda59-dc24-50d2-93ff-8affa9feffb8 | note | ○ Subject to client approval oversized material up to 500mm can be used in general fill at the following depths: 600mm or greater in depth below subgrade for stockpiles, road surfaces and embankments, or 2m or greater in depth below the footprints of structures.
dce5ac04-f693-509c-a6b3-2ebebcba7c42 | note | ○ Rock fill may be used >600mm below subgrade level.
41c0933b-5d94-550d-8cf7-39b243dc4961 | note | ○ Material containing a high proportion of large particles may be used in embankments using the Mechanical interlock method of construction.Maximum layer thickness 500mm.
46837dee-32c0-53a6-9d17-ff07221c7e8f | note | Frequency - As required
5f766555-e044-53b1-8d65-3f86e6c06f19 | note | Thiess HP/WP Check - HP
d1404653-b3df-5b6b-a697-a65cbf269dc0 | note | Inspector HP/WP Sign Off - WP
ce87cdd3-a9d0-4757-87ac-a2ea0fef9fb5 | signoff | WITNESS POINT
39df1a89-b400-4f6a-b068-a0ce2d3b0a8b | checkpoint | EC1.5 - Trim embankment
b6161dae-c37e-5e66-afec-102e28e5ccd0 | note | Responsibility - SUP / SURV
db15ec6c-0fb7-5015-97ad-7b1db5e7f266 | note | Test Method - Field
50bbc415-a3fc-5d69-aaf3-55b1d84f8d36 | note | Conformance Criteria - Trim all embankment to the lines and levels shown on the drawings in accordance with the following tolerances: Top of bulk earthworks +/-50mm; Road subgrades & under buildings & structures +0mm to -25mm.
3d9fe111-61b0-5165-ad56-3439aaa484d6 | note | Frequency - As required
080e8708-cbfa-5d10-a02b-897d3d617cab | note | Thiess HP/WP Check - HP
10b4ef1c-dad3-53bc-a762-8fbf3aba37a1 | note | Inspector HP/WP Sign Off - HP
2456b688-6f43-425d-b0ac-2af98045b4fa | signoff | HOLD POINT
836357fc-3e4c-4451-a173-3e657eb706b6 | checkpoint | EC1.6 - Proof rolling
e383c7ba-7517-5fe1-b83c-121bf6ce2c2c | note | Responsibility - ENG/SUP
6ef541cc-2c29-50f9-9bbb-66ae1cbd7327 | note | Test Method - Field Test
8d3648f3-7440-5502-8fe1-08b378df709d | note | Conformance Criteria - Proof-roll embankment finished surface under a standard 8 tonne axle load or 10,000L water cart or heavy self propellled smooth drum roller dynapac 620D or equivalent, to confirm that in the Inspector's opinion, deflections are negligible.
90944651-d678-5c95-a7f1-08f0dbe2c70e | note | Frequency - As required
df90c852-a5c1-5852-b384-1ccc0703ed92 | note | Thiess HP/WP Check - HP
45a06049-4ccc-5fa4-8cea-b75345a03dd9 | note | Inspector HP/WP Sign Off - HP
a46f56dd-fd73-4d13-b3b2-efa98fe73ed2 | signoff | HOLD POINT
2056572e-b705-4f91-981b-da286938b639 | checkpoint | EC1.7 - Surface level check and survey pick-up
6a68517f-e29a-540a-a166-b4ed1f6cc0aa | note | Responsibility - SURV
463ad56d-2dfe-5b12-967d-2e9d9176efe6 | note | Test Method - Survey / Field Test
b987ce65-2b06-5023-91f8-ddcef3797e25 | note | Conformance Criteria - Surface level picked up as per Table 10 C15 (DXF file format, volume calculated and filr saved in Construction Team Sharepoint and detailed in register
5e8239db-904d-5e22-863e-bb8645b2ffd5 | note | Frequency - As required
590d7183-81b5-5457-99b3-3ffac96b3b49 | note | Thiess HP/WP Check - HP
a0a0b0f2-922a-5f5a-83f3-21e33d5bcb84 | note | Inspector HP/WP Sign Off - HP
3315d813-4d2a-4914-9e0a-bbdb04f27890 | signoff | HOLD POINT
cd09000b-518f-46ba-8ae5-98753bd77965 | checkpoint | EC1.8 - QA close out
5f98f2d3-89ee-5c8c-b473-d73e0e57bef0 | note | Responsibility - ENG
e350a75b-9841-500c-96b5-73fd23a695e7 | note | Test Method - Visual
864c182e-1c34-5189-b0fc-5df02f7a0727 | note | Conformance Criteria - GDP permits closed. ITP closed. Approved MDR.
163b2fc0-398b-53e7-9368-7252f7f13d9c | note | Frequency - As required
4de988bf-f463-5ec2-ac20-2b34de1ad1ef | note | Thiess HP/WP Check - HP
324c1887-2a4a-596e-a703-e3e18fd31702 | note | Inspector HP/WP Sign Off - WP
361d46ee-d8e9-4f66-b43f-ad76ae5b1f3d | signoff | WITNESS POINT
16032528-d2b5-4c24-a800-78e1763a1773/1 | checklist | ITP-009 Unbound Gravel Pavements | itp | ITP-009 Unbound Gravel Pavements | 46 | aebef361-b439-4327-98d3-6b6e9f08281a
2ac16c39-8a1f-4d3c-891c-400476a3c65d | section | 1.0 Pre-Construction
26324e01-52be-4068-8fea-22c36ef22220 | checkpoint | GP1.1 - Drawings supplied most current IFC | DELETE
ce02b22f-bd6d-5b1f-a166-8a128612ca85 | note | Responsibility - ENG | DELETE
d9d949bb-0f4a-5392-83f9-a9da5e4b8d65 | note | Test Method - Visual | DELETE
ea5a6775-7bd4-5396-a748-a150ccd8322f | note | Conformance Criteria - Reviewed drawing register | DELETE
24180e7b-e081-59ea-8b00-dd6aae2a2fe9 | note | Frequency - Prior to works | DELETE
f6cec98c-4f58-5269-9e9e-cc57c8ceaf3f | note | HP/WP - HP | DELETE
2c971e9e-c82a-49d9-a3c5-d4e3b1fb3084 | signoff | HOLD POINT | DELETE
12c42d3e-2a61-423b-accd-5b7924a373d3 | checkpoint | GP1.2 - Management Plans submitted and approved as per PMP | DELETE
61634936-80f1-5c18-a1f4-e2fc0bdb8824 | note | Responsibility - ENG | DELETE
502883bb-0775-5315-a1b5-952d69a6918b | note | Test Method - Visual | DELETE
73d5a38e-2cd0-5cb9-903a-449e3aaaf099 | note | Conformance Criteria - Approved Package MP’s | DELETE
7123f834-f4ce-5e36-a2b5-0c2fcdb84cfb | note | Frequency - Prior to works | DELETE
b046604c-9cd6-5b8c-bd8f-3d420c91d398 | note | HP/WP - HP | DELETE
83ec0c54-5b43-40bf-9fbb-fcc5ac627825 | signoff | HOLD POINT | DELETE
209c2651-94d0-4c60-a70a-e367067269f4 | checkpoint | GP1.3 - Inspection Test Plan (ITP) submitted and approved | DELETE
5a2783e2-7f33-592e-9391-e1e026631214 | note | Responsibility - ENG | DELETE
a6868bf0-84cc-5fd1-8734-805ddb277708 | note | Test Method - Visual | DELETE
994b87ac-921c-5312-a2fd-90786d75e492 | note | Conformance Criteria - Approved ITP revision | DELETE
99921d14-6884-5e36-a20b-2967515c10c6 | note | Frequency - Prior to works | DELETE
a76a9108-08c4-55f6-b41b-67231acb772a | note | HP/WP - HP | DELETE
d63a7625-3baf-4def-9bfe-787bfd11af10 | signoff | HOLD POINT | DELETE
a5d920a2-92e0-4ae4-9a7d-43072889cd49 | checkpoint | GP1.4 - Lot Register/ WBS submitted and approved | DELETE
bc7038be-d55a-51e0-9376-5d9a70df762b | note | Responsibility - ENG | DELETE
8c35490e-856d-534e-97f8-bda3697a6d3c | note | Test Method - Visual | DELETE
68e66969-d275-586e-bc9f-9c38829f8e1b | note | Conformance Criteria - Approved WBS | DELETE
fe354df8-13a8-567e-9e01-f7e313bd4da1 | note | Frequency - Prior to works | DELETE
4cc1ba4e-3ea0-5b00-871a-0178fb0d89b9 | note | HP/WP - WP | DELETE
43392d70-4aef-4e61-b27e-dd683e7de79d | signoff | WITNESS POINT | DELETE
563f08b5-d8e8-490b-a79e-23c0c5f2269e | checkpoint | GP1.5 - Pavement material compliance testing | DELETE
593ae87f-da9b-59ae-ae9d-6f58f67f9946 | note | Responsibility - ENG | DELETE
86d480fc-801a-5af2-b700-357aceef6db7 | note | Test Method - Visual | DELETE
78a36930-34ea-5c71-af59-c32d8b146a62 | note | Conformance Criteria - Test results comply with the details on the drawings or where not specified the specification | DELETE
18f6bab0-e4ae-5ef7-805a-9b5c3f97df9a | note | Frequency - Prior to works | DELETE
aa4e6c65-9d25-5c3b-a871-9af3f2032b36 | note | HP/WP - HP | DELETE
4eb72e8b-ca63-4d96-884e-50f418adc881 | signoff | HOLD POINT | DELETE
63bd5c14-6cb7-4109-8991-abe461f60a13 | checkpoint | GP1.6 - Stockpile locations | DELETE
afe8589b-95ed-549d-8723-f470a09872e4 | note | Responsibility - ENG | DELETE
d2248fac-bb4d-51bb-adea-9d213bbefec6 | note | Test Method - Visual | DELETE
2d90b044-8f14-5627-ad5f-a94d40cfbc0a | note | Conformance Criteria - Stockpile locations shown on the drawings or approved by client’s rep | DELETE
c3ac073e-b195-5b07-95e6-f8f426b79e0f | note | Frequency - Prior to works | DELETE
9e88f1c9-12bd-5213-a2fb-b750cf73c3d6 | note | HP/WP - HP | DELETE
0084a942-5284-4325-9493-163a0f456c87 | signoff | HOLD POINT | DELETE
fa88868d-6bb1-45bb-ac41-e4cb101fbc32 | checkpoint | GP1.7 - Underlying lot & ITP signed off and conforming | DELETE
495b547f-3d5d-507e-a05b-7b0b42b069db | note | Responsibility - ENG | DELETE
f793f566-538a-5dc8-8cb2-ac38d08e933f | note | Test Method - Visual | DELETE
24c395ba-0b40-595e-a5dc-91df7ec24c92 | note | Conformance Criteria - Subgrade prep ITP Signed | DELETE
8b579c9f-c1e8-5713-bcb1-b494aa313939 | note | Frequency - Prior to works | DELETE
87b7a7b7-c1a0-5856-8483-378eba4f4b7f | note | HP/WP - HP | DELETE
55e62c5c-3fa9-4794-8301-d3f671bdff85 | signoff | HOLD POINT | DELETE
0a53f102-f70c-4fe7-93ec-f75e6288762d | section | 2.0 Construction | DELETE
329b4b8d-55b7-4ff3-b5e2-da7253cb9846 | checkpoint | GP2.8 - Subgrade preparation under pavements | DELETE
813a4aa0-0839-5906-879a-21f3c4942019 | note | Responsibility - ENG | DELETE
b5d820bd-1c01-5b6d-9e21-e68b078dfeb0 | note | Test Method - Visual/Field Test | DELETE
7f857e7f-47ff-5c39-990f-5b70ce0959a8 | note | Conformance Criteria - If subgrade material is less than CBR10, subgrade shall be boxed and replaced with 150 mm of CBR10 or greater material. Subgrades shall be trimmed and compacted to within 15 mm of the established grade or cross section. Compaction requirement: 98% modified maximum dry density at +/- 2% OMC. | DELETE
497bbdbb-dbd3-57df-9298-4d8f84db87b3 | note | Frequency - As required | DELETE
3df73ae8-6903-5847-b8de-67ce8c9ec74b | note | HP/WP - HP | DELETE
0ff70cca-b90e-4385-a8e3-3a142edc6f63 | signoff | HOLD POINT | DELETE
4cbd14c8-7eff-4f23-9854-c1c89c0236f8 | checkpoint | EC2.9 - Surface level check/ and survey pick-up | DELETE
883f4cc6-bc29-56d1-8dfe-01f24bdb2d8a | note | Responsibility - SURV | DELETE
e51b3cd9-5768-53b9-9b15-f4eaf56fec03 | note | Test Method - Survey/Field Test | DELETE
952de667-1597-5a53-b992-cc52cf73fd55 | note | Conformance Criteria - Surface level pick-up submitted to company | DELETE
ac38d1e5-da5a-5444-bf29-5dd5fb516946 | note | Frequency - As required | DELETE
e8519609-0672-5689-a68c-a721fe80a59b | note | HP/WP - HP | DELETE
64c35c74-e7a8-4e61-951c-6077599f6746 | signoff | HOLD POINT | DELETE
c74cb16c-7f6a-45a7-abca-82c1ace91fde | checkpoint | EC2.10 - Proof roll subgrade prior to placement of pavement materials | DELETE
4dd0e68e-5238-56b7-90b9-48207da80e30 | note | Responsibility - ENG | DELETE
ad04ce6c-e5e6-51a5-947e-30ee064bab27 | note | Test Method - Visual | DELETE
d14fa7ef-05d5-5790-a297-a75c9759270b | note | Conformance Criteria - Subgrades under pavements shall be proofrolled under a 10,000L water cart or heavy, self-propelled, smooth drum vibrating roller capable of operating in variable frequency modes, to confirm that, in the principal’s opinion, deflections are negligible | DELETE
9fc2f4e1-8e59-5022-a52c-0c709409fc8d | note | Frequency - As required | DELETE
8c05f25c-74a2-5829-9933-2aeed5ddcd49 | note | HP/WP - HP | DELETE
42dc5316-9d2a-40ea-b02e-6b42f5119a67 | signoff | HOLD POINT | DELETE
c871f5e0-768f-462e-8f0a-89391baa67fa | checkpoint | EC2.11 - Placement of pavement material layers | DELETE
75dead7b-9800-5972-8788-71375a3ccb5a | note | Responsibility - ENG | DELETE
e03186fa-dac3-5291-ae1b-13b6d239b318 | note | Test Method - Visual/Field Test | DELETE
55210035-c2a4-5e5d-a4cd-95bc1a5acbbe | note | Conformance Criteria - All materials delivered to site shall be accompanied by test certificates. | DELETE
4dc03d51-94e8-5045-8153-9b0aa6c8add7 | note | ○ Each layer shall be free from sticks, organic matter, clay lumps and other deleterious material, and be spread and compacted in a uniform thickness minimum 75mm, maximum 250mm as per the details on the drawings. | DELETE
84c4f96e-917f-57ed-bf0f-97cca21c28f7 | note | ○ The deviation from a 3m long straight-edge placed anywhere on the surface of a layer shall not exceed 8mm. | DELETE
0d94d6ff-9317-5744-b0b9-8af7986febde | note | ○ Pavement layer thickness tolerances: Base -0mm to +30mm; Sub Base -15mm to +30mm. | DELETE
baf41884-2d3c-575c-b605-063cb9553c30 | note | ○ Finished pavement surface level tolerance: Base -15mm to +25mm | DELETE
b2ea26ab-d495-51b2-87f3-4b2027094ca0 | note | ○ Horizontal tolerances: Base, centreline/crown -150mm to +50mm, edgeline/changepoint -100mm to +200mm; Sub Base, centreline/crown +/-200mm, change point -100mm to +400mm | DELETE
7c67790c-4c12-5700-aa18-cedafea91338 | note | Compaction requirements: | DELETE
5959fa76-0e9d-5ed6-b8be-7ca15b25af3b | note | ○ Base & Sub Base 100% standard relative dry density (RDD) maximum degree of saturation 70%. | DELETE
4dbce34c-5477-5944-9356-6c0f39a8066e | note | ○ Compliance testing frequency as per table in Specification Annexure A clause 5. | DELETE
caf13e1b-a77d-580c-8e46-e9c8f951c5bd | note | Frequency - As required | DELETE
e2e094f8-7189-5554-b44f-cb72006d1903 | note | HP/WP - HP | DELETE
954eae12-3372-460e-ba45-58cb8b0aeef7 | signoff | HOLD POINT | DELETE
fe6baa0e-4119-49b3-bf93-46470a42c919 | checkpoint | EC2.12 - Surface level check/ and survey pick-up | DELETE
242375b7-945d-505a-ad98-29f77818bf0c | note | Responsibility - SURV | DELETE
db301325-72b3-579b-a48a-7dbe4fe0e789 | note | Test Method - Survey/Field Test | DELETE
45add8df-cbf6-59b2-9035-9265ae203c65 | note | Conformance Criteria - Surface level as per the pavement layer details on the drawings, and all layers as per the tolerances listed in item 11 of this ITP. | DELETE
13b8182e-2cb1-5065-81a9-1e3ae533de8c | note | Frequency - As required | DELETE
6a2c4aeb-7f64-5b52-9ea4-431a16f7d7d4 | note | HP/WP - HP | DELETE
59daa3e2-cdaf-40f2-b690-3f6d54bd2217 | signoff | HOLD POINT | DELETE
3cbbed25-f06a-476b-858f-61b9405a30e9 | section | 3.0 Post Construction | DELETE
62907706-957c-49b3-8c5e-8410f080c594 | checkpoint | EC3.13 - Works completed and update ITP/ Lot Register/ MDR and close out of GDP | DELETE
064f8f32-5c1f-597e-9def-5e082eb9eb59 | note | Responsibility - ENG | DELETE
06f4f82d-14fa-5206-b688-fb664667c5da | note | Test Method - Visual | DELETE
e4485279-3a36-5c51-9bb1-4ff1e39e0722 | note | Conformance Criteria - ITP closed. | DELETE
5c6ab4e5-79dc-5996-8e9f-604b6528f9b7 | note | ○ Approved MDR | DELETE
2e339af6-9f26-532a-8380-2f27563ada13 | note | Frequency - As required | DELETE
2dcb3626-803b-59a5-9b33-7ceb37b4b296 | note | HP/WP - HP | DELETE
f63ab955-f79d-4581-a627-ceb70a5f6c45 | signoff | HOLD POINT | DELETE