## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
6796a4b7-50fd-4c6d-82a5-85be75cf9074 | checklist | ITP-001 Clear & Grub | itp | ITP-001 Clear & Grub
65c63129-50bb-463f-92ee-20d59b94b854 | section | Clear & Grub
489aefec-c9f3-4977-a3a2-44421446c676 | checkpoint | GC1.1 - Underlying lot & ITP signed off and conforming
98434abf-234a-51f2-b704-be1a9de86c51 | note | Responsibility - ENG
a024fe55-4ba9-5fc2-90b0-30f84dcbf2ab | note | Test Method - Visual
c07fbf52-8dec-534f-86e3-08b175a65330 | note | Conformance Criteria - Pre-construction lots closed out
e1d80108-10e4-512a-8cc8-0f00f2bac03b | note | Frequency - As required
f9e55d9e-59ba-5f88-bb29-b5db805daafa | note | Link to ITP - PC1.19
fca88b3e-0751-4e64-9fb1-95b6b63e64e1 | checkpoint | GC1.2 - Ground Disturbance Permit (GDP)
978d432b-1bf4-5a25-966a-0242c9412fc0 | note | Responsibility - ENV ENG
27d61d67-c12f-5e77-8a4c-768e9625f3ae | note | Test Method - Visual
be5d205a-b9ff-54d1-b330-aa333b7d1c1d | note | Conformance Criteria - Approved GDP saved in Construction Team Sharepoint and detailed in register
7633d20b-f11f-5995-86cf-aed4deaa66cb | note | Frequency - Prior to works (Check if this has already been completed at ITP Pre-construction stage)
745df801-8762-5343-9bc5-24556ea12758 | note | Link to ITP - PC1.15
cb5ab8ae-d69c-5ee2-91ca-0800fc89d36b | note | Thiess HP/WP Check - HP
8a408bda-3df9-5830-9111-e26350854a3f | note | Inspector HP/WP Sign Off - HP
cfb9396b-4caa-4b96-929a-0a16ccc834e0 | signoff | HOLD POINT
266269d8-b950-43e5-8543-c2b3eab8d43e | checkpoint | GC1.3 - Cultural Heritage(CH) Clearance Survey
b8f79f88-33e3-5a43-b05c-403c36639c7b | note | Responsibility - CH
0e203685-3016-5af6-ae94-1d263da12700 | note | Test Method - Visual
a4a19328-b1b2-510d-9b2e-07f9784576c8 | note | Conformance Criteria - Approved CH Clearance Survey saved in Construction Team Sharepoint and detailed in register
c93283a8-55f9-53e7-8163-c2de509c1163 | note | ○ Areas of CH clearly demarcated
f57d0f4b-5423-5a20-8558-e37664f08df1 | note | Frequency - Prior to works (Check if this has already been completed at ITP Pre-construction stage)
5f20b016-d0b5-55d5-9184-cb86e8b0f012 | note | Link to ITP - PC1.14
3896cd71-e6fa-58cb-bd16-2acb3c739ffd | note | Thiess HP/WP Check - HP
3ca3b303-baf1-52c4-9ef1-cdd42acdb33e | note | Inspector HP/WP Sign Off - HP
8a8883cc-c2ec-4e86-ba9b-57c2adc9e3ee | signoff | HOLD POINT
119b407c-9217-4c0c-9ca3-9c66f881bd0d | checkpoint | GC1.4 - GDP survey set out
dce5e84f-f9f2-540a-b62f-aa2e935083b3 | note | Responsibility - SURV
92afeb73-849d-514d-8ef0-6bddcb23b669 | note | Test Method - Field
0b6a5774-e8fd-55f9-a4a9-84135097e415 | note | Conformance Criteria - Area of works pegged and clearly defined to GDP.
6c7911b2-c9c9-5950-b9f3-592c22486d25 | note | ○ Clearing pegs installed at nominal intervals to ensure no over-clearing.
19446839-e2f6-53e7-82b8-ec70f940c706 | note | Frequency - Prior to works (Check if this has already been completed at ITP Pre-construction stage)
d1727a01-d642-5cc9-8818-87157736286c | note | Link to ITP - PC1.16
52904e09-81dc-5864-859a-f401f642031c | note | Thiess HP/WP Check - HP
ee42d4d2-bc79-57b9-b00e-e5f7974afa85 | note | Inspector HP/WP Sign Off - WP
13e9538e-221b-4fc7-ae63-d227ec979ef1 | signoff | WITNESS POINT
6055ae09-38c0-4d75-8692-5490848b29c6 | checkpoint | GC1.5 - Survey of pegs to confirm correct GDP survey set out
451f8ff7-04fc-5756-a7c9-a1f2fef60040 | note | Responsibility - ENV
27c69dcb-afc4-5a17-8f63-f9fccc4fff1e | note | Test Method - Visual
6b68dcd0-e127-5bed-87ab-be08f8b3bdcf | note | Conformance Criteria - Pegs to be surveyed and sent back to the engineer. This is then to be confirmed by the environmental team
979643f1-6d72-55b7-b267-312537028d54 | note | Frequency - Prior to works (Check if this has already been completed at ITP Pre-construction stage)
47065cb1-ead6-58cf-b42e-7491e23ea648 | note | Link to ITP - PC1.17
85315615-bbb5-5426-849c-3c10a3947590 | note | Thiess HP/WP Check - HP
1d4cb4c3-398d-5b5c-bc2f-2ad264f00d6b | note | Inspector HP/WP Sign Off - WP
a7e84b21-dcff-49c6-b00b-58e21ae71760 | signoff | WITNESS POINT
3964e4a0-038f-4c0c-8288-e14042cae2a0 | checkpoint | GC1.6 - Survey natural surface
5888dfc7-fbf2-59fb-968c-3a9227538bd5 | note | Responsibility - SURV
31390e86-a343-59bf-89eb-e1b35e6b183d | note | Test Method - Field
5ec29348-8393-5210-a775-b08b034326fc | note | Conformance Criteria - Check survey pick up of work area and digital file saved in Construction Team Sharepoint and detailed in register.
b54d678d-e8cf-58fe-aea6-cc2cd8c4e7e8 | note | ○ Surface area shape file created and uploaded to Qfield
c56aca32-35c2-53f2-a49c-e32d9049ce9f | note | Frequency - Prior to works (Check if this has already been completed at ITP Pre-construction stage)
7b985af9-5568-5ffd-8af8-403e5eb641de | note | Link to ITP - PC1.9
494a4c99-c566-5b31-bad5-c426312d71b2 | note | Thiess HP/WP Check - HP
46aa4abd-5343-5354-818e-cedd5ce47aef | note | Inspector HP/WP Sign Off - HP
70bca751-c0f6-4cff-adff-6dbb5d00d58a | signoff | HOLD POINT
63f12227-eb41-494e-838a-7d5b664e38ff | checkpoint | GC1.7 - Fauna Spotter Catcher (FSC) Pre-Clearance Survey
405c2945-db79-5dbd-be91-2f679f7767e4 | note | Responsibility - ENG
1422c724-163c-5156-bca5-5d837c6a6a6e | note | Test Method - Visual
172902e2-5637-5499-bdef-8ca418fbe155 | note | Conformance Criteria - FSC pre-clearance survey completed within 2 weeks of construction.
50912c86-e7d6-51e0-ab93-5c320d6e4154 | note | ○ Habitat vegetation, threatened species demarcated.
17ce7cd5-86f2-591e-8dd4-3d61d8a0d7a3 | note | Frequency - Prior to works (Check if this has already been completed at ITP Pre-construction stage)
984fb003-8603-5061-b15b-3893a5445bcf | note | Link to ITP - PC1.13
bb372c82-2c7e-5055-89b3-098f9b6d897b | note | Thiess HP/WP Check - HP
e866b3f2-05be-5635-b01c-137d88a97720 | note | Inspector HP/WP Sign Off - HP
7d15fd4b-0569-4ef4-9355-92f207ac998e | signoff | HOLD POINT
b9a47c3d-acaa-46a8-a5f1-c6f2a00bd24a | checkpoint | GC1.8 - Mandatory GDP Pre-Clearing walk
d6720244-96ce-5b56-b3f0-c10db1cc3706 | note | Responsibility - SUP OP ENG ENV
5d409e5b-dc2a-56a0-8272-3865a72fa972 | note | Test Method - Field
1a74e138-0dca-584f-9941-1b0680245e5d | note | Conformance Criteria - Walkthrough with FSC, Supervisor, Surveyor, PM or Senior Engineer, operations that will be undertaking the clearing
261187f5-9219-5bb8-9157-20435b52d7f2 | note | Frequency - Prior to works (Check if this has already been completed at ITP Pre-construction stage)
d4ec68cf-6bc8-58d4-b816-c05ae99b3ea9 | note | Link to ITP - PC1.18
84c1612e-a9e7-53ee-a41e-7f6105eec780 | note | Thiess HP/WP Check - HP
f5cd13cb-fc71-5e52-a9a5-133ebe733e51 | note | Inspector HP/WP Sign Off - WP
770649e0-e1bd-44b7-92f3-f827029b4c07 | signoff | WITNESS POINT
96356e00-b597-41a7-be38-ca41842ab0df | checkpoint | GC1.9 - Clearing of vegetation
4ad76604-a732-5f00-9202-8b479ba6a09f | note | Responsibility - SUP
160b8fc7-a7f6-5d83-b268-e1aaa26d4321 | note | Test Method - Visual
afd40b38-8546-5d46-b008-32e8c6f6d1f4 | note | Conformance Criteria - FSC individual on site at works during clearing operations.
b0a60139-c641-5810-8191-a3b4d22dfebe | note | ○ Habitat vegetation, threatened species and cultural heritage areas demarcated
b69d176b-96b4-5d45-9aa2-af9173cac2d2 | note | Frequency - As required
b596ec02-f4aa-5645-a935-4d7777f98606 | note | Thiess HP/WP Check - HP
d24f16aa-677d-5eb7-b1c3-48d78cc9f8c4 | note | Inspector HP/WP Sign Off - WP
a7af8165-3a25-45f7-b0f4-c5c6827e3060 | signoff | WITNESS POINT
2ffd8602-4159-4631-b51f-fb50d097b50f | checkpoint | GC1.10 - Stockpile Cleared Vegetation
6ee3953f-8735-54f5-89e5-f208aec95df3 | note | Responsibility - SUP
dd7b1d88-2f7f-5ad0-9131-e4a6399a168c | note | Test Method - Visual
92ca0ab2-2216-5ca8-a440-49b9a542ab8f | note | Conformance Criteria - Cleared vegetation loaded and hauled to approved stockpile location
3387fd36-cd13-5095-87ff-d7937b609226 | note | Frequency - As required
3563f903-fe3e-5750-9c03-7bb8024f8ce7 | note | Link to ITP - PC1.11
8ad94a31-975a-5c99-8ca0-6636fb57e981 | note | Thiess HP/WP Check - HP
10a24508-4e40-532b-9d55-58c51ec51adc | note | Inspector HP/WP Sign Off - WP
aaf1e0b1-b8f8-426f-bf9f-6bb0df391867 | signoff | WITNESS POINT
668916bf-b68c-4a79-a23e-e790bbe46f1c | checkpoint | GC1.11 - Erosion and sediment control
be16683f-6acc-519f-8e55-b4bc294ff9f9 | note | Responsibility - SUP
46dfae90-06f8-5f4e-857b-bfd837333e53 | note | Test Method - Visual
c6dd806e-baa9-5e10-a07e-51f568dd4282 | note | Conformance Criteria - Erosion and sediment control measures to be implemented whereever possible after clearing has been completed.
27238811-fa23-5cb2-b8af-a292a3025dce | note | Frequency - After clearing
62509e03-b70a-5049-a275-c2aacb3714ae | note | Link to ITP - PC1.10
3c1a6503-66f6-5eb7-be27-47b33e6a9cfb | note | Thiess HP/WP Check - HP
65e4534a-f135-5b93-bd94-cb77a4b83a92 | note | Inspector HP/WP Sign Off - HP
fa877d86-55e1-456c-9e59-c94fd9b13286 | signoff | HOLD POINT
15100512-873e-4694-b8bb-6ae6e682538e | checkpoint | GC1.12 - QA close out
2123b05c-fda5-5cef-ba89-eb0e7e09d771 | note | Responsibility - ENG
7cbe0163-db58-5298-a5ce-55e4205257e2 | note | Test Method - Visual
e3dfd798-8daa-5d94-a78e-aefcba19b2f1 | note | Conformance Criteria - Works completed and update ITP/Lot register/MDR and close out of GDP
c975079d-ffaa-54ef-8b9d-b3003d95f4a0 | note | Frequency - As required
da06f814-8fbd-5785-9bc4-6286327f6abb | note | Thiess HP/WP Check - HP
aac6fe69-eb96-56eb-87d9-32d99c7afd4c | note | Inspector HP/WP Sign Off - HP
12b79af7-f40a-4688-b33d-60e2db049043 | signoff | HOLD POINT
b86ac2fb-a936-4959-bc2c-0b212ce6cb6a | checklist | ITP-002 Topsoil Stripping | itp | ITP-002 Topsoil Stripping
8749f0ea-dcaf-40a1-a9fb-38172bde624a | section | Topsoil Stripping
916380c8-3601-4c5d-aaec-d8f5ce265520 | checkpoint | TS1.1 - Underlying lot & ITP signed off and conforming
ae37fa4e-a8c8-5621-99d3-c3093ffbd813 | note | Responsibility - ENG
eaa1749a-e2ec-5b85-8edd-42ddd734d8a2 | note | Test Method - Visual
dae7b959-a92f-50a9-80f0-f8e4f50ef610 | note | Conformance Criteria - Clear & Grubbing ITP closed out
eeadea39-f306-52fc-83e8-4c96215d2126 | note | Frequency - Prior to works
b23b17a7-7376-533d-9afe-1423f0cb849c | note | Link to ITP - GC1.12
6c621a60-d7a2-4f30-86cf-79266b7cfff1 | checkpoint | TS1.2 - Survey Set out
a04a85f3-030f-5947-93a2-83065c379130 | note | Responsibility - Surv
b0740eeb-b1e8-565d-b6bb-e79334e3c6b7 | note | Test Method - Field
8795b855-e66e-55e4-ae20-2c067a367fa7 | note | Conformance Criteria - Areas of work to be set out by surveyor and/or models in plant
c707d4ab-6d68-5bb7-aa60-78dc74f21831 | note | Frequency - As required
225fa33d-4b6f-5408-b2e1-861b17ce1c7b | note | Thiess HP/WP Check - HP
c0fab7ed-3a57-510c-99ca-1308ec25b414 | note | Inspector HP/WP Sign Off - WP
92c3d114-4ca0-4687-9ab6-1be8c3bbaf48 | signoff | WITNESS POINT
ef0f707e-77c6-47e0-b7b6-f00e62939a07 | checkpoint | TS1.3 - Strip topsoil, load & haul to approved stockpile location
944babb1-ca24-540f-903e-b2314fa26865 | note | Responsibility - ENG
a591edf9-2637-5776-97cf-4ac30f68fd7f | note | Test Method - Visual
93eddc67-b978-54f9-8611-85f084d83259 | note | Conformance Criteria - Provisional depth of topsoil strip shall be 100 mm unless shown otherwise on the drawings.
8e938ca4-1f2e-543e-b9b6-75e0ac18fd76 | note | ○ Stripped topsoil loaded and hauled to approved stockpile location.
e13284e2-f46f-585b-bcd5-00fe9807e382 | note | ○ Stockpile locations located minimum 40m from watercourses and not exceed 2m in height.
48714638-6934-566f-8a20-7f697f7d162d | note | ○ Native seeding of topsoil stockpiles as agreed with Company.
e05858cc-a4bd-5b6a-9caf-8cde8db7aa22 | note | Frequency - As required
9463ad6a-351e-5eee-973e-cc0598eb1f1c | note | Link to ITP - PC1.11
10901a46-aadc-5279-b7e6-6b0eef29320f | note | Thiess HP/WP Check - HP
cabcfed7-1ef9-558c-b8c6-22527fc21bc5 | note | Inspector HP/WP Sign Off - WP
d2bc2732-0651-43bb-8cb4-971bf9e1c4ff | signoff | WITNESS POINT
071da937-196f-4dbf-ac54-4880807d9d2f | checkpoint | TS1.4 - Topsoil location, destination and quantity catalogued.
2f69d885-0944-5510-bc4d-b099d07f8d6e | note | Responsibility - ENG
76b50feb-f81f-5024-9cc6-1a08b9096a8d | note | Test Method - Visual
cfd53ca6-93ea-522e-990b-36f528577392 | note | Conformance Criteria - Topsoil register to be maintained with information on topsoil volumes and stockpile locations
9fef3602-e591-50a2-8b1e-b28b30b00301 | note | Frequency - As required
de9b897a-7bf0-558d-a79a-ab5d0a872b6e | note | Link to ITP - PC1.11
4278a0ee-23c0-5b19-8a90-69a59d37c005 | note | Thiess HP/WP Check - HP
d7122674-faca-594e-887a-749570912de2 | note | Inspector HP/WP Sign Off - HP
05dccf20-f68b-4781-954e-06157df5e77b | signoff | HOLD POINT
c6e48c99-ba54-4abd-bc57-c3bcd1e665fd | checkpoint | TS1.5 - Surface level check and survey pick-up
765c1ef7-26db-5fcb-81b9-462bb14fbba4 | note | Responsibility - SURV
6503a485-f9c8-558d-811b-469336ece816 | note | Test Method - Survey / Field Test
64c8342e-8aae-5f7c-a4e3-df39e8aecf3b | note | Conformance Criteria - Stripped surface level picked up as per Table 10 C15 (DXF file format, volume calculated and filr saved in Construction Team Sharepoint and detailed in register
162e926d-aa9c-5849-b1af-ef6f44f75ea6 | note | Frequency - As required
2ed18220-a06f-52d7-9f65-00887d5aad21 | note | Thiess HP/WP Check - HP
9e188d56-9fad-5d14-b173-8c642a6c6397 | note | Inspector HP/WP Sign Off - HP
af4ae563-b4e9-47a2-a180-1d478211e8ec | signoff | HOLD POINT
ae6c69bd-ecc2-454a-9bff-6080c8c1c94a | checkpoint | TS1.6 - QA close out
8efc1984-16d2-53ba-a057-5431c08fd38b | note | Responsibility - ENG
0e4486bc-38e8-544f-ac30-fb17669c1687 | note | Test Method - Visual
c7e83a05-827a-55ab-a626-c824caa8593d | note | Conformance Criteria - GDP permits closed. ITP closed. Approved MDR.
d228505a-fca4-59be-b984-2e29b12b43a9 | note | Frequency - As required
e910bce3-f30b-59aa-b87d-43474fc1cf31 | note | Thiess HP/WP Check - HP
ef4ec3ef-ada0-5aae-b30f-6405d1fe60ab | note | Inspector HP/WP Sign Off - HP
5e2f8d5f-e7ee-48e0-844a-1e4cf9f054a9 | signoff | HOLD POINT
1e0915ac-c4f2-4889-bc14-8ff55ed38f8d | checklist | ITP-003 Subgrade/Foundation Preparation | itp | ITP-003 Subgrade/Foundation Preparation
3888cb15-c6e9-4774-94f4-ef0136a8d2b8 | section | Subgrade/Foundation Preparation
ac475546-f2ce-4c02-a316-d1bc173edfa8 | checkpoint | SP.1.1 - Underlying lot & ITP signed off and conforming
0ba38702-7e4a-5305-999e-9d0c380b72b1 | note | Responsibility - ENG
cd2dc35a-9502-5741-8b68-f7ea4a27f70c | note | Test Method - Visual
cdae2c66-de7c-5ca1-aaa5-1dcaadf88613 | note | Conformance Criteria - Topsoil ITP closed out
39fb73af-ee7e-5cfb-a384-6dabf3434961 | note | Frequency - Prior to Works
8ee4a552-2995-58d0-9e48-752e910a3518 | note | Link to ITP - TS1.6
2897bed4-d43c-43af-aa95-e7d21d62accd | checkpoint | SP.1.2 - Embankment fill material
6698839b-9391-5658-8be4-54b8641f1d75 | note | Responsibility - ENG
afc74dae-bdf5-5e03-929d-edad53d7c4be | note | Test Method - Visual
e98679c2-b70a-536b-9a9c-bef3a3d5405e | note | Conformance Criteria - Ensure CBR10 subgrade replacement materials have been approved for use and within specification
6171a00d-a560-5761-b6c3-27e3f1536543 | note | Frequency - Prior to works (Check if this has already been completed at ITP Pre-construction stage)
cd5ca6cd-ecd1-5805-9164-3664d4d56063 | note | Link to ITP - PC1.12
8ebc67a8-3f8e-5cfc-aa2c-2ab9989333fa | note | Thiess HP/WP Check - HP
c22e0b29-ee08-5f77-a31c-95c7a96e983a | note | Inspector HP/WP Sign Off - WP
e6f51fb7-6c5b-4f3e-b073-2d76ec83af4c | signoff | WITNESS POINT
bf2a450e-c73d-4e58-b6c5-f8d0ad38ec50 | checkpoint | SP.1.3 - Proof rolling
6ac50545-6961-5f6e-9358-6a0ee1fb360f | note | Responsibility - SUP
c709b948-1ca6-56d0-9cf6-aefd7aedbedc | note | Test Method - Field
c378f6ef-6f7b-516a-8e9d-004032c7b05c | note | Conformance Criteria - All subgrades and foundations shall be proof-rolled under a standard 8 tonne axle load or 10,000L water cart or heavy self propellled smooth drum roller dynapac 620D or equivalent to confirm that, in the Inspector (Sedgman) s opinion, deflections are negligible
3a550ce8-816b-5397-a561-01745103d955 | note | Frequency - As required
ffbdbde8-4eed-59a2-a503-187d9143d7f6 | note | Thiess HP/WP Check - HP
118fb4dc-b6f4-5712-8aa5-f3abc584a348 | note | Inspector HP/WP Sign Off - HP
6e4cdf2a-ea9e-4e8c-aef7-9e25439a1400 | signoff | HOLD POINT
f18384a0-36b1-404a-ba16-b643c5ba2214 | checkpoint | SP.1.3A - Survey Set out
4b25c72b-e94d-529d-aa6b-3835cde661fb | note | Responsibility - Surv
6db7605f-6648-5850-b3e9-c41e7f2cfe70 | note | Test Method - Field
d0b3b03b-7fa3-511c-b9b7-9c1db665c392 | note | Conformance Criteria - Areas of work to be set out by surveyor and/or models in plant
662d8646-ee30-5fd1-9ce4-7ccc7f1318a9 | note | Frequency - As required
57f8ebaa-8d19-5e99-8c43-2d16b8aff760 | note | Thiess HP/WP Check - HP
45364d23-92d3-5007-895d-5930c2185259 | note | Inspector HP/WP Sign Off - WP
4d57dd0c-68ce-48ab-bd54-2cee86b3fca9 | signoff | WITNESS POINT
dbba825e-74ac-4f55-a21f-fc1ed370c529 | checkpoint | SP.1.4 - Removal and replacement of unsuitable material
747e0dbf-fcba-5695-b1a3-01b9361dabf7 | note | Responsibility - SUP
30352755-f0c8-5be8-bb2c-b08aec36a9b4 | note | Test Method - Field
21dbc2ce-af3d-5371-a91b-5b924c2fdfbc | note | Conformance Criteria - Determination of unsuitable material by the Level 1 GITA or Inspector (Sedgman) is required prior to the removal of any unsuitable material. Unsuitable material criteria is in the specification.
e4d39c20-3fe5-5de7-bc69-b4f7f854c5fd | note | Frequency - As required
153058c6-af8e-59bf-ba0a-0d361dab80d0 | note | Link to ITP - PC1.12
c84d290d-5958-537c-9c8e-48a52d608cc3 | note | Thiess HP/WP Check - HP
47ac2868-dfa4-5963-aa63-9fdf4d28309a | note | Inspector HP/WP Sign Off - HP
abc7c254-a1c2-4d1e-a2cc-9dda06113411 | signoff | HOLD POINT
4fd12e0e-f712-429a-8540-2f342f7bb820 | checkpoint | SP.1.5 - Subgrade/Foundation preparation
53ba4411-a5de-531c-961b-c446ae05e42d | note | Responsibility - SUP
d0ce048c-197d-5912-80e4-60df6073967c | note | Test Method - Field
36fa4a64-d46f-5f5c-ba5f-c800dda0a565 | note | Conformance Criteria - Foundations for embankments to be ripped 200m deep, moisture conditioned then compacted. Density requirements: < 300mm from finished level under roads & structures minimum RDD 97%, all other areas and depths RDD 95%, moisture content -1% to +2%, normal level of testing 1 test per 500m3, reduced level of testing 1 test per 1,000m3.
aa96d8ee-81e4-5cf0-9311-27c35702a144 | note | ○ All material exposed in cuttings at subgrade level minimum CBR 3 or DCP 150kpa. If CBR2: Remove & replace with CBR10 select fill 150mm deep. If CBR1: Remove & replace with CBR10 select fill 250mm deep
0d516928-6b59-57fe-b7ca-1ee4b1414d64 | note | Frequency - As required
7ad79ff9-eae9-5987-9e5b-82402f192491 | note | Link to ITP - PC1.12
ed5e1566-2280-51c3-be8e-1eb5461ee755 | note | Thiess HP/WP Check - HP
0e74b08d-944f-5d4f-a1a0-598735ce57d8 | note | Inspector HP/WP Sign Off - HP
c760cec8-8ceb-4a0d-a985-5324d40c2be8 | signoff | HOLD POINT
187efc59-29ad-49ed-8390-8b60becf1967 | checkpoint | SP.1.6 - Trim subgrade
b3913e7c-bebc-5d12-9a25-bb41ac3c832f | note | Responsibility - SUP / SURV
ae93ba34-1d60-5116-972f-c6a9676fd814 | note | Test Method - Field
a76edf78-b419-5b0e-8f24-353676836a66 | note | Conformance Criteria - Trim all subgrade to the lines and levels shown on the drawings in accordance with the following tolerances: Top of bulk earthworks +/-50mm; Road subgrades & under buildings & structures +0mm to -25mm.
549c5914-07e3-55e7-bad0-0bbf1fce3fab | note | Frequency - As required
ffcc823b-be30-5129-a036-a226605a90d8 | note | Thiess HP/WP Check - HP
f45a1c01-4b58-5b13-93cd-bdb9bab52ee2 | note | Inspector HP/WP Sign Off - HP
f23b4a57-60f2-4a1f-bbca-c06f05da3796 | signoff | HOLD POINT
71594be2-04a9-4642-8c27-46fc02041e66 | checkpoint | SP.1.7 - Surface level check and survey pick-up
ae3e3dc0-bbb7-5161-ab48-8f3e93da7c89 | note | Responsibility - SURV
0233e3da-d7b0-57cb-a28f-791670b10318 | note | Test Method - Survey / Field Test
181a65b6-888f-5718-abc5-1c5ea421f1f5 | note | Conformance Criteria - Surface level picked up as per Table 10 C15 (DXF file format, volume calculated and filr saved in Construction Team Sharepoint and detailed in register
8205adaf-59f9-5e9c-94e0-2407ce8f2386 | note | Frequency - As required
816da858-ab98-54c1-b51c-3cfa04e1791f | note | Thiess HP/WP Check - HP
8fd83ed0-b72c-5af0-9b4a-dc40044dbcee | note | Inspector HP/WP Sign Off - HP
4bcc759d-350a-4250-8f6b-244794b056e2 | signoff | HOLD POINT
cf8c9bf4-266f-4abf-8026-2827cb980a71 | checkpoint | SP.1.8 - QA close out
f480ed2e-dad9-5d6f-bd96-060b4d89131c | note | Responsibility - ENG
1a40051b-4408-5dcb-b87a-220c77689e1a | note | Test Method - Visual
f5308beb-802e-5f5c-af91-fc47fbd956cb | note | Conformance Criteria - GDP permits closed. ITP closed. Approved MDR.
5dd34aff-46bd-5dab-b2af-b6da8a1c725f | note | Frequency - As required
348d3807-5f57-5b32-ba96-d3d360a60099 | note | Thiess HP/WP Check - HP
b9692b12-b245-507c-a77b-b367d15bbc3d | note | Inspector HP/WP Sign Off - HP
fe791962-27f7-473b-bde7-91e7f40b4125 | signoff | HOLD POINT
010e0c6d-951b-4ef9-941a-9ea0f881fde8 | checklist | ITP-004 RCP Installation | itp | ITP-004 RCP Installation
bcd810f0-bd1c-493c-a0f7-4aa16e546710 | section | 1.0 Pre-Construction
1b3a1513-b678-4b99-b6d3-43cc70619a41 | checkpoint | RCP1.1 - Drawings supplied most current IFC
a4aacebf-171b-5589-81ef-e7db3359c74e | note | Responsibility - ENG
df665c3b-ed53-581f-a541-00db45ac308e | note | Test Method - Visual
8a2663ba-3a19-5fbd-a510-b4447a77b6af | note | Conformance Criteria - Reviewed drawing register
e1fc5ac9-094e-5c3f-b9b8-6a1cad559c19 | note | Frequency - Prior to works
dc6fe15c-1fb7-58ab-bd9c-70e33c087ca7 | note | HP/WP - HP
78a3b4cb-df5e-4259-bd01-0d06330e8e78 | signoff | HOLD POINT
a3ff5f79-821c-4bbc-8a0d-c574a2deea4b | checkpoint | RCP1.2 - Define RCP ID
bd3ab7df-c91e-50ed-9c41-b6c6b564eeb1 | note | Responsibility - ENG
f2cd55c9-a1ad-5d00-8b04-cfdea5a6ddcc | note | Test Method - Visual
7a92402f-d212-5ba3-932f-a049223bbf1a | note | Conformance Criteria - Inspection Register. Allocate ID for reinforced concrete pipe, define work area
3eabb13e-a5fc-55d1-9e5e-0c2304fa3e88 | note | Frequency - Prior to works
01fa1a7c-777c-5326-96dd-c13febbaac90 | note | HP/WP - HP
9b40fdda-d960-4284-a862-8dfb98171065 | signoff | HOLD POINT
e2eaff84-907c-4e99-a499-7f1652a18357 | checkpoint | RCP1.3 - Lot Register/ WBS submitted and approved
9d4aa403-6f6a-56b3-9372-ec231ffee1e7 | note | Responsibility - ENG
64c2a9f9-6b2b-5b57-8a32-fb3bd9d4174e | note | Test Method - Visual
ba7ba610-14b2-5188-a1e6-92386ddc6c3c | note | Conformance Criteria - Approved WBS
17885f00-406b-5763-9247-ed7adbacc4bf | note | Frequency - Prior to works
5adf77d9-fa43-553f-82e4-d6e8eb9048d2 | note | HP/WP - WP
ca05ac74-ea8b-45d4-83f9-bab5020bb454 | signoff | WITNESS POINT
eee4d041-394d-4bdc-9161-bd3ffe86de15 | checkpoint | RCP1.4 - Underlying lot & ITP signed off and conforming
7e277ac4-11ad-5e40-9244-52e7e58a8071 | note | Responsibility - ENG
0c8f7f10-d540-5ed9-a151-284222351156 | note | Test Method - Visual
f0367775-9636-538b-b3e2-cfee1452cc27 | note | Conformance Criteria - Subgrade prep ITP Signed
4627fa70-eb8e-5276-a9f6-2e41cf56ff42 | note | Frequency - Prior to works
b5bb2635-6b24-5837-88d6-392ed9200951 | note | HP/WP - HP
6ae1236e-00fd-41d0-adcb-7fe315b39cb5 | signoff | HOLD POINT
9fd03587-637a-44af-9e2e-3403e67262d6 | checkpoint | RCP1.5 - Certificate of compliance for RCP Material
8ba8d961-bcba-575b-a70c-8221d691db4a | note | Responsibility - ENG
fb518153-c4c9-599d-9784-df1212063dd3 | note | Test Method - Written
5fa30fd3-a30c-5c0d-b147-18f8f133a4fc | note | Conformance Criteria - Supplier to provide certificates indicating manufacturing processes, materials, thicknesses, classes, and diameters (Only culverts with materials & dimensions complying with the culvert schedule & specification to be used).
8cf8f6f2-49a8-5b2f-8d01-435496f6c210 | note | Frequency - Per pipe
dadf5e5f-dbe9-5839-8f7c-dce6dde67535 | note | HP/WP - HP
b344cfc7-f523-4fa2-80a8-9b815274c179 | signoff | HOLD POINT
21e2741c-a798-4e5a-98ea-a31953dcc9a3 | checkpoint | RCP1.6 - Inspect reinforced pipe culverts for damage
510ea7b2-1f35-5a8c-be2d-a617092ba77b | note | Responsibility - ENG/SV
3307ff91-9395-5339-ae22-fed4c21b27b9 | note | Test Method - Visual
c605fc15-0b95-5237-bf71-4fad6d6f87ef | note | Conformance Criteria - Prior to installation, Pipes are checked for damages and accepted/rejected and documented on Incoming Goods Inspection form
b707dbed-6891-5e5f-996b-f590d76e0587 | note | Frequency - Per pipe
fc05bda0-7cfd-566c-b319-df86a9634428 | note | HP/WP - HP
17ecaae1-e8c3-400e-ae7e-b91084f51cfa | signoff | HOLD POINT
da327277-4581-4fec-9efc-c9ce2dfc1626 | section | 2.0 Construction
5f99f083-bd7a-4240-bb56-a6513b0ad898 | checkpoint | RCP2.7 - Trench Excavation
c62dd798-30d9-55b6-9719-cb98ed9e671c | note | Responsibility - SV/SC
1c623934-6d2d-5d7b-8e83-f6226c870251 | note | Test Method - Visual
192f5475-7e7a-55bf-b802-3502072f98b0 | note | Conformance Criteria - Trenches should be excavated to the required width and grade indicated on the IFC Drawings, with allowance made for benching for excavations greater than 1.5 meters.
4d99e440-ce89-5b56-b3d4-0f2fde0da81f | note | ○ Excavations must be kept free from water until work below ground level us adequately set or protected
26e33e4b-e8e6-54aa-87e7-3c1a0727a43a | note | Frequency - As required
28ba21a3-654e-513b-8455-8a42b0612b39 | note | HP/WP - HP
84dd3f76-d9bd-4de2-aefd-c9b56cc67b8c | signoff | HOLD POINT
9abc2cf3-3ebd-40c3-a008-5c8afe13ab60 | checkpoint | RCP2.8 - Bedding
7a995bcf-015e-5546-9827-de648a94a4d1 | note | Responsibility - SV/SC
76ab9dd0-7895-5420-8f1c-ed2586e46a53 | note | Test Method - Visual
2711b593-0da7-5a67-b619-3ef4e4329c9b | note | Conformance Criteria - Culverts shall be bedded as detailed on the Drawings. Proposed
957c6294-5252-5c6b-ad8f-c46338a51a43 | note | Frequency - As required
40873e2e-581a-55ae-85e2-45f5188c79e7 | note | HP/WP - HP
0094bca9-f5e9-444c-b170-f3eaa36d3310 | signoff | HOLD POINT
980cb612-3b1f-4948-be4f-ea2d97c5ad43 | checkpoint | RCP2.9 - RCP Installation
f986d57c-aa74-5859-b681-d4d43425e32a | note | Responsibility - SV/SC
ec0fb102-ee15-58c8-a28a-cff8bc7e8645 | note | Test Method - Written/survey
0959b8c6-7d24-5417-ab64-96e0a95e728d | note | Conformance Criteria - Culverts are to be installed to the line, level, and grade shown on the IFC Drawings. Inlet and outlet invert levels shall be as shown in the Drawings plus or minus 10mm. Inverts shall be smooth and of uniform gradient throughout each culvert length.
b0760e81-3fb9-5f87-8386-e4352f120eb0 | note | Tolerances:
e0408b1f-90d2-5e4d-8940-1ce733429e5d | note | ○ Vertical level: ± 10mm
f980cab6-dba3-5de1-a198-55d97da85384 | note | ○ Horizontal Alignment: ± 25mm
5c5c42b8-59fa-5640-97ce-c7cf3a315b86 | note | Frequency - As required
9bd65722-6507-5be8-84ba-d465c52382ff | note | HP/WP - HP
f0cf5b45-b952-4de6-b5c3-522098197da4 | signoff | HOLD POINT
6744fe45-cbe1-42fc-9e07-36442691798f | checkpoint | RCP2.10 - Backfilling of culvert
f6a2f34f-0089-5d78-b186-01c03bdb80df | note | Responsibility - ENG/SV
5ac2048e-d459-5ceb-954d-56ca75cfcf62 | note | Test Method - Visual
95968821-c489-5dc4-b025-745a8334401b | note | Conformance Criteria - Backfilling and compaction shall be carried out in horizontal layers of uniform thickness not exceeding 200 mm of uncompacted selected fill material for 300 mm all around the pipe or culvert. Compaction in this zone shall generally be by hand tampers to a minimum density of 95% of the standard maximum dry density at +/- 2% optimum moisture content. Compaction of backfill in the remainder of the trench to subgrade level shall be to a minimum 98% modified MDD at +/-2% OMC shall be advised
92f38c01-2aa7-5ebe-af6c-1d0ded24edd0 | note | Frequency - As required
d884d3c9-653e-56ae-9678-7a54f64f3c21 | note | HP/WP - HP
0e7e983c-c392-42ac-810c-7028e1deca5f | signoff | HOLD POINT
969947be-626a-40d1-bc13-819f2e7cc7b3 | checkpoint | RCP2.11 - End Treatment – Headwall & Wingwalls (Reinforcement)
7d724690-d36d-53cd-a673-65d07ed5cc12 | note | Responsibility - ENG/SV
086fbb4c-5b7a-5a48-9d37-3b7e13829cf4 | note | Test Method - Visual
5114ec53-3c27-58ea-be63-b51987298736 | note | Conformance Criteria - Reinforcement installed as per IFC design drawings
087035a4-ead7-5a9e-817e-c939b19c4ad2 | note | Frequency - V
cfdd3212-9157-50b6-ba02-12ecf47edf45 | note | HP/WP - HP
9d7f81c7-2bd0-44da-8a2e-2a2081fc04ab | signoff | HOLD POINT
d182e6b8-e74b-4565-8218-4bed820fd55c | checkpoint | RCP2.12 - End Treatment – Headwall & Wingwalls (Formwork)
7cdb1916-fc65-590d-a4eb-fa79d6946c8c | note | Responsibility - ENG/SV
f85ccf81-f09f-5dff-9f20-137a1b59c880 | note | Test Method - Visual/Field Survey
04c00cb2-0e94-5702-b4b1-b892e31f337f | note | Conformance Criteria - Formwork installed as per IFC design drawings.
6474c17e-0a90-50e2-bac3-18a3ce994be3 | note | Tolerances:
5fe57c4b-dda0-5203-9bd7-63206b00d494 | note | ○ Variation in cross-sectional Dimensions: + 5mm
d6ea1f61-ea27-5460-8ed7-0106e259c934 | note | ○ Variation in overall dimensions: + 10mm
9e8f26a3-2dee-5221-adaf-f9a929d50c7e | note | ○ Variation in surface level: + 5mm
4894c764-4eed-5101-a19c-37e50b168ace | note | Frequency - Each inlet/outlet
7525f319-694c-51ff-ad26-e50f5e7d21f6 | note | HP/WP - HP
51f2810b-9de3-4564-85e9-1784f4711ae2 | signoff | HOLD POINT
dbd762d8-b5af-4b90-bb78-eb60a39c9f5a | checkpoint | RCP2.13 - End Treatment – Headwall & Wingwalls (Concrete)
237b4e5c-5984-53e2-90af-25bfa6b49276 | note | Responsibility - SC/SV
6e4694ab-2d41-5ee1-b575-390eb90dc7a7 | note | Test Method - Visual
b794ad17-dbc8-5670-8315-71a072c71eaf | note | Conformance Criteria - Concrete placed and compacted to specified strength (N40) and slump (max100mm).
0fbaa609-c1f4-513e-84c0-9e0c811c0ca9 | note | Frequency - Each inlet/outlet
2239c767-8b55-5af5-a9ed-18f41f9a517f | note | HP/WP - HP
fe6cada3-8994-4551-8fa6-65904ce0e6d7 | signoff | HOLD POINT
7cb7c32d-7d51-439b-bca5-bdba7c65b1eb | checkpoint | RCP2.14 - Rock Protection
1aca3833-d4ee-5f5b-95b6-a3e81fe9907c | note | Responsibility - SC/SV
21d2ef86-da78-5e3f-b1f6-465e6dc1d09c | note | Test Method - Visual
6e7ec58d-8826-5eab-8eb3-008e9894cd23 | note | Conformance Criteria - Dimensions and class of rock protection shall be as specified in the Culvert Schedule and supplied IFC Drawings.
74276163-6b6b-58a5-9c83-d5bfe438ecd8 | note | Frequency - Each inlet/outlet
cb9f8697-2a81-50d5-bad7-6053d541410b | note | HP/WP - HP
299c20d8-e330-4fd8-bd71-87bb5629e5c2 | signoff | HOLD POINT
a3293d54-d437-40ba-832e-fa3f5b592ca3 | section | 3.0 Post Construction
511e13d7-a7ba-4110-af10-f7d0a9723274 | checkpoint | RCP3.15 - Works completed and update ITP/ Lot Register/ MDR and close out of GDP
cc4c4d61-91aa-5702-bb71-30191f88ba22 | note | Responsibility - ENG
04968476-c886-53ef-8b56-116cf3dcb036 | note | Test Method - Visual
8e2e92e8-66da-5e87-834e-c0f6429d05c6 | note | Conformance Criteria - GDP permits closed.
81bfe09f-ab3a-5f27-a301-6fbe6e38a7cc | note | ○ ITP closed.
5954fb59-df58-5672-81a1-47f1247e9cf9 | note | ○ Approved MDR
f6c3fe36-be45-5f35-b78f-ca66fec32398 | note | Frequency - As required
71bcd464-bfc3-5a88-94ec-5e66074455df | note | HP/WP - HP
0985de39-1d78-45e8-833f-3a49b66440df | signoff | HOLD POINT
e75b191c-dd7a-40a2-a54d-7b0af1535acf | checklist | ITP-008 Embankment Construction | itp | ITP-008 Embankment Construction
e8558513-7ab6-48d1-98de-433944eb476e | section | Embankment Construction
4a614c52-e477-4c8c-b9e8-f9f66f963fae | checkpoint | EC1.1 - Underlying lot & ITP signed off and conforming
635d023a-43cc-507d-b6a4-24cad7028583 | note | Responsibility - ENG
7a8f9240-8a69-5c27-80fb-9d3502e0f1b1 | note | Test Method - Visual
783de080-e185-55a5-b451-0ac7c73b29a8 | note | Conformance Criteria - Subgrade/Foundation Preparation ITP signed off
ba80dbfd-0503-5808-bd81-935e41563a00 | note | Frequency - Prior to works
e20c78d0-1941-5154-ac0b-ffc993dea396 | note | Link to ITP - SP.1.9
3f344af9-d08a-5865-81ef-d9da96d5e264 | note | Thiess HP/WP Check - HP
7db41919-c6e1-5e66-90ec-00c0aa29a5c9 | note | Inspector HP/WP Sign Off - WP
51d9a739-4898-4980-a216-4b966f532089 | signoff | WITNESS POINT
492095ef-bc3f-4c0b-b398-01ff56260bd6 | checkpoint | EC1.2 - Embankment fill material
98a574b1-314a-575b-aca7-fe9482091f7c | note | Responsibility - ENG
627647d6-75a4-5752-8fb3-d2056f51c319 | note | Test Method - Visual
723a775a-1db8-5bf8-8f2a-c909a29ed3c3 | note | Conformance Criteria - Ensure embankment fill materials have been approved for use and within specification
8bd82068-6705-521e-814f-145754eb5f73 | note | Frequency - Prior to works (Check if this has already been completed at ITP Pre-construction stage)
a780ca05-c85c-5f5f-85c1-2b0adbf240d3 | note | Link to ITP - PC1.12
9a67a0a0-915a-56ff-b4f5-9cb31fe49ffc | note | Thiess HP/WP Check - HP
2b09a7b7-e569-5fd1-aea6-8705fa41ac77 | note | Inspector HP/WP Sign Off - WP
a8f80374-068c-4565-8062-7727b7ea763c | signoff | WITNESS POINT
6493e315-0ff4-4f7a-9623-6ef291088e0c | checkpoint | EC1.3 - Survey Set out
2c32f299-db28-5f0d-9219-dad69aa702da | note | Responsibility - Surv
b538f08c-0104-5524-b035-0648db232fbd | note | Test Method - Field
4f98f1fa-6f4a-54b5-9861-396450f47579 | note | Conformance Criteria - Areas of work to be set out by surveyor and/or models in plant
7fd90e11-4239-5ae5-b1f6-d92dd61588ac | note | Frequency - As required
cea1e636-bbb1-5c17-b1d7-a6c6b4e0e266 | note | Thiess HP/WP Check - HP
e6df3954-8c47-523e-9c9a-036c5c7a7d0d | note | Inspector HP/WP Sign Off - WP
78e12c6e-590d-4b8c-8cee-4a2451ccdfef | signoff | WITNESS POINT
ccdc3a9c-ac5e-4033-8c3b-ff3b1cb8c838 | checkpoint | EC1.4 - Place, moisture condition & compact embankment fill
cac8963c-7cf9-5eff-8b81-1bef0d83b70e | note | Responsibility - SUP/GeoTech
3617b082-f963-5109-83e7-e68d12666756 | note | Test Method - Field Test
5503e2c0-6737-5ccf-91b7-cf28d197e969 | note | Conformance Criteria - Layer thickness minimum 150mm maximum 300mm.
45b6b68f-e933-5ad8-83b0-7eb3946a126c | note | ○ Density requirements: < 300mm from finished level under roads & structures minimum RDD 97%, all other areas and depths RDD 95%, moisture content -1% to +2%, normal level of testing 1 test per 500m3, reduced level of testing 1 test per 1,000m3.
466bda59-dc24-50d2-93ff-8affa9feffb8 | note | ○ Subject to client approval oversized material up to 500mm can be used in general fill at the following depths: 600mm or greater in depth below subgrade for stockpiles, road surfaces and embankments, or 2m or greater in depth below the footprints of structures.
dce5ac04-f693-509c-a6b3-2ebebcba7c42 | note | ○ Rock fill may be used >600mm below subgrade level.
41c0933b-5d94-550d-8cf7-39b243dc4961 | note | ○ Material containing a high proportion of large particles may be used in embankments using the Mechanical interlock method of construction.Maximum layer thickness 500mm.
46837dee-32c0-53a6-9d17-ff07221c7e8f | note | Frequency - As required
5f766555-e044-53b1-8d65-3f86e6c06f19 | note | Thiess HP/WP Check - HP
d1404653-b3df-5b6b-a697-a65cbf269dc0 | note | Inspector HP/WP Sign Off - WP
ce87cdd3-a9d0-4757-87ac-a2ea0fef9fb5 | signoff | WITNESS POINT
39df1a89-b400-4f6a-b068-a0ce2d3b0a8b | checkpoint | EC1.5 - Trim embankment
b6161dae-c37e-5e66-afec-102e28e5ccd0 | note | Responsibility - SUP / SURV
db15ec6c-0fb7-5015-97ad-7b1db5e7f266 | note | Test Method - Field
50bbc415-a3fc-5d69-aaf3-55b1d84f8d36 | note | Conformance Criteria - Trim all embankment to the lines and levels shown on the drawings in accordance with the following tolerances: Top of bulk earthworks +/-50mm; Road subgrades & under buildings & structures +0mm to -25mm.
3d9fe111-61b0-5165-ad56-3439aaa484d6 | note | Frequency - As required
080e8708-cbfa-5d10-a02b-897d3d617cab | note | Thiess HP/WP Check - HP
10b4ef1c-dad3-53bc-a762-8fbf3aba37a1 | note | Inspector HP/WP Sign Off - HP
2456b688-6f43-425d-b0ac-2af98045b4fa | signoff | HOLD POINT
836357fc-3e4c-4451-a173-3e657eb706b6 | checkpoint | EC1.6 - Proof rolling
e383c7ba-7517-5fe1-b83c-121bf6ce2c2c | note | Responsibility - ENG/SUP
6ef541cc-2c29-50f9-9bbb-66ae1cbd7327 | note | Test Method - Field Test
8d3648f3-7440-5502-8fe1-08b378df709d | note | Conformance Criteria - Proof-roll embankment finished surface under a standard 8 tonne axle load or 10,000L water cart or heavy self propellled smooth drum roller dynapac 620D or equivalent, to confirm that in the Inspector's opinion, deflections are negligible.
90944651-d678-5c95-a7f1-08f0dbe2c70e | note | Frequency - As required
df90c852-a5c1-5852-b384-1ccc0703ed92 | note | Thiess HP/WP Check - HP
45a06049-4ccc-5fa4-8cea-b75345a03dd9 | note | Inspector HP/WP Sign Off - HP
a46f56dd-fd73-4d13-b3b2-efa98fe73ed2 | signoff | HOLD POINT
2056572e-b705-4f91-981b-da286938b639 | checkpoint | EC1.7 - Surface level check and survey pick-up
6a68517f-e29a-540a-a166-b4ed1f6cc0aa | note | Responsibility - SURV
463ad56d-2dfe-5b12-967d-2e9d9176efe6 | note | Test Method - Survey / Field Test
b987ce65-2b06-5023-91f8-ddcef3797e25 | note | Conformance Criteria - Surface level picked up as per Table 10 C15 (DXF file format, volume calculated and filr saved in Construction Team Sharepoint and detailed in register
5e8239db-904d-5e22-863e-bb8645b2ffd5 | note | Frequency - As required
590d7183-81b5-5457-99b3-3ffac96b3b49 | note | Thiess HP/WP Check - HP
a0a0b0f2-922a-5f5a-83f3-21e33d5bcb84 | note | Inspector HP/WP Sign Off - HP
3315d813-4d2a-4914-9e0a-bbdb04f27890 | signoff | HOLD POINT
cd09000b-518f-46ba-8ae5-98753bd77965 | checkpoint | EC1.8 - QA close out
5f98f2d3-89ee-5c8c-b473-d73e0e57bef0 | note | Responsibility - ENG
e350a75b-9841-500c-96b5-73fd23a695e7 | note | Test Method - Visual
864c182e-1c34-5189-b0fc-5df02f7a0727 | note | Conformance Criteria - GDP permits closed. ITP closed. Approved MDR.
163b2fc0-398b-53e7-9368-7252f7f13d9c | note | Frequency - As required
4de988bf-f463-5ec2-ac20-2b34de1ad1ef | note | Thiess HP/WP Check - HP
324c1887-2a4a-596e-a703-e3e18fd31702 | note | Inspector HP/WP Sign Off - WP
361d46ee-d8e9-4f66-b43f-ad76ae5b1f3d | signoff | WITNESS POINT
16032528-d2b5-4c24-a800-78e1763a1773 | checklist | ITP-009 Unbound Gravel Pavements | itp | ITP-009 Unbound Gravel Pavements
2ac16c39-8a1f-4d3c-891c-400476a3c65d | section | 1.0 Pre-Construction
26324e01-52be-4068-8fea-22c36ef22220 | checkpoint | GP1.1 - Drawings supplied most current IFC
ce02b22f-bd6d-5b1f-a166-8a128612ca85 | note | Responsibility - ENG
d9d949bb-0f4a-5392-83f9-a9da5e4b8d65 | note | Test Method - Visual
ea5a6775-7bd4-5396-a748-a150ccd8322f | note | Conformance Criteria - Reviewed drawing register
24180e7b-e081-59ea-8b00-dd6aae2a2fe9 | note | Frequency - Prior to works
f6cec98c-4f58-5269-9e9e-cc57c8ceaf3f | note | HP/WP - HP
2c971e9e-c82a-49d9-a3c5-d4e3b1fb3084 | signoff | HOLD POINT
12c42d3e-2a61-423b-accd-5b7924a373d3 | checkpoint | GP1.2 - Management Plans submitted and approved as per PMP
61634936-80f1-5c18-a1f4-e2fc0bdb8824 | note | Responsibility - ENG
502883bb-0775-5315-a1b5-952d69a6918b | note | Test Method - Visual
73d5a38e-2cd0-5cb9-903a-449e3aaaf099 | note | Conformance Criteria - Approved Package MP’s
7123f834-f4ce-5e36-a2b5-0c2fcdb84cfb | note | Frequency - Prior to works
b046604c-9cd6-5b8c-bd8f-3d420c91d398 | note | HP/WP - HP
83ec0c54-5b43-40bf-9fbb-fcc5ac627825 | signoff | HOLD POINT
209c2651-94d0-4c60-a70a-e367067269f4 | checkpoint | GP1.3 - Inspection Test Plan (ITP) submitted and approved
5a2783e2-7f33-592e-9391-e1e026631214 | note | Responsibility - ENG
a6868bf0-84cc-5fd1-8734-805ddb277708 | note | Test Method - Visual
994b87ac-921c-5312-a2fd-90786d75e492 | note | Conformance Criteria - Approved ITP revision
99921d14-6884-5e36-a20b-2967515c10c6 | note | Frequency - Prior to works
a76a9108-08c4-55f6-b41b-67231acb772a | note | HP/WP - HP
d63a7625-3baf-4def-9bfe-787bfd11af10 | signoff | HOLD POINT
a5d920a2-92e0-4ae4-9a7d-43072889cd49 | checkpoint | GP1.4 - Lot Register/ WBS submitted and approved
bc7038be-d55a-51e0-9376-5d9a70df762b | note | Responsibility - ENG
8c35490e-856d-534e-97f8-bda3697a6d3c | note | Test Method - Visual
68e66969-d275-586e-bc9f-9c38829f8e1b | note | Conformance Criteria - Approved WBS
fe354df8-13a8-567e-9e01-f7e313bd4da1 | note | Frequency - Prior to works
4cc1ba4e-3ea0-5b00-871a-0178fb0d89b9 | note | HP/WP - WP
43392d70-4aef-4e61-b27e-dd683e7de79d | signoff | WITNESS POINT
563f08b5-d8e8-490b-a79e-23c0c5f2269e | checkpoint | GP1.5 - Pavement material compliance testing
593ae87f-da9b-59ae-ae9d-6f58f67f9946 | note | Responsibility - ENG
86d480fc-801a-5af2-b700-357aceef6db7 | note | Test Method - Visual
78a36930-34ea-5c71-af59-c32d8b146a62 | note | Conformance Criteria - Test results comply with the details on the drawings or where not specified the specification
18f6bab0-e4ae-5ef7-805a-9b5c3f97df9a | note | Frequency - Prior to works
aa4e6c65-9d25-5c3b-a871-9af3f2032b36 | note | HP/WP - HP
4eb72e8b-ca63-4d96-884e-50f418adc881 | signoff | HOLD POINT
63bd5c14-6cb7-4109-8991-abe461f60a13 | checkpoint | GP1.6 - Stockpile locations
afe8589b-95ed-549d-8723-f470a09872e4 | note | Responsibility - ENG
d2248fac-bb4d-51bb-adea-9d213bbefec6 | note | Test Method - Visual
2d90b044-8f14-5627-ad5f-a94d40cfbc0a | note | Conformance Criteria - Stockpile locations shown on the drawings or approved by client’s rep
c3ac073e-b195-5b07-95e6-f8f426b79e0f | note | Frequency - Prior to works
9e88f1c9-12bd-5213-a2fb-b750cf73c3d6 | note | HP/WP - HP
0084a942-5284-4325-9493-163a0f456c87 | signoff | HOLD POINT
fa88868d-6bb1-45bb-ac41-e4cb101fbc32 | checkpoint | GP1.7 - Underlying lot & ITP signed off and conforming
495b547f-3d5d-507e-a05b-7b0b42b069db | note | Responsibility - ENG
f793f566-538a-5dc8-8cb2-ac38d08e933f | note | Test Method - Visual
24c395ba-0b40-595e-a5dc-91df7ec24c92 | note | Conformance Criteria - Subgrade prep ITP Signed
8b579c9f-c1e8-5713-bcb1-b494aa313939 | note | Frequency - Prior to works
87b7a7b7-c1a0-5856-8483-378eba4f4b7f | note | HP/WP - HP
55e62c5c-3fa9-4794-8301-d3f671bdff85 | signoff | HOLD POINT
0a53f102-f70c-4fe7-93ec-f75e6288762d | section | 2.0 Construction
329b4b8d-55b7-4ff3-b5e2-da7253cb9846 | checkpoint | GP2.8 - Subgrade preparation under pavements
813a4aa0-0839-5906-879a-21f3c4942019 | note | Responsibility - ENG
b5d820bd-1c01-5b6d-9e21-e68b078dfeb0 | note | Test Method - Visual/Field Test
7f857e7f-47ff-5c39-990f-5b70ce0959a8 | note | Conformance Criteria - If subgrade material is less than CBR10, subgrade shall be boxed and replaced with 150 mm of CBR10 or greater material. Subgrades shall be trimmed and compacted to within 15 mm of the established grade or cross section. Compaction requirement: 98% modified maximum dry density at +/- 2% OMC.
497bbdbb-dbd3-57df-9298-4d8f84db87b3 | note | Frequency - As required
3df73ae8-6903-5847-b8de-67ce8c9ec74b | note | HP/WP - HP
0ff70cca-b90e-4385-a8e3-3a142edc6f63 | signoff | HOLD POINT
4cbd14c8-7eff-4f23-9854-c1c89c0236f8 | checkpoint | EC2.9 - Surface level check/ and survey pick-up
883f4cc6-bc29-56d1-8dfe-01f24bdb2d8a | note | Responsibility - SURV
e51b3cd9-5768-53b9-9b15-f4eaf56fec03 | note | Test Method - Survey/Field Test
952de667-1597-5a53-b992-cc52cf73fd55 | note | Conformance Criteria - Surface level pick-up submitted to company
ac38d1e5-da5a-5444-bf29-5dd5fb516946 | note | Frequency - As required
e8519609-0672-5689-a68c-a721fe80a59b | note | HP/WP - HP
64c35c74-e7a8-4e61-951c-6077599f6746 | signoff | HOLD POINT
c74cb16c-7f6a-45a7-abca-82c1ace91fde | checkpoint | EC2.10 - Proof roll subgrade prior to placement of pavement materials
4dd0e68e-5238-56b7-90b9-48207da80e30 | note | Responsibility - ENG
ad04ce6c-e5e6-51a5-947e-30ee064bab27 | note | Test Method - Visual
d14fa7ef-05d5-5790-a297-a75c9759270b | note | Conformance Criteria - Subgrades under pavements shall be proofrolled under a 10,000L water cart or heavy, self-propelled, smooth drum vibrating roller capable of operating in variable frequency modes, to confirm that, in the principal’s opinion, deflections are negligible
9fc2f4e1-8e59-5022-a52c-0c709409fc8d | note | Frequency - As required
8c05f25c-74a2-5829-9933-2aeed5ddcd49 | note | HP/WP - HP
42dc5316-9d2a-40ea-b02e-6b42f5119a67 | signoff | HOLD POINT
c871f5e0-768f-462e-8f0a-89391baa67fa | checkpoint | EC2.11 - Placement of pavement material layers
75dead7b-9800-5972-8788-71375a3ccb5a | note | Responsibility - ENG
e03186fa-dac3-5291-ae1b-13b6d239b318 | note | Test Method - Visual/Field Test
55210035-c2a4-5e5d-a4cd-95bc1a5acbbe | note | Conformance Criteria - All materials delivered to site shall be accompanied by test certificates.
4dc03d51-94e8-5045-8153-9b0aa6c8add7 | note | ○ Each layer shall be free from sticks, organic matter, clay lumps and other deleterious material, and be spread and compacted in a uniform thickness minimum 75mm, maximum 250mm as per the details on the drawings.
84c4f96e-917f-57ed-bf0f-97cca21c28f7 | note | ○ The deviation from a 3m long straight-edge placed anywhere on the surface of a layer shall not exceed 8mm.
0d94d6ff-9317-5744-b0b9-8af7986febde | note | ○ Pavement layer thickness tolerances: Base -0mm to +30mm; Sub Base -15mm to +30mm.
baf41884-2d3c-575c-b605-063cb9553c30 | note | ○ Finished pavement surface level tolerance: Base -15mm to +25mm
b2ea26ab-d495-51b2-87f3-4b2027094ca0 | note | ○ Horizontal tolerances: Base, centreline/crown -150mm to +50mm, edgeline/changepoint -100mm to +200mm; Sub Base, centreline/crown +/-200mm, change point -100mm to +400mm
7c67790c-4c12-5700-aa18-cedafea91338 | note | Compaction requirements:
5959fa76-0e9d-5ed6-b8be-7ca15b25af3b | note | ○ Base & Sub Base 100% standard relative dry density (RDD) maximum degree of saturation 70%.
4dbce34c-5477-5944-9356-6c0f39a8066e | note | ○ Compliance testing frequency as per table in Specification Annexure A clause 5.
caf13e1b-a77d-580c-8e46-e9c8f951c5bd | note | Frequency - As required
e2e094f8-7189-5554-b44f-cb72006d1903 | note | HP/WP - HP
954eae12-3372-460e-ba45-58cb8b0aeef7 | signoff | HOLD POINT
fe6baa0e-4119-49b3-bf93-46470a42c919 | checkpoint | EC2.12 - Surface level check/ and survey pick-up
242375b7-945d-505a-ad98-29f77818bf0c | note | Responsibility - SURV
db301325-72b3-579b-a48a-7dbe4fe0e789 | note | Test Method - Survey/Field Test
45add8df-cbf6-59b2-9035-9265ae203c65 | note | Conformance Criteria - Surface level as per the pavement layer details on the drawings, and all layers as per the tolerances listed in item 11 of this ITP.
13b8182e-2cb1-5065-81a9-1e3ae533de8c | note | Frequency - As required
6a2c4aeb-7f64-5b52-9ea4-431a16f7d7d4 | note | HP/WP - HP
59daa3e2-cdaf-40f2-b690-3f6d54bd2217 | signoff | HOLD POINT
3cbbed25-f06a-476b-858f-61b9405a30e9 | section | 3.0 Post Construction
62907706-957c-49b3-8c5e-8410f080c594 | checkpoint | EC3.13 - Works completed and update ITP/ Lot Register/ MDR and close out of GDP
064f8f32-5c1f-597e-9def-5e082eb9eb59 | note | Responsibility - ENG
06f4f82d-14fa-5206-b688-fb664667c5da | note | Test Method - Visual
e4485279-3a36-5c51-9bb1-4ff1e39e0722 | note | Conformance Criteria - ITP closed.
5c6ab4e5-79dc-5996-8e9f-604b6528f9b7 | note | ○ Approved MDR
2e339af6-9f26-532a-8380-2f27563ada13 | note | Frequency - As required
2dcb3626-803b-59a5-9b33-7ceb37b4b296 | note | HP/WP - HP
f63ab955-f79d-4581-a627-ceb70a5f6c45 | signoff | HOLD POINT
625146e1-7fb0-4141-87ad-3630a8a9885d | checklist | Ω (DEPRECATED) ITP-000 Pre-construction (v0) | itp | ITP-000 Pre-construction
afab5920-763b-41e2-b04f-389f3d863f0f | section | Pre-construction
d5f2de5b-1844-4b8b-9494-00345366394e | checkpoint | PC1.1 - Construction Management Plan
9cb08030-a1b4-58b4-aa30-19759969d214 | note | Responsibility - ENG
d97fd768-106c-5aed-8a49-28134e3d84bd | note | Test Method - Visual
40d7ec2a-577f-590f-8a34-904cf05aeb60 | note | Conformance Criteria - Approved Construction Management Plan saved in Construction Team Sharepoint and detailed in register
b132816d-9c22-58a5-8505-653a25659938 | note | Frequency - Prior to works
8d264537-c84a-59ee-8506-57055b051946 | note | Thiess HP/WP Check - HP
9c63b04d-3123-5f87-a40d-243882371884 | note | Inspector HP/WP Sign Off - WP
24a3466b-fbf5-43de-b7ca-11b4744cff97 | signoff | WITNESS POINT
39eaf1a6-ee0d-4100-9bf0-c837b429ac24 | checklist | Ω (DEPRECATED) ITP-000 Pre-construction (v1) | itp | ITP-000 Pre-construction
51535b1a-ac26-4769-bc85-1f7ba1beade1 | section | Pre-construction
dccbd29c-6e53-42a4-aa77-56d5a2245e5c | checkpoint | PC1.2 - Lot Register/ WBS
731f8e63-9c21-51d9-8e55-9d9b575b5560 | note | Responsibility - ENG
5067a1db-2194-5c58-9d4a-8e6cb1f8cf52 | note | Test Method - Visual
ea6fa4bd-af40-557b-a1b1-ef2c1fe6b6cf | note | Conformance Criteria - Lot register saved in Construction Team Sharepoint and detailed in register
94588b25-c4ac-5621-ae43-e8a1da908b68 | note | Frequency - Prior to works
a6e495d4-a85e-5c8b-9e94-d0483d48b40e | note | Thiess HP/WP Check - WP
147f889c-d6d7-50b8-b9a2-f8c4d49faaf0 | note | Inspector HP/WP Sign Off - WP
4fcac2b7-4adc-4364-b8a4-7412fb080e6a | signoff | WITNESS POINT
f72a1074-063a-4d47-a7f1-0395bd9eb44b | checkpoint | PC1.3 - Construction procedures
51a8cb8d-2c61-53cb-99e3-e639f64c30c6 | note | Responsibility - ENG
933726ca-6948-5c00-90d7-15d6999cd3de | note | Test Method - Visual
93830690-3c17-57f0-ba13-a8310246c567 | note | Conformance Criteria - Construction procedures saved in Construction Team Sharepoint and detailed in register
6d6147dd-ff23-59a0-90f0-99695566b1f5 | note | Frequency - Prior to works
bbc2999f-f76d-515c-8153-7442c2461dbd | note | Thiess HP/WP Check - HP
7797c642-0f5a-5b06-af1d-9511c315b41f | note | Inspector HP/WP Sign Off - WP
9a028711-23bb-4193-9607-8ddc0bae556b | signoff | WITNESS POINT
9798f2ba-d8c2-48f2-a4f5-d710b962012a | checkpoint | PC1.4 - Excavation permit
95d3c806-8063-5e27-9668-d0b242086300 | note | Responsibility - ENG
8916aac1-51a6-5ce0-8291-cb123c58ade7 | note | Test Method - Visual
f265cb18-d913-5d79-a643-61a578d8f806 | note | Conformance Criteria - Approved Excavation Permit saved in Construction Team Sharepoint and detailed in register
7f93843b-9275-5f5c-8251-435da3789f4b | note | Frequency - Prior to works
8e60b629-9f32-500e-add6-a101551735db | note | Thiess HP/WP Check - HP
0f1e7ca5-4178-5015-bfab-f0176438b559 | note | Inspector HP/WP Sign Off - WP
0793db85-0e32-4baa-a740-27bcc77097e7 | signoff | WITNESS POINT
e25f76c5-b49e-4616-8bf9-5aa7766491c5 | checkpoint | PC1.5 - Dial before you dig check
57a4f0a8-3f8d-5d0e-93ec-6e1a94d3278c | note | Responsibility - ENG
c23a4f48-c772-5fa4-9fcd-b9218b736d35 | note | Test Method - Visual
6363e9c4-d829-5d6c-afdb-b270d7ea490f | note | Conformance Criteria - In date DBYD certificate saved in Construction Team Sharepoint and detailed in register
8c0a1cb2-a6f1-5dd6-901f-16f0e1910bc4 | note | Frequency - Prior to works
81f1fe66-23c8-5d52-9a8f-401f164b4895 | note | Thiess HP/WP Check - HP
62029c75-459c-56b7-9133-1ccc3d7189c2 | note | Inspector HP/WP Sign Off - WP
f89bc0d0-c7d9-4e30-a447-98e5649ba193 | signoff | WITNESS POINT
1afaa620-9ec9-4f52-aefc-23b6fce4cf53 | checkpoint | PC1.6 - Traffic control plan
96b6c5da-dcdf-5ade-bda1-2dd57041593b | note | Responsibility - ENG
756c5fce-de98-5311-8a4b-0df638afd89a | note | Test Method - Visual
3a87cab9-fbc4-5d6a-9ce5-102913bdc911 | note | Conformance Criteria - Traffic control plansaved in Construction Team Sharepoint and detailed in register
10d26ef2-b36a-5071-bd09-c1f8a4c5e39c | note | Frequency - Prior to works
b7f85538-7ac7-5097-8cc0-77faceb9d107 | note | Thiess HP/WP Check - HP
cacb7889-fac6-52a0-bdd7-4b5e86efaec6 | note | Inspector HP/WP Sign Off - WP
c70f264d-517d-40d2-86a2-61ad62419bd1 | signoff | WITNESS POINT
8f7e8f93-0c5e-4834-ba08-0c7b3abcfb02 | checkpoint | PC1.7 - Inspection Test Plan (ITP) submitted and approved
4363e8b0-8dcd-5c88-b25a-db546e0f5a1f | note | Responsibility - ENG
5e97c6ee-75bb-5768-b9e7-ba49656e6d63 | note | Test Method - Visual
4d52017a-5463-5b85-b8a2-3490bd5784db | note | Conformance Criteria - Approved ITPs relevant to the works saved in Construction Team Sharepoint and detailed in register
d2440ea8-6546-56a1-8021-c92d68f9da8d | note | Frequency - Prior to works
7976b1a3-9bf9-5c3a-a4e8-fcf344a5ee9b | note | Thiess HP/WP Check - HP
23bd4684-ca52-5fd9-a24c-746a633febbc | note | Inspector HP/WP Sign Off - WP
89fc55c4-d4a5-4806-9cb7-b5fdd80d1182 | signoff | WITNESS POINT
92b8e7de-0df5-4bd4-84f2-ed1d9583bda8 | checkpoint | PC1.8 - IFC drawings
dc75979a-20a0-5198-8f40-76724f87d807 | note | Responsibility - ENG
5e63740a-41ee-5679-ae88-2d7a1934463a | note | Test Method - Visual
ac97cf8d-b749-5685-bf0b-1e8b850118fb | note | Conformance Criteria - IFC drawings and revisions transmitted from theThiess Technical Services team and detailed in register
4eef36e5-3799-5ded-867a-de41840304f3 | note | Frequency - Prior to works
338676cc-0a7f-5cc4-b981-b7d3d80cc0ee | note | Thiess HP/WP Check - HP
e7452242-72fe-5ea2-b8a8-5a1113f5edf5 | note | Inspector HP/WP Sign Off - WP
d8b918de-ee98-4b11-9e9b-7f7d3f6b19b1 | signoff | WITNESS POINT
d052d567-770d-41f4-afa2-c174d6f29b37 | checkpoint | PC1.9 - Erosion and sediment control plan
0a1d5052-5415-595f-8bed-9139b638007a | note | Responsibility - ENV ENG
9533c9b2-6961-53e0-87af-23d55c41ba75 | note | Test Method - Visual
0f432034-d55b-593b-ac9f-fda7d25cf71a | note | Conformance Criteria - Approved Erosion and Sediment Control Plan saved in Construction Team Sharepoint and detailed in register
0a6a815d-69fe-515d-9c35-c2add07f9b11 | note | Frequency - Prior to works
2559b787-9a4c-5975-a49f-033d91a8272b | note | Thiess HP/WP Check - HP
281a1ef7-5a88-5fc5-ad2c-eae8a63115b1 | note | Inspector HP/WP Sign Off - HP
ad97dae8-4823-426a-ac7e-5254da201e9e | signoff | HOLD POINT
0dddaa81-7464-47f7-90d2-0d5115acd6d1 | checkpoint | PC1.10 - Approved stockpile locations
06dc5854-4fd1-599c-8ef9-94764f959249 | note | Responsibility - ENG
33273c30-deca-50be-93e6-e195869ffbd7 | note | Test Method - Visual
1b9e3f79-a398-5254-9d11-bcfa22c56fbe | note | Conformance Criteria - All stockpile locations to be nominated and approved prior to commencement of activity.
c6d4ccea-a004-51f0-ad47-d7bc6d8aae81 | note | ○ Topsoil register to be maintained with information on topsoil volumes and stockpile locations.
e17e1457-fbe9-54d1-be3f-e7a481ff5179 | note | Frequency - Prior to works
1e774b75-714f-5165-a028-87be80be1650 | note | Thiess HP/WP Check - HP
599e6b3d-22bf-5c13-8c36-8fdf7f17f781 | note | Inspector HP/WP Sign Off - HP
474b6e42-eabe-40f3-bbd3-43605e9adf8a | signoff | HOLD POINT
95d44b0d-a0ff-4806-8aae-b5928f44fc01 | checkpoint | PC1.11 - Embankment fill materials
fdb76142-99c9-55c7-8098-97b80702bf80 | note | Responsibility - ENG
7ccde0eb-d330-5eb3-b587-f42d4c1dd53c | note | Test Method - Visual
f7c7398e-42e6-5c31-941a-f186e2b66f19 | note | Conformance Criteria - Embankment fill materials have been approved for use and in accordance with the requirements in the specification.
19f448f4-3314-5630-99f5-74a35dde96f6 | note | ○ General fill material as per Table A3-1 Cut/fill material properties in the specification:
40acf6ee-7928-5d79-90bc-c98badb4606c | note | ○ Less than 30% passing 0.075mm sieve
57c7c285-386d-5bc9-8fae-e6450218c790 | note | ○ Liquid limit 20% to 60% Soaked CBR = or >3% (STD compaction @ OMC)
ead91126-8b1c-5b92-aae2-945b752557a7 | note | ○ 1 test per 5,000 m3
9193395c-6e53-549e-b314-3ef8a4544b39 | note | ○ Subgrade replacement material CBR10.
4a1f5779-21c3-55d4-85f7-6eaafb7b52ef | note | ○ Select Fill as per the details in Table A3-2 Select fill material properties & Table A3-3 Select fill grading envelope.
eabb899f-69c7-5124-96f4-33e7fbce683c | note | Frequency - Prior to works
64d2f340-b7fd-5a5a-9b03-ae4d09f98563 | note | Thiess HP/WP Check - HP
89ebe463-c0f5-56bd-a9d4-f58461278a09 | note | Inspector HP/WP Sign Off - WP
e97f3805-6609-4c7a-847e-469d22f8c748 | signoff | WITNESS POINT
07aecab2-8e27-4719-bd19-1c267e693f81 | checkpoint | PC1.12 - QA close out
e1e833cd-7a61-51eb-9747-58e7ce7a1842 | note | Responsibility - ENG
be630aec-8448-550b-9b22-0ad6f23eb76d | note | Test Method - Visual
b1ce9316-1d43-56d0-8f25-dcfa9c5697e2 | note | Conformance Criteria - Works completed and update ITP/Lot register/MDR and close out of GDP
0fda6c46-7778-5ac7-8a3e-e4554528dc37 | note | Frequency - As required
4f7f58c0-5220-5a52-ac2b-a5fcf91bacee | note | Thiess HP/WP Check - HP
8b1a8832-b0d6-5ba8-b862-009772c75ad2 | note | Inspector HP/WP Sign Off - HP
14d0655d-3699-4033-bf1d-d54efd28e116 | signoff | HOLD POINT
3aa92da8-33cf-4aa7-ae9a-445014f17036 | checklist | Ω (DEPRECATED) ITP-003 Subgrade/Foundation Preparation (v0) | itp | ITP-003 Subgrade/Foundation Preparation
3888cb15-c6e9-4774-94f4-ef0136a8d2b8 | section | Subgrade/Foundation Preparation
ac475546-f2ce-4c02-a316-d1bc173edfa8 | checkpoint | SP.1.1 - Underlying lot & ITP signed off and conforming
0ba38702-7e4a-5305-999e-9d0c380b72b1 | note | Responsibility - ENG
cd2dc35a-9502-5741-8b68-f7ea4a27f70c | note | Test Method - Visual
cdae2c66-de7c-5ca1-aaa5-1dcaadf88613 | note | Conformance Criteria - Topsoil ITP closed out
39fb73af-ee7e-5cfb-a384-6dabf3434961 | note | Frequency - Prior to Works
8ee4a552-2995-58d0-9e48-752e910a3518 | note | Link to ITP - TS1.6
2897bed4-d43c-43af-aa95-e7d21d62accd | checkpoint | SP.1.2 - Embankment fill material
6698839b-9391-5658-8be4-54b8641f1d75 | note | Responsibility - ENG
afc74dae-bdf5-5e03-929d-edad53d7c4be | note | Test Method - Visual
e98679c2-b70a-536b-9a9c-bef3a3d5405e | note | Conformance Criteria - Ensure CBR10 subgrade replacement materials have been approved for use and within specification
6171a00d-a560-5761-b6c3-27e3f1536543 | note | Frequency - Prior to works (Check if this has already been completed at ITP Pre-construction stage)
cd5ca6cd-ecd1-5805-9164-3664d4d56063 | note | Link to ITP - PC1.12
8ebc67a8-3f8e-5cfc-aa2c-2ab9989333fa | note | Thiess HP/WP Check - HP
c22e0b29-ee08-5f77-a31c-95c7a96e983a | note | Inspector HP/WP Sign Off - WP
e6f51fb7-6c5b-4f3e-b073-2d76ec83af4c | signoff | WITNESS POINT
f18384a0-36b1-404a-ba16-b643c5ba2214 | checkpoint | SP.1.3 - Survey Set out
4b25c72b-e94d-529d-aa6b-3835cde661fb | note | Responsibility - Surv
6db7605f-6648-5850-b3e9-c41e7f2cfe70 | note | Test Method - Field
d0b3b03b-7fa3-511c-b9b7-9c1db665c392 | note | Conformance Criteria - Areas of work to be set out by surveyor and/or models in plant
662d8646-ee30-5fd1-9ce4-7ccc7f1318a9 | note | Frequency - As required
57f8ebaa-8d19-5e99-8c43-2d16b8aff760 | note | Thiess HP/WP Check - HP
45364d23-92d3-5007-895d-5930c2185259 | note | Inspector HP/WP Sign Off - WP
4d57dd0c-68ce-48ab-bd54-2cee86b3fca9 | signoff | WITNESS POINT
dbba825e-74ac-4f55-a21f-fc1ed370c529 | checkpoint | SP.1.4 - Removal and replacement of unsuitable material
747e0dbf-fcba-5695-b1a3-01b9361dabf7 | note | Responsibility - SUP
30352755-f0c8-5be8-bb2c-b08aec36a9b4 | note | Test Method - Field
21dbc2ce-af3d-5371-a91b-5b924c2fdfbc | note | Conformance Criteria - Determination of unsuitable material by the Level 1 GITA or Inspector (Sedgman) is required prior to the removal of any unsuitable material. Unsuitable material criteria is in the specification.
e4d39c20-3fe5-5de7-bc69-b4f7f854c5fd | note | Frequency - As required
153058c6-af8e-59bf-ba0a-0d361dab80d0 | note | Link to ITP - PC1.12
c84d290d-5958-537c-9c8e-48a52d608cc3 | note | Thiess HP/WP Check - HP
47ac2868-dfa4-5963-aa63-9fdf4d28309a | note | Inspector HP/WP Sign Off - HP
abc7c254-a1c2-4d1e-a2cc-9dda06113411 | signoff | HOLD POINT
4fd12e0e-f712-429a-8540-2f342f7bb820 | checkpoint | SP.1.5 - Subgrade/Foundation preparation
53ba4411-a5de-531c-961b-c446ae05e42d | note | Responsibility - SUP
d0ce048c-197d-5912-80e4-60df6073967c | note | Test Method - Field
36fa4a64-d46f-5f5c-ba5f-c800dda0a565 | note | Conformance Criteria - Foundations for embankments to be ripped 200m deep, moisture conditioned then compacted. Density requirements: < 300mm from finished level under roads & structures minimum RDD 97%, all other areas and depths RDD 95%, moisture content -1% to +2%, normal level of testing 1 test per 500m3, reduced level of testing 1 test per 1,000m3.
aa96d8ee-81e4-5cf0-9311-27c35702a144 | note | ○ All material exposed in cuttings at subgrade level minimum CBR 3 or DCP 150kpa. If CBR2: Remove & replace with CBR10 select fill 150mm deep. If CBR1: Remove & replace with CBR10 select fill 250mm deep
0d516928-6b59-57fe-b7ca-1ee4b1414d64 | note | Frequency - As required
7ad79ff9-eae9-5987-9e5b-82402f192491 | note | Link to ITP - PC1.12
ed5e1566-2280-51c3-be8e-1eb5461ee755 | note | Thiess HP/WP Check - HP
0e74b08d-944f-5d4f-a1a0-598735ce57d8 | note | Inspector HP/WP Sign Off - HP
c760cec8-8ceb-4a0d-a985-5324d40c2be8 | signoff | HOLD POINT
187efc59-29ad-49ed-8390-8b60becf1967 | checkpoint | SP.1.6 - Trim subgrade
b3913e7c-bebc-5d12-9a25-bb41ac3c832f | note | Responsibility - SUP / SURV
ae93ba34-1d60-5116-972f-c6a9676fd814 | note | Test Method - Field
a76edf78-b419-5b0e-8f24-353676836a66 | note | Conformance Criteria - Trim all subgrade to the lines and levels shown on the drawings in accordance with the following tolerances: Top of bulk earthworks +/-50mm; Road subgrades & under buildings & structures +0mm to -25mm.
549c5914-07e3-55e7-bad0-0bbf1fce3fab | note | Frequency - As required
ffcc823b-be30-5129-a036-a226605a90d8 | note | Thiess HP/WP Check - HP
f45a1c01-4b58-5b13-93cd-bdb9bab52ee2 | note | Inspector HP/WP Sign Off - HP
f23b4a57-60f2-4a1f-bbca-c06f05da3796 | signoff | HOLD POINT
bf2a450e-c73d-4e58-b6c5-f8d0ad38ec50 | checkpoint | SP.1.7 - Proof rolling
6ac50545-6961-5f6e-9358-6a0ee1fb360f | note | Responsibility - SUP
c709b948-1ca6-56d0-9cf6-aefd7aedbedc | note | Test Method - Field
c378f6ef-6f7b-516a-8e9d-004032c7b05c | note | Conformance Criteria - Proof-roll subgrade/foundation surface prior to placement of embankment fill. Proof roll under a standard 8 tonne axle load or 10,000L water cart or heavy self propellled smooth drum roller dynapac 620D or equivalent to confirm that, in the Inspector (Sedgman) s opinion, deflections are negligible
3a550ce8-816b-5397-a561-01745103d955 | note | Frequency - As required
ffbdbde8-4eed-59a2-a503-187d9143d7f6 | note | Thiess HP/WP Check - HP
118fb4dc-b6f4-5712-8aa5-f3abc584a348 | note | Inspector HP/WP Sign Off - HP
6e4cdf2a-ea9e-4e8c-aef7-9e25439a1400 | signoff | HOLD POINT
71594be2-04a9-4642-8c27-46fc02041e66 | checkpoint | SP.1.8 - Surface level check and survey pick-up
ae3e3dc0-bbb7-5161-ab48-8f3e93da7c89 | note | Responsibility - SURV
0233e3da-d7b0-57cb-a28f-791670b10318 | note | Test Method - Survey / Field Test
181a65b6-888f-5718-abc5-1c5ea421f1f5 | note | Conformance Criteria - Surface level picked up as per Table 10 C15 (DXF file format, volume calculated and filr saved in Construction Team Sharepoint and detailed in register
8205adaf-59f9-5e9c-94e0-2407ce8f2386 | note | Frequency - As required
816da858-ab98-54c1-b51c-3cfa04e1791f | note | Thiess HP/WP Check - HP
8fd83ed0-b72c-5af0-9b4a-dc40044dbcee | note | Inspector HP/WP Sign Off - HP
4bcc759d-350a-4250-8f6b-244794b056e2 | signoff | HOLD POINT
cf8c9bf4-266f-4abf-8026-2827cb980a71 | checkpoint | SP.1.9 - QA close out
f480ed2e-dad9-5d6f-bd96-060b4d89131c | note | Responsibility - ENG
1a40051b-4408-5dcb-b87a-220c77689e1a | note | Test Method - Visual
f5308beb-802e-5f5c-af91-fc47fbd956cb | note | Conformance Criteria - GDP permits closed. ITP closed. Approved MDR.
5dd34aff-46bd-5dab-b2af-b6da8a1c725f | note | Frequency - As required
348d3807-5f57-5b32-ba96-d3d360a60099 | note | Thiess HP/WP Check - HP
b9692b12-b245-507c-a77b-b367d15bbc3d | note | Inspector HP/WP Sign Off - HP
fe791962-27f7-473b-bde7-91e7f40b4125 | signoff | HOLD POINT