## zres_siteapp_NEW
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
b86ac2fb-a936-4959-bc2c-0b212ce6cb6a | checklist | ITP-002 Topsoil Stripping | itp | ITP-002 Topsoil Stripping
8749f0ea-dcaf-40a1-a9fb-38172bde624a | section | Topsoil Stripping
916380c8-3601-4c5d-aaec-d8f5ce265520 | checkpoint | TS1.1 - Underlying lot & ITP signed off and conforming
ae37fa4e-a8c8-5621-99d3-c3093ffbd813 | note | Responsibility - ENG
eaa1749a-e2ec-5b85-8edd-42ddd734d8a2 | note | Test Method - Visual
dae7b959-a92f-50a9-80f0-f8e4f50ef610 | note | Conformance Criteria - Clear & Grubbing ITP closed out
eeadea39-f306-52fc-83e8-4c96215d2126 | note | Frequency - Prior to works
b23b17a7-7376-533d-9afe-1423f0cb849c | note | Link to ITP - GC1.6
6c621a60-d7a2-4f30-86cf-79266b7cfff1 | checkpoint | TS1.2 - Survey Set out
a04a85f3-030f-5947-93a2-83065c379130 | note | Responsibility - Surv
b0740eeb-b1e8-565d-b6bb-e79334e3c6b7 | note | Test Method - Field
8795b855-e66e-55e4-ae20-2c067a367fa7 | note | Conformance Criteria - Areas of work to be set out by surveyor and/or models in plant
c707d4ab-6d68-5bb7-aa60-78dc74f21831 | note | Frequency - As required
225fa33d-4b6f-5408-b2e1-861b17ce1c7b | note | Thiess HP/WP Check - HP
c0fab7ed-3a57-510c-99ca-1308ec25b414 | note | Inspector HP/WP Sign Off - WP
92c3d114-4ca0-4687-9ab6-1be8c3bbaf48 | signoff | WITNESS POINT
ef0f707e-77c6-47e0-b7b6-f00e62939a07 | checkpoint | TS1.3 - Strip topsoil, load & haul to approved stockpile location
944babb1-ca24-540f-903e-b2314fa26865 | note | Responsibility - ENG
a591edf9-2637-5776-97cf-4ac30f68fd7f | note | Test Method - Visual
93eddc67-b978-54f9-8611-85f084d83259 | note | Conformance Criteria - Provisional depth of topsoil strip shall be 100 mm unless shown otherwise on the drawings.
8e938ca4-1f2e-543e-b9b6-75e0ac18fd76 | note | ○ Stripped topsoil loaded and hauled to approved stockpile location.
e13284e2-f46f-585b-bcd5-00fe9807e382 | note | ○ Stockpile locations located minimum 40m from watercourses and not exceed 2m in height.
48714638-6934-566f-8a20-7f697f7d162d | note | ○ Native seeding of topsoil stockpiles as agreed with Company.
e05858cc-a4bd-5b6a-9caf-8cde8db7aa22 | note | Frequency - As required
9463ad6a-351e-5eee-973e-cc0598eb1f1c | note | Link to ITP - PC1.10
10901a46-aadc-5279-b7e6-6b0eef29320f | note | Thiess HP/WP Check - HP
cabcfed7-1ef9-558c-b8c6-22527fc21bc5 | note | Inspector HP/WP Sign Off - WP
d2bc2732-0651-43bb-8cb4-971bf9e1c4ff | signoff | WITNESS POINT
071da937-196f-4dbf-ac54-4880807d9d2f | checkpoint | TS1.4 - Topsoil location, destination and quantity catalogued.
2f69d885-0944-5510-bc4d-b099d07f8d6e | note | Responsibility - ENG
76b50feb-f81f-5024-9cc6-1a08b9096a8d | note | Test Method - Visual
cfd53ca6-93ea-522e-990b-36f528577392 | note | Conformance Criteria - Topsoil register to be maintained with information on topsoil volumes and stockpile locations
9fef3602-e591-50a2-8b1e-b28b30b00301 | note | Frequency - As required
de9b897a-7bf0-558d-a79a-ab5d0a872b6e | note | Link to ITP - PC1.10
4278a0ee-23c0-5b19-8a90-69a59d37c005 | note | Thiess HP/WP Check - HP
d7122674-faca-594e-887a-749570912de2 | note | Inspector HP/WP Sign Off - HP
05dccf20-f68b-4781-954e-06157df5e77b | signoff | HOLD POINT
c6e48c99-ba54-4abd-bc57-c3bcd1e665fd | checkpoint | TS1.5 - Surface level check and survey pick-up
765c1ef7-26db-5fcb-81b9-462bb14fbba4 | note | Responsibility - SURV
6503a485-f9c8-558d-811b-469336ece816 | note | Test Method - Survey / Field Test
64c8342e-8aae-5f7c-a4e3-df39e8aecf3b | note | Conformance Criteria - Stripped surface level picked up as per Table 10 C15 (DXF file format, volume calculated and filr saved in Construction Team Sharepoint and detailed in register
162e926d-aa9c-5849-b1af-ef6f44f75ea6 | note | Frequency - As required
2ed18220-a06f-52d7-9f65-00887d5aad21 | note | Thiess HP/WP Check - HP
9e188d56-9fad-5d14-b173-8c642a6c6397 | note | Inspector HP/WP Sign Off - HP
af4ae563-b4e9-47a2-a180-1d478211e8ec | signoff | HOLD POINT
ae6c69bd-ecc2-454a-9bff-6080c8c1c94a | checkpoint | TS1.6 - QA close out
8efc1984-16d2-53ba-a057-5431c08fd38b | note | Responsibility - ENG
0e4486bc-38e8-544f-ac30-fb17669c1687 | note | Test Method - Visual
c7e83a05-827a-55ab-a626-c824caa8593d | note | Conformance Criteria - GDP permits closed. ITP closed. Approved MDR.
d228505a-fca4-59be-b984-2e29b12b43a9 | note | Frequency - As required
e910bce3-f30b-59aa-b87d-43474fc1cf31 | note | Thiess HP/WP Check - HP
ef4ec3ef-ada0-5aae-b30f-6405d1fe60ab | note | Inspector HP/WP Sign Off - HP
5e2f8d5f-e7ee-48e0-844a-1e4cf9f054a9 | signoff | HOLD POINT