## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | 03.01 - Removal of Existing Drainage Structures and Concrete Slabs | itp |  |  |  |  | 03.01 - Removal of Existing Drainage Structures and Concrete Slabs | 37f0083d-44ef-41d9-9846-b55fe6725faa
section | Details
checkpoint | Culverts and culvert end structures shall be removed or demolished where specified in the drawings.
label | Acceptance Criteria and Frequency (Project Specific) - Culvert Removal - Per Culvert
label | Check Item - Check Item
label | Reference - MRTS03 Cl 9.2
checkpoint | If existing culvert components are to be removed and re-used, they shall be removed and stacked in a manner which avoids damaging the components.
label | Acceptance Criteria and Frequency (Project Specific) - Visual - Per Culvert
label | Check Item - Check Item
label | Reference - MRTS03 Cl 9.2
checkpoint | Removed components which are not to be salvaged, nor reused, shall be removed from the Site and disposed.
label | Acceptance Criteria and Frequency (Project Specific) - Visual - Per Culvert
label | Check Item - Check Item
label | Reference - MRTS03 Cl 9.2
checkpoint | Excavations carried out and the void left by the removed culvert or end structure shall be backfilled to reinstate the area to a safe and free draining state.
label | Acceptance Criteria and Frequency (Project Specific) - Visual - Per Culvert
label | Check Item - Check Item
label | Reference - MRTS03 Cl 9.2
checkpoint | Existing kerbs, channels, kerbs and channels, kerb crossings and concrete slabs shall be removed or demolished where specified in the drawings.
label | Acceptance Criteria and Frequency (Project Specific) - Visual - Per Kerb
label | Check Item - Check Item
label | Reference - MRTS03 Cl 9.4
checkpoint | Any Kerb and Channel or concrete slab to be removed is saw cut at removal extents or removed to existing joint (or removed in its entirety) where specified in the drawings and no damage shall occur to adjacent work
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS03 Cl. 9.4
checkpoint | Kerb excavations backfilled to flush with the surrounding area.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS03 Cl. 9.4
checkpoint | Final Verification
note | Project Manager Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
note | Client Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
signoff | Signature
checklist | 03.03 - Culvert Component/End Structure Insitu Cast | itp |  |  |  |  | 03.03 - Culvert Component/End Structure Insitu Cast | 7d790023-8b59-4add-93b6-8b21d34eeaa6
section | Details
checkpoint | Concrete Conforms with Cl 6.1 (MRTS 70), Concrete Mortar conforms to Cl6.2, Steel Reinforcing conforms to MRTS71, Rock Masonry conforms to Cl33, Grouted Rock Pitching complies with Cl 34, Steel Wire Matresses comply with Cl 37
label | Acceptance Criteria and Frequency (Project Specific) - Visual, MRTS70 ITP
label | Check Item - Check Item
label | Reference - MRTS03 Cl 14.2, Cl 15.2, Cl16.2
checkpoint | Cast-in-situ end structures such as headwalls, wingwalls, aprons and kerbs to culverts constructed in the locations specified on the project drawings and comply with standard drawings 1304, 1305 for pipe culverts and 1240, 1250 & 1260 for box culverts as applicable
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS03 Cl 15.3
checkpoint | Where material on or against which culvert bases are to be constructed is other than rock, the material is compacted as per bottom of excavations in accordance with MRTS04 General Earthworks.
label | Acceptance Criteria and Frequency (Project Specific) - Visual, ITP
label | Check Item - Check Item
label | Reference - MRTS03 Cl 15.3
checkpoint | Endwalls, wingwalls and concrete aprons constructed without a foundation bedding unless specified otherwise in the drawings.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS03 Cl 15.3
checkpoint | Endwalls and wingwalls seperated with an expansion gap unless otherwise specified on the drawings.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS03 Cl 15.3
checkpoint | Supplementary Requirements Completed as per Clause 52 MRTS03 & MRTS03.1 Cl 6
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS03.1 Cl. 6
checkpoint | Construction of culvert base, walls or endwalls shall include the construction of integral nib or cutoff walls where relevant
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS03 Cl 17.3, Cl 18.3
checkpoint | Construction of culvert base, walls or endwalls shall comply with the Geometrics Section stated in Clause 1.5. MRTS03.1. For Each Structural Element, testing requirements must contain: Dimensional, Positional, and Relative Position
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS03.1 Cl 1.5
checkpoint | Final Verification
note | Project Manager Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
note | Client Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
signoff | Signature
checklist | 04.01 - Clearing & Grubbing | itp |  |  |  |  | 04.01 - Clearing & Grubbing | 347fa727-1efc-4ddd-ae32-75e999adef71
section | Details
checkpoint | Extent of Clearing has been checked and marked according to the Vegetation Removal Notification nu the Project Arborist
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS04 Cl 7.2.1
checkpoint | Tree Protection Zones installed as per Arborists recommendations
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS51.1 Cl 9.1
checkpoint | Clearing operations and other environmental operations to be supervised by Project Arborist, SQP Contaminated Land and environmental representative where required
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS51.1 Cl 9.1
checkpoint | Any trees, shrubs and overhanging branches to be left undisturbed shall be clearly marked prior to clearing operations reaching the areas concerned.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Hold Point 2
label | Reference - MRTS04 Cl. 7.2.2
holdpoint | HOLD POINT
checkpoint | Any trees required by the Administrator for use as marketable timber shall be as nominated in Clause 2.3 of Annexure MRTS04.1. Such trees shall be clearly marked by the Contractor prior to clearing operations reaching the areas concerned
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Hold Point 3
label | Reference - MRTS04 Cl. 7.2.3
holdpoint | HOLD POINT
checkpoint | As soon as practicable and prior to initial earthworks operations (clearing and grubbing) for any stage or section of the Works, erosion and sediment controls associated with drainage paths flowing through the Works area is being installed.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Hold Point 2
label | Reference - MRTS52 Cl. 7.1
holdpoint | HOLD POINT
checkpoint | Hollow timber which is identified as being suitable for fauna habitat logs relocated to areas clear of construction activities
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS04 Cl. 7.2.5
checkpoint | Cleared and grubbed material other than that mulched under Clause 7.2.4 shall be disposed of in any areas stated in Clause 5 of Annexure MRTS04.1 to this Technical Specification. If no such disposal instructions are stated, the cleared and grubbed material shall be removed from the Site and disposed of in accordance with all relevant statutory requirements, including the requirements in MRTS51 Environmental Management. Cl. 7.2.7
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS04 Cl. 7.2.7
checkpoint | The scope of clearing and grubbing shall include the items as per Annexure MRTS04.1 Cl. 1.2 & Cl. 1.4
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS04 Cl. 7.2.8, MRTS04.1 Cl 1.2 Cl 1.4
checkpoint | Trees shall be clasified as a Mature Tree if they have a diameter greater than 100mm diameter. Diameter of trees may be checked by Adminstrator to confirm if Mature.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS04.1 Cl13.1
checkpoint | The additional width for clearing and grubbing is 1.0m from toe of embankments as per Annexure MRTS04.1 Cl. 1.1
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS04.1 Cl. 1.1
checkpoint | Material not to be removed from within drip lines of existing plants to be retained except where this would result in unsuitable material being left beneath embankments. Root systems of existing plants to be retained are preserved where practical.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS04 Cl. 8.4.3
checkpoint | Additional Requirements for Clearing and Grubbing AS Per MRTS04.1 Cl 1.4 have been followed
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS04.1 Cl 1.4
checkpoint | Final Verification
note | Project Manager Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
note | Client Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
signoff | Signature
checklist | 04.08 - Stripping of Topsoil | itp |  |  |  |  | 04.08 - Stripping of Topsoil | bdb2fc37-3ead-4226-a310-8804c0cc3a39
section | Details
checkpoint | Where site topsoil is required to be supplied in accordance with MRTS16 Landscape and Revegetation Works, topsoil shall be stripped 100mm (+/-25mm) depth, or from areas and depths as specified in Clause 2 of Annexure MRTS04.1
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS04 Cl. 8.2, MRTS04.1 Cl. 2
checkpoint | Soil stripped from site which is considered suitable for use as a manufactured site topsoil shall be tested and ameliorated in accordance with MRTS16 Landscape and Revegetation works
label | Acceptance Criteria and Frequency (Project Specific) - Insitu topsoil - 1/2500m2, min.1/soil type
label | ○ Stockpile Topsoil - 2/500m3, min.1/soil type
label | ○ Manufactured Site Topsoil Compliance - 2/500m3, min.1/soil type
label | Check Item - Check Item
label | Reference - MRTS04 Cl. 8.3
checkpoint | No areas are available within the limits of the site for the disposal of excess and unsuitable material, with the exception of excess topsoil. Excess topsoil may be uniformly distributed on cleared and grubbed areas which are outside the road embankment formation.
label | Acceptance Criteria and Frequency (Project Specific) - Check Item
label | Check Item - Check Item
label | Reference - MRTS04.1 Cl. Cl. 5
checkpoint | Stockpile site locations are to be nominated by the Contractor and approved by the Administrator. The Administrator is not obliged to approve any stockpile site location within the road reserve. Stockpile sites shall not be placed within 50 m of a watercourse or within the 20% Annual Exceedance Probability (i.e. Q5) flood zone of a watercourse, unless approved by the Administrator. No native vegetation shall be cleared for stockpile sites located outside the area defined under Clause 7A of Annexure A (Contract Details) to the General Conditions of Contract, unless approved by the Administrator.
label | ○ Stockpile sites shall not be placed within the Tree Protection Zone defined in Clause 9.1.2 of Annexure MRTS51.1.
label | ○ Preference should be given to existing stockpile sites or existing cleared areas. No guarantee will be given as to stockpile site suitability, condition or availability. In the event that the establishment of stockpile sites requires clearing, grubbing or earthworks to be undertaken, a Cultural Heritage risk assessment and environmental survey must be undertaken prior to any works being undertaken. The Contractor shall advise the Administrator of any such requirements HOLD POINT. No clearing or works beyond the defined project extent may proceed without approval from the Administrator and the TMR Environmental Officer.
label | ○ All costs associated with undertaking necessary earthworks activities required for stockpile sites shall be deemed to be included in the Contractor’s schedule unit rates for the corresponding earthworks items.
label | Acceptance Criteria and Frequency (Project Specific) - Check Item
label | Check Item - Hold Point
label | Reference - MRTS04.1 Cl. 2.2
holdpoint | HOLD POINT
checkpoint | Material not to be removed from within drip lines of existing plants to be retained except where this would result in unsuitable material being left beneath embankments. Root systems of existing plants to be retained are preserved where practical.
label | Acceptance Criteria and Frequency (Project Specific) - Check Item
label | Check Item - Hold Point
label | Reference - MRTS04 Cl. 8.4.3
holdpoint | HOLD POINT
checkpoint | Stripped material shall be stockpiled in the locations nominated by the Contractor, as stated in Cl. 2.2 of Annexure MRTS04.1.
label | Topsoil Stockpiles are;
label | ○ Less than 3m High
label | ○ Less than 10m wide
label | ○ Appropriately battered, drained or otherwise protected to prevent erosion and segregation
label | ○ Stockpiled for the minimum duration
label | ○ Stockpile sites shall not be placed within 50m of a watercourse or within the Q5 flood zone of a watercourse.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS04 Cl. 8.4.1, MRTS04.1 Cl. 2.2
checkpoint | The Contractor must install erosion and sediment controls associated with drainage paths flowing through the works area prior to earthworks.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Hold Point 2
label | Reference - MRTS52 Cl. 7.1
holdpoint | HOLD POINT
checkpoint | All stripped areas, other than areas beneath road embankments or above road cuttings, shall be left in a neat, free-draining condition with side slopes not steeper than one in four unless otherwise specified. They shall be treated to conform with the landscape, revegetation and environmental requirements of the Contract.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS04 Cl 8.4.5
checkpoint | Prior to any further Works over the stripped area, an As Constructed survey of the stripped area shall be undertaken as specified in MRTS56 Construction Surveying and notice of such Works provided to the Administrator.
label | Acceptance Criteria and Frequency (Project Specific) - As Constructed Survey
label | Check Item - Survey Report
label | Reference - MRTS04 Cl 8.4.5
checkpoint | Final Verification
note | Project Manager Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
note | Client Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
signoff | Signature
checklist | 04.10 - Backfill | itp |  |  |  |  | 04.10 - Backfill | 8222edf3-bf16-4708-83f6-c954ef9ea809
section | Details
checkpoint | Prior to incorporating any backfill material, stockpile or source test results as specified in Appendix A shall be submitted demonstrating material meets the specified requirements.
label | Acceptance Criteria and Frequency (Project Specific) - Written
label | Check Item - Hold Point 11
label | Reference - MRTS04 Cl19.1
holdpoint | HOLD POINT
checkpoint | Material for backfill shall be as shown on the drawings or as specified elsewhere in the Contract. Where not so shown or specified, material shall be earth backfill material complying with the requirements of Clause 19.2.2. Earth Backfill Material shall comply with the requirements of Earth Fill Material Class A1, Class A2 or Class B specified in Clause 14.2.2 except that 100% of the material shall pass 25.0 mm test sieve.
label | Acceptance Criteria and Frequency (Project Specific) - Grading
label | Check Item - Witness Point 6
label | Reference - MRTS04 Cl19.2.2, Cl19.3.1
checkpoint | Unless specified otherwise in Clause 19.3 or elsewhere in the Contract, backfill shall be compacted using the compacted layer method of construction in accordance with the requirements of Clause 15, except as may be modified by the requirements of Clause 19.
label | Acceptance Criteria and Frequency (Project Specific) - RDD 1/500m2/300mm Lift - min 4/lot
label | Check Item - Check Item
label | Reference - MRTS04 Cl19.3.1
checkpoint | Backfill around In Place units (pipes, culverts, pits and so on) not placed until completed and inspected by Administrator and any curing period has elapsed.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Hold Point 12
label | Reference - MRTS04 Cl19.3.3
holdpoint | HOLD POINT
checkpoint | Where material is placed on opposite sides of a culvert, structure, conduit etc. the difference in level of compacted material on opposing sides shall not exceed 150mm, unless shown otherwise on the drawings.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS04 Cl19.3.3
checkpoint | Foundation bedding, haunch, side and overlay zones for concrete pipe culverts shall be as per standard drawing 1359.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS04 Cl19.3.4
checkpoint | Construction Testing Requirements: Test Method
label | Acceptance Criteria and Frequency (Project Specific) -
textbox | Max. Lot Size
textbox | Min. Testing Frequency
textbox | Min. No. of Tests
label | Check Item - MRTS04
label | Reference - Table A3
checkpoint | Relative Moisture - Rainfall zone: High (>1000mm), Class A1/A2: 70% - 100%, Class B: 80% - 110%
label | Acceptance Criteria and Frequency (Project Specific) - Each culvert/structure
label | ○ 1 per 100m3
label | ○ 2 per lot
label | Check Item - Check Item
label | Reference - Table A1
checkpoint | Relative Compaction - Top 300mm below Subgrade = 97%, Greater than 300mm below Subgrade = 95%
label | Acceptance Criteria and Frequency (Project Specific) - Each culvert/structure
label | ○ 1 per 100m3
label | ○ 2 per lot
label | Check Item - Check Item
label | Reference - Table A1
checkpoint | Stockpile Testing Requirements: Test Method
label | Acceptance Criteria and Frequency (Project Specific) -
textbox | Min. Testing Frequency:
textbox | Quarry Source
textbox | Other Source
label | Check Item - MRTS04
label | Reference - Table A3
checkpoint | Grading
label | Acceptance Criteria and Frequency (Project Specific) - 5000t, 1000m3
label | Check Item - Check Item
label | Reference - Table A1
checkpoint | Plasticity Index
label | Acceptance Criteria and Frequency (Project Specific) - 5000t, 1000m3
label | Check Item - Check Item
label | Reference - Table A1
checkpoint | Linear Shrinkage
label | Acceptance Criteria and Frequency (Project Specific) - 5000t, 1000m3
label | Check Item - Check Item
label | Reference - Table A1
checkpoint | Emerson Class Number: AS 1289.3.8.1
label | Acceptance Criteria and Frequency (Project Specific) - 5000t, 1000m3
label | Check Item - Check Item
label | Reference - Table A1
checkpoint | Soaked CBR and Swell (For earth backfill in subgrade only)
label | Acceptance Criteria and Frequency (Project Specific) - 4000t, 200m3
label | Check Item - Check Item
label | Reference - Table A1
checkpoint | Final Verification
note | Project Manager Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
note | Client Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
signoff | Signature
checklist | 04.05 - Embankment | itp |  |  |  |  | 04.05 - Embankment | 2cc90eb6-0203-42af-99d4-428902d4288b
section | Details
checkpoint | General fill material used for the construction of road embankments sourced from general excavations on site or imported. Where embankments are zoned (ref Table 14.2.2 / Clause 14.2 - Annexure MRTS04.1), material is suitable for each zone.
textbox | General Fill Class:
label | Acceptance Criteria and Frequency (Project Specific) - General fill material Class A
label | ○ WPI< 1200, PI>= 7,
label | ○ % passing .075mm 15 - 30
label | General fill material Class B
label | ○ 1200 < WP < 2200
label | General fill material Class C
label | ○ 2200 < WP < 3200
label | General fill material Class D
label | ○ 3200 < WP < 4000, PI <=50
label | – CBR as Specified
label | Check Item - Check Item
label | Reference - MRTS04 Cl14.3.1 Table 14.3.1
checkpoint | Rock Fill shall consist of sound igneous, metamorphic or sedimentary rock or combination of these rock groups that will not disintegrate in water or when exposed to the weather. Rock Fill shall be free from overburden, Spoil, shale, clayey materials and organic matter. Rock Fill shall be either sourced from a quarry (or quarries) registered under Transport and Main Road's Quarry Registration System (QRS) or any other suitable source and shall comply with the properties stated in Table 14.2.3. Rock shall be angular in shape and the least dimension of the rock shall not be less than half its greatest dimension
label | Acceptance Criteria and Frequency (Project Specific) - Table 14.2.3
label | Check Item - Check Item
label | Reference - MRTS04 Cl14.2.3
checkpoint | Where embankments are to be constructed on or against any slopes or batter of existing embankments (including batters resulting from the partial construction of Embankment, for example, Core Zone), steps shall be cut as follows:
label | a) where the ground surface has a slope steeper than 1V to 8H and shallower than 1V to 4H, a series of horizontal steps not less than 300 mm high shall be cut into the ground surface to be covered by the Embankment.
label | ○ Such steps shall be constructed both longitudinally and transversely (refer Figure 14.3.3(a))
label | b) where the existing slope or batter has a slope steeper than 1V to 4H, a series of horizontal steps not less than 600 mm high shall be cut into the ground surface to be covered by the Embankment
label | Check Item - Check Item
checkpoint | Compaction methods suitable for material type
textbox | Compaction Method:
label | Acceptance Criteria and Frequency (Project Specific) - Table 15.2
label | Check Item - Check Item
label | Reference - MRTS04 Cl15.2
checkpoint | Compacted Layer Method: Embankment compacted to required density (by characteristic Value). Refer to Table 15.3-B MRTS04 for more information. Fill material placed uniformly in layers. Uncompacted layer thicknesses;
label | – General Fill 150-300mm
label | – Fill in Water Retaining Fill 150-200mm
label | – Subgrade 100- 200mm
label | – Backfill except Sand 100mm-100mm
label | – Sand 150-300mm
label | Acceptance Criteria and Frequency (Project Specific) - RDD%
label | ○ Insitu - >95%
label | ○ Bottom of Excavations - >95%
label | ○ Subgrade (A/B) - >97%
label | ○ Subgrade (C/D)' - 90>96% Subgrade (C/D)* - > 95%
label | ○ Road Embankment(A/B) ->95%
label | ○ Road Embkmnt(C/D)' -90<96%
label | ○ Road Embkmnt(C/D)* ->95%
label | ○ Levee Embkmnt(A/B) - >97%
label | ○ Backfill(Sand) - >70%
label | ○ Backfill(Not Sand) - >95%
label | ' High Rainfall Zone
label | *Low Rainfall Zone
label | Check Item - Check Item
label | Reference - MRTS04 Cl15.3
checkpoint | Compacted Layer Method: Embankment moisture content within ranges specified
textbox | Rainfall Zone:
label | Acceptance Criteria and Frequency (Project Specific) - Table 15.3C
label | Check Item - Check Item
label | Reference - MRTS04 Cl15.3
checkpoint | Where required, each layer rolled with the mechanical interlock method until no further permanent visible lowering of the surface occurs and layer thickness no greater than specified in Table 15.4
label | Acceptance Criteria and Frequency (Project Specific) - Table 15.4
label | Check Item - Witness Point 4
label | Reference - MRTS04 Cl15.4
checkpoint | Geotextile placed at interchange between compaction methods
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS04 14.3.2
checkpoint | Within Geometric Tolerance
label | Acceptance Criteria and Frequency (Project Specific) - MRTS04.1 Cl1.2
label | Check Item - Check Item
label | Reference - MRTS04.1 Cl1.2
checkpoint | Construction Testing Requirements: Test Method
label | Acceptance Criteria and Frequency (Project Specific) -
textbox | Max. Lot Size
textbox | Min. Testing Frequency
textbox | Min. No. of Tests
label | Check Item - MRTS04
label | Reference - Table A3
label | Note - Table 15.3A: Layer Thickness, Min: 150mm & Max: 300mm
checkpoint | Relative Moisture: Q250, Rainfall zone: Medium (500mm - 1000mm), Class A1 & B1: 70% - 90%
label | Acceptance Criteria and Frequency (Project Specific) - 2000m2
label | ○ 1 per 500m2/per layer
label | ○ 4 per lot
label | Check Item - Check Item
label | Reference - Table A1
checkpoint | Relative Compaction: Q140A, Top 300mm below Subgrade = 97%, Greater than 300mm below Subgrade = 95%
label | Acceptance Criteria and Frequency (Project Specific) - 2000m2
label | ○ 1 per 500m2/per layer
label | ○ 4 per lot
label | Check Item - Check Item
label | Reference - Table A1
checkpoint | Grading: Q103A
label | Acceptance Criteria and Frequency (Project Specific) - 2000m2
label | ○ 1 per 1000m2/per layer
label | ○ 2 per lot
label | Check Item - Check Item
label | Reference - Table A1
checkpoint | Plasticity Index: Q105
label | Acceptance Criteria and Frequency (Project Specific) - 2000m2
label | ○ 1 per 1000m2/per layer
label | ○ 2 per lot
label | Check Item - Check Item
label | Reference - Table A1
checkpoint | Stockpile Testing Requirements: Test Method
label | Acceptance Criteria and Frequency (Project Specific) -
textbox | Max. Lot Size
textbox | Min. Testing Frequency
textbox | Min. No. of Tests
label | Check Item - MRTS04
label | Reference - Table A3
checkpoint | Grading: Q103A
label | Acceptance Criteria and Frequency (Project Specific) - 2000m3
label | ○ 1 per 1000m3
label | ○ 2 per lot
label | Check Item - Check Item
label | Reference - Table A1
checkpoint | Plasticity Index: Q105
label | Acceptance Criteria and Frequency (Project Specific) - 2000m3
label | ○ 1 per 1000m3
label | ○ 2 per lot
label | Check Item - Check Item
label | Reference - Table A1
checkpoint | Emerson Class Number: As 1289.3.8.1
label | Acceptance Criteria and Frequency (Project Specific) - 2000m3
label | ○ 1 per 1000m3
label | ○ 2 per lot
label | Check Item - Check Item
label | Reference - Table A1
checkpoint | Prior to incorporating any Earth or Rock Fill Material into the Works, the Contractor shall submit stockpile or source tests results as specified in Appendix A which demonstrate the source meets the specified material requirements
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Hold Point 8
label | Reference - MRTS04 Cl. 14.2.1
holdpoint | HOLD POINT
checkpoint | Final Verification
note | Project Manager Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
note | Client Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
signoff | Signature
checklist | 04.06 - General Excavation | itp |  |  |  |  | 04.06 - General Excavation | 9799bde9-0abe-4294-a42c-baf0fe4bf412
section | Details
checkpoint | Where Unsuitable Material (in accordance with the provisions of Cl. 9.2) or potentially Unsuitable Material is encountered on site, the Contactor shall, before proceeding to remove or cover such material, notify the Administrator. Once Identified the Unsuitable material shall be removed and disposed of in accordance with the provisions of Cl.11
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Hold Point 4
label | Reference - MRTS04 Cl. 9.4
holdpoint | HOLD POINT
checkpoint | When the level of excavation has reached subgrade level, the Contractor shall carry out the requirements of the relevant provisions of Clause 18.3.3 and cease excavation until the subgrade treatment type has been determined in accordance with Clause 18.3.3.
label | Acceptance Criteria and Frequency (Project Specific) - Annexure MRTS04 Clause 13.3.2.1
label | Check Item - Hold Point 6
label | Reference - MRTS04 Cl. 13.3.2.1, Cl. 18.3.3
holdpoint | HOLD POINT
checkpoint | Material below the finished lines and levels of cuttings, which is Unsuitable Material in accordance with the provisions of Clause 9.2, shall be removed and disposed of in accordance with the provisions of Clause 9.4. Backfilling of the excavation shall not commence until an As Constructed Survey of the excavation have been met as specified in MRTS56 Construction Surveying and notice of such Works provided to the Administrator.
label | ○ Where Unsuitable Material has been removed, the excavation shall be backfilled to the finished surface level with appropriate Fill Material as specified on the drawings or in accordance with Clause 18 and Clause 19. Technical Specification, MRTS04 General Earthworks Transport and Main Roads Specifications, November 2022 30.
label | ○ After backfilling of the excavated area has been completed, an As Constructed Survey shall be undertaken as specified in MRTS56 Construction Surveying and notice of such Works provided to the Administrator
label | Acceptance Criteria and Frequency (Project Specific) - Annexure MRTS0 Clause 13.3.2.2
label | Check Item - Hold Point 6
label | Reference - MRTS04 Cl.13.3.2.2
holdpoint | HOLD POINT
checkpoint | Excavation completed to the shapes, lines and dimensions and other requirements shown on the drawings and tolerances specified
label | Acceptance Criteria and Frequency (Project Specific) - MRTS04 Clause 6
label | Check Item - Check Item
label | Reference - MRTS04 Cl. 6, Cl.13.3.1 Table 6.3.1
checkpoint | Protection of excavations in accordance with MRTS04 Cl.13.3.3.3
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS04 Cl. 13.3.3.3
checkpoint | Dewatering of excavations shall comply with requirements of EMP
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS04 Cl. 13.3.8
checkpoint | Batters in cuttings shall be free of loose material and shall be trimmed neatly to the shapes specified.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS04 Cl. 16.1
checkpoint | If any section of a batter has been over-excavated beyond the tolerance limit specified, the Contractor shall re-form the batter to the average batter slope shown on the drawings, using an approved rectification method
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS04 Cl. 13.3.2.4
checkpoint | Trench excavations and excavations for structures shall be carried out to the dimensions shown on the drawings or, where not so shown, to the minimum dimensions necessary to construct the Works accurately and safely under the Contract. Prior to any excavation Works or trench excavations, an assessment is to be undertaken to identify cadastral marks that may need protecting as specified in MRTS56 Construction Surveying and notice of such Works provided to the Administrator
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS04 Cl. 13.3.3.1
checkpoint | Material which is Unsuitable Material in accordance with the provisions of Clause 9.2 shall not be reused in the Works but shall be removed and disposed of in accordance with the provisions of Clause 9.4
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS04 Cl. 13.3.3.2
checkpoint | Final Verification
note | Project Manager Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
note | Client Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
signoff | Signature
checklist | 04.11 - Demolition of Road Furniture | itp |  |  |  |  | 04.11 - Demolition of Road Furniture | 1ed88023-bd70-4c17-a607-58a6fc86af62
section | Details
checkpoint | Road furniture to be removed are as listed in MRTS14.1.
label | Check Item - Check Item
label | Reference - MRTS14.1
checkpoint | Existing road furniture demolished and removed avoiding damage to any adjacent work.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS14 Cl.7.3
checkpoint | Resulting excavations are backfilled and finished so the area is in a safe and free-draining state
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS14 Cl.7.3
checkpoint | Milestone - Dismantling and removal shall not commence until expiration of the seven day period. Hold Point 2
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Milestone
label | Reference - MRTS14 Cl.7.3
checkpoint | The items of road furniture to be removed and re-erected shall be as listed in Clause 4 of Annexure MRTS14.1. Not less than seven days prior to commencement of dismantling and removal of any road existing furniture, the Contractor shall submit a schedule of items of existing road furniture to be dismantled for re-erection in accordance with the provisions of the design documentation.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Hold Point 2
label | Reference - MRTS14 Cl.9
holdpoint | HOLD POINT
checkpoint | Final Verification
note | Supervisor/QA Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
note | Project Manager Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
signoff | Signature
checklist | 28.01 - Contractor's Camp and Site Facilities | itp |  |  |  |  | 28.01 - Contractor's Camp and Site Facilities | c756dde2-9940-4d6e-a3aa-ca2f27e22f3e
section | Details
checkpoint | Location of facilities within areas given in MRTS 28.1 Cl. 1 or through private arrangements.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS28 Cl. 4.2
checkpoint | Properly constructed toilets, rubbish receptacles and wash facilities provided. The Contractor shall supply, equip, service and neatly maintain all necessary buildings, workshops, first aid facilities, parking areas and storage areas for the satisfactory completion of the Work.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS28 Cl. 4.3
checkpoint | If so stated in Clause 3 of Annexure MRTS28.1, the Contractor shall provide a separate room for the Administrator within the Contractor’s site facilities. The office accommodation is for exclusive use of the Administrator during Work Under the Contract and the size and any amenities required to be provided by the Contractor as stated in the Clause 3 of Annexure MRTS28.1. To encourage collaboration between all parties, the room shall be in the same building with the rest of the Contractor's staff and is to enable private meetings as required between the Administrator and the Principal.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS28 Cl. 4.4.2
checkpoint | Contractors camp complies with all requirements of MRTS52 and included in the E&SC plan.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS28 Cl. 4.5.7
checkpoint | Contractors camp complies with all requirements of MRTS28 a with a proposed site facility layout submitted to the administrator.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS28 Cl.4.5.1
checkpoint | Contractors camp complies with all requirements of MRTS28.1 Annexure
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS28.1, C.l 3
checkpoint | Supplementary Requirements completed as per C.L 8.1 & 8.2 & 8.3
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS28.1 Cl. 8, Additional Obbligation Documents
checkpoint | Final Verification
note | Supervisor/QA Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
note | Project Manager Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
signoff | Signature
checklist | 16.01 - Landscape and Revegetation Works | itp |  |  |  |  | 16.01 - Landscape and Revegetation Works | 19f71020-f39e-4bb0-8f6a-a317cd84edea
section | Details
checkpoint | Soil Management Plan prepared in accordance with Form A of Appendix MRTS16. Construction and regular Updates submitted to the Administrator for approval
label | Acceptance Criteria and Frequency (Project Specific) - Written Acceptance
label | Check Item - Hold Point 1
label | Reference - MRTS16 Cl 5.2.1
holdpoint | HOLD POINT
checkpoint | Non-Potable Water Plan and permits submitted to the Administrator
label | Acceptance Criteria and Frequency (Project Specific) - Plan
label | Check Item - Hold Point 2
label | Reference - MRTS16 Cl 5.2.2
holdpoint | HOLD POINT
checkpoint | Seed Supply Proposal submitted to the Administrator within 30 days of Possession of Site
label | Acceptance Criteria and Frequency (Project Specific) - Plan
label | Check Item - Hold Point 3
label | Reference - MRTS16 Cl 5.3.1
holdpoint | HOLD POINT
checkpoint | Plant Supply Proposal submitted to the Administrator within 30 days of Possession of Site
label | Acceptance Criteria and Frequency (Project Specific) - Plan
label | Check Item - Hold Point 5
label | Reference - MRTS16 Cl 5.3.3
holdpoint | HOLD POINT
checkpoint | Plant Harvesting Proposal submitted to the Administrator prior to harvesting plants
label | Acceptance Criteria and Frequency (Project Specific) - Plan
label | Check Item - Hold Point 6
label | Reference - MRTS16 Cl 5.3.4
holdpoint | HOLD POINT
checkpoint | Materials imported to Site shall be free of prohibited or restricted biosecurity matter
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS16 Cl 7
checkpoint | Materials are stored to ensure no deterioration or contamination occurs
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS16 Cl 7
checkpoint | Materials; including pesticides, soil amelioration agents, soil, seeding, turf, mulch, matting, plants water, plant bed edging and irrigation systems, comply with requirements and specifications set out in MRTS16 Clause 7 where applicable
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS16 Cl 7
checkpoint | containerised plants and ex ground stock in accordance with MRTS16 Cl. 7.6.2
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS16 Cl 7.6.2
checkpoint | The extent and types of vegetation treatments are installed as specified in the contract and/or shown on the drawings
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS16 Cl 8
checkpoint | Ground preparation works carried out within the drip line of retained vegetation, 300mm of paths, kerbs, road furniture or structures and in accordance with TMR Standard Drawings 1644 and 1646
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS16 Cl 8.4 TMR SD 1644
checkpoint | Site is weed free prior to ground preparation operations
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Witness Point
label | Reference - MRTS16 Cl 8.3
checkpoint | Administrator notified at least 3 days before each of the following: application and incorporation of amelioration agents, ripping, cultivation, roughening
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Witness Point
label | Reference - MRTS16 Cl 8.1.1, Cl 8.4.1.1, Cl 8.4.1.2, Cl 8.4.1.3, Cl 8.4.1.4
checkpoint | Stockpiled topsoil is in accordance to Form D - Manufactured Site Topsoil Compliance Testing prior to being used
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Hold Point 7
label | Reference - MRTS16 Cl 8.2.1
holdpoint | HOLD POINT
checkpoint | Amelioration agents, where specified in the Soil Management Plan – Construction, shall be spread over the subsoil surface at the specified rates prior to subsoil operations
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Hold Point 8
label | Reference - Cl 8.4.1.1
holdpoint | HOLD POINT
checkpoint | The contractor shall submit 1kg samples (plus test certificates) of proposed amelioration agents 4 weeks prior to use for direction as to their suitability.
label | Acceptance Criteria and Frequency (Project Specific) - Test Reports, Samples
label | Check Item - HOLD POINT
label | Reference - CTS16 Cl. 3.1.6
holdpoint | HOLD POINT
checkpoint | The Contractor shall give at least three days notice before installation of topsoil. Topsoil installed evenly over the surface, within 3 days of subsoil preparation and Topsoil shall be spread to the depths described in the relevant vegetation works operation, and allow for settlement after installation.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Witness Point
label | Reference - MRTS16 Cl 8.4.2.1
checkpoint | Turf shall be installed within two days from the completion of the topsoil operations, Turf shall be installed by spreading fertiliser over the topsoil and raking the surface smooth
label | b) to the prepared surface that has been moistened with a solution of water and wetting agent
label | c) on the day turf is delivered to site
label | d) by laying rolls parallel to the contour, in a staggered brick pattern, and
label | e) by watering, within 2 hours of installation, with a solution of water and wetting agent until the topsoil layer is moist. Watering shall be applied in multiple applications to ensure surface erosion does not occur.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS16 Cl 8.5.2.
checkpoint | Hydromulch Seeding installed in accordance with Cl 8.5.1.3, with equipment producing a uniformly applied, homogenous slurry that is applied indirectly, and from at least 2 directions with no watering on the day of installation.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS16 Cl 8.5.1.3
checkpoint | Single Pass Hydromulch Seeding installed in accordance with Table 8.2.1.4
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS16 Cl 8.2.1.4
checkpoint | Fertilisers are broadcast evenly over topsoil in accordance to manufacturer's recommendation and the prepared surface has had a water and a wetting agent applied
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS16 Cl 8.5.1.3
checkpoint | Turf installed within 2 days of topsoil, within 24 hours of delivery and in accordance to Table 8.5.2 with initial watering on the day of installation and at least 25L/m2
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS16 Cl 8.5.2
checkpoint | Mulching be manufactured in accordance with Clause 8.2.2
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS16 Cl 7.6.3.1
checkpoint | Matting shall be installed in accordance to 8.5.1.7 and according to manufacturers recommendations and in accordance with TMR Standard Drawing 1648.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS16 Cl 8.5.1.7 TMR SD 1648
checkpoint | Plants installed within 5 days of mulch or matting and within 48 hours of delivery with initial watering on the day of installation, as soon as practical after planting and in accordance with Table 8.5.3.1 and 8.5.3.2
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS16 Cl 8.5.3.2
checkpoint | Administrator notified of plant delivery to allow for inspections
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Witness Point
label | Reference - MRTS16 Cl 8.5.3.1 & Cl8.5.3.2
checkpoint | Prior to installing plants, plants shall be set out in accordance with Clause 8.5.3.3 The Contractor shall give two days notice prior to delivery of plants to allow inspection of the plants
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Hold Point 11
label | Reference - MRTS16 Cl 8.5.3.3
holdpoint | HOLD POINT
checkpoint | <25L Container Plants installed as per Cl 8.5.3.1 and Table 8.5.3.1 while ≥25L container plants installed as per Cl 8.5.3.2 and Table 8.5.3.2
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS16 Cl 8.5.3.2, Cl 8.5.3.1
checkpoint | Plant mats installed in accordance with TMR Standard Drawing 1647, type of organic matting shall be as specified in Clause 3.4.3 of the Annexure MRTS16.1
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS16 Cl 8.7.6.4 TMR SD 1648
checkpoint | Stakes and guying shall be in accordance with Table 7.6.5 TMR Standard Drawings 1653 and 1655 while Guying shall be installed with containers ≥200L, ex-ground and transplanted trees and in accordance with TMR SD 1656
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS16 Cl 7.6.5 TMR SD 1653, TMR SD 1655, TMR SD 1656
checkpoint | Certificate of commencement of landscape and revegetation works establishment period issued and is a minimum of 90 days
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Milestone
label | Reference - MRTS16 Cl 9.1
checkpoint | The Contractor shall care for the installed vegetation treatments to ensure their long term sustainability and to meet the completion criteria of Clause 9.1.2
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS16 Cl 9.1.1
checkpoint | If a plant failure is determine to relate to the species, a substitute species has been proposed and submitted to the administrator for suitability
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Hold Point 10
label | Reference - MRTS16 Cl 9.1.1.5, Cl 9.2.1.5
holdpoint | HOLD POINT
checkpoint | Certificate of commencement of landscape and revegetation works monitoring period issued and is a minimum of 90 days unless otherwise specified in Clause 4.2 of the Annexure MRTS16.1
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Milestone
label | Reference - MRTS16 Cl 9.2
checkpoint | All Monitoring operations; including, watering, fertilising, weed, pest and disease control, mowing, slashing and brush cutting, pruning, and repair and reinstallation of failed plants, comply with Clause 9.2.1
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS16 Cl 9.2.1
checkpoint | Certificate of finalisation of landscape and revegetation works monitoring period issued
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Milestone
label | Reference - MRTS16 Cl 9.2
checkpoint | Final Verification
note | Supervisor/QA Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
note | Project Manager Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
signoff | Signature
checklist | 52.01 - Erosion and Sediment Control | itp |  |  |  |  | 52.01 - Erosion and Sediment Control | 2aa43ab3-86f6-46ce-89d7-12f2a1601309
section | Details
checkpoint | No construction work to commence before an Erosion and Sediment Control Plan has been submitted to the Administrator and assessed as suitable.
label | Acceptance Criteria and Frequency (Project Specific) - Check Item
label | Check Item - Hold Point 1
label | Reference - MRTS52 Cl. 6.1
holdpoint | HOLD POINT
checkpoint | The Contractor must install erosion and sediment controls associated with drainage paths flowing through the works area.
label | Acceptance Criteria and Frequency (Project Specific) - Check Item
label | Check Item - Hold Point 2
label | Reference - MRTS52 Cl. 7.1
holdpoint | HOLD POINT
checkpoint | Releases from site must not cause scour at the area of discharge. Water must only be released at the discharge point nominated within the ESCP and as deemed acceptable by the Administrator.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Records
label | Reference - MRTS52 Cl. 8.1
checkpoint | The Contractor shall install a proprietary rain gauge and keep record of the rainfall depth of each rain event
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Records
label | Reference - MRTS51 Cl. 8.2.3.2.1
checkpoint | The Contractor shall maintain all erosion and sediment controls in effective working order including reconfiguring drainage lines as required during the construction process to ensure dirty water is directed into sediment controls at all times. Reuse of the water collected in sediment ponds or basins for dust suppression and roadworks is preferred over release into the environment. Where water is being stored for dust suppression the required design capacity of the basins shall be available.
label | ○ Sediment basins and other sediment controls shall be operated and maintained in a manner that minimises the risk of environmental harm. The design capacity of the upper settling volume shall be made available within 120 hours of the most recent rainfall event which causes runoff.
label | ○ The sediment storage zone shall be maintained at all times with the accumulated sediment removed in a manner that does not allow the sediment to be conveyed into a watercourse or offsite.
label | ○ Where coagulants or flocculants are used to treat stormwater, they must not cause harm to the receiving waters or environment. A jar test or streaming current detector (SCV) must be undertaken to estimate volumes of the coagulant or flocculant required and to reduce the risk of overdosing.
label | ○ Coagulants or flocculants containing aluminium (including alum and PAC) shall not be used when water is being discharged to an acidic environment where natural pH is less than 6.0 (such as wallum stream or wetland).
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS51 Cl. 7.2
checkpoint | The Contractor shall remove temporary controls when permanent measures are in place and/or Site stabilisation has occurred. This should occur prior to the end of the Defects Liability Period or the end of the Landscape and Revegetation Works Monitoring Period whichever is the later. The Contractor will not receive a Final Certificate until these temporary controls have been removed from the Site. Any areas used for erosion and sediment control shall be rehabilitated to the satisfaction of Administrator.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS51 Cl. 7.3
checkpoint | The Contractor is required to conduct daily visual assessments of erosion and sediment control structures to verify their condition and effectiveness. The Contractor shall also conduct weekly site inspections. Where any defect or damage is identified it is required that they be rectified immediately. This information must be recorded at the time of inspection, and both daily and weekly records submitted in the Contractor’s Weekly Site Inspection Reports (refer Clause 7.1 of MRTS51). The Contractor's ESCP’s and EMP(C) shall document detailed response procedures to address any observed or documented sediment release or erosion.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Records
label | Reference - MRTS51 .1 Cl. 4.1.1
checkpoint | Independent ESC audits shall be undertaken in accordance with Section 9.1 of MRTS52 and includes one audit immediately following clearing and grubbing, one audit during any cut/fill activities and one audit at the end of major earthworks. Reports shall be submitted to the Administrator within three days of the audit.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Records
label | Reference - MRTS51.1 Cl. 4.1.3
checkpoint | Final Verification
note | Project Manager Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
note | Client Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
signoff | Signature
checklist | 51.00 - Environmental Management Systems | itp |  |  |  |  | 51.00 - Environmental Management Systems | 31ce4bdc-f0da-4b33-a1d7-6780c1f0ca44
section | Details
checkpoint | Environmental Management Plan (Construction) EMP (C) submitted in accordance with Conditions of Contract.
label | Check Item - Milestone
label | Reference - MRTS51 Cl. 6.3
checkpoint | Works under the Contract shall not start until the EMP (C) is assessed for suitability by the Administrator.
label | Check Item - Hold Point 1
label | Reference - MRTS51 Cl. 6.3
holdpoint | HOLD POINT
checkpoint | Any amendments to the EMP (C) shall be submitted on a monthly basis and be assessed for suitability by the Administrator.
label | Check Item - Hold Point 2
label | Reference - MRTS51 Cl. 6.4
holdpoint | HOLD POINT
checkpoint | Environmental site inspections to be conducted daily against all licences, permits, approvals and other environmental performance requirements. All Inspection to be documented with records being submitted to the Administrator on a Weekly basis.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS51 Cl. 7.1
checkpoint | The Contractor shall be responsible for the management of the below inline with the requirements outlined within the Additional Obligation Documents and MRTS51.1:
label | ○ Landfill Gas Requirements
label | ○ Contaminated Land Requirements
label | ○ Water Quality Requirements
label | ○ Bio Security Requirements
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - Contract Documents
checkpoint | The Contractor shall be responsible for the management of Indigenous and non-Indigenous cultural heritage artefacts, sites and values within the worksite BCC organised Cultural Heritage Training completed and applicable inspection where required
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS51 Cl. 8.4.1
checkpoint | The contractor shall at all times take measures to assist in minimising noise associated with construction activities so as not to cause environmental nuisance or harm.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS51 Cl. 8.5.2
checkpoint | Project records shall include all noise monitoring results if required
label | Check Item - Check Item
label | Reference - MRTS51 Cl. 8.6.3
checkpoint | Condition survey may need to be conducted prior to commencement of activities as per Annexure MRTS51.1 Cl. 5.5 Copies of condition survey to be forward to Administrator 5 working days before any works that cause vibration start.
label | Check Item - Check Item
label | Reference - MRTS51 Cl. 8.6.2.3
checkpoint | Where identified in Cl. 4.3 of Annexure MRTS51.1 the contractor shall undertake vibration monitoring at vibration sensitive receptors.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS51.1 Cl. 8.6.1
checkpoint | Project records that show compliance with the VMP and shall include all noise monitoring results (if required)
label | Check Item - Check Item
label | Reference - MRTS51.1 Cl. 8.6.2
checkpoint | The contractor shall ensure that construction activities do not result in air quality impacts that cause environmental nuisance or harm. Burning of material shall not be permitted
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS51 Cl. 8.7.3
checkpoint | The contractor shall be responsible for the management of acid Sulphate Soils and shall address the requirements of MRTS04 General earthworks including the requirements concerning the management of acid sulphate soils
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS51 Cl. 8.8
checkpoint | The contractor shall be responsible for the management of contaminated sites ( contaminated soils, waste dumps, unexploded ordinances ) within the worksite . The contractor shall address the requirements of MRTS04 General earthworks including the requirements concerning the management of acid sulphate soils
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS51 Cl. 8.9.1
checkpoint | The contractor shall take all due care to not harm native fauna. Areas of significance and related management requirements are stated in Cl. 7 of Annexure MRTS51.1. Contact details for emergency wildlife care shall be included on project emergency contact list. Carry out Dawn and Dusk Frog Calling prior to Clearing works and other requirement Frog management where required inline with additional obligation documents
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS51 Cl. 8.10.1
checkpoint | A pre-clearing and post clearing report must be provided by the koala spotter.
label | Check Item - Check Item
label | Reference - MRTS51.1 Cl. 8.10.3
checkpoint | The contractor shall be responsible for the management of vegetation within the worksite. The daily site inspections shall include visual assessments of vegetation management measures.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS51 Cl. 8.11.1
checkpoint | All declared pest known to occur within the worksite and associated management requirements are stated in Cl. 9.1 of Annexure MRTS51.1.The contractor shall manage all declared pests (Animals and Plants ) within the worksite by preventing their spread on and off site
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS51 Cl. 8.12.2
checkpoint | No waste or litter shall be burnt on site. No waste or litter shall be buried on site unless approved by the Administrator and the administering authority.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS51 Cl. 8.13.2
checkpoint | Fire Ant Inspection Carried out with TMR prior to works commencing. Certificates for applicable imported Items where required.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - BCC Supplied Certificate
checkpoint | Monthly reporting requirements up-to-date copies of all monitoring results and tracking registers (including waste registers) within 5 business days of the end of a calendar month and upon request.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS51.1 Cl4.2
checkpoint | Maintan a animal tamping register inline with the SMP
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - SMP requirement
checkpoint | The contractor shall be responsible for the management of all chemicals and fuels within the worksite so as not to cause environmental nuisance or harm. The contractor shall ensure spill kits response equipment are available on site for use in emergency
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS51 Cl. 8.14.1
checkpoint | Final Verification
note | Project Manager Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
note | Client Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
signoff | Signature
checklist | 70.01 - MRTS70 Special Class Concrete | itp |  |  |  |  | 70.01 - MRTS70 Special Class Concrete | 75c16999-beb7-4b55-9059-290bc55880da
section | Details
checkpoint | The Contractor shall nominate the special class concrete mix to be used in the Works not less than four weeks prior to the commencement of concreting operations.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Milestone
label | Reference - MRTS70 Cl 9.2
checkpoint | Procedure for hot weather concreting submitted 2 weeks prior to first concrete pour.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Milestone
label | Reference - MRTS70 Cl 13.1
checkpoint | Procedure for curing submitted 2 weeks prior to first concrete pour.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Milestone
label | Reference - MRTS70 Cl 15.11.1
checkpoint | Procedure for temperature control submitted 4 weeks prior to first concrete pour
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Milestone
label | Reference - MRTS70 Cl15.5
checkpoint | When requested by the Adminstrator, mix designs shall have a trial mix completed. each trial mix shall be a Witness Point with a notice peroid of 3 days.
label | Acceptance Criteria and Frequency (Project Specific) - f'c Each Mix
label | Check Item - Witness Point
label | Reference - MRTS70 Cl 15.1.1
checkpoint | No concrete shall be placed in the Works until approval of the mix design has been obtained from the Administrator
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Hold Point 1
label | Reference - MRTS70 Cl 15.1
holdpoint | HOLD POINT
checkpoint | Concrete placed within 1 hour (conc. Temp<=32 degrees) or 45 mins (32>conc. temp < 35 degrees) from the time of charging the mixer unless a retardant is used and approved by the Administrator. No concrete may be placedthe temperature of the concrete is less than 10°C or exceeds 35°C
label | Acceptance Criteria and Frequency (Project Specific) - 10< Temp <35 Continuous
label | Check Item - Check Item
label | Reference - MRTS70 Cl 13.1
checkpoint | Falsework details provided to Administrator at least 4 weeks prior to erection.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Milestone
label | Reference - MRTS70 Cl 15.3
checkpoint | Design and erection of falsework, its founding, support and time, order and manner of release approved by the Administrator.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Hold Point 2
label | Reference - MRTS70 Cl 15.3
holdpoint | HOLD POINT
checkpoint | No concrete placed until falsework, formwork, reinforcement and stressing materials inspected by administrator, foreign material removed from forms and equipment and placement procedures approved.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Hold Point 3
label | Reference - MRTS70 Cl 15.4.1
holdpoint | HOLD POINT
checkpoint | Concrete operations shall not commence until all relevant procedures, listed in Table 5.2 have been approved by the Administrator.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Hold Point 4
label | Reference - MRTS70 Cl 15.6
holdpoint | HOLD POINT
checkpoint | No concrete shall be placed in the Works until:
label | a) the formwork and reinforcement have been inspected
label | b) all foreign material has been completely removed from the forms
label | c) the mixing, batching, and compaction equipment have been approved by the Administrator.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Hold Point 5
label | Reference - MRTS70 Cl 15.6.1
holdpoint | HOLD POINT
checkpoint | Administrator to be present for placement of concrete, given 24 hours notice.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Witness Point
label | Reference - MRTS70 Cl 15.6.1
checkpoint | Concrete slump is within tolerance (AS 1379 table 6) of approved target slump.
label | Acceptance Criteria and Frequency (Project Specific) -
label | Slump Test: ¦¦ Spread Test:
label | <60 - ±10 ¦¦ 500 - 600(HWC) ±80
label | 60<80 - ±15 ¦¦ 650 - 700(HWC) ±50
label | 80<110 - ±20
label | 110<150 - ±30
label | 150< 200 - ±40
label | Every Load
label | Check Item - Check Item
label | Reference - MRTS70 AS 1379 Table 6
checkpoint | Samples for testing taken as required in accordance with claus 12. - min 2 cylinders/sample
label | Acceptance Criteria and Frequency (Project Specific) - 1-3 Loads - Every Load
label | ○ 4-10 Loads - 4 Samples
label | ○ 11-23 Loads - 5 Samples
label | ○ >24 Loads - n/4
label | Check Item - Test Results
label | Reference - MRTS70 Cl 15.2
checkpoint | Compaction of concrete commences immediately after deposition in accordance with approved procedures and equipment - The number of vibrators to be used by the Contractor shall be not less than one for each 10 m³ of concrete placed per hour
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS70 Cl 16.5.2
checkpoint | Fresh concrete shall not be placed against concrete which has taken its initial set.If an interruption greater than 45 minutes occurs, a construction joint approved by the Administrator shall be placed.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS70 Cl.16.5.1
checkpoint | Construction joints shown in the Drawings are mandatory. The use of construction joints elsewhere in the concrete work shall require the prior approval of the Designer
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Hold Point 7
label | Reference - MRTS70 Cl 15.13
holdpoint | HOLD POINT
checkpoint | Forms, falsework and centring shall remain in position until the times stated in Cl15.8 and table 15.8 have elapsed after completion of concreting
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Hold Point 6
label | Reference - MRTS70 Cl 15.8
holdpoint | HOLD POINT
checkpoint | Forms shall be removed with care, without hammering and wedging, and in a manner which shall not injure the concrete or disturb the remaining supports. Centres shall be lowered gradually and uniformly in such a manner as to avoid injurious stress in any part of the structure
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Witness Point
label | Reference - MRTS70 Cl 15.8
checkpoint | Following removal of forms
label | ○ Fins and unwanted projections are ground off
label | ○ Pockets and honeycombed areas repaired using approved methods
label | ○ Where required in the drawings surfaces achieve class 1 finish or are bagged within 4 hours of stripping, then cured
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS70 Cl 16.8.1
checkpoint | Positional tolerances, listed in Table 15.7.3, refer to the departure of any point, plane or component of a structure from its correct position within the layout of the structure as shown in the Drawings.
label | Acceptance Criteria and Frequency (Project Specific) - Visual < Specified MRTS70 Cl15.7.3
label | Check Item - Check Item
label | Reference - MRTS70 Cl 15.7.3
checkpoint | Acceptance or Rejection of Hardened Concrete
label | Acceptance Criteria and Frequency (Project Specific) - a) < 0.9 Fc (Any sample)
label | b) < Fc (Ave 3 consective samples from Lot)
label | c) > 1.4 Fc (Ave 3 consective samples from Lot)
label | In addition
label | d) < 0.5 (Fc+Ft) (10 or more samples for Class of concrete in 4 consective weeks)
label | Check Item - Test Results
label | Reference - MRTS70 Cl 12.5
checkpoint | Final Verification
note | Project Manager Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
note | Client Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
signoff | Signature
checklist | 70.02 - MRTS70 Normal Class Concrete | itp |  |  |  |  | 70.02 - MRTS70 Normal Class Concrete | e6fe82a7-e19c-41e6-bf33-99a454a1e40f
section | Details
checkpoint | Concrete class - The strength grade of concrete and maximum nominal aggregate size used shall be as specified on the Drawings.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS70 Cl 17.1
checkpoint | Submission of long distance travel procedure - Where travel times are, by necessity, longer than 90 min as listed in AS 1379, a procedure for longdistance travel or extended placement times shall be submitted to the Administrator
label | Check Item - Milestone
label | Reference - MRTS70 Cl 17.6.1
checkpoint | Acceptance and rejection of hardened concrete - Acceptance and rejection of hardened concrete shall be on a production assessment basis in accordance with AS 1379 except as noted below. Concrete for the following applications shall betested on a project assessment basis, where more than 25 m³ of concrete is used:
label | a) signpost footings and plinths with dimension greater than 150 mm
label | b) spill through or rock grouting, and
label | c) manually placed kerb and channel on or alongside concrete base.
label | ○ Production assessment reports in accordance with AS 1379 shall be submitted to the Administrator
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Test Results
label | Reference - MRTS70 Cl 17.8
checkpoint | Approval of falsework - All formwork shall be subject to inspection and approval by the Administrator
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - HOLD POINT
label | Reference - MRTS70 Cl 17.10
holdpoint | HOLD POINT
checkpoint | Approval of formwork - All formwork shall be subject to inspection and approval by the Administrator
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - HOLD POINT
label | Reference - MRTS70 Cl 17.11
holdpoint | HOLD POINT
checkpoint | Supports (bar chairs and spacers) - All bar chairs and spacers shall comply with AS/NZS 2425
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS70 Cl 17.11.1
checkpoint | Where concrete work is constructed on ground surfaces or on a foundation bedding, a polythene sheet separator of thickness not less than 100 μm shall be employed between the ground / bedding and the concrete
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS70 Cl 17.12.1
checkpoint | Approval to place concrete - No concrete shall be placed in the Works until the formwork and reinforcement have been inspected, and all foreign material has been completely removed from the forms.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - HOLD POINT
label | Reference - MRTS70 Cl 17.12.1
holdpoint | HOLD POINT
checkpoint | Placing of concrete - The placing operation shall be conducted in the presence of the Administrator and the Contractor shall give at least 24 hours notice to the Administrator of the time that placing shall start.
label | Check Item - Witness Point
label | Reference - MRTS70 Cl 17.12.1
checkpoint | Removal of formwork - For cast-in-situ concrete, forms, falsework and centring shall remain in position until 72 hours has elapsed.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - HOLD POINT
label | Reference - MRTS70 Cl 17.16
holdpoint | HOLD POINT
checkpoint | Final Verification
note | Project Manager Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
note | Client Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
signoff | Signature