## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP029 - Topsoil and Grassing | itp |  |  |  |  | FH-ZU2-QU-ITP029 - Topsoil and Grassing - Rev 0
section | 1.0 - Preliminary Activities
checkpoint | 1.1 - Check for correct documentation
label | Frequency - Prior to commencing any activity
label | Acceptance Criteria - Current revision drawing is being used including the subcontractors copy. Current Revision to be obtained via Aconex.
label | Reference Documents - Drawings and Aconex
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP signed
label | HP*
label | Responsibility - Project Engineer, Site Engineer
date | Date Completed:
checkpoint | 1.2 - Implementation of all measures and controls
label | Frequency - Prior to commencing any activity
label | Acceptance Criteria - All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WP
label | Reference Documents - PSP, EMP, TMP, SWMS, WP
label | Inspection/Test Method - Inspect
label | Record of conformity - This ITP signed
label | HP*
label | Responsibility - Project Engineer, Site Engineer
date | Date Completed:
checkpoint | 1.3 - Material Approval
label | Frequency - Prior to hydro seeding
label | Acceptance Criteria - Hydro mulch supplier are either to be Flexterra HP-FGM, Vital Bon, or Hydro Mulch 1000 unless agreed otherwise by Melbourne Airport.
label | Reference Documents - Grassing Spec cl. 7.2
label | Inspection/Test Method - Verify
label | Record of conformity - ACONEX, This ITP signed
label | HP
label | Responsibility - Project Engineer, Site Engineer
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 2.0 - Herbicide
checkpoint | 2.1 - Topsoil Material
label | Frequency - Prior to topsoil placement
label | Acceptance Criteria - Topsoil material is to be virgin topsoil free from clay lumps larger than 50mm in diameter, contaminants, pest, weeds, stones, subsoil, tree, and shrub roots.
label | Reference Documents - Grassing Spec cl. 7.4
label | Inspection/Test Method - Visual Inspecti on
label | Record of conformity - This ITP signed
label | HP*
label | Responsibility - Project Engineer, Site Engineer, Enviro & Sustainability Advisor
date | Date Completed:
section | 3.0 - Placement of top soil
checkpoint | 3.1 - Topsoil placement
label | Frequency - Each Lot
label | Acceptance Criteria - APAM engineering standard (MAS- CVL-001-V1-1-Grassing-Standard – Dec 2022) calls for a uniform thickness of not less than 100mm of topsoil prior to seeding and subject to the Contractor making necessary allowance for compaction of the topsoil prior to Hydro mulching.
label | Reference Documents - Grassing Spec cl. 5.2
label | Inspection/Test Method - Verify
label | Record of conformity - Survey data
label | HP*
label | Responsibility - Project Engineer, Site Engineer, Foreman
date | Date Completed:
section | 4.0 - Hydro seeding
checkpoint | 4.1 - Grass Seeds
label | Frequency - Each Lot
label | Acceptance Criteria - Grass seed to be used during hydroseeding is to be the following:
label | ○ 50% Common Couch & 50% Colosseum Ryegrass during the warmer seasons (October to March)
label | ○ 100% Ryegrass during cooler seasons (April to September)
label | – Use of other grass seeds to be approved by Environment and Sustainability Manager.
label | Reference Documents - Grassing Spec cl. 7.1
label | Inspection/Test Method - Verify
label | Record of conformity - Aconex material submission
label | HP
label | Responsibility - Project Engineer, Site Engineer, Enviro & Sustainability Advisor
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.2 - Coverage / Tolerances
label | Frequency - Each Lot
label | Acceptance Criteria - A minimum of 95% healthy cover it to be achieved. 95% grass coverage will not take into account any growing weeds as part of the cover.
label | Reference Documents - Grassing Spec cl. 5.6
label | Inspection/Test Method - Visual Inspecti on
label | Record of conformity - This signed ITP
label | HP*
label | Responsibility - Project Engineer, Site Engineer
date | Date Completed:
checkpoint | 4.3 - Stabilisation Treatment
label | Frequency - Prior to opening area to airport traffic
label | Acceptance Criteria - Use of Vital Bon-Matt Stonewall, or equivalent, is to be prioritised instead of the use of bitumen emulsion in areas prone to jet blast following topsoil and seeding. FH will use bitumen emulsion if directed by APAM Operations.
label | ○ Use of alternative stabiliser to be used for the works is subject to approval by Environment and Sustainability Manager.
label | Reference Documents - Grassing Spec cl. 4.9
label | Inspection/Test Method - Verify
label | Record of conformity - This signed ITP
label | HP*
label | Responsibility - Project Engineer, Site Engineer, Enviro & Sustainability Manager
date | Date Completed:
checkpoint | 4.4 - Hydro seeding
label | Frequency - Each lot
label | Acceptance Criteria - Application rates shall be more than six tonnes/ha flexterra or alternative (vital bon / hydro mulch 1000) unless agreed otherwise.
label | Reference Documents - Grassing Spec cl. 5.5
label | Inspection/Test Method - Visual inspecti on
label | Record of conformity - This signed ITP
label | HP*
label | Responsibility - Project Engineer, Site Engineer, Foreman
date | Date Completed:
checkpoint | Reinstatement of Disturbed Surfaces
label | Frequency - As Required
label | Acceptance Criteria - Hydro mulched areas are not to be trafficked for 3 months or until grass has been established.
label | Reference Documents - Grassing Spec cl. 5.5
label | Inspection/Test Method - Visual inspection
label | Record of conformity - This signed ITP
label | HP*
label | Responsibility - Site Engineer, Foreman
date | Date Completed:
section | 5.0 - Post Construction
checkpoint | 5.1 - Reinstatement of Disturbed Surfaces
label | Frequency - As Required
label | Acceptance Criteria - Disturbed surfaces are to be reinstated to their original condition. In areas prone to jet blast, the topsoil surface should be sprayed with bitumen emulsion, Vital Bon-Matt Stonewall, or equivalent, following seeding if grass strike has not been achieved prior to opening the area to aircraft traffic.
label | Reference Documents - Grassing Spec cl. 4.13
label | Inspection/Test Method - Inspection Point
label | Record of conformity - This signed ITP
label | IP
label | Responsibility - Project Engineer, Site Engineer
date | Date Completed:
checkpoint | Final Inspection
note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Work Completed On:
date | Date: