## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP 34 - B30 Backfill of Structures | itp |  |  |  |  | ITP 34 - B30 Backfill of Structures
section | Lot Information
checkpoint | Lot Information complete
textbox | Lot Opened On
textbox | Date of Works
textbox | Lot Type
textbox | Start Chainage
textbox | End Chainage
textbox | Offset
textbox | Control Line
section | 1. Preliminary
checkpoint | 1.1 - B30 Material Approval
label | Requirements / Reference - B30: cl 6.2.1
label | Acceptance Criteria - Select Backfill for Structures
label | Chemical testing -
label | ○ pH >=5.5
label | ○ S04<=1000mg/L
label | ○ Chlorides<= 200mg/l
label | Particle Size Distribution -
label | ○ As per B30 table B30.2
label | ○ Coeff uniformity >=5
label | ○ PI<=15
label | Notification / Frequency - Per stockpile. 1 test per 500m3
label | Inspection - ACPL - H
label | Inspection - Client - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.2 - Age of Structure and B30 Extents
label | Requirements / Reference - B30: cl 6.3
label | Acceptance Criteria - Age of structure
label | ○ Wait at least 7 days or 75% of the specified minimum 28-day compressive strength of the member is achieved before commencing backfilling of structure.
label | NOTE -
label | ○ Date last pour on RW1/Abutment B: 22/10/24
label | ○ Date start backfill RW1 Abutmnt B:27/11/24
label | ○ Waiting period: 5 weeks
label | ○ Date of last pour on RW2: 19/11/2024
label | ○ Date start backfill RW2: 16/12/2024
label | ○ Waiting Period: 4 weeks
label | B30 Extents
label | ○ Ensure excavation will allow backfilling of B30 within a distance of H/2 from edge of base slab, where H is the distance between the base of the footing and the top of the wall as indicated in B30/E
label | Notification / Frequency - Once per Structure
label | Inspection - ACPL - S
section | 2. Construction
checkpoint | 2.1 - Backfill against several sides of a structure
label | Requirements / Reference - B30: 6.4.5
label | Acceptance Criteria - Real time monitoring of the Abutment during the B30 placement
label | Notification / Frequency - Per Lot
label | Inspection - ACPL - S
checkpoint | 2.2 - Placing and Compaction - B30 Select Backfill
label | Requirements / Reference - B30: cl 6.4
label | Acceptance Criteria - Moisture requirements:
label | ○ Moisture between 60-90% of OMC
label | Compaction Requirements:
label | ○ 98% relative compaction using T173 and T166 and determine characteristic relative value of compaction per Q6.
label | Notification / Frequency - Per Lot
label | Inspection - ACPL - H
label | Comments / Attachments / Records - The greater of one test per layer, or one per 50m2 or one per day
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 - Maximum layer thickness- B30 select backfill
label | Requirements / Reference - B30: table B30.5
label | Acceptance Criteria - Maximum layer thickness:
label | ○ 150mm
label | Notification / Frequency - Per lot
label | Inspection - ACPL - S
checkpoint | 2.4 - Drainage Zone behind the retaining structures
label | Requirements / Reference - Cl. 6.5
label | Acceptance Criteria - Installation of Drainage Material (Strip Drains)
label | Notification / Frequency - Per Structure
label | Inspection - ACPL - S
section | Review by Project Engineer
checkpoint-no-value | Review by Project Engineer
button | Any non-conformances? | YES, NO
textbox | No's:
button | Closed Out | YES, NO
button | All work has been satisfactorily completed. | YES, NO
textbox | Name:
holdpoint | Add signature
section | Lot Verification
checkpoint | Lot Verification complete
textbox | Lot Verified By:
textbox | Lot Closed Date:
button | Submitted to Client | Yes, No, N/A
button | Reviewed by Client | Yes, No, N/A
textbox | Submission Comments:
section-nested-checklists | NCR