## to_add
Step Id | Warnings | State | Checklist Template | Type | addStep | addPost | Tier 1 | Tier 2 | Tier 3 | Tier 4 | Tier 5 | Tier 6
285e5b99-2f1b-5b37-b97b-19d74666da3e |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Minor Concrete Works | ITP - 114 - Footpath Construction Rev B (Peacockes East) | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - 6.01 - General | 7.01.04 - Defect, Snag and Punch List
e5de1086-7f06-5d41-910a-c6e240640e13 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Minor Concrete Works | ITP - 114 - Footpath Construction Rev C (Peacockes East) | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 7.01.04 - Defect, Snag and Punch List
70eb1358-8957-5d2e-9481-c84b49b06f6e |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Minor Concrete Works | ITP - 114 - Footpath Construction Rev C Peacockes West | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 7.01.04 - Defect, Snag and Punch List
caeea63a-8849-56db-8dca-1d8688ff53dc |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 SIL | SECTION 7 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - 7.02 Site Post Construction Activities | 7.01.04 - Defect, Snag and Punch List
2140c9dd-ef98-5a0f-b031-1db9b9c2b327 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 BULK EARTHWORKS | SECTION 8 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - Site Post Construction Activities | 8.1.4 - Defect, Snag and Punch List
8aa2b6f0-2515-5050-85e1-2eeddd987d8b |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CENTRE AND PERIMETER SUBSOILS | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 6.01.04 - Defect, Snag and Punch List
3a677565-1d75-5820-bd42-fcb69efbd132 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 PAVEMENT DRAINS | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 6.01.04 - Defect, Snag and Punch List
a0c483c5-ec73-52a0-bef6-9fad914539cd |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | SWD03 POND | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 6.01.04 - Defect, Snag and Punch List
44bcea1d-5532-5b3a-8b3d-f02f8e69c04d |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | ITP - 116 - Pavement SIL Rev C | SECTION 7 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 7.01.04 - Defect, Snag and Punch List
d93fe0d6-de3a-52ab-a5a8-51cef63fea40 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 3 | AREA 3 CH995-CH1255 BULK EARTHWORKS | SECTION 8 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - Site Post Construction Activities | 8.1.4 - Defect, Snag and Punch List
8abe101f-62f3-5cf5-907d-fcebaa0bc6d1 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 3 | ITP - Pavement SIL | SECTION 7 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - 7.02 Site Post Construction Activities | 7.01.04 - Defect, Snag and Punch List
295ed9a0-340c-5c83-9654-01f3a7e8f08a |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 3 | ITP - Subsoil Drainage - Rev C | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 6.01.04 - Defect, Snag and Punch List
215fa706-b7b8-55f1-a2fe-a32644a8a218 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 3 | ITP - Pavement Drains - Rev B | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 6.01.04 - Defect, Snag and Punch List
f71ca5b6-7692-5904-8be8-a46d316369ef |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1270 - CH1860 & South Diversion Road Tie-In BULK EARTHWORKS | SECTION 8 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - Site Post Construction Activities | 8.1.4 - Defect, Snag and Punch List
450c2824-c414-5473-ba04-bf90fa30cda5 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | ITP - Subsoil Drainage - Rev C (Gully Drainage Blanket Ch1430) | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 6.01.04 - Defect, Snag and Punch List
1b7aa790-d338-5119-8ab0-e768a8ed1e02 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1360-CH1860 SIL (COOMBES SAND) | SECTION 7 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - 7.02 Site Post Construction Activities | 7.01.04 - Defect, Snag and Punch List
7db6fbe3-c765-58ff-b80a-bad826fe12a5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1270-CH1360 SIL (100mm BLUE BROWN ROCK) | SECTION 7 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 7.01.04 - Defect, Snag and Punch List
c370c3ed-075e-5f1e-a3ed-8697c75fdf24 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | ITP - 113 - Pavement Drains Rev D | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 6.01.04 - Defect, Snag and Punch List
c1bbdca3-8263-5dc9-a5f7-e077ece443e5 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | ITP - 112 - Subsoil Drains Rev D (SWALE) | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 6.01.04 - Defect, Snag and Punch List
6925ad75-92c6-5983-a6e4-0fa2671e878e |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | ITP - 119 - Rain Garden Rev B | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 6.01.04 - Defect, Snag and Punch List
1478b6aa-a49d-549e-85d7-9bdd6e2ccd7a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PW CH1270-CH1860 & FULL WIDTH CH1860-CH2100 BULK EARTHWORKS | SECTION 8 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - Site Post Construction Activities | 8.1.4 - Defect, Snag and Punch List
b699561d-8cec-5502-ab35-b69a11cb3dd4 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PW CH1270-CH1860 & FULL WIDTH CH1860-CH2100 SIL (100mm BLUE BROWN ROCK) | SECTION 7 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 7.01.04 - Defect, Snag and Punch List
3fdd26e9-9e9b-5266-9147-a98e128e7cb8 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | ITP - 112 - Subsoil Drains Rev D (Swale) | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 6.01.04 - Defect, Snag and Punch List
07443bdb-12ce-5e08-a2e0-231e86129609 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | ITP - 113 - Pavement Drains/ Perimeter and Centre Subsoil Rev D | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 6.01.04 - Defect, Snag and Punch List
ca2319fb-fde5-5166-8788-45108ad87902 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | ITP - 113 - Pavement Drains Rev D | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 6.01.04 - Defect, Snag and Punch List
e411119d-271e-5415-bec9-031a60e9c8b3 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PEACOCKES WEST RAIN GARDENS | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 6.01.04 - Defect, Snag and Punch List
38e62e9a-8c6a-51bd-a710-97b624b0d9b5 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 BULK EARTHWORKS | SECTION 8 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - Site Post Construction Activities | 8.1.4 - Defect, Snag and Punch List
8e5f8186-e2ab-5821-8fa4-ab95e262042a |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 SIL | SECTION 7 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 7.01.04 - Defect, Snag and Punch List
54f8ea01-cc7a-5d87-a013-9f15cdc5b2a4 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 PAVEMENT DRAINS | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 6.01.04 - Defect, Snag and Punch List
123ad1d9-719f-52bd-8243-533925971115 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 SUBSOILS (CENTER & PERIMETER) | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 6.01.04 - Defect, Snag and Punch List
4b38c751-9615-5373-aa48-6ec3c46cd800 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 1st Pour (ABT D & Span C-D) | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.04 - Defect, Snag and Punch List
ab321cd8-b5d3-5534-bbc2-974a83bec7d0 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 2nd Pour (Pier C & Span BC) | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.04 - Defect, Snag and Punch List
7b5dcb72-01cf-577c-90db-98d1ca5cec3d |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 3rd Pour (Pier B & Span AB) | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.04 - Defect, Snag and Punch List
cc63c117-610a-5dfe-81c9-3771b97b4500 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 4th Pour (ABT A & Span AB remaining) | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.04 - Defect, Snag and Punch List
2c2d2a12-a5c9-5947-a5de-0646aca721c4 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | EGB Pier B & Pier C Light Corbels | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.04 - Defect, Snag and Punch List
1150336d-c783-5c89-856f-94fe0e55b6a1 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Off Bridge Light Pole Foundation ABT A & D | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.04 - Defect, Snag and Punch List
933a97ee-491d-5fae-aac9-6ca8fe554a6f |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.04 - Defect, Snag and Punch List
62cf2267-6760-5e73-97f4-f2e97adf99f0 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Bridge Deck & Crosshead | Insitu Concrete for 1st Pour (ABT A & Span A-B) | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.04 - Defect, Snag and Punch List
306dc7a3-21fb-5f5e-bf01-32edec1adb85 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Bridge Deck & Crosshead | Insitu Concrete for 2nd Pour (Pier B & Span A-B) | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.04 - Defect, Snag and Punch List
037405a7-790f-59ba-91b0-e27d7cbb07dd |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Bridge Deck & Crosshead | Insitu Concrete for 3rd Pour (PIER C & Span B-C) | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.04 - Defect, Snag and Punch List
45b0c406-dc49-5fc7-9cc6-3599a722e514 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Bridge Deck & Crosshead | Insitu Concrete for 4th Pour (ABT D & Span CD remaining) | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.04 - Defect, Snag and Punch List
dba7d323-a480-51ea-bfe3-6bbb4e73ae48 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Bridge Deck & Crosshead | MGB Pier C Light Corbel | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.04 - Defect, Snag and Punch List
0e29fc2b-f5ee-5ffe-9a08-2ab10f029ec4 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Off Bridge Light Pole Foundation ABT A & D | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.04 - Defect, Snag and Punch List
95f43a78-e54b-576d-ad9e-c961a4cd7f37 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Minor Concrete Works | Whatukooruru Drive | ITP - 114 - Footpath Construction Rev B (Whatukooruru Drive) | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - 6.01 - General | 7.01.04 - Defect, Snag and Punch List
ca7ea69c-e91f-5868-83ad-fd5aaa7b8fcf |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Minor Concrete Works | Whatukooruru Drive | ITP - 114 - Footpath Construction Rev C (Whatukooruru Drive) | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 7.01.04 - Defect, Snag and Punch List
7b1975a4-e068-5fe4-81d5-e2cc73d7a004 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Minor Concrete Works | Concrete Island | ITP - 134 - Concrete Islands Infill Construction Rev A (Whatukooruru Drive) | 6.01 - General | 6.01.04 - Defect, Snag and Punch List
d7dea77b-4e25-5c7f-9ac4-9a9b6b0b9a13 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Minor Concrete Works | Concrete Island | ITP - 134 - Concrete Islands Infill Construction Rev A (Peacockes Road) | 6.01 - General | 6.01.04 - Defect, Snag and Punch List
69d374ff-8e8b-564b-b706-fa200064f16e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1520-1740 BULK EARTHWORKS | SECTION 8 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - Site Post Construction Activities | 8.1.4 - Defect, Snag and Punch List
d226069e-f978-50d7-b33f-8f8c4a146a5c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1540-CH1740 SIL | SECTION 7 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - 7.02 Site Post Construction Activities | 7.01.04 - Defect, Snag and Punch List
cc9e651d-8929-5540-986d-604db9d69a09 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1540-CH1740 SUBSOILS (CENTRE & PERIMETER) | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 6.01.04 - Defect, Snag and Punch List
79a01b02-7250-5c8b-b739-54155b36da45 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1540-CH1740 SUBSOILS (SWALE) | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 6.01.04 - Defect, Snag and Punch List
cb74c849-c4c0-54d4-b9cb-f21633ba4d01 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1540-CH1740 PAVEMENT DRAINS | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 6.01.04 - Defect, Snag and Punch List
0d374fd2-18ba-5b77-813a-3f5d22430e03 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 BULK EARTHWORKS | SECTION 8 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - Site Post Construction Activities | 8.1.4 - Defect, Snag and Punch List
c6c339ab-3c9e-5088-b7a1-9ed89c5e09c1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 SIL | SECTION 7 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - 7.02 Site Post Construction Activities | 7.01.04 - Defect, Snag and Punch List
77fd035f-0e38-5274-ab67-865223b8b754 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 SUBSOIL DRAINAGE (CENTRE & PERIMETER) | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 6.01.04 - Defect, Snag and Punch List
d5d1e4cf-5541-54c4-acd9-5ec452408232 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 PAVEMENT DRAINS | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 6.01.04 - Defect, Snag and Punch List
799a844c-10f3-5f7d-9a10-cda12eeaad59 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH2030 SUBSOIL (SWALE) | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 6.01.04 - Defect, Snag and Punch List
f66bea79-1326-5e83-9a28-936736701214 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | ITP - 119 - Rain Garden Rev B Road A | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 6.01.04 - Defect, Snag and Punch List
861fbef9-80fb-509f-bdf1-89945d74dfcf |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 BULK EARTHWORKS | SECTION 8 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - Site Post Construction Activities | 8.1.4 - Defect, Snag and Punch List
72c4712c-37ec-5d41-9323-160f44041a9d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990 - CH2150 FULL WIDTH & CH2150 - CH2250 WEST BOUND SAND SIL | SECTION 7 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - 7.02 Site Post Construction Activities | 7.01.04 - Defect, Snag and Punch List
dde7107e-06ed-56f8-a9cd-42b8f5f8d65d |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C SUBSOIL (GULLIES) | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 6.01.04 - Defect, Snag and Punch List
0a64d7be-636f-524e-978a-a1d5d166fc85 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 SUBSOIL DRAINAGE (CENTRE & PERIMETER) | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 6.01.04 - Defect, Snag and Punch List
292598a1-d13f-51fe-9db0-7f0336ead368 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 PAVEMENT DRAINS | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 6.01.04 - Defect, Snag and Punch List
aeb62a6a-e0a6-5039-ac1f-847953fc663f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH2150 - CH2250 EAST BOUND ROCK SIL | SECTION 7 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 7.01.04 - Defect, Snag and Punch List
79a9088d-aacf-53e9-9594-24be28bdf05a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Pier Crossheads Downstand | EGB Pier B Crosshead | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.04 - Defect, Snag and Punch List
0370e3c1-4be2-50ef-a6bc-314e2f9a34a8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Pier Crossheads Downstand | EGB Pier C Crosshead | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.04 - Defect, Snag and Punch List
a2b81038-369e-5ef0-ab6d-46ea90877673 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Settlement Slabs | Abutment A | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.04 - Defect, Snag and Punch List
eaf7ddb7-dffa-5a8c-b23e-0293707d29f8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Settlement Slabs | Abutment D | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.04 - Defect, Snag and Punch List
ee960ead-824d-5d76-be30-dc087493328a |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 3rd Pour on 13/9/2024 | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.04 - Defect, Snag and Punch List
e46297e6-679e-5cab-ab20-8eebec22da34 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 1st Pour on 3/9/2024 | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.04 - Defect, Snag and Punch List
39150faa-d041-5265-b3dc-1626b1b86da3 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 2nd Pour on 9/9/2024 | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.04 - Defect, Snag and Punch List
fa33d048-f33d-52e9-953d-835c7c031689 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | Last Pour on 20/9/2024 | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.04 - Defect, Snag and Punch List
8024ecc7-918c-531c-b3e7-1a1cdce41305 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Transition Barriers | EGB Transition Barriers | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.04 - Defect, Snag and Punch List
f37524c2-a13c-5455-b900-efa377883d39 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Abutments | EGB Abutment A Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.04 - Defect, Snag and Punch List
720cfab0-5783-5bed-9515-49cfe0cbc27f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Abutments | EGB Abutment D Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.04 - Defect, Snag and Punch List
5d02888c-6f21-5bbf-8ac6-ae64238d973a |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Capping Slab | Abutment A | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.04 - Defect, Snag and Punch List
0ab12962-5056-5a3f-94f3-ddd6cb7fd452 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Capping Slab | Abutment D | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.04 - Defect, Snag and Punch List
508ccbda-1cf7-58d9-bf9c-b58348b4b5fb |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.04 - Defect, Snag and Punch List
ede24bf4-71a8-52b8-8a48-a4b2cd9ced5d |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | MGB Pier B | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.04 - Defect, Snag and Punch List
85feac22-1b59-53c4-8cac-6832b040bb6e |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | MGB Pier C | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.04 - Defect, Snag and Punch List
61b74cae-e4ce-593b-86fa-483c01c0ab5e |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Settlement Slabs | Abutment A Settlement Slab | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.04 - Defect, Snag and Punch List
3c9aa55b-4975-534e-9def-b34be4801868 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Settlement Slabs | Abutment D Settlement Slab | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.04 - Defect, Snag and Punch List
718a8483-f5c7-52f2-b2fd-27e4489d3855 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Bridge Barriers | Stitch Pour QA | 1st Pour on 11/10/2024 | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.04 - Defect, Snag and Punch List
d93d6a4f-9ff4-503c-8685-50d729833d1f |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Bridge Barriers | Stitch Pour QA | 2nd pour on 18/10/2024 | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.04 - Defect, Snag and Punch List
7ab8de25-32c0-5875-88f1-2c275a07303d |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Bridge Barriers | Stitch Pour QA | 3rd Stitch Pour on 25.10.2024 | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.04 - Defect, Snag and Punch List
a5a74fc9-c75f-5d8c-9793-d02e2abc5574 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Bridge Barriers | Stitch Pour QA | 4th Stitch Pour on 30.10.2024 | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.04 - Defect, Snag and Punch List
f2c93085-cd6e-5feb-b04d-5e88fa1938c2 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Bridge Barriers | Stitch Pour QA | Last Stitch Pour on 1.11.2024 | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.04 - Defect, Snag and Punch List
d88cf742-8202-5d71-80eb-262770013db3 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Bridge Barriers | MGB Transition Barriers | MGB Transition Barrier | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.04 - Defect, Snag and Punch List
801e7f5e-3281-593b-aac1-441137da87b7 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Abutments | MGB Abutment A Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.04 - Defect, Snag and Punch List
b4b47855-dfc8-51cc-95f1-0f05485c27e2 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Abutments | MGB Abutment D Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.04 - Defect, Snag and Punch List
66271e54-d5dc-5901-9cfe-6b9cbdc66907 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 1 | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.04 - Defect, Snag and Punch List
7fcf5660-19d6-505e-9842-cc91253168a6 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 2 | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.04 - Defect, Snag and Punch List
0b1c2217-fc12-597a-b301-41cea519cdba |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 3 | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.04 - Defect, Snag and Punch List
86f8be09-228c-5532-b365-7a90c366863a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 1 | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.04 - Defect, Snag and Punch List
1742c5ff-56b7-5ad1-8066-e981b3a6738a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 2 | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.04 - Defect, Snag and Punch List
8ca203de-f75e-57c9-a7c4-0b8f3e35a20c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 3 | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.04 - Defect, Snag and Punch List
7bce7df9-b216-523f-8335-328ef0341ffe |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B1 | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.04 - Defect, Snag and Punch List
1796c706-1670-52e9-a376-f0eb8ab93878 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B2 | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.04 - Defect, Snag and Punch List
b5e4b0b1-bb44-5b93-acc8-c9070812d955 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B3 | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.04 - Defect, Snag and Punch List
2e35dd31-eb2b-51e7-b32a-705993f69da9 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B4 | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.04 - Defect, Snag and Punch List
950d0154-4c63-5ebb-bfc1-5a7f29fe57cd |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C1 | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.04 - Defect, Snag and Punch List
01e660f7-a998-5d76-8fd1-a3efd496ac43 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C2 | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.04 - Defect, Snag and Punch List
2b6d4d79-3f27-548d-a8d0-823992d65a04 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C3 | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.04 - Defect, Snag and Punch List
62898a66-cb3b-5f9c-b1c8-421ed38138f1 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C4 | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.04 - Defect, Snag and Punch List