## Table 1
Project Scope: FRP | [20 empty] | Ref: RR-SEPD-BESS-ITP-004
Project: BESS Alinta Wagerup Peaking Power Station | [20 empty] | Revision: 00
ITP Description: Sheet Piling
Work Pack number: RR-SEPD-CI-SOW-004-00
Client: SEPD
Prepared By: | [6 empty] | Sign & Date: |  |  | Reviewed & Approved By: | [10 empty] | Sign & Date:
Juan Orozco – Project Engineer | [9 empty] | Ronan Egan – Project Manager
Reviewed & Approved By: | [6 empty] | Sign & Date: |  |  | Reviewed & Approved By: | [10 empty] | Sign & Date:
Artur Krupinski - Project Controls | [9 empty] | Jake Scott – Site Supervisor
Definitions
Hold Point |  | A point beyond which a work process must not proceed without the nominated authority’s express authorization.
Witness Point |  | A point in a work process where the Contractor must give prior notice to the nominated authority and the option of attendance may be exercised by the nominated authority.
Responsibility | [5 empty] | Method |  |  |  | Frequency | [8 empty] | Verification Requirement
SUP | Supervisor |  |  |  |  | I | Inspection |  |  | PW |  | Prior to works | [6 empty] | HP |  |  | Hold Point
SE | Site Engineer |  |  |  |  | R | Review |  |  | PL |  | Per lot | [6 empty] | WP |  |  | Witness Point
PE | Project Engineer |  |  |  |  | S | Survey | [11 empty] | M |  |  | Milestone
SPE | Senior Project Engineer |  |  |  |  | T | Test | [11 empty] | V |  |  | Verification
PM | Project Manager | [17 empty] | NA |  |  | Not Available
SV | Surveyor
QM | Quality Manager
QR | Quality Representative
ER | Environmental Representative
IV | Independent Verifier
Contractor Name |  |  |  |  | ROBAR Rentals | [10 empty] | ITP no. |  |  |  | RR-SEPD-BESS-ITP-004-00
Responsible Engineer |  |  |  |  | Juan Orozco | [10 empty] | Work Pack no. |  |  |  | RR-SEPD-CI-SOW-004-00
Responsible Supervisor |  |  |  |  | Jake Scott
Location
Description
Item no. | Inspection/Test Point |  |  | Responsibility | Specification Reference |  |  | Conformance Criteria Summary |  |  | Method |  | Frequency |  | Reviewer |  | Hold/Witness Point Requirements | [6 empty] | Records or Checklist Document Number
[17 empty] | ROBAR | SEPD |  |  |  |  | Client
Section 1: Preliminaries
Remarks / NCR No. / HP No. / RFI No. / Notice Date
1.1 | Review of approved construction drawings and specifications |  |  | SE/PE | WBS-SS-CI- SPC-0007 |  |  | Approved IFC drawings and project specifications available on-site |  |  | R |  | PW |  |  |  | V | NA |  |  |  |  | NA | IFC Drawings
1.2 | Site condition check and access preparation |  |  | SE/PE | WBS-SS-CI- SPC-0007 |  |  | Site cleared, accessible, and suitable for sheet piling works |  |  | R |  | PW |  |  |  | V | NA |  |  |  |  | NA
1.3 | Site safety induction and toolbox talks |  |  | S E | WBS-SS-CI- SPC-0007 |  |  | All personnel inducted and briefed on safety, site-specific risks |  |  | R |  | P W |  |  |  | V | NA |  |  |  |  | NA | Site inductions records
1.4 | Inspection of plant and equipment (e.g., excavator, vibro head) |  |  | SE/PE | WBS-SS-CI- SPC-0007 |  |  | All equipment calibrated and operational |  |  | R |  | PW |  |  |  | V | NA |  |  |  |  | NA | Calibration/P re-start
Section 2: Piling Works
2.1 | Verification of work permits |  |  | SE/PE | WBS-SS-CI- SPC-0007 |  |  | All necessary permits for works are in place (GDA/GDP) |  |  | R |  | PL |  |  |  | V | V |  |  |  |  | NA | GDA/GDP
2.2 | Review of material, certificates & technical specifications |  |  | SE/PE | WBS-SS-CI- SPC-0007 |  |  | Verify mill certificates & compliance with AS 2159 |  |  | R |  | PW |  |  |  | HP | HP |  |  |  |  | NA | Product certificate of compliance
2.3 | Surveying of centre line of points for sheet pile(s). |  |  | SE/PE | WBS-SS-CI- DRG-0251 |  |  | Confirm correct position as per drawings |  |  | R |  | PW |  |  |  | HP | HP |  |  |  |  | NA | TWD FIC
2.4 | Installation Monitoring |  |  | SE/PE | WBS-SS-CI- SPC-0007 AS 2159 Manufacturer’ s Technical Data |  |  | Monitor driving sequence, depth and alignment |  |  | R |  | PW |  |  |  | HP | HP |  |  |  |  | NA | IFC Drawings FIC
2.5 | Check vertical alignment during driving of sheet pile, and adjust if required |  |  | SE/PE | WBS-SS-CI- SPC-0007 |  |  | Correct positioning of all embedded items as per drawings |  |  | R |  | PW |  |  |  | WP | WP |  |  |  |  | NA | IFC Drawings FIC
2.6 | Ensure sheet piles are interlocked effectively as per technical specifications |  |  | SE/PE | WBS-SS-CI- DRG-0251 AS 2159 Manufacturer’ s Technical Data |  |  | Batch plant adheres to mix design, and delivery meets timing requirements |  |  | R |  | PW |  |  |  | V | NA |  |  |  |  | NA | FIC
Section 3: Final Inspection
3.1 | Pile Verticality Check |  |  | SE/PE | WBS-SS-CI- DRG-0251 |  |  | Ensure piles are plumb and no gaps or misalignment |  |  | S |  | PL |  |  |  | V | V |  |  |  |  | NA | FIC
3.2 | As-Built Survey |  |  | SE/PE | WBS-SS-CI- DRG-0251 |  |  | Confirm final location, depth & alignment |  |  | R |  | PL |  |  |  | V | V |  |  |  |  | NA | FIC
3.3 | Engineer’s Final Sign-Off |  |  | SE/PE | WBS-SS-CI- SPC-0007 AS 2159 |  |  | Ensure compliance with design |  |  | R |  | PL |  |  |  | WP | WP |  |  |  |  | NA | FIC
3.5 | Final inspection and acceptance |  |  | SE/PE | WBS-SS-CI- SPC-0007 |  |  | Finished levels, dimensions within tolerances |  |  | R |  | PL |  |  |  | V | V |  |  |  |  | NA | FIC
Document sign-off
Close-out
Company |  |  | Name | [5 empty] | Position |  |  |  |  | Signature |  |  |  |  | Date (DD/MM/YYYY)
ROBAR
SEPD