## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | RR-SEPD-BESS-ITP-006-00 - Sheet piling - Layer | itp |  |  |  |  | RR-SEPD-BESS-ITP-006-00 - Sheet piling
section | Section 1: Preliminaries
checkpoint | 1.1 - Review of approved construction drawings and specifications
label | Responsibility - SE/PE
label | Specification Reference - WBS-SS-CI-SPC-0007
label | Conformance Criteria Summary - Approved IFC drawings and project specifications available on-site
label | Method - R
label | Frequency - PW
label | Hold/Witness Point Requirements: ROBAR - V
label | Hold/Witness Point Requirements: SEPD - NA
label | Hold/Witness Point Requirements: Client - NA
label | Records or Checklist Document Number - IFC Drawings
checkpoint | 1.2 - Site condition check and access preparation
label | Responsibility - SE/PE
label | Specification Reference - WBS-SS-CI-SPC-0007
label | Conformance Criteria Summary - Site cleared, accessible, and suitable for sheet piling works
label | Method - R
label | Frequency - PW
label | Hold/Witness Point Requirements: ROBAR - V
label | Hold/Witness Point Requirements: SEPD - NA
label | Hold/Witness Point Requirements: Client - NA
label | Records or Checklist Document Number -
checkpoint | 1.3 - Site safety induction and toolbox talks
label | Responsibility - S E
label | Specification Reference - WBS-SS-CI-SPC-0007
label | Conformance Criteria Summary - All personnel inducted and briefed on safety, site-specific risks
label | Method - R
label | Frequency - P W
label | Hold/Witness Point Requirements: ROBAR - V
label | Hold/Witness Point Requirements: SEPD - NA
label | Hold/Witness Point Requirements: Client - NA
label | Records or Checklist Document Number - Site inductions records
checkpoint | 1.4 - Inspection of plant and equipment (e.g., excavator, vibro head)
label | Responsibility - SE/PE
label | Specification Reference - WBS-SS-CI-SPC-0007
label | Conformance Criteria Summary - All equipment calibrated and operational
label | Method - R
label | Frequency - PW
label | Hold/Witness Point Requirements: ROBAR - V
label | Hold/Witness Point Requirements: SEPD - NA
label | Hold/Witness Point Requirements: Client - NA
label | Records or Checklist Document Number - Calibration/P re-start
section | Section 2: Piling Works
checkpoint | 2.1 - Verification of work permits
label | Responsibility - SE/PE
label | Specification Reference - WBS-SS-CI-SPC-0007
label | Conformance Criteria Summary - All necessary permits for works are in place (GDA/GDP)
label | Method - R
label | Frequency - PL
label | Hold/Witness Point Requirements: ROBAR - V
label | Hold/Witness Point Requirements: SEPD - V
label | Hold/Witness Point Requirements: Client - NA
label | Records or Checklist Document Number - GDA/GDP
checkpoint | 2.2 - Review of material, certificates & technical specifications
label | Responsibility - SE/PE
label | Specification Reference - WBS-SS-CI-SPC-0007
label | Conformance Criteria Summary - Verify mill certificates & compliance with AS 2159
label | Method - R
label | Frequency - PW
label | Hold/Witness Point Requirements: ROBAR - HP
label | Hold/Witness Point Requirements: SEPD - HP
label | Hold/Witness Point Requirements: Client - NA
label | Records or Checklist Document Number - Product certificate of compliance
holdpoint | HOLD POINT
checkpoint | 2.3 - Surveying of centre line of points for sheet pile(s).
label | Responsibility - SE/PE
label | Specification Reference - WBS-SS-CI-DRG-0251
label | Conformance Criteria Summary - Confirm correct position as per drawings
label | Method - R
label | Frequency - PW
label | Hold/Witness Point Requirements: ROBAR - HP
label | Hold/Witness Point Requirements: SEPD - HP
label | Hold/Witness Point Requirements: Client - NA
label | Records or Checklist Document Number - TWD FIC
holdpoint | HOLD POINT
checkpoint | 2.4 - Installation Monitoring
label | Responsibility - SE/PE
label | Specification Reference - WBS-SS-CI-SPC-0007, AS 2159 Manufacturer’s Technical Data
label | Conformance Criteria Summary - Monitor driving sequence, depth and alignment
label | Method - R
label | Frequency - PW
label | Hold/Witness Point Requirements: ROBAR - HP
label | Hold/Witness Point Requirements: SEPD - HP
label | Hold/Witness Point Requirements: Client - NA
label | Records or Checklist Document Number - IFC Drawings FIC
holdpoint | HOLD POINT
checkpoint | 2.5 - Check vertical alignment during driving of sheet pile, and adjust if required
label | Responsibility - SE/PE
label | Specification Reference - WBS-SS-CI-SPC-0007
label | Conformance Criteria Summary - Correct positioning of all embedded items as per drawings
label | Method - R
label | Frequency - PW
label | Hold/Witness Point Requirements: ROBAR - WP
label | Hold/Witness Point Requirements: SEPD - WP
label | Hold/Witness Point Requirements: Client - NA
label | Records or Checklist Document Number - IFC Drawings FIC
checkpoint | 2.6 - Ensure sheet piles are interlocked effectively as per technical specifications
label | Responsibility - SE/PE
label | Specification Reference - WBS-SS-CI-DRG-0251, AS 2159 Manufacturer’s Technical Data
label | Conformance Criteria Summary - Batch plant adheres to mix design, and delivery meets timing requirements
label | Method - R
label | Frequency - PW
label | Hold/Witness Point Requirements: ROBAR - V
label | Hold/Witness Point Requirements: SEPD - NA
label | Hold/Witness Point Requirements: Client - NA
label | Records or Checklist Document Number - FIC
section | Section 3: Final Inspection
checkpoint | 3.1 - Pile Verticality Check
label | Responsibility - SE/PE
label | Specification Reference - WBS-SS-CI-DRG-0251
label | Conformance Criteria Summary - Ensure piles are plumb and no gaps or misalignment
label | Method - S
label | Frequency - PL
label | Hold/Witness Point Requirements: ROBAR - V
label | Hold/Witness Point Requirements: SEPD - V
label | Hold/Witness Point Requirements: Client - NA
label | Records or Checklist Document Number - FIC
checkpoint | 3.2 - As-Built Survey
label | Responsibility - SE/PE
label | Specification Reference - WBS-SS-CI-DRG-0251
label | Conformance Criteria Summary - Confirm final location, depth & alignment
label | Method - R
label | Frequency - PL
label | Hold/Witness Point Requirements: ROBAR - V
label | Hold/Witness Point Requirements: SEPD - V
label | Hold/Witness Point Requirements: Client - NA
label | Records or Checklist Document Number - FIC
checkpoint | 3.3 - Engineer’s Final Sign-Off
label | Responsibility - SE/PE
label | Specification Reference - WBS-SS-CI-SPC-0007, AS 2159
label | Conformance Criteria Summary - Ensure compliance with design
label | Method - R
label | Frequency - PL
label | Hold/Witness Point Requirements: ROBAR - WP
label | Hold/Witness Point Requirements: SEPD - WP
label | Hold/Witness Point Requirements: Client - NA
label | Records or Checklist Document Number - FIC
checkpoint | 3.5 - Final inspection and acceptance
label | Responsibility - SE/PE
label | Specification Reference - WBS-SS-CI-SPC-0007
label | Conformance Criteria Summary - Finished levels, dimensions within tolerances
label | Method - R
label | Frequency - PL
label | Hold/Witness Point Requirements: ROBAR - V
label | Hold/Witness Point Requirements: SEPD - V
label | Hold/Witness Point Requirements: Client - NA
label | Records or Checklist Document Number - FIC
section | Document Sign-off
checkpoint | Close-out
textbox | SEPD - Name:
textbox | SEPD - Position:
date | SEPD - Date:
signoff | Add Signature
checklist | RR-SEPD-BESS-ITP-005-01 - Drainage installation - Layer | itp |  |  |  |  | RR-SEPD-BESS-ITP-005-01 - Drainage installation
section | Section 1: Preliminaries & Permits
checkpoint | 1.1 - Collect and verify information (Site boundary, utilities, survey map, design drawings)
label | Responsibility - SE/PE
label | Specification Reference - WBS-SS-CI-SPC-0006
label | Conformance Criteria Summary - Results included in work pack
label | Method - R
label | Frequency - PW
label | Hold/Witness Point Requirements: ROBAR - V
label | Hold/Witness Point Requirements: SEPD - NA
label | Hold/Witness Point Requirements: Client - NA
label | Records or Checklist Document Number - IFC Drawings
checkpoint | 1.2 - Permit approval (GDA/GDP)
label | Responsibility - SE/PE
label | Specification Reference - WBS-SS-CI-SPC-0006
label | Conformance Criteria Summary - Approved excavation permit (GDP) prior to commencing works
label | Method - R
label | Frequency - PW
label | Hold/Witness Point Requirements: ROBAR - HP
label | Hold/Witness Point Requirements: SEPD - HP
label | Hold/Witness Point Requirements: Client - NA
label | Records or Checklist Document Number - RR-SEPD-CI- SOW-002-01
holdpoint | HOLD POINT
checkpoint | 1.3 - Site set-out
label | Responsibility - SE/PE
label | Specification Reference - WBS-SS-CI-SPC-0006
label | Conformance Criteria Summary - Verify levels, site boundaries, and physical bounds per IFC drawings
label | Method - R
label | Frequency - PW
label | Hold/Witness Point Requirements: ROBAR - V
label | Hold/Witness Point Requirements: SEPD - NA
label | Hold/Witness Point Requirements: Client - NA
label | Records or Checklist Document Number - IFC Drawings
checkpoint | 1.4 - Sediment control plan
label | Responsibility - SE/PE
label | Specification Reference - WBS-SS-PM-PLN-0024, WAE230103- 03-003 TM Rev0
label | Conformance Criteria Summary - Sediment control measures in place
label | Method - R
label | Frequency - PW
label | Hold/Witness Point Requirements: ROBAR - V
label | Hold/Witness Point Requirements: SEPD - NA
label | Hold/Witness Point Requirements: Client - NA
label | Records or Checklist Document Number - SEPD environmental plan
checkpoint | 1.5 - Dust control plan
label | Responsibility - SE/PE
label | Specification Reference - PP3 section 1.5 and section 4.1
label | Conformance Criteria Summary - Dust control measures in place
label | Method - R
label | Frequency - PW
label | Hold/Witness Point Requirements: ROBAR - V
label | Hold/Witness Point Requirements: SEPD - NA
label | Hold/Witness Point Requirements: Client - NA
label | Records or Checklist Document Number - SEPD environmental plan
section | Section 2: Materials
checkpoint | 2.1 - Import fill material inspection
label | Responsibility - SE/PE
label | Specification Reference - WBS-SS-CI-SPC-0006
label | Conformance Criteria Summary - Material certificate and test report for particle size distribution, moisture content, MMDD
label | Method - R
label | Frequency - PW
label | Hold/Witness Point Requirements: ROBAR - V
label | Hold/Witness Point Requirements: SEPD - V
label | Hold/Witness Point Requirements: Client - NA
label | Records or Checklist Document Number - Material certificates
checkpoint | 2.2 - Verify suitable foundation material (compaction >95% MMDD)
label | Responsibility - SE/PE
label | Specification Reference - WBS-SS-CI-SPC-0006
label | Conformance Criteria Summary - Geotechnical test results showing compliance
label | Method - R
label | Frequency - PW
label | Hold/Witness Point Requirements: ROBAR - HP
label | Hold/Witness Point Requirements: SEPD - HP
label | Hold/Witness Point Requirements: Client - NA
label | Records or Checklist Document Number - Test results
holdpoint | HOLD POINT
checkpoint | 2.3 - Quality documentation RCP & precast drainage pits
label | Responsibility - SE/PE
label | Specification Reference - WBS-SS-CI-SPC-0006
label | Conformance Criteria Summary - Supplier’s quality system certifications
label | ○ Product of compliance to AS 4058, AS 3500, AS 3996. (Load rating & liner shall align with design drawings)
label | Method - R
label | Frequency - PW
label | Hold/Witness Point Requirements: ROBAR - HP
label | Hold/Witness Point Requirements: SEPD - HP
label | Hold/Witness Point Requirements: Client - NA
label | Records or Checklist Document Number - Supplier’s documents
holdpoint | HOLD POINT
checkpoint | 2.4 - Delivery acceptance of RCP
label | Responsibility - SE/PE
label | Specification Reference - WBS-SS-CI-SPC-0006, AS/NZS 4058
label | Conformance Criteria Summary - Acceptability of defects of RCP’s.
label | ○ Fibre RCPs shall be rejected if fractures and cracks wider than 0.1 mm and deeper than 0.3 mm are present.
label | Method - R
label | Frequency - PW
label | Hold/Witness Point Requirements: ROBAR - HP
label | Hold/Witness Point Requirements: SEPD - HP
label | Hold/Witness Point Requirements: Client - NA
label | Records or Checklist Document Number - Delivery dockets
holdpoint | HOLD POINT
section | Section 3: Construction
checkpoint | 3.1 - Excavated trench
label | Responsibility - SE/PE
label | Specification Reference - WBS-SS-CI-SPC-0006
label | Conformance Criteria Summary - Inspection following excavation of trench. Wacker plate to be use for compacting base.
label | Method - I
label | Frequency - PL
label | Hold/Witness Point Requirements: ROBAR - V
label | Hold/Witness Point Requirements: SEPD - V
label | Hold/Witness Point Requirements: Client - NA
label | Records or Checklist Document Number - IFC Drawings
checkpoint | 3.2 - Bedding
label | Responsibility - SE/PE
label | Specification Reference - WBS-SS-CI-0006
label | Conformance Criteria Summary - Material to be compacted at 100mm depth minimum.
label | Method - I
label | Frequency - PL
label | Hold/Witness Point Requirements: ROBAR - V
label | Hold/Witness Point Requirements: SEPD - V
label | Hold/Witness Point Requirements: Client - NA
label | Records or Checklist Document Number - IFC Drawings
checkpoint | 3.3 - Placement of concrete pipes
label | Responsibility - SE/PE
label | Specification Reference - WBS-SS-CI-SPC-0006 IFC drawings
label | Conformance Criteria Summary - Placed and joint in accordance with the manufacturer’s specifications
label | ○ Female ends upstream and lifting holes uppermost. Lifting holes in pipes shall be filled with plugs provided by pipe manufacturer
label | Method - T
label | Frequency - PL
label | Hold/Witness Point Requirements: ROBAR - HP
label | Hold/Witness Point Requirements: SEPD - HP
label | Hold/Witness Point Requirements: Client - NA
label | Records or Checklist Document Number - This ITP
holdpoint | HOLD POINT
checkpoint | 3.4 - As-built survey prior to backfilling
label | Responsibility - SE E
label | Specification Reference - WBS-SS-CI-0006
label | Conformance Criteria Summary - Variation of reduced level of invert from specified level:
label | ○ Whitin +/- 10 mm of specified position. Invert of structure shall not impede the gravity flow of water into or from structure
label | Method - I
label | Frequency - PL
label | Hold/Witness Point Requirements: ROBAR - V
label | Hold/Witness Point Requirements: SEPD - V
label | Hold/Witness Point Requirements: Client - NA
label | Records or Checklist Document Number - Survey report
checkpoint | 3.5 - Installation of precast drainage structures
label | Responsibility - SE/PE
label | Specification Reference - WBS-SS-CI-SPC-0006, AS 3500 Design drawings
label | Conformance Criteria Summary - Inspection pit cover to be installed flush with the final surface
label | ○ Where precast drainage structure is used, the external joint with pipe shall be strengthened with a concrete fill circling the joint.
label | Method - T
label | Frequency - PL
label | Hold/Witness Point Requirements: ROBAR - HP
label | Hold/Witness Point Requirements: SEPD - HP
label | Hold/Witness Point Requirements: Client - NA
label | Records or Checklist Document Number - Test results, NER engineer specifications
holdpoint | HOLD POINT
checkpoint | 3.6 - Trench/Precast drainage item backfill
label | Responsibility - SE/PE
label | Specification Reference - WBS-SS-CI-SPC-0006, PPR
label | Conformance Criteria Summary - Unless specified otherwise, backfill layers shall be maximum 300 mm layers.
label | Method - S
label | Frequency - PL
label | Hold/Witness Point Requirements: ROBAR - V
label | Hold/Witness Point Requirements: SEPD - V
label | Hold/Witness Point Requirements: Client - NA
label | Records or Checklist Document Number - Compaction report
section | Section 4: Final Inspection
checkpoint | 4.1 - Air pressure test
label | Responsibility - SE E
label | Specification Reference - WBS-SS-CI-SPC-0006, AS 4033.2
label | Conformance Criteria Summary - The pipe system must not lose more than a defined amount of pressure within the test duration.
label | ○ PVC - 25 kPa (3.5 psi) – pressure drop
label | ○ ≤3.5 kPa (0.5 psi) in 5 min.
label | ○ Concrete - 25-50 kPa (3.5-7.0 psi) – pressure drop ≤10% drop in 5 min.
label | Method - S
label | Frequency - PL
label | Hold/Witness Point Requirements: ROBAR - V
label | Hold/Witness Point Requirements: SEPD - V
label | Hold/Witness Point Requirements: Client - NA
label | Records or Checklist Document Number - WBS-SS-CI- ITP-920049
checkpoint | 4.2 - Finish level compliance with design drawings
label | Responsibility - SE/PE
label | Specification Reference - WBS-SS-CI-SPC-0006
label | Conformance Criteria Summary - As-built drawings.
label | Method - S
label | Frequency - PL
label | Hold/Witness Point Requirements: ROBAR - V
label | Hold/Witness Point Requirements: SEPD - V
label | Hold/Witness Point Requirements: Client - NA
label | Records or Checklist Document Number - WBS-SS-CI- ITP-920049
checkpoint | 4.3 - Final Inspection Checklist (FIC) completion
label | Responsibility - SE/PE
label | Specification Reference - WBS-SS-CI-SPC-0006
label | Conformance Criteria Summary - Signed FIC
label | Method - R
label | Frequency - PL
label | Hold/Witness Point Requirements: ROBAR - V
label | Hold/Witness Point Requirements: SEPD - V
label | Hold/Witness Point Requirements: Client - NA
label | Records or Checklist Document Number - WBS-SS-CI- ITP-920049
section | Document Sign-off
checkpoint | Close-out
textbox | SEPD - Name:
textbox | SEPD - Position:
date | SEPD - Date:
signoff | Add Signature
checklist | RR-SEPD-BESS-FIC-005-01 - Drainage installation - | [5 empty] | RR-SEPD-BESS-FIC-005-01 - Drainage installation
section | Part 1 – Preliminaries (photos where applicable)
checkpoint | Review of approved construction drawings and specifications
label | All drawings and specifications approved and up to date
label | WBS-SS-CI-SPC-006
checkpoint | Verification of permits
label | All relevant permits (GDA/GDP) in place
label | GDA/GDP
checkpoint | Site access and safety preparation
label | Site access cleared and made safe
label | WBS-SS-CI-SPC-006
checkpoint | Safety inductions and toolbox talks
label | All personnel inducted; safety briefings completed
label | Induction record
checkpoint | Environmental controls in place
label | Dust, noise, and sediment barriers installed and functioning
label | SEPD environmental requirements
section | Part 2 – Excavation and trenching (photos where applicable)
checkpoint | Trench depth and width comply with design
label | Set-out verified and matches IFC drawings
label | Site IFC Drawings AS/NZS 3500
checkpoint | Stable trench walls (benching, battering)
label | Trenches deeper than 1.5m require benching, or battering unless certified by a geotechnical engineer.
label | WBS-SS-CI-SPC-006 AS 4744
checkpoint | Pipes inspected for defects before installation
label | Material certs from manufacturer and visual inspection
label | Material to align with design drawings and load rating
label | Manufacturer certifications
checkpoint | No water accumulation in trenches
label | No standing water or excessive moisture inside the trench.
label | AS/NZS 3500
checkpoint | Exclusion zones around excavation established
label | Proper barricades and signage placed around excavation area.
label | AS 1742
checkpoint | Spoil stockpiles located at least 1m from trench edges
label | Stockpiles away from excavation to maintain safety of batters
label | WBS-SS-CI-SPC-0006
checkpoint | Access and egress (ladders, steps) provided for trenches deeper than 1.2m
label | Access and egress for each trench.
label | WHS
section | Part 3 – Bedding & Pipe Installation (photos where applicable)
checkpoint | Correct bedding material used (sand, gravel, etc.)
label | Material complies with particle size, moisture content, MMDD
label | WBS-SS-CI-SPC-0006 Test material results
checkpoint | Bedding compacted to required density
label | Layers placed in maximum 300mm (loose) thickness
label | WBS-SS-CI-SPC-0006
checkpoint | Pipes and materials inspected for defects before installation
label | Installed to design grade ±10mm and alignment within 5mm tolerance.
label | AS/NZS 3500
checkpoint | Pipes laid at correct grade and alignment
label | Levels and grading match design tolerances (+/- 20mm)
label | WBS-SS-CI-SPC-0006, Survey Report
checkpoint | Correct pipe jointing method used (rubber ring, solvent weld, etc.)
label | Joints must be fully engaged and sealed per manufacturer specifications
label | Manufacturer specifications
section | Part 4 – Backfilling and compaction (photos where applicable)
checkpoint | Initial backfill material placed evenly around pipes
label | Site-won material approved by geotechnical engineer
label | Geotechnical report AS/NZS 3725
checkpoint | No large rocks or debris in backfill
label | No rocks or debris in backfill
label | WBS-SS-CI-SPC-0006
checkpoint | Backfilling in controlled layers (300mm lifts)
label | Backfill in uniform layers of maximum 300mm thickness
label | WBS-SS-CI-SPC-0006 Drainage drawings
checkpoint | Backfill shall be placed to a depth of 300mm above collars of pipes or conduits
label | Minimum 300mm above collars of pipes
label | WBS-SS-CI-SPC-0006
checkpoint | Compaction tests performed and passed (Proctor Density, NDM, etc.)
label | Compacted to 93% MMDD
label | WBS-SS-CI-SPC-0006 AS 1289 TQ # 66
checkpoint | Surface reinstated as per project specs (concrete, asphalt, topsoil)
label | Backfill to match existing ground levels with ±10mm tolerance.
label | IFC drawings
section | Part 5 – Final inspections and acceptance (photos where applicable)
checkpoint | Air pressure test
label | The pipe system must not lose more than a defined amount of pressure within the test duration.
label | PVC - 25 kPa (3.5 psi) – pressure drop ≤3.5 kPa (0.5 psi) in 5 min.
label | Concrete - 25-50 kPa (3.5- 7.0 psi) – pressure drop ≤10% drop in 5 min.
label | WBS-SS-CI-SPC-0006 AS 4033.2
checkpoint | As-built survey verification
label | As-built levels and layout match design
label | As-Built Drawings Survey Report
checkpoint | Removal of temporary works
label | All temporary structures, barriers, and access points removed
label | Site inspection
checkpoint | Final inspection sign-off
label | All drainage activities completed and accepted
label | WBS-SS-CI-SPC-0006
section | Document Sign-off
checkpoint | Close-out
textbox | SEPD - Name:
textbox | SEPD - Position:
date | SEPD - Date:
signoff | Add Signature