## to_add
Step Id | Warnings | State | Checklist Template | Type | addStep | addPost | Tier 1 | Tier 2 | Tier 3 | Tier 4 | Tier 5 | Tier 6
fb9c2a78-d30f-4806-afab-178c76229b51 |  | not-started | RR-SEPD-BESS-ITP-002-02 - Concrete slabs | checklist | FALSE | FALSE | FRP | North Retaining Wall | Type 1 | Base Slab | RR-SEPD-BESS-ITP-002-02 - Concrete Slab
9a203011-531a-4daa-8ffd-38d08a4d6896 |  | work-in-progress | RR-SEPD-BESS-ITP-002-02 - Concrete slabs | checklist | FALSE | FALSE | Tier 1: FRP; Tier 2: Lot 001 - Base Slab Pour #01 - (WB-04)(WB-05)(WB-09); Tier 3: RR-SEPD-BESS-ITP-002-02 - Concrete slabs
7950fafc-9d14-4f4c-8f44-2feb74405121 |  | work-in-progress | RR-SEPD-BESS-ITP-002-02 - Concrete slabs | checklist | FALSE | FALSE | Tier 1: FRP; Tier 2: Lot 002 - Base Slab Pour #02 - (WB-06)(WB-10); Tier 3: RR-SEPD-BESS-ITP-002-02 - Concrete slabs
361f0a78-e462-4e1a-82a5-c2279e400a3d |  | work-in-progress | RR-SEPD-BESS-ITP-002-02 - Concrete slabs | checklist | FALSE | FALSE | Tier 1: FRP; Tier 2: Lot 003 - Base Slab Pour #03 - (WB-11); Tier 3: RR-SEPD-BESS-ITP-002-02 - Concrete slabs
09119204-b478-4825-8052-a8c5f6775544 |  | not-started | RR-SEPD-BESS-ITP-002-02 - Concrete slabs | checklist | FALSE | FALSE | Tier 1: FRP; Tier 2: Lot 004 - Base Slab Pour #04 - (WB-07)(WB-08); Tier 3: RR-SEPD-BESS-ITP-002-02 - Concrete slabs
b3b925d2-81fc-41af-9898-e0bddabdce16 |  | work-in-progress | RR-SEPD-BESS-ITP-002-02 - Concrete slabs | checklist | FALSE | FALSE | Tier 1: FRP; Tier 2: Lot 005 - Base Slab Pour #05 - (NB-01)(NB-02); Tier 3: RR-SEPD-BESS-ITP-002-02 - Concrete slabs
324c05ff-21e6-43af-b5da-471605e3d750 |  | not-started | RR-SEPD-BESS-ITP-002-02 - Concrete slabs | checklist | FALSE | FALSE | Tier 1: FRP; Tier 2: Lot 006 - Base Slab Pour #06 - (NB-05)(NB-06); Tier 3: RR-SEPD-BESS-ITP-002-02 - Concrete slabs
2db6a7a8-80b2-43d3-815d-72d12ddd5ece |  | not-started | RR-SEPD-BESS-ITP-002-02 - Concrete slabs | checklist | FALSE | FALSE | Tier 1: FRP; Tier 2: Lot 007 - Base Slab Pour #07 - (NB-07)(NB-08a); Tier 3: RR-SEPD-BESS-ITP-002-02 - Concrete slabs
8bf41e61-054e-40e3-80ed-96101fde45b5 |  | not-started | RR-SEPD-BESS-ITP-002-02 - Concrete slabs | checklist | FALSE | FALSE | Tier 1: FRP; Tier 2: Lot 008 - Base Slab Pour #08 - (NB-08b); Tier 3: RR-SEPD-BESS-ITP-002-02 - Concrete slabs
a596cac1-c478-467d-993c-a6d2a172f0a5 |  | work-in-progress | RR-SEPD-BESS-ITP-002-02 - Concrete slabs | checklist | FALSE | FALSE | Tier 1: FRP; Tier 2: Lot 009 - Retaining Wall Pour #09 - (NB-02); Tier 3: RR-SEPD-BESS-ITP-002-02 - Concrete slabs
a4e64c52-f35c-439b-ba43-ad38cb8dd789 |  | not-started | RR-SEPD-BESS-ITP-002-02 - Concrete slabs | checklist | FALSE | FALSE | Tier 1: FRP; Tier 2: Lot 010 - Retaining Wall Pour #10 - (WB-09)(WB-11); Tier 3: RR-SEPD-BESS-ITP-002-02 - Concrete slabs
298a3de5-41a5-4e12-96ac-9431afca5b0b |  | work-in-progress | RR-SEPD-BESS-ITP-002-02 - Concrete slabs | checklist | FALSE | FALSE | Tier 1: FRP; Tier 2: Lot 011 - Retaining Wall Pour #11 - (NB-01); Tier 3: RR-SEPD-BESS-ITP-002-02 - Concrete slabs - Layer
a0d87862-b385-4dae-b796-4522dd01107e |  | not-started | RR-SEPD-BESS-ITP-002-02 - Concrete slabs | checklist | FALSE | FALSE | Tier 1: FRP; Tier 2: Lot 012 - Retaining Wall Pour #12 - (NB-07); Tier 3: RR-SEPD-BESS-ITP-002-02 - Concrete slabs - Layer
9e4ceb51-3f8d-4d02-bcb1-aa3ef51c4039 |  | work-in-progress | RR-SEPD-BESS-ITP-002-02 - Concrete slabs | checklist | FALSE | FALSE | Tier 1: FRP; Tier 2: Lot 013 - Retaining Wall Pour #13 - (WB-10)(NB-05); Tier 3: RR-SEPD-BESS-ITP-002-02 - Concrete slabs - Layer
ea34685b-d2b0-48e3-9ab3-0de14f2e656a |  | work-in-progress | RR-SEPD-BESS-ITP-002-02 - Concrete slabs | checklist | FALSE | FALSE | Tier 1: FRP; Tier 2: Lot 014 - Retaining Wall Pour #14 - (WB-07); Tier 3: RR-SEPD-BESS-ITP-002-02 - Concrete slabs - Layer
4148a100-16fe-4558-bdc0-c78f00322b2a |  | work-in-progress | RR-SEPD-BESS-ITP-002-02 - Concrete slabs | checklist | FALSE | FALSE | Tier 1: FRP; Tier 2: Lot 015 - Retaining Wall Pour #15 - (NB-06)(NB-08a)(NB-08b); Tier 3: RR-SEPD-BESS-ITP-002-02 - Concrete slabs - Layer
6f7f6f43-1035-44fa-adcf-4b34012e0571 |  | work-in-progress | RR-SEPD-BESS-ITP-002-02 - Concrete slabs | checklist | FALSE | FALSE | Tier 1: FRP; Tier 2: Lot 016 - Retaining Wall Pour #16 - (WB-05); Tier 3: RR-SEPD-BESS-ITP-002-02 - Concrete slabs - Layer
7d0b97c9-b29a-499b-88f6-5dba51196261 |  | work-in-progress | RR-SEPD-BESS-ITP-002-02 - Concrete slabs | checklist | FALSE | FALSE | FRP | Lot 017 - Base Slab Pour #17 - (SB-11)(SB-12)(SB-13a) | Area Ref - Bays | Bases | RR-SEPD-BESS-ITP-002-02 - Bays 11,12,13a
5919247c-30c9-4bca-8c70-b90cb21616f4 |  | not-started | RR-SEPD-BESS-ITP-002-02 - Concrete slabs | checklist | FALSE | FALSE | Tier 1: FRP; Tier 2: Lot 018 - Retaining Wall Pour #18 - (WB-08); Tier 3: RR-SEPD-BESS-ITP-002-02 - Concrete slabs - Layer
26de9fe1-cd5d-428c-a17c-6f1bd2b211aa |  | work-in-progress | RR-SEPD-BESS-ITP-002-02 - Concrete slabs | checklist | FALSE | FALSE | Tier 1: FRP; Tier 2: Lot 019 - Pour #19 ¦ Bay 13: FTG058(6) FTG059(7-8) FTG060(9-10) Bay 14: FTG053(5-6) FTG054(8) FTG055(9-10); Tier 3: RR-SEPD-BESS-ITP-002-02 - Concrete slabs - Strip Footing Pour 1
143fcb09-d3d1-4485-afc6-ca5749d14a8b |  | work-in-progress | RR-SEPD-BESS-ITP-002-02 - Concrete slabs | checklist | FALSE | FALSE | Tier 1: FRP; Tier 2: Lot 019 - Pour #19 ¦ Bay 13: FTG058(6) FTG059(7-8) FTG060(9-10) Bay 14: FTG053(5-6) FTG054(8) FTG055(9-10); Tier 3: RR-SEPD-BESS-ITP-002-02 - Concrete slabs - Pour 2
781522c1-3dfd-4548-825a-6fa870218767 |  | not-started | RR-SEPD-BESS-ITP-002-02 - Concrete slabs | checklist | FALSE | FALSE | Tier 1: FRP; Tier 2: Lot 020 - Pour #20 ¦ Bay 13: FTG056(1-2) FTG057(3-4) FTG058(5) ¦ Bay 14: FTG051(1-2) FTG052(3-4); Tier 3: RR-SEPD-BESS-ITP-002-02 - Concrete slabs - Strip Footings Pour 1
7741c910-bb1f-4c94-8f81-dfa164e69615 |  | not-started | RR-SEPD-BESS-ITP-002-02 - Concrete slabs | checklist | FALSE | FALSE | Tier 1: FRP; Tier 2: Lot 020 - Pour #20 ¦ Bay 13: FTG056(1-2) FTG057(3-4) FTG058(5) ¦ Bay 14: FTG051(1-2) FTG052(3-4); Tier 3: RR-SEPD-BESS-ITP-002-02 - Concrete slabs - Layer
bf3bac7c-f3f7-4bbf-87bc-a927a02812bf |  | not-started | RR-SEPD-BESS-ITP-002-02 - Concrete slabs | checklist | FALSE | FALSE | Tier 1: FRP; Tier 2: Lot 020 - Pour #20 ¦ Bay 13: FTG056(1-2) FTG057(3-4) FTG058(5) ¦ Bay 14: FTG051(1-2) FTG052(3-4); Tier 3: RR-SEPD-BESS-ITP-002-02 - Concrete slabs - Pour 2
9f311f12-4e4e-48d1-a578-f2266df4e5f0 |  | not-started | RR-SEPD-BESS-ITP-002-02 - Concrete slabs | checklist | FALSE | FALSE | Tier 1: FRP; Tier 2: Lot 021 - Retaining Wall Pour #21 - (WB-06); Tier 3: RR-SEPD-BESS-ITP-002-02 - Concrete slabs - Layer
95650c6d-5fb8-4621-9e78-6ddffc2785ed |  | not-started | RR-SEPD-BESS-ITP-002-02 - Concrete slabs | checklist | FALSE | FALSE | Tier 1: FRP; Tier 2: Lot 022 - Pour #22 ¦ Bay 14: FTG054(7) ¦ Bay 16: FTG041(1-2) FTG42(3-4) FTG043(5-6) FTG044(7-8) FTG045(9); Tier 3: RR-SEPD-BESS-ITP-002-02 - Concrete slabs - Layer
d432053e-6ae9-46bf-8b89-647141362435 |  | not-started | RR-SEPD-BESS-ITP-002-02 - Concrete slabs | checklist | FALSE | FALSE | Tier 1: FRP; Tier 2: Lot 023 - Pour #23 ¦ Bay 8 FTG001(2) FTG002(4) FTG003(5-6); Tier 3: RR-SEPD-BESS-ITP-002-02 - Concrete slabs - Layer
7dee6254-c897-4d70-b6cd-cfff555d6f34 |  | not-started | RR-SEPD-BESS-ITP-002-02 - Concrete slabs | checklist | FALSE | FALSE | Tier 1: FRP; Tier 2: Lot 024 - Pour #24 ¦ Bay 8 FTG002(3) FTG004(7-8); Tier 3: RR-SEPD-BESS-ITP-002-02 - Concrete slabs - Layer
e30ba24c-d9de-4dc2-820d-20e618135c70 |  | not-started | RR-SEPD-BESS-ITP-002-02 - Concrete slabs | checklist | FALSE | FALSE | Tier 1: FRP; Tier 2: Lot 025 - Pour #25 ¦ Bay 15 FTG046(1-2) FTG049(7-8) FTG050(9); Tier 3: RR-SEPD-BESS-ITP-002-02 - Concrete slabs - Layer
4b8f7e9d-cc9e-4de5-8bc9-11cec19202d1 |  | not-started | RR-SEPD-BESS-ITP-002-02 - Concrete slabs | checklist | FALSE | FALSE | Tier 1: FRP; Tier 2: Lot 026 - Pour #26 ¦ Bay 15 FTG047(3-4) FTG048(5-6); Tier 3: RR-SEPD-BESS-ITP-002-02 - Concrete slabs - Layer
1a6125f7-45e5-41c8-9c3d-541511e70f31 |  | not-started | RR-SEPD-BESS-ITP-002-02 - Concrete slabs | checklist | FALSE | FALSE | Tier 1: FRP; Tier 2: Lot 027 - Pour #27 ¦ Bay 08 FTG001(1) FTG005(9-10); Tier 3: RR-SEPD-BESS-ITP-002-02 - Concrete slabs - Layer
71e042ed-d981-4395-9e13-4ea5d560e3a9 |  | not-started | RR-SEPD-BESS-ITP-002-02 - Concrete slabs | checklist | FALSE | FALSE | Tier 1: FRP; Tier 2: Lot 028 - Pour #28 ¦ Retaining Wall Pour - (SB-12); Tier 3: RR-SEPD-BESS-ITP-002-02 - Concrete slabs - Layer
d7688cd8-c6f2-4ff7-91c1-03fc3edef9b8 |  | not-started | RR-SEPD-BESS-ITP-002-02 - Concrete slabs | checklist | FALSE | FALSE | Tier 1: FRP; Tier 2: Lot 029 - Pour #29 ¦ Base Slab - (EB-03); Tier 3: RR-SEPD-BESS-ITP-002-02 - Concrete slabs - Layer
765b6912-47e6-455f-82cc-b9f07686baad |  | not-started | RR-SEPD-BESS-ITP-002-02 - Concrete slabs | checklist | FALSE | FALSE | Tier 1: FRP; Tier 2: Lot 030 - Base Slab Pour #30 - (EB-04)(EB-05); Tier 3: RR-SEPD-BESS-ITP-002-02 - Concrete slabs - Layer
72d8a4e0-48e1-4851-8962-e01be3b7c6e3 |  | not-started | RR-SEPD-BESS-ITP-002-02 - Concrete slabs | checklist | FALSE | FALSE | Tier 1: FRP; Tier 2: Lot 031 - Base Slab Pour #31 - (EB-06)(EB-07); Tier 3: RR-SEPD-BESS-ITP-002-02 - Concrete slabs - Layer
afebda48-1416-492a-9fb8-aaff5ff60054 |  | not-started | RR-SEPD-BESS-ITP-002-02 - Concrete slabs | checklist | FALSE | FALSE | Tier 1: FRP; Tier 2: Lot 032 - Base Slab Pour #32 - (EB-08); Tier 3: RR-SEPD-BESS-ITP-002-02 - Concrete slabs - Layer
b676386a-7e6d-4294-bcfd-2bd8f9d3ebe4 |  | not-started | RR-SEPD-BESS-ITP-002-02 - Concrete slabs | checklist | FALSE | FALSE | Tier 1: FRP; Tier 2: Lot 033 - Base Slab & Upstand Pour #33 - (SB-13b); Tier 3: RR-SEPD-BESS-ITP-002-02 - Concrete slabs - Layer
5e1f1a7c-5670-4a34-9010-d63227cf6eb4 |  | not-started | RR-SEPD-BESS-ITP-002-02 - Concrete slabs | checklist | FALSE | FALSE | Tier 1: FRP; Tier 2: Lot 035 - Pour #35 ¦ Bay 7 (1,7,8,9,10) Bay 15 & 16 (10,10); Tier 3: RR-SEPD-BESS-ITP-002-02 - Concrete slabs - Layer
0378cc93-e886-4387-bc50-177aab66db87 |  | not-started | RR-SEPD-BESS-ITP-002-02 - Concrete slabs | checklist | FALSE | FALSE | Tier 1: FRP; Tier 2: Lot 036 - Base Slab Pour #36 - (SB-14); Tier 3: RR-SEPD-BESS-ITP-002-02 - Concrete slabs - Layer
49432aae-4533-492c-b59f-11757af055dc |  | not-started | RR-SEPD-BESS-ITP-002-02 - Concrete slabs | checklist | FALSE | FALSE | Tier 1: FRP; Tier 2: Lot 037 - Retaining Wall Pour #37 - (SB-11); Tier 3: RR-SEPD-BESS-ITP-002-02 - Concrete slabs - Layer
f806bccb-fa32-4e30-a599-43263a5c9074 |  | not-started | RR-SEPD-BESS-ITP-002-02 - Concrete slabs | checklist | FALSE | FALSE | Tier 1: FRP; Tier 2: Lot 038 - Retaining Wall Pour # 38 - (SB-13)(SB-14); Tier 3: RR-SEPD-BESS-ITP-002-02 - Concrete slabs - Layer
679dea34-4bdd-4c79-b19e-d53c9ed201ed |  | not-started | RR-SEPD-BESS-ITP-002-02 - Concrete slabs | checklist | FALSE | FALSE | Tier 1: FRP; Tier 2: Lot 042 - Strip Footings Pour #42 - Bay 6 (FTG016;FTG017;FTG018.5); Tier 3: RR-SEPD-BESS-ITP-002-02 - Concrete slabs - Layer
db53cb55-e70b-4d20-a028-63b34d404861 |  | not-started | RR-SEPD-BESS-ITP-002-02 - Concrete slabs | checklist | FALSE | FALSE | Tier 1: FRP; Tier 2: Lot 041 - Base Slab Pour #41 (1/2 NB-03b); Tier 3: RR-SEPD-BESS-ITP-002-02 - Concrete slabs - Layer
d254af26-3dfb-4a20-bb26-564df2b659ee |  | not-started | RR-SEPD-BESS-ITP-002-02 - Concrete slabs | checklist | FALSE | FALSE | Tier 1: FRP; Tier 2: Lot 042 - Base Slab Pour #42 (1/2 NB-04); Tier 3: RR-SEPD-BESS-ITP-002-02 - Concrete
6f8846c7-80d8-416f-942e-720cf37c4cc8 |  | not-started | RR-SEPD-BESS-ITP-002-02 - Concrete slabs | checklist | FALSE | FALSE | Tier 1: FRP; Tier 2: Lot XXX - Retaining Wall #XX - (WB-04); Tier 3: RR-SEPD-BESS-ITP-002-02 - Concrete slabs - Bay 10
df6f721e-3850-482a-98ab-d49ba74a12ea |  | not-started | RR-SEPD-BESS-ITP-002-02 - Concrete slabs | checklist | FALSE | FALSE | Tier 1: FRP; Tier 2: Lot 04 - (1/2 NB-04) Type 4; Tier 3: RR-SEPD-BESS-ITP-002-02 - Concrete slabs - Layer