## Resources - For Use V1
Type | Name | Values | Prompting Name
Checklist | AHU Rough In |  | AHU Rough In
Checkpoint | Unit Model Number correct & Labelled with a clear photo of Both Model & Serial Numbers
Checkpoint | Vibration mounts installed
Checkpoint | Pipework roughed in
Checkpoint | Condensate drains installed to tundish/waste point provided and hose clamps fitted
Checkpoint | All solid ductwork installed as per drawings, including flexible connections
Checkpoint | Dampers installed (NRD, VC, FD, MVCD) and all fully opened
Checkpoint | All cushion heads installed, including flexible connections, and set out as per the drawing layout
Checkpoint | (Fit-Off) Grilles/louvres installed
Checkpoint | (Fit-Off) Filters installed and are removable
Checkpoint | (Fit-Off) Condensate drains terminated at tundish and tested
Checklist | AHU Commissioning |  | AHU Commissioning
Checkpoint | Unit Operational, checked for vibration and noise
Checklist | AC Branch Box Rough In |  | AC Branch Box Rough In
Checkpoint | Unit Model Number correct & Labelled with a clear photo of Both Model & Serial Numbers
Checkpoint | Model Number correct & Labelled
Checkpoint | Vibration mounts installed
Checklist | AC Branch Box Pipe & Drains |  | AC Branch Box Pipe & Drains
Checkpoint | Unit Model Number correct & Labelled with a clear photo of Both Model & Serial Numbers
Checkpoint | Refrigeration pipework roughed in
Checkpoint | Condensate drain pipework installed and hose clamps fitted
Checklist | Auto Refill Units |  | Auto Refill Units
Checkpoint | Unit Model Number correct & Labelled with a clear photo of Both Model & Serial Numbers
Checkpoint | Pipework connected and no leaks
Checklist | Boiler |  | Boiler
Checkpoint | Unit Model Number correct & Labelled with a clear photo of Both Model & Serial Numbers
Checkpoint | Pipework connected and no leaks
Checkpoint | Gas connected and leak tested
Checkpoint | Flue installed
Checkpoint | Operation tested
Checklist | AC Ducted Unit Rough In |  | AC Ducted Unit Rough In
Checkpoint | Unit Model Number correct & Labelled with a clear photo of Both Model & Serial Numbers
Checkpoint | Vibration mounts installed
Checkpoint | Pipework roughed in
Checkpoint | Condensate drains installed to tundish/waste point provided and hose clamps fitted
Checkpoint | All solid ductwork installed as per drawings, including flexible connections
Checkpoint | Dampers installed (NRD, VC, FD, MVCD) and all fully opened
Checkpoint | All cushion heads installed, including flexible connections, and set out as per the drawing layout
Checkpoint | (Fit-Off) Grilles/louvres installed
Checkpoint | (Fit-Off) Filters installed and are removable
Checkpoint | (Fit-Off) Condensate drains installed and terminated to correct location and tested
Checklist | AC Ducted Unit Commissioning |  | AC Ducted Unit Commissioning
Checkpoint | Check Operation of unit
Checkpoint | Check for noise and vibration
Checklist | AC High wall mounted Rough In |  | AC High wall mounted Rough In
Checkpoint | Unit Model Number correct & Labelled with a clear photo of Both Model & Serial Numbers
Checkpoint | Refrigeration pipework roughed in to correct location
Checkpoint | Condensate drains installed to tundish/waste point provided
Checkpoint | (Fit-Off) The wall mount was fitted off and checked for level
Checkpoint | (Fit-Off) Condensate drains terminated at tundish and tested
Checklist | AC Outdoor unit (Stand Alone) Fit Off |  | AC Outdoor unit (Stand Alone) Fit Off
Checkpoint | Unit Model Number correct & Labelled with a clear photo of Both Model & Serial Numbers
Checkpoint | Condensate drains installed to tundish/waste point provided
Checkpoint | System pressure tested to 400PSI
Checklist | AC Outdoor unit (Stand Alone) Commissioning |  | AC Outdoor unit (Stand Alone) Commissioning
Checkpoint | System evacuated and valves opened
Checkpoint | Operation checked
Checklist | AC Outdoor unit (VRF) Fit Off |  | AC Outdoor unit (VRF) Fit Off
Checkpoint | Unit Model Number correct & Labelled with a clear photo of Both Model & Serial Numbers
Checkpoint | Vibration mounts installed
Checkpoint | Condensate drains installed to tundish/waste point provided
Checkpoint | System pressure tested to 400PSI
Checklist | AC Outdoor unit (VRF) Commissioning |  | AC Outdoor unit (VRF) Commissioning
Checkpoint | System evacuated and valves opened - Photo of vac stat required
Checkpoint | Operation checked
Checklist | AC Outdoor unit (VRV) Fit Off |  | AC Outdoor unit (VRV) Fit Off
Checkpoint | Unit Model Number correct & Labelled with a clear photo of Both Model & Serial Numbers
Checkpoint | Vibration mounts installed
Checkpoint | Condensate drains installed to tundish/waste point provided
Checkpoint | System pressure tested to 400PSI
Checklist | AC Outdoor unit (VRV) Commissioning |  | AC Outdoor unit (VRV) Commissioning
Checkpoint | System evacuated and valves opened - Photo of vac stat required
Checkpoint | Operation checked
Checklist | Cassette Rough In |  | Cassette Rough In
Checkpoint | Unit Model Number correct & Labelled with a clear photo of Both Model & Serial Numbers
Checkpoint | vibration mounts installed
Checkpoint | Condensate drain installed including hose clamps
Checkpoint | Refrigeration pipework installed including insulation over flare nuts
Checkpoint | (Fit-Off) Fascia fitted square and plugged loom connected
Checklist | Cassette Commissioning |  | Cassette Commissioning
Checkpoint | check drain fitted of at tundish with air break
Checkpoint | Check Operation of unit heat/cool & louvre operation
Checklist | CHW FCU Rough In |  | CHW FCU Rough In
Checkpoint | Unit Model Number correct & Labelled with a clear photo of Both Model & Serial Numbers
Checkpoint | vibration mounts installed
Checkpoint | CHW pipework roughed in and connected to unit
Checkpoint | Condensate drains installed to tundish/waste point provided and hose clamps fitted
Checkpoint | All solid ductwork installed as per drawings, including flexible connections
Checkpoint | Dampers installed (NRD, VC, FD, MVCD) and all fully opened
Checkpoint | All cushion heads installed, including flexible connections, and set out as per the drawing layout
Checkpoint | (Fit-Off) Grilles/louvres installed
Checkpoint | (Fit-Off) Filters installed and are removable
Checkpoint | (Fit-Off) Check drain fitted off at tundish with air break
Checklist | CHW FCU Commissioning |  | CHW FCU Commissioning
Checkpoint | Check Operation of unit
Checkpoint | Check for noise and vibration
Checklist | CHW & HHW Pipework |  | CHW & HHW Pipework
Checkpoint | Pipework installed as per Shop Drawings & Schematic
Checkpoint | Pipework Pressure Tested
Checkpoint | Pipework checked for leaks & Labelled correctly
Checkpoint | Pipework lagging and cladding complete
Checklist | Chiller |  | Chiller
Checkpoint | Unit Model Number correct & Labelled with a clear photo of Both Model & Serial Numbers
Checkpoint | Vibration mounts installed
Checkpoint | Pipework connected and no leaks
Checkpoint | Operation tested
Checklist | Demo |  | Demo
Checkpoint | All flexible connections & cushion heads Demo as per drawing.
Checkpoint | All Rubbish Removed Area Clean And Tidy
Checklist | Demo & Decommission |  | Demo & Decommission
Checkpoint | Electrical isolated and made safe
Checkpoint | All Rubbish Removed Area Clean And Tidy
Checklist | AC Ducted Unit Ductwork |  | AC Ducted Unit Ductwork
Checkpoint | All solid ductwork installed as per drawings, including flexible connections
Checkpoint | Grilles/louvres installed
Checklist | Ductwork Rough In |  | Ductwork Rough In
Checkpoint | All weatherproof louvre installed as per drawings, including sealed & cleaned
Checkpoint | All solid ductwork installed as per drawings, including flexible / Spiral Duct connections
Checkpoint | Dampers installed (NRD, VC, FD, MVCD) and all fully opened
Checkpoint | (Fit-Off) Duct Blank Connected, as per drawing
Checklist | ERV Rough In |  | ERV Rough In
Checkpoint | Unit Model Number correct & Labelled with a clear photo of Both Model & Serial Numbers
Checkpoint | Vibration mounts installed
Checkpoint | Pipework roughed in
Checkpoint | Condensate drains installed to tundish/waste point provided and hose clamps fitted
Checkpoint | All solid ductwork installed as per drawings, including flexible connections
Checkpoint | Dampers installed (NRD, VC, FD, MVCD) and all fully opened
Checkpoint | Cowls installed
Checkpoint | All cushion heads installed, including flexible connections, and set out as per the drawing layout
Checkpoint | (Fit-Off) Grilles/louvres installed
Checkpoint | (Fit-Off) Filters installed and are removable
Checkpoint | (Fit-Off) Check drain fitted of at tundish with air break
Checklist | ERV Commissioning |  | ERV Commissioning
Checkpoint | Unit Operational, checked for vibration and noise
Checklist | Evap Cooler Rough In |  | Evap Cooler Rough In
Checkpoint | Unit Model Number correct & Labelled with a clear photo of Both Model & Serial Numbers
Checkpoint | Vibration mounts installed
Checkpoint | Water connection complete
Checkpoint | Drain to point of discharge installed
Checkpoint | All solid ductwork installed as per drawings, including flexible connections
Checkpoint | (Fit-Off) Dampers installed (NRD, VC, FD, MVCD) and all fully opened
Checkpoint | (Fit-Off) All cushion heads installed, including flexible connections, and set out as per the drawing layout
Checklist | Evap Commissioning |  | Evap Commissioning
Checkpoint | Unit Operational, checked for vibration and noise
Checklist | Expansion Tank |  | Expansion Tank
Checkpoint | Unit Model Number correct & Labelled with a clear photo of Both Model & Serial Numbers
Checkpoint | Vibration mounts installed
Checkpoint | Pipework connected and no leaks
Checklist | Fans Rough In |  | Fans Rough In
Checkpoint | Unit Model Number correct & Labelled with a clear photo of Both Model & Serial Numbers
Checkpoint | Vibration mounts installed
Checkpoint | All solid ductwork installed as per drawings, including flexible connections
Checkpoint | Dampers installed (NRD, VC, FD, MVCD) and all fully opened
Checkpoint | All cushion heads installed, including flexible connections, and set out as per the drawing layout
Checkpoint | (Fit-Off) Filters installed and are removable
Checkpoint | (Fit-Off) Grilles/louvres installed
Checklist | Fan Commissioning |  | Fan Commissioning
Checkpoint | Check for noise and vibration
Checklist | Ceiling Fans Rough In |  | Ceiling Fans Rough In
Checkpoint | Unit Model Number correct & Labelled with a clear photo of Both Model & Serial Numbers
Checkpoint | All cushion heads installed, including flexible connections, and set out as per the drawing layout
Checkpoint | (Fit-Off) Grilles/louvres installed
Checklist | Ceiling Fan Commissioning |  | Ceiling Fan Commissioning
Checkpoint | Check for noise and vibration
Checklist | Fire Damper & Pipework Penetration Checklist |  | Fire Damper & Pipework Penetration Checklist
Checkpoint | Fire treatment was installed correctly as per the Drawing, sealed and labelled with Photo on both sides.
Checklist | Flexible Connection & Cushin Heads |  | Flexible Connection & Cushin Heads
Checkpoint | All flexible connections & cushion heads are Installed s per drawings, including ductwork connections.
Checklist | MSSB Checklist |  | MSSB Checklist
Checkpoint | MSSB mounted in position
Checkpoint | MSSB Fitted off
Checkpoint | Main power connected to MSSB
Checklist | Package Unit |  | Package Unit
Checkpoint | Unit Model Number correct & Labelled with a clear photo of Both Model & Serial Numbers
Checkpoint | Vibration mounts installed
Checkpoint | All solid ductwork installed as per drawings, including flexible connections
Checkpoint | Dampers installed (NRD, VC, FD, MVCD) and all fully opened
Checkpoint | Overflashings installed
Checkpoint | Drains installed to waste point
Checkpoint | Operation tested
Checklist | Pumps |  | Pumps
Checkpoint | Unit Model Number correct & Labelled with a clear photo of Both Model & Serial Numbers
Checkpoint | Vibration mounts installed
Checkpoint | Pipework connected and no leaks
Checkpoint | Operation tested
Checklist | Radiators (HHW) ROUGH IN |  | Radiators (HHW) ROUGH IN
Checkpoint | backing plate installed prior to plaster
Checkpoint | (Fit-Off) Radiator Installed c/w pipework covers
Checkpoint | (Fit-Off) Checked for leaks
Checkpoint | (Fit-Off) Low temperature cover installed (As Applicable)
Checklist | Rangehood Rough In |  | Rangehood Rough In
Checkpoint | All weatherproof louvre installed as per drawings, including sealed & cleaned
Checkpoint | All solid ductwork installed as per drawings, including flexible / Spiral Duct connections
Checkpoint | All flexible ductwork installed
Checklist | Refrigeration Pipe |  | Refrigeration Pipe
Checkpoint | Pipework installed as per Schematic and Shop Drawings
Checkpoint | Actual Pipe Meters Recorded on schematic
Checkpoint | Pipework Pressure Tested @400 psi
Checklist | Roof Cowl (RC) |  | Roof Cowl (RC)
Checkpoint | RC Model Number correct, installed & RC Labelled
Checkpoint
Checklist | Spiral Ductwork |  | Spiral Ductwork
Checkpoint | All solid Spiral ductwork installed as per drawings, including flexible connections
Checklist | VAV |  | VAV
Checkpoint | Unit Model Number correct & Labelled with a clear photo of Both Model & Serial Numbers
Checkpoint | VAV installed, Model Number correct & unit Labelled
Checklist | As Built Markups |  | As Built Markups
Checkpoint | Need ability to add new checklist that we can name on site
Checklist | Builders Works |  | Builders Works
Checkpoint | Attach photos, files and comments as required - pass once complete
Checklist | Day Rate Works |  | Day Rate Works
Checkpoint | Need ability to add new checklist that we can name on site
Checklist | On-site Defects |  | On-site Defects
Checkpoint | Attach photos, files and comments as required - pass once complete
Checklist | Consultant Defects |  | Consultant Defects
Checkpoint | Attach photos, files and comments as required - pass once complete
Checklist | Drawings |  | Drawings
Checkpoint | Site Issued Drawings
Checklist | Delivery Docket |  | Delivery Docket
Checkpoint | Please take photo of delivery docket
Text | Date
Text | Work Area
Text | Material
Text | Supplier/Subcontractor
Checklist | Drafting & Design Issues |  | Drafting & Design Issues
Checkpoint | Need ability to add new checklist that we can name on site
Checklist | Installation Overview |  | Installation Overview
Checkpoint | Installation progress - Weekly Photo's of highlighted plans required
Checklist | Toolbox Meetings |  | Toolbox Meetings
Checkpoint | Site Meetings
Checklist | Site Issues |  | Site Issues
Checkpoint | Attach photos, files and comments as required - pass once complete
Checklist | SWMS |  | SWMS
Checkpoint | SWMS & Safety Plan submitted
Checklist | Working Permits |  | Working Permits
Checkpoint | Please take a photo of work permit
Text | Description of Permit
Text | Work Area