## Checklist Templates
Id | Type | Name | Values | Prompting Name
b3e8b1a1-a2a7-4a88-a43a-c9428e887f86 | checklist | 0. Add New Checklist |  | New Checklist:
d78a024d-f1d9-4e2b-91ff-26b86b435d73 | checkpoint | Attach photos, files and comments as required - pass once complete
cc8c2794-8ed1-48b0-8cda-bf623c2a9228 | checklist | 1. Builders Works & Site Issues |  | Builders Works & Site Issues
07fd980e-ab72-46d7-914d-58247d9564f2 | checkpoint | Attach photos, files and comments as required - pass once complete
d645931d-05cb-4e36-a006-56809ba39ad6 | checklist | 2. Day Rate Works |  | Day Rate Works
228602cc-90ed-46ad-85db-70742435b6f6 | checkpoint | Attach photos, files and comments as required - pass once complete
3bf38588-a95e-4b6f-a98d-1ae5601ade84 | checklist | 3. Drafting & Design Issues |  | Drafting & Design Issues
84b84eda-c655-4e56-be60-9ae6f11ef2a0 | checkpoint | Attach photos, files and comments as required - pass once complete
ca79d26e-d48d-4299-8391-4bc04f9023cd | checklist | 4. As Built Markups |  | As Built Markups
d35017bd-bb81-4af3-ba52-90a06b4d4a28 | checkpoint-no-value | Drawings
| checklist | AC Branch Box Rough In |  | AC Branch Box Rough In
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
| checkpoint | Unit Model Number correct & Labelled with a clear photo of Both Model & Serial Numbers
| checkpoint | Model Number correct & Labelled
| checkpoint | Vibration mounts installed
| checklist | AC Ducted Unit Commissioning |  | AC Ducted Unit Commissioning
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
| checkpoint | Check Operation of unit
| checkpoint | Check for noise and vibration
| checklist | AC Ducted Unit Ductwork |  | AC Ducted Unit Ductwork
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
| checkpoint | All solid ductwork installed as per drawings, including flexible connections
| checkpoint | Grilles/louvres installed
| checklist | AC Ducted Unit Rough In |  | AC Ducted Unit Rough In
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
| checkpoint | Unit Model Number correct & Labelled with a clear photo of Both Model & Serial Numbers
| checkpoint | Vibration mounts installed
| checkpoint | Pipework roughed in
| checkpoint | Condensate drains installed to tundish/waste point provided and hose clamps fitted
| checkpoint | All solid ductwork installed as per drawings, including flexible connections
| checkpoint | Dampers installed (NRD, VC, FD, MVCD) and all fully opened
| checkpoint | All cushion heads installed, including flexible connections, and set out as per the drawing layout
| checkpoint | (Fit-Off) Grilles/louvres installed
| checkpoint | (Fit-Off) Filters installed and are removable
| checkpoint | (Fit-Off) Condensate drains installed and terminated to correct location and tested
| checklist | AC High wall mounted Rough In |  | AC High wall mounted Rough In
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
| checkpoint | Unit Model Number correct & Labelled with a clear photo of Both Model & Serial Numbers
| checkpoint | Refrigeration pipework roughed in to correct location
| checkpoint | Condensate drains installed to tundish/waste point provided
| checkpoint | (Fit-Off) The wall mount was fitted off and checked for level
| checkpoint | (Fit-Off) Condensate drains terminated at tundish and tested
| checklist | AC Outdoor unit (Stand Alone) Commissioning |  | AC Outdoor unit (Stand Alone) Commissioning
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
| checkpoint | System evacuated and valves opened
| checkpoint | Operation checked
| checklist | AC Outdoor unit (Stand Alone) Fit Off |  | AC Outdoor unit (Stand Alone) Fit Off
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
| checkpoint | Unit Model Number correct & Labelled with a clear photo of Both Model & Serial Numbers
| checkpoint | Condensate drains installed to tundish/waste point provided
| checkpoint | System pressure tested to 400 PSI
| checklist | AC Outdoor unit (VRF) Commissioning |  | AC Outdoor unit (VRF) Commissioning
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
| checkpoint | System evacuated and valves opened - Photo of vac stat required
| checkpoint | Operation checked
| checklist | AC Outdoor unit (VRF) Fit Off |  | AC Outdoor unit (VRF) Fit Off
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
| checkpoint | Unit Model Number correct & Labelled with a clear photo of Both Model & Serial Numbers
| checkpoint | Vibration mounts installed
| checkpoint | Condensate drains installed to tundish/waste point provided
| checkpoint | System pressure tested to 400 PSI
| checklist | AC Outdoor unit (VRV) Commissioning |  | AC Outdoor unit (VRV) Commissioning
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
| checkpoint | System evacuated and valves opened - Photo of vac stat required
| checkpoint | Operation checked
| checklist | AC Outdoor unit (VRV) Fit Off |  | AC Outdoor unit (VRV) Fit Off
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
| checkpoint | Unit Model Number correct & Labelled with a clear photo of Both Model & Serial Numbers
| checkpoint | Vibration mounts installed
| checkpoint | Condensate drains installed to tundish/waste point provided
| checkpoint | System pressure tested to 400 PSI
| checklist | AHU Commissioning |  | AHU Commissioning
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
| checkpoint | Unit Operational, checked for vibration and noise
| checklist | AHU Rough In |  | AHU Rough In
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
| checkpoint | Unit Model Number correct & Labelled with a clear photo of Both Model & Serial Numbers
| checkpoint | Vibration mounts installed
| checkpoint | Pipework roughed in
| checkpoint | Condensate drains installed to tundish/waste point provided and hose clamps fitted
| checkpoint | All solid ductwork installed as per drawings, including flexible connections
| checkpoint | Dampers installed (NRD, VC, FD, MVCD) and all fully opened
| checkpoint | All cushion heads installed, including flexible connections, and set out as per the drawing layout
| checkpoint | (Fit-Off) Grilles/louvres installed
| checkpoint | (Fit-Off) Filters installed and are removable
| checkpoint | (Fit-Off) Condensate drains terminated at tundish and tested
| checklist | Auto Refill Units |  | Auto Refill Units
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
| checkpoint | Unit Model Number correct & Labelled with a clear photo of Both Model & Serial Numbers
| checkpoint | Pipework connected and no leaks
| checklist | Boiler |  | Boiler
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
| checkpoint | Unit Model Number correct & Labelled with a clear photo of Both Model & Serial Numbers
| checkpoint | Pipework connected and no leaks
| checkpoint | Gas connected and leak tested
| checkpoint | Flue installed
| checkpoint | Operation tested
| checklist | Branch Box Pipe & Drains |  | Branch Box Pipe & Drains
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
| checkpoint | Unit Model Number correct & Labelled with a clear photo of Both Model & Serial Numbers
| checkpoint | Refrigeration pipework roughed in
| checkpoint | Condensate drain pipework installed and hose clamps fitted
| checklist | Cassette Commissioning |  | Cassette Commissioning
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
| checkpoint | check drain fitted of at tundish with air break
| checkpoint | Check Operation of unit heat/cool & louvre operation
| checklist | Cassette Rough In |  | Cassette Rough In
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
| checkpoint | Unit Model Number correct & Labelled with a clear photo of Both Model & Serial Numbers
| checkpoint | vibration mounts installed
| checkpoint | Condensate drain installed including hose clamps
| checkpoint | Refrigeration pipework installed including insulation over flare nuts
| checkpoint | (Fit-Off) Fascia fitted square and plugged loom connected
| checklist | Ceiling Fan Commissioning |  | Ceiling Fan Commissioning
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
| checkpoint | Check for noise and vibration
| checklist | Ceiling Fans Rough In |  | Ceiling Fans Rough In
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
| checkpoint | Unit Model Number correct & Labelled with a clear photo of Both Model & Serial Numbers
| checkpoint | All cushion heads installed, including flexible connections, and set out as per the drawing layout
| checkpoint | (Fit-Off) Grilles/louvres installed
| checklist | Chiller |  | Chiller
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
| checkpoint | Unit Model Number correct & Labelled with a clear photo of Both Model & Serial Numbers
| checkpoint | Vibration mounts installed
| checkpoint | Pipework connected and no leaks
| checkpoint | Operation tested
| checklist | CHW & HHW Pipework |  | CHW & HHW Pipework
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
| checkpoint | Pipework installed as per Shop Drawings & Schematic
| checkpoint | Pipework Pressure Tested
| checkpoint | Pipework checked for leaks & Labelled correctly
| checkpoint | Pipework lagging and cladding complete
| checklist | CHW FCU Commissioning |  | CHW FCU Commissioning
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
| checkpoint | Check Operation of unit
| checkpoint | Check for noise and vibration
| checklist | CHW FCU Rough In |  | CHW FCU Rough In
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
| checkpoint | Unit Model Number correct & Labelled with a clear photo of Both Model & Serial Numbers
| checkpoint | vibration mounts installed
| checkpoint | CHW pipework roughed in and connected to unit
| checkpoint | Condensate drains installed to tundish/waste point provided and hose clamps fitted
| checkpoint | All solid ductwork installed as per drawings, including flexible connections
| checkpoint | Dampers installed (NRD, VC, FD, MVCD) and all fully opened
| checkpoint | All cushion heads installed, including flexible connections, and set out as per the drawing layout
| checkpoint | (Fit-Off) Grilles/louvres installed
| checkpoint | (Fit-Off) Filters installed and are removable
| checkpoint | (Fit-Off) Check drain fitted off at tundish with air break
| checklist | Defect |  | Defect
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
| checkpoint | Defect rectified
| checklist | Delivery Docket |  | Delivery Docket
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
| checkpoint | Please take photo of delivery docket
715a3156-51bd-5ee2-a700-639c8df43548 | textbox | Date
774fc8f2-e596-50d2-8eb2-06cc7993aa7e | textbox | Work Area
ebdef555-3afc-586a-91d6-3738417a5db2 | textbox | Material
e16407c8-e274-529b-b899-d29c7047f338 | textbox | Supplier/Subcontractor
| checklist | Demo |  | Demo
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
| checkpoint | All flexible connections & cushion heads Demo as per drawing.
| checkpoint | All Rubbish Removed Area Clean And Tidy
| checklist | Demo & Decommission |  | Demo & Decommission
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
| checkpoint | Electrical isolated and made safe
| checkpoint | All Rubbish Removed Area Clean And Tidy
| checklist | Ductwork Rough In |  | Ductwork Rough In
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
| checkpoint | All weatherproof louvre installed as per drawings, including sealed & cleaned
| checkpoint | All solid ductwork installed as per drawings, including flexible / Spiral Duct connections
| checkpoint | Dampers installed (NRD, VC, FD, MVCD) and all fully opened
| checkpoint | (Fit-Off) Duct Blank Connected, as per drawing
| checklist | Electric Duct Heater |  | Electric Duct Heater
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
| checkpoint | Unit Model Number correct & Labelled with a clear photo of Both Model & Serial Numbers
| checkpoint | Electric Duct Heater installed, Model Number correct & unit Labelled
| checklist | ERV Commissioning |  | ERV Commissioning
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
| checkpoint | Unit Operational, checked for vibration and noise
| checklist | ERV Rough In |  | ERV Rough In
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
| checkpoint | Unit Model Number correct & Labelled with a clear photo of Both Model & Serial Numbers
| checkpoint | Vibration mounts installed
| checkpoint | Pipework roughed in
| checkpoint | Condensate drains installed to tundish/waste point provided and hose clamps fitted
| checkpoint | All solid ductwork installed as per drawings, including flexible connections
| checkpoint | Dampers installed (NRD, VC, FD, MVCD) and all fully opened
| checkpoint | Cowls installed
| checkpoint | All cushion heads installed, including flexible connections, and set out as per the drawing layout
| checkpoint | (Fit-Off) Grilles/louvres installed
| checkpoint | (Fit-Off) Filters installed and are removable
| checkpoint | (Fit-Off) Check drain fitted of at tundish with air break
| checklist | Evap Commissioning |  | Evap Commissioning
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
| checkpoint | Unit Operational, checked for vibration and noise
| checklist | Evap Cooler Rough In |  | Evap Cooler Rough In
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
| checkpoint | Unit Model Number correct & Labelled with a clear photo of Both Model & Serial Numbers
| checkpoint | Vibration mounts installed
| checkpoint | Water connection complete
| checkpoint | Drain to point of discharge installed
| checkpoint | All solid ductwork installed as per drawings, including flexible connections
| checkpoint | (Fit-Off) Dampers installed (NRD, VC, FD, MVCD) and all fully opened
| checkpoint | (Fit-Off) All cushion heads installed, including flexible connections, and set out as per the drawing layout
| checklist | Expansion Tank |  | Expansion Tank
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
| checkpoint | Unit Model Number correct & Labelled with a clear photo of Both Model & Serial Numbers
| checkpoint | Vibration mounts installed
| checkpoint | Pipework connected and no leaks
| checklist | Fan Commissioning |  | Fan Commissioning
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
| checkpoint | Check for noise and vibration
| checklist | Fans Rough In |  | Fans Rough In
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
| checkpoint | Unit Model Number correct & Labelled with a clear photo of Both Model & Serial Numbers
| checkpoint | Vibration mounts installed
| checkpoint | All solid ductwork installed as per drawings, including flexible connections
| checkpoint | Dampers installed (NRD, VC, FD, MVCD) and all fully opened
| checkpoint | All cushion heads installed, including flexible connections, and set out as per the drawing layout
| checkpoint | (Fit-Off) Filters installed and are removable
| checkpoint | (Fit-Off) Grilles/louvres installed
| checklist | Fire Damper & Pipework Penetration Checklist |  | Fire Damper & Pipework Penetration Checklist
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
| checkpoint | Fire treatment was installed correctly as per the Drawing, sealed and labelled with Photo on both sides.
| checklist | Flexible Connection & Cushion Heads |  | Flexible Connection & Cushion Heads
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
| checkpoint | All flexible connections & cushion heads are Installed as per drawings, including ductwork connections.
| checklist | Installation Overview |  | Installation Overview
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
| checkpoint | Installation progress - Weekly Photos of highlighted plans required
| checklist | MSSB Checklist |  | MSSB Checklist
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
| checkpoint | MSSB mounted in position
| checkpoint | MSSB Fitted off
| checkpoint | Main power connected to MSSB
| checklist | Package Unit |  | Package Unit
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
| checkpoint | Unit Model Number correct & Labelled with a clear photo of Both Model & Serial Numbers
| checkpoint | Vibration mounts installed
| checkpoint | All solid ductwork installed as per drawings, including flexible connections
| checkpoint | Dampers installed (NRD, VC, FD, MVCD) and all fully opened
| checkpoint | Overflashings installed
| checkpoint | Drains installed to waste point
| checkpoint | Operation tested
| checklist | Project Details |  | Project Details
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
| checkpoint-no-value | Project Details:
d7a28f01-28d6-5e26-b66e-4ef91554de64 | note | Project Number:
c95679a2-2e3d-53fe-af9d-66fd408a3e3c | note | Builder:
fa48dc47-4365-5f78-ade6-490577a5dd8c | note | Project Manager:
| checklist | Pumps |  | Pumps
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
| checkpoint | Unit Model Number correct & Labelled with a clear photo of Both Model & Serial Numbers
| checkpoint | Vibration mounts installed
| checkpoint | Pipework connected and no leaks
| checkpoint | Operation tested
| checklist | Radiators (HHW) ROUGH IN |  | Radiators (HHW) ROUGH IN
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
| checkpoint | backing plate installed prior to plaster
| checkpoint | (Fit-Off) Radiator Installed c/w pipework covers
| checkpoint | (Fit-Off) Checked for leaks
| checkpoint | (Fit-Off) Low temperature cover installed (As Applicable)
| checklist | Rangehood Rough In |  | Rangehood Rough In
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
| checkpoint | All weatherproof louvre installed as per drawings, including sealed & cleaned
| checkpoint | All solid ductwork installed as per drawings, including flexible / Spiral Duct connections
| checkpoint | All flexible ductwork installed
| checklist | Refrigeration Pipe |  | Refrigeration Pipe
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
| checkpoint | Pipework installed as per Schematic and Shop Drawings
| checkpoint | Actual Pipe Meters Recorded on schematic
| checkpoint | Pipework Pressure Tested @400 psi
| checklist | Roof Cowl (RC) |  | Roof Cowl (RC)
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
| checkpoint | RC Model Number correct, installed & RC Labelled
checkpoint
| checklist | Spiral Ductwork |  | Spiral Ductwork
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
| checkpoint | All solid Spiral ductwork installed as per drawings, including flexible connections
| checklist | SWMS |  | SWMS
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
| checkpoint | SWMS & Safety Plan submitted
6062ebda-33ce-4e87-b020-e2dbf3aba4cd | checklist | Toolbox Meetings |  | Toolbox Meetings
f232dc52-f17a-4a6e-8f5d-6a0eee874bf5 | checkpoint | Toolbox/Pre start Talks
74bc5935-ffbe-50d4-9a54-28006b34fbfc | textbox | Workplace:
79a69737-f89f-5139-941a-ecbc87be2405 | textbox | Subject of Talk:
f7a35581-a749-543a-ae4b-d916a9ccd968 | textbox | Presented By:
e8b23741-0d6a-5e11-9b12-7d0965f87a3e | textbox | Duration:
6ff8007f-80e2-5701-89e4-0a28f4d611ea | note | Persons Present
99c51870-18f8-5525-a59b-64c0c497ea34 | textbox | Name:
0eceabce-12d9-5845-ad8a-d3930a09f8cc | textbox | Name:
5343772f-2894-55a1-b77b-cd1ebaf25fd3 | textbox | Name:
a92fa7b6-846a-55e6-9d06-f6a0080f7c9e | note | Points Raised/Comments:
700d7082-47de-5d14-bb3d-b43e6c769969 | note | Corrective Action
14b6bd4e-163d-5b05-8eb0-fd40edd309f2 | textbox | Action:
02426721-1751-5e34-9b49-3d0a5770685e | textbox | Action By:
1058edee-4705-4e41-b063-af5b5b428f2c | checkpoint | Action Completed Sign Off:
b17b0d54-5a6e-58db-95d7-909349f54a36 | note | Corrective Action
31d16baa-a6a8-55bc-9a32-afbbb70fc1e8 | textbox | Action:
b38e1240-8ebb-5eef-9699-f02cf420f693 | textbox | Action By:
2d3d8845-aecb-4ba0-8345-f03e1d748c08 | checkpoint | Action Completed Sign Off:
539155a6-70ca-5066-8f80-ac2bae6fe3d8 | note | Corrective Action
bd569ca6-72a9-5cb2-8f28-200e24b30429 | textbox | Action:
3bc1946c-8c0f-5dd0-8aa5-63171d4864f2 | textbox | Action By:
1159ed7f-9af5-445a-a81c-3fd7e2b607ea | checkpoint | Action Completed Sign Off:
| checklist | Toolbox Meetings (Site Meetings) |  | Toolbox Meetings
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
| checkpoint | Site Meetings
| checklist | VAV |  | VAV
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
| checkpoint | Unit Model Number correct & Labelled with a clear photo of Both Model & Serial Numbers
| checkpoint | VAV installed, Model Number correct & unit Labelled
| checklist | Working Permits |  | Working Permits
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
| checkpoint | Please take a photo of work permit
6365a5b7-a5d6-5c9d-be36-c32d11729a3b | textbox | Description of Permit
b60af7e5-dd30-5345-b21a-daf8c86fcfdc | textbox | Work Area