## Checklist Templates
Id | Type | Name | Values | Prompting Name | Resource Id
b3e8b1a1-a2a7-4a88-a43a-c9428e887f86 | checklist | 0. Add New Checklist |  | New Checklist: | 6e3eb524-192e-475e-a7dd-864644779ed8
d78a024d-f1d9-4e2b-91ff-26b86b435d73 | checkpoint | Attach photos, files and comments as required - pass once complete
d19aeb7c-610f-4d58-905c-ccac002655d3 | checklist | AC Branch Box Pipe & Drains |  | AC Branch Box Pipe & Drains | 4b62a5e3-508f-4e8c-826b-c4fce82893c5
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
84b9963a-d661-4eb9-9169-e26c68798fe1 | checkpoint | Unit Model Number correct & Labelled with a clear photo of Both Model & Serial Numbers
8245659c-b162-4209-8e40-74726625e209 | checkpoint | Refrigeration pipework roughed in
7e71dd82-306c-4ec8-a774-0b9161095aae | checkpoint | Condensate drain pipework installed and hose clamps fitted
746a34b2-0106-4476-9580-ed031c68f84d | checklist | AC Branch Box Rough In |  | AC Branch Box Rough In | 0e0a0261-8848-4c4d-bd5a-157f27b4aed7
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
5a78e12b-15cd-4829-9b40-8299d75c46a4 | checkpoint | Unit Model Number correct & Labelled with a clear photo of Both Model & Serial Numbers
f682b65c-ef03-4cf7-b63a-d421193fe721 | checkpoint | Model Number correct & Labelled
c759b167-6e28-49bc-98ea-0dd84061ff38 | checkpoint | Vibration mounts installed
0ed4cfb6-9b97-4581-b5cd-8fc8edd91178 | checklist | AC Ducted Unit Commissioning |  | AC Ducted Unit Commissioning | 09263809-e787-4a63-9f4f-92dc5d304505
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
e0352358-6b5a-433f-a019-eee7b365765a | checkpoint | Check Operation of unit
ea958383-4d38-4024-aa1e-85beabdac407 | checkpoint | Check for noise and vibration
b6fbdd2c-3ec9-44ed-8df7-1ee3cc2b4b6b | checklist | AC Ducted Unit Ductwork |  | AC Ducted Unit Ductwork | 01ee976a-2ad5-43e3-b661-bc6dec7671a0
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
881afc2e-ef97-4a9c-b09e-f0904f3ec8cb | checkpoint | All solid ductwork installed as per drawings, including flexible connections
1d187948-8bcb-4535-8abd-c042d7920766 | checkpoint | Grilles/louvres installed
1337ba3c-f3c5-412e-bcb9-8e954bd4fa35 | checklist | AC Ducted Unit Rough In |  | AC Ducted Unit Rough In | 412bfb3c-7f22-402f-b71c-4e90c9eaf506
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
53aa21c8-9574-439f-9a17-4fa5b32df62e | checkpoint | Unit Model Number correct & Labelled with a clear photo of Both Model & Serial Numbers
a95f1859-f19b-46f8-837e-63685db11255 | checkpoint | Vibration mounts installed
6fc915f9-e757-4d5c-879c-bb65fea5fdfb | checkpoint | Pipework roughed in
234b0214-5eb7-4322-a6a6-243bd4917445 | checkpoint | Condensate drains installed to tundish/waste point provided and hose clamps fitted
4d279ff5-7c28-438f-896f-1212fe8c9b2e | checkpoint | All solid ductwork installed as per drawings, including flexible connections
7cb43253-dbe5-40db-933c-a51bd21dcd90 | checkpoint | Dampers installed (NRD, VC, FD, MVCD) and all fully opened
074ad86a-c9a8-4c03-9ceb-c7296d8694e5 | checkpoint | All cushion heads installed, including flexible connections, and set out as per the drawing layout
82d2fbb6-4d4e-47f7-8b49-841321a5d23c | checkpoint | (Fit-Off) Grilles/louvres installed
74740633-5fe2-4967-8d3e-99f3eee901da | checkpoint | (Fit-Off) Filters installed and are removable
ea19a7ba-0c4c-4edc-acd7-054009542cd2 | checkpoint | (Fit-Off) Condensate drains installed and terminated to correct location and tested
c968b5d4-b93b-48a4-bd71-5edd5507e5a4 | checklist | AC High wall mounted Rough In |  | AC High wall mounted Rough In | e108a904-52e4-474b-a236-f4f5d59fc173
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
9478abdc-3d54-4cea-8bb0-aa82cf4e8844 | checkpoint | Unit Model Number correct & Labelled with a clear photo of Both Model & Serial Numbers
46b78ef6-b453-46b2-9463-8a5c69eaae9c | checkpoint | Refrigeration pipework roughed in to correct location
5dfe344b-1764-4d09-8fe4-f632e7176ab0 | checkpoint | Condensate drains installed to tundish/waste point provided
90489f55-7540-4d17-8b96-b385fb16316f | checkpoint | (Fit-Off) The wall mount was fitted off and checked for level
034a6505-5185-42a1-af4a-a52216128285 | checkpoint | (Fit-Off) Condensate drains terminated at tundish and tested
525bb408-e771-4741-901c-62f893433fe5 | checklist | AC Outdoor unit (Stand Alone) Commissioning |  | AC Outdoor unit (Stand Alone) Commissioning | a83a1bac-f180-4be8-a74e-90a1250841f6
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
c86365c7-feba-4360-b5f9-e9ea5cb8a16c | checkpoint | System evacuated and valves opened
5b60b240-cee2-490d-b013-e35ffbecbee8 | checkpoint | Operation checked
6ffa10ec-3286-464b-aed4-daddd2f771ae | checklist | AC Outdoor unit (Stand Alone) Fit Off |  | AC Outdoor unit (Stand Alone) Fit Off | 6485c77d-5c07-4188-a38f-8cb2972f9246
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
faeae2f1-cf00-48b5-9dca-206a5d041151 | checkpoint | Unit Model Number correct & Labelled with a clear photo of Both Model & Serial Numbers
6f48ad13-54be-4d43-a90b-7c2bf2041de5 | checkpoint | Condensate drains installed to tundish/waste point provided
155f0c8a-159e-4647-ab2a-7b6281b86265 | checkpoint | System pressure tested to 400PSI
fa68e34a-6b4e-4cc2-b72e-ef41ebdf2c9b | checklist | AC Outdoor unit (VRF) Commissioning |  | AC Outdoor unit (VRF) Commissioning | 3b41b42b-67db-4c39-8085-00b61e3889e5
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
e34ce673-a770-44db-915e-662cf9384476 | checkpoint | System evacuated and valves opened - Photo of vac stat required
c9cb5696-4d83-49c5-8d90-5afa5d22e420 | checkpoint | Operation checked
76ef5823-42c7-4a10-aa93-caac85d42e45 | checklist | AC Outdoor unit (VRF) Fit Off |  | AC Outdoor unit (VRF) Fit Off | aac0aed8-50c7-4c97-95eb-b7452ef4add4
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
680a6acd-111e-4e16-8237-6dc110ec2d7c | checkpoint | Unit Model Number correct & Labelled with a clear photo of Both Model & Serial Numbers
b68bfff2-e2e7-4600-8d66-f12438883f16 | checkpoint | Vibration mounts installed
003c4597-9f4c-41bd-ba78-381ca87c4824 | checkpoint | Condensate drains installed to tundish/waste point provided
ead2069c-d666-46a8-9c4e-69b8a47a03e1 | checkpoint | System pressure tested to 400PSI
b442f9c8-b074-4aab-8c83-79ec3db7585f | checklist | AC Outdoor unit (VRV) Commissioning |  | AC Outdoor unit (VRV) Commissioning | dd7622fd-8c75-4335-8520-c71c3942a91c
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
3aef0162-1599-4f93-90c5-102384a3ecab | checkpoint | System evacuated and valves opened - Photo of vac stat required
fd65a8a6-7b0a-46ab-8990-98a0075752ce | checkpoint | Operation checked
9874a44f-20e3-4253-8d0d-2dca6aa687b0 | checklist | AC Outdoor unit (VRV) Fit Off |  | AC Outdoor unit (VRV) Fit Off | de083b36-1ac4-44a4-a61c-39966133f7ac
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
598c84c8-9393-43c0-98af-2a8c90507d03 | checkpoint | Unit Model Number correct & Labelled with a clear photo of Both Model & Serial Numbers
00b12997-dbce-4a15-85ca-403ffe97f801 | checkpoint | Vibration mounts installed
b69d013e-1af7-49cd-a293-fff4a1323b95 | checkpoint | Condensate drains installed to tundish/waste point provided
12714026-f28e-4daa-8131-ecbafca2005b | checkpoint | System pressure tested to 400PSI
d1909bb0-ae3c-4c22-9767-a0606b17aee7 | checklist | AHU Commissioning |  | AHU Commissioning | 1944d6d9-9838-41e3-a298-21a8111068ae
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
b4c0600a-5ae9-4a5a-817e-4f243a5b007b | checkpoint | Unit Operational, checked for vibration and noise
a35a9b62-12af-4116-8c01-48529fbd1216 | checklist | AHU Rough In |  | AHU Rough In | 0aa424fa-07f7-4d46-a88d-de04942a8aa3
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
8b3f09a0-1d95-44aa-af49-e1142d8a5679 | checkpoint | Unit Model Number correct & Labelled with a clear photo of Both Model & Serial Numbers
5a3cfd90-5578-4f1d-84c5-c7b4fe72a1f3 | checkpoint | Vibration mounts installed
729b4d08-e4be-4831-939e-7470688cb546 | checkpoint | Pipework roughed in
4510cb68-90c3-4ebc-b3d5-5b3fc27024ea | checkpoint | Condensate drains installed to tundish/waste point provided and hose clamps fitted
c0c0f1f1-f29e-4dbb-a14a-a91106903abc | checkpoint | All solid ductwork installed as per drawings, including flexible connections
2d6cac5b-8846-4737-a208-b183cec2aa36 | checkpoint | Dampers installed (NRD, VC, FD, MVCD) and all fully opened
176fb547-cf7a-4bd1-8859-67a20d72899f | checkpoint | All cushion heads installed, including flexible connections, and set out as per the drawing layout
429907fd-4ed7-47f3-921a-024e771c0891 | checkpoint | (Fit-Off) Grilles/louvres installed
07b9252a-ab54-4430-9539-7e58e7b1d82b | checkpoint | (Fit-Off) Filters installed and are removable
c23396cd-e928-4187-82cc-da4dbfdf107c | checkpoint | (Fit-Off) Condensate drains terminated at tundish and tested
f8c17bd8-4ce6-415a-ba5f-23280bd3e302 | checklist | As Built Markups |  | As Built Markups | 575241ec-8f24-4139-8a02-62f77119f3fa
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
f0b703d7-c4e2-403b-b80c-0779ba781769 | checkpoint | Need ability to add new checklist that we can name on site
be54cb9c-30d0-40fa-9c09-e05233568cef | checklist | Auto Refill Units |  | Auto Refill Units | 3d514a4d-dd41-4dc3-834f-d781de81708e
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
d8c901db-412f-4ebe-9162-dd39c0ab1dae | checkpoint | Unit Model Number correct & Labelled with a clear photo of Both Model & Serial Numbers
1481f08c-9698-498e-90a7-8ac66e615b7e | checkpoint | Pipework connected and no leaks
40734b02-142f-42d1-aafb-46f7444103b6 | checklist | Boiler |  | Boiler | 71de01d7-1bea-4cca-ac15-45bbfe88eb55
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
3dd95ab3-5567-4f59-a575-6a230806b64e | checkpoint | Unit Model Number correct & Labelled with a clear photo of Both Model & Serial Numbers
a0068c91-ef06-4a74-9804-7a138cfa122a | checkpoint | Pipework connected and no leaks
aa09689a-4f40-4f6a-a2c0-7f3f3729ff35 | checkpoint | Gas connected and leak tested
4d7d5895-ca7d-4425-a37c-ccd08f8bd181 | checkpoint | Flue installed
3ad350ef-ee9d-4650-a2a0-7318c7c46f30 | checkpoint | Operation tested
88b718a5-dd55-4ee4-8e78-e7f1cc3d6f4b | checklist | Builders Works |  | Builders Works | 908cfd46-f2ef-44fc-9bb8-0d54699eedd8
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
ca8cd67f-2dd9-4942-881c-ea8cbaa78558 | checkpoint | Attach photos, files and comments as required - pass once complete
ad3eccfd-578d-4545-bf80-7a30201ceae4 | checklist | Cassette Commissioning |  | Cassette Commissioning | ead04965-ff65-44ea-960f-fddf15d4f40d
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
f5a20246-983c-4035-9d29-7fed7ddb3be0 | checkpoint | check drain fitted of at tundish with air break
33a62b47-79ba-40d3-a521-47a17826de3c | checkpoint | Check Operation of unit heat/cool & louvre operation
4251b305-547e-48c2-8be3-15487687517f | checklist | Cassette Rough In |  | Cassette Rough In | 71d5ae54-2dc6-42f5-8f94-aa7768b44341
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
a74d55ea-1700-4d8f-a874-5095e001dc5b | checkpoint | Unit Model Number correct & Labelled with a clear photo of Both Model & Serial Numbers
22b8fc59-e190-4092-97da-b1fc04a77339 | checkpoint | vibration mounts installed
b3bd98e0-7593-4fbf-9d5c-f52992f29788 | checkpoint | Condensate drain installed including hose clamps
fd4e60e2-be30-484d-8285-2a2102dd6fd5 | checkpoint | Refrigeration pipework installed including insulation over flare nuts
edc25d45-543a-45e8-a7eb-5420035070f2 | checkpoint | (Fit-Off) Fascia fitted square and plugged loom connected
adbacbde-7e4e-490a-bb24-d52da7167424 | checklist | Ceiling Fan Commissioning |  | Ceiling Fan Commissioning | 5c8f7527-f4d3-4a94-9827-dd460589d258
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
1a11b62d-482e-4623-b635-f80ce43c5ec5 | checkpoint | Check for noise and vibration
e6b2ae35-dd66-4b72-9c78-2a7b672e5a29 | checklist | Ceiling Fans Rough In |  | Ceiling Fans Rough In | 7c580ab5-5f1e-46ed-888a-a209acc95873
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
d4dde129-f401-4d04-bf4b-68c55a66bd13 | checkpoint | Unit Model Number correct & Labelled with a clear photo of Both Model & Serial Numbers
e4c3f48f-4aa3-45db-985c-a3ef3a0e2fb1 | checkpoint | All cushion heads installed, including flexible connections, and set out as per the drawing layout
4d3bb1d9-c923-4f1b-ad5d-f1275d8b637a | checkpoint | (Fit-Off) Grilles/louvres installed
8a567812-b7cb-4cf0-9938-ece6dbe66152 | checklist | Chiller |  | Chiller | 5537fdbc-154c-4c9f-807b-81a3055d410d
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
d391b9ae-1367-476f-affd-7792db3cd748 | checkpoint | Unit Model Number correct & Labelled with a clear photo of Both Model & Serial Numbers
6edf7ab5-58a7-44f5-955f-8c94e3e38129 | checkpoint | Vibration mounts installed
d66f1ad5-5049-4742-8355-5f6d14947ad6 | checkpoint | Pipework connected and no leaks
da887c2d-d168-4fe8-99e1-830bab1927b3 | checkpoint | Operation tested
d8808107-2ad9-4de2-b274-2e75a3291238 | checklist | CHW & HHW Pipework |  | CHW & HHW Pipework | fc6f1c88-7d01-4cd6-b602-20c21350b669
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
f2885865-27c5-43d2-ac4f-5af70d15eedb | checkpoint | Pipework installed as per Shop Drawings & Schematic
8baf4bd8-269f-405c-a68f-c85c4896dcc9 | checkpoint | Pipework Pressure Tested
d2a17a5d-8f2e-4c44-b71a-3d41bb26f74f | checkpoint | Pipework checked for leaks & Labelled correctly
9d1be3fb-1fa7-487d-bf3b-e90208b3086f | checkpoint | Pipework lagging and cladding complete
9cd191de-f194-4783-a21d-6820942ed893 | checklist | CHW FCU Commissioning |  | CHW FCU Commissioning | a3d5741a-98a4-4ea5-a4f0-b3e1871d6ff7
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
f3c5839c-c0bc-489d-b4d3-e315eb67ab7f | checkpoint | Check Operation of unit
171ec240-a3f5-48fd-b579-8f8b678c60ca | checkpoint | Check for noise and vibration
702a8c4b-0f3e-4bed-83b1-e252facc7ff4 | checklist | CHW FCU Rough In |  | CHW FCU Rough In | 02e71823-dd1e-4288-a868-bd0dce7a68ec
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
297a2ff3-0316-40e4-9bc2-de4553695ff3 | checkpoint | Unit Model Number correct & Labelled with a clear photo of Both Model & Serial Numbers
f85e54bf-65c4-4ed8-b726-26fec8eddc68 | checkpoint | vibration mounts installed
4c818f88-9437-4f84-9479-8e7572687f2c | checkpoint | CHW pipework roughed in and connected to unit
2a9b7b61-4409-4955-a74e-5a3c2b92e7b6 | checkpoint | Condensate drains installed to tundish/waste point provided and hose clamps fitted
7c6a4183-6cdd-4d9b-96dc-8c89ed7db573 | checkpoint | All solid ductwork installed as per drawings, including flexible connections
8e0d56e1-a31d-4d7d-b256-dc7e6ed4d415 | checkpoint | Dampers installed (NRD, VC, FD, MVCD) and all fully opened
b6892eb1-3adb-4139-ae83-cb39af1ce3e7 | checkpoint | All cushion heads installed, including flexible connections, and set out as per the drawing layout
c3f8f37a-f5c2-456e-a92a-16fa318a0eae | checkpoint | (Fit-Off) Grilles/louvres installed
f54d3097-dce2-48be-a459-7242c39dc875 | checkpoint | (Fit-Off) Filters installed and are removable
7dcc9712-235f-44bd-9cb0-fb0963bed925 | checkpoint | (Fit-Off) Check drain fitted off at tundish with air break
00ec9387-0d1f-4b81-8baf-87bdc1d8e7df | checklist | Day Rate Works |  | Day Rate Works | e18ac2bf-abc6-4e09-b5a3-107d96d56ebf
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
829b42a6-b265-4544-a8aa-2f2729b22fca | checkpoint | Need ability to add new checklist that we can name on site
94840040-6874-43cd-8a63-61f48f3d9a0a | checklist | Defect |  | Defect | 5c1947f7-2422-4333-924b-2989ef994c50
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
b0f074a2-003c-4acf-8431-080a0f4aa5cc | checkpoint | Attach photos, files and comments as required - pass once complete
7569b72f-a0b1-4155-b5db-a9992a4037e3 | checklist | Delivery Docket |  | Delivery Docket | f3a5d82a-e33c-458b-8c99-9559b49c220f
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
0e9c2132-bca5-4ccc-93a4-9ab4a61db87c | checkpoint | Please take photo of delivery docket
5b93596d-9ee3-54b0-aa7e-9025a0c2c371 | textbox | Date
cd68bf35-b7be-59f0-bb48-254813967672 | textbox | Work Area
39b33a54-65ab-523c-ab6e-16bc1123fe2d | textbox | Material
d6f83707-19e7-5a81-ad2f-45bf65cfa609 | textbox | Supplier/Subcontractor
7bd6f6a2-b9fc-4bd5-9d21-e45acb530570 | checklist | Demo |  | Demo | 89f6660e-1d68-4900-bf24-8496cc98a24a
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
560a6b28-476c-452e-a2d2-bc123d306159 | checkpoint | All flexible connections & cushion heads Demo as per drawing.
02e15875-9fb8-45d8-9614-e1321ba3c963 | checkpoint | All Rubbish Removed Area Clean And Tidy
1458bc15-34d3-4eed-abd9-0e7c0ccc9437 | checklist | Demo & Decommission |  | Demo & Decommission | d87bfa6d-1e33-4931-a798-ce4c1d87eb5d
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
2a754435-bd7b-4386-9f05-e3f79bc3bc99 | checkpoint | Electrical isolated and made safe
3ebbf379-977e-4fd2-a247-a0d699304172 | checkpoint | All Rubbish Removed Area Clean And Tidy
3d44671d-f3e2-4367-992c-edbf156b8d67 | checklist | Drafting & Design Issues |  | Drafting & Design Issues | 6ae7d63d-1d58-4565-bda2-6eeb005d0ce9
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
3f7a22f2-7216-4034-b40b-07429cce5fd7 | checkpoint | Need ability to add new checklist that we can name on site
3c72bff3-4d3f-475b-80a5-ef8dc4e6d302 | checklist | Drawings |  | Drawings | 6fbe9b52-3511-45d9-82ae-f8d54f77406d
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
a832bb2b-4487-4415-b05f-c709036f5ebc | checkpoint | Site Issued Drawings
a6ee2ad5-418e-4931-befa-07cf61912894 | checklist | Ductwork Rough In |  | Ductwork Rough In | 5d3be24b-ed1e-4a4d-9f29-0a576a502cce
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
7bf3d420-1fed-4959-984e-a4358f8cbfa7 | checkpoint | All weatherproof louvre installed as per drawings, including sealed & cleaned
213ac82c-900f-4960-a184-ab4f6898b7ac | checkpoint | All solid ductwork installed as per drawings, including flexible / Spiral Duct connections
9229e6d2-8b7d-46e0-a8a6-d82387439576 | checkpoint | Dampers installed (NRD, VC, FD, MVCD) and all fully opened
f0ffb9f6-2092-4d4a-a162-f5e0f3c8a9ae | checkpoint | (Fit-Off) Duct Blank Connected, as per drawing
761f24a3-0631-4d6b-bf7a-4b8e25493c6d | checklist | ERV Commissioning |  | ERV Commissioning | 8ed81e99-4b09-468d-a4e5-329daa24f174
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
f978d166-e2f6-4542-a94b-8b7baef2e98b | checkpoint | Unit Operational, checked for vibration and noise
57365109-5456-489d-8c3b-60b03b00ec7c | checklist | ERV Rough In |  | ERV Rough In | df90f1ab-f541-4873-8377-6fb9f85f5d88
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
3f619054-e43c-48ac-8559-2f989377148c | checkpoint | Unit Model Number correct & Labelled with a clear photo of Both Model & Serial Numbers
7c8aab0e-f2f0-4749-a565-5fca1bc041f6 | checkpoint | Vibration mounts installed
722ecb0d-bc13-433e-a4e1-5efdf089bf97 | checkpoint | Pipework roughed in
aa7776e4-db9b-4426-8a95-b7bc7bf33ea6 | checkpoint | Condensate drains installed to tundish/waste point provided and hose clamps fitted
485c5a88-e17b-401c-898f-97f779f96eac | checkpoint | All solid ductwork installed as per drawings, including flexible connections
4592b62c-df6a-43f6-9b69-bd27aa7e7f1d | checkpoint | Dampers installed (NRD, VC, FD, MVCD) and all fully opened
a779ecb0-0c8b-447d-b7da-af0cc4b8b731 | checkpoint | Cowls installed
f5c5b99e-1f3f-4c09-80c5-de0ded2ede32 | checkpoint | All cushion heads installed, including flexible connections, and set out as per the drawing layout
fe7e4c5f-52aa-46ee-b22c-2b1baf96c293 | checkpoint | (Fit-Off) Grilles/louvres installed
948729a2-edcd-4058-9e1d-1457cfc26f7f | checkpoint | (Fit-Off) Filters installed and are removable
508e1774-f3cd-47e8-a4f5-23142add4174 | checkpoint | (Fit-Off) Check drain fitted of at tundish with air break
39424322-8718-4a44-b64b-db6b22200a3c | checklist | Evap Commissioning |  | Evap Commissioning | e5c65eda-b741-4449-9e5b-2a0fdad5b2de
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
4c96e777-7a61-4766-a08e-17330f43a848 | checkpoint | Unit Operational, checked for vibration and noise
a0828fbd-3a55-4b92-83f8-dcb572a912da | checklist | Evap Cooler Rough In |  | Evap Cooler Rough In | d8eea99c-9a34-4af2-b7d2-36e055be64c8
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
60f6c4e1-f9b7-41ef-821d-8accb6b3577a | checkpoint | Unit Model Number correct & Labelled with a clear photo of Both Model & Serial Numbers
4aadde9d-947f-4c5e-9830-d5c131c8651c | checkpoint | Vibration mounts installed
bcce2d9e-cec6-4369-aeda-d86f056edae1 | checkpoint | Water connection complete
a792a44c-3f49-4959-ac92-b97c6a07b0a9 | checkpoint | Drain to point of discharge installed
e4c282e8-dd25-4745-8f96-d2865538df18 | checkpoint | All solid ductwork installed as per drawings, including flexible connections
59d77d8e-5457-4efd-a47d-05236d296c52 | checkpoint | (Fit-Off) Dampers installed (NRD, VC, FD, MVCD) and all fully opened
eb774f06-ef23-43e6-ae69-da766291d382 | checkpoint | (Fit-Off) All cushion heads installed, including flexible connections, and set out as per the drawing layout
96934aaa-05a7-416b-bf6e-9f9ba03d418c | checklist | Expansion Tank |  | Expansion Tank | a5f1e047-0775-4e61-b3ea-c3be7931bce3
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
a00b3cdf-9a40-4b37-9b90-05c316a7ee2d | checkpoint | Unit Model Number correct & Labelled with a clear photo of Both Model & Serial Numbers
a2e38910-e68b-47e8-ac79-acc247d91f37 | checkpoint | Vibration mounts installed
ef303877-b032-4847-942b-0a434d19233b | checkpoint | Pipework connected and no leaks
fc1ab150-d0de-4ac7-92e5-cd477f9d49b9 | checklist | Fan Commissioning |  | Fan Commissioning | 4f18bce3-01da-4c29-9c5b-385cf85a6559
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
98cf880b-8830-4aba-a4ca-d960e4769f2a | checkpoint | Check for noise and vibration
db7a9ed8-b4c2-4910-875a-fa1566cdc2ce | checklist | Fans Rough In |  | Fans Rough In | a409ca6b-09ea-4856-b15b-46e5fd3e4481
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
bc98769d-2add-4e72-9ce8-c35158fdaa33 | checkpoint | Unit Model Number correct & Labelled with a clear photo of Both Model & Serial Numbers
f70b733a-1b52-490a-b302-3a0d9149dae9 | checkpoint | Vibration mounts installed
e9d55eb2-d51b-4415-9275-44d280d658ab | checkpoint | All solid ductwork installed as per drawings, including flexible connections
74b9ce73-d671-45d3-8709-ca6daf7f064e | checkpoint | Dampers installed (NRD, VC, FD, MVCD) and all fully opened
68d4db94-d72c-445e-8304-9f8ecdb49edf | checkpoint | All cushion heads installed, including flexible connections, and set out as per the drawing layout
cbaf1d08-8eb0-4d52-a204-a482ccabf3c2 | checkpoint | (Fit-Off) Filters installed and are removable
6bd6fb79-914e-47ed-88c3-a979c20f4162 | checkpoint | (Fit-Off) Grilles/louvres installed
f864f4c7-9386-4882-852c-0a5d13e3d122 | checklist | Fire Damper & Pipework Penetration Checklist |  | Fire Damper & Pipework Penetration Checklist | feb21692-fb03-41ac-8cf1-ffaf8fb0808d
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
a22a1e31-d3f3-4a53-95d7-8c95492c18e4 | checkpoint | Fire treatment was installed correctly as per the Drawing, sealed and labelled with Photo on both sides.
8176a240-e100-4d08-8ba0-b79bba71cb5d | checklist | Flexible Connection & Cushin Heads |  | Flexible Connection & Cushin Heads | c22b2bb6-4927-4b2e-8e50-05f64e84bcc6
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
9dcab87b-7d83-43f5-be14-2da32411e8aa | checkpoint | All flexible connections & cushion heads are Installed s per drawings, including ductwork connections.
91bbfebc-6662-4c10-a0ab-3a9088e9ea9c | checklist | Installation Overview |  | Installation Overview | b181f00a-ac3b-4e65-a279-af94ed728960
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
e1740216-dbdb-4c4f-afbd-b8b01d08de58 | checkpoint | Installation progress - Weekly Photo's of highlighted plans required
36ad3a11-a76b-436f-9ebe-e9e201510a4c | checklist | MSSB Checklist |  | MSSB Checklist | 9bb8f7e1-a453-4775-9377-c36ed13b5bf4
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
69196f5f-c72a-4552-8424-91baf1c417ca | checkpoint | MSSB mounted in position
8e161dab-dba5-4f54-bdb0-61fe5935800d | checkpoint | MSSB Fitted off
64150c94-46c7-48ad-a5ee-ae7c1ddff481 | checkpoint | Main power connected to MSSB
bced1fef-0154-4726-9e9a-44e9e513a2b6 | checklist | Package Unit |  | Package Unit | f5c880f2-9afa-4e9d-b1c1-aebdee73f007
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
d01dbfe3-84dc-451b-8ff7-761aeea89d1a | checkpoint | Unit Model Number correct & Labelled with a clear photo of Both Model & Serial Numbers
36d8e055-616a-4f2f-bac1-ba4fb9cddd3c | checkpoint | Vibration mounts installed
ff3df963-2e8d-48c1-a8b3-86e864eb214f | checkpoint | All solid ductwork installed as per drawings, including flexible connections
8f137ca4-c4ac-4fdf-b2cf-e13fb816db4d | checkpoint | Dampers installed (NRD, VC, FD, MVCD) and all fully opened
0d769d44-9376-4c34-9c6e-610798c9f21d | checkpoint | Overflashings installed
049ce3d9-76ea-4173-8aa7-8e25e50e2e74 | checkpoint | Drains installed to waste point
d00ae535-cff0-480b-9333-2abac400c23b | checkpoint | Operation tested
6fedd0ec-ed0c-44a3-ba84-3a7b8f3fa6cd | checklist | Pumps |  | Pumps | 09cb0758-d0cf-4618-ab63-1de627bd43c6
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
00e671cc-7bb7-4d43-8826-b4f06db49850 | checkpoint | Unit Model Number correct & Labelled with a clear photo of Both Model & Serial Numbers
fcf7d78c-77db-4223-ab2f-bfe7a7495023 | checkpoint | Vibration mounts installed
8f794075-9d6f-4e61-bb58-c24b70ef7bdb | checkpoint | Pipework connected and no leaks
d40467e0-0aaf-4a64-9b60-9ee170c7e98f | checkpoint | Operation tested
a30b0cd7-cc77-4390-aad8-1d0b88152a4f | checklist | Radiators (HHW) ROUGH IN |  | Radiators (HHW) ROUGH IN | eda9c4c0-11df-48b6-a5c8-94ce83538391
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
7b956fe0-218e-40b2-ad53-c3f22470f126 | checkpoint | backing plate installed prior to plaster
baf8a3a6-4d8a-42c5-b92e-17b2d170673e | checkpoint | (Fit-Off) Radiator Installed c/w pipework covers
e1c34bb0-bd39-4a71-8ec8-7308c3c005f5 | checkpoint | (Fit-Off) Checked for leaks
6dd85a11-d543-46a6-84b2-fe261c00da19 | checkpoint | (Fit-Off) Low temperature cover installed (As Applicable)
170f8f1b-fa7f-49f1-9e71-9adb3f4ae8bf | checklist | Rangehood Rough In |  | Rangehood Rough In | e895b1f7-205e-4374-94b5-332a1c8f8a6c
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
b61ca8b4-9b83-4f68-91dc-737da78dfc2f | checkpoint | All weatherproof louvre installed as per drawings, including sealed & cleaned
76451aed-632c-4d6c-828e-ac11a60918bb | checkpoint | All solid ductwork installed as per drawings, including flexible / Spiral Duct connections
81bb2ba3-5a0b-470f-8bd6-bbd4e3f1667d | checkpoint | All flexible ductwork installed
91b4813f-b825-4afd-8fea-1ecf244c87c7 | checklist | Refrigeration Pipe |  | Refrigeration Pipe | 3661c85f-e864-45aa-8a25-0d08af31755c
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
22732920-e07d-4ae8-a9ed-4756420dced5 | checkpoint | Pipework installed as per Schematic and Shop Drawings
26c99903-2838-4bae-b26f-02f6e71e8471 | checkpoint | Actual Pipe Meters Recorded on schematic
112fb8ed-d173-4c93-ba69-24528e620667 | checkpoint | Pipework Pressure Tested @400 psi
4c9dcf2a-3af8-4f74-baac-ad285ba898a8 | checklist | Roof Cowl (RC) |  | Roof Cowl (RC) | f38a9c13-8f25-494a-a1b6-397effd7b4cb
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
b5410d0a-f173-456b-ac34-d3f672b9b91c | checkpoint | RC Model Number correct, installed & RC Labelled
517ce1c0-1fc7-42cd-97ae-76d08d7abebd | checkpoint
367f75a0-daea-4b07-93c3-de24a7c83750 | checklist | Site Issues |  | Site Issues | b9c72760-5baa-417f-ae4d-7db4d779a899
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
fb1db3f4-8ffd-4b84-84da-c9eac1f9738f | checkpoint | Attach photos, files and comments as required - pass once complete
7df43e98-13b1-4875-803b-29ed581d6828 | checklist | Spiral Ductwork |  | Spiral Ductwork | 3202075a-9481-4857-8ef4-9e8993b1e5a3
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
581bdaa5-d3d7-4d4d-ad5f-98d66cf6b350 | checkpoint | All solid Spiral ductwork installed as per drawings, including flexible connections
5f8d97bf-5b5e-4c0e-b86a-da2f70cdef74 | checklist | SWMS |  | SWMS | 05d9ebbb-9abb-489a-9d05-e0c5563e8260
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
2b920296-2f0b-4cd6-bcfb-c4bfcabed32d | checkpoint | SWMS & Safety Plan submitted
6062ebda-33ce-4e87-b020-e2dbf3aba4cd | checklist | Toolbox Meetings |  | Toolbox Meetings | 80bcdd52-916e-4522-82bf-f0ec1bf9cd5b
f232dc52-f17a-4a6e-8f5d-6a0eee874bf5 | checkpoint | Toolbox/Pre start Talks
74bc5935-ffbe-50d4-9a54-28006b34fbfc | textbox | Workplace:
79a69737-f89f-5139-941a-ecbc87be2405 | textbox | Subject of Talk:
f7a35581-a749-543a-ae4b-d916a9ccd968 | textbox | Presented By:
e8b23741-0d6a-5e11-9b12-7d0965f87a3e | textbox | Duration:
6ff8007f-80e2-5701-89e4-0a28f4d611ea | note | Persons Present
99c51870-18f8-5525-a59b-64c0c497ea34 | textbox | Name:
0eceabce-12d9-5845-ad8a-d3930a09f8cc | textbox | Name:
5343772f-2894-55a1-b77b-cd1ebaf25fd3 | textbox | Name:
a92fa7b6-846a-55e6-9d06-f6a0080f7c9e | note | Points Raised/Comments:
700d7082-47de-5d14-bb3d-b43e6c769969 | note | Corrective Action
14b6bd4e-163d-5b05-8eb0-fd40edd309f2 | textbox | Action:
02426721-1751-5e34-9b49-3d0a5770685e | textbox | Action By:
1058edee-4705-4e41-b063-af5b5b428f2c | checkpoint | Action Completed Sign Off:
b17b0d54-5a6e-58db-95d7-909349f54a36 | note | Corrective Action
31d16baa-a6a8-55bc-9a32-afbbb70fc1e8 | textbox | Action:
b38e1240-8ebb-5eef-9699-f02cf420f693 | textbox | Action By:
2d3d8845-aecb-4ba0-8345-f03e1d748c08 | checkpoint | Action Completed Sign Off:
539155a6-70ca-5066-8f80-ac2bae6fe3d8 | note | Corrective Action
bd569ca6-72a9-5cb2-8f28-200e24b30429 | textbox | Action:
3bc1946c-8c0f-5dd0-8aa5-63171d4864f2 | textbox | Action By:
1159ed7f-9af5-445a-a81c-3fd7e2b607ea | checkpoint | Action Completed Sign Off:
c9647af0-cd4a-43b9-80b6-4e8e10e2fa2f | checklist | Toolbox Meetings (Site Meetings) |  | Toolbox Meetings (Site Meetings) | 3ab41b91-02a7-43a7-8d30-e47ce7201968
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
f6141aab-02c7-4c1c-933c-1d152471ca1e | checkpoint | Site Meetings
36e02189-808d-4c35-971c-02fcf5ad2298 | checklist | VAV |  | VAV | 1d17f5ad-fa31-44fe-9dc9-c50a73d3a713
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
e65d7930-a0b3-4554-96a9-8216165cc285 | checkpoint | Unit Model Number correct & Labelled with a clear photo of Both Model & Serial Numbers
057b02ce-4fed-4164-beee-1a28a3827520 | checkpoint | VAV installed, Model Number correct & unit Labelled
94464ba1-40f6-4aaa-8713-8fc0ca2169e8 | checklist | Working Permits |  | Working Permits | a6ab31c1-3e40-4cb1-ba20-f0c1860da82c
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
0cadd3f2-8a41-4545-8ef7-6e92f214ad62 | checkpoint | Please take a photo of work permit
97798809-bbc0-5dca-9ec7-64a99c1be04f | textbox | Description of Permit
c5e2b185-f16d-5ee6-85f3-50d1fbe21c39 | textbox | Work Area