## Checklists
type | name | values
checklist-sectioned | Precast Components ITP
section | Manufacturing Documents
checkpoint | Shop drawings reviewed and updated. Issued "As For Construction" |  | upload a copy to CONQA?
section | Pre-Pour Checks
checkpoint | Final Inspection - all placed in accordance with approved shop drawings
tickbox | 5T Lifting Anchors | 2
tickbox | Reinforcement
tickbox | ID Plate | 1
tickbox | 40 Panel Mix
checkpoint | Upload sufficient number of photos pre pour
section | Concrete Pour Checks
checkpoint | Concrete Strength correct as per Construction Sciences Concrete Compressive Strength Report
tickbox | All Concrete Dockets Attached
section | Installation
checkpoint | All PPE and safety requirements in place. Machinery inspections complete.
checkpoint | Notification of Inspection - all in accordance with approved shop drawings, correct size and location
tickbox | Set out
checkpoint | Installation of precast panels including backpropping. Correct location, connections, finish confirmed against shop drawings.
checkpoint | Grouting and sealing
checkpoint | Remove backpropping when instructed by consulting Engineers.
section | Final Inspection
checkpoint | All approvals, certificates, data warranties, guarantees, manuals, as-built drawings collected.
checklist | Checkers Checklist
checkpoint | Overall Measurements
checkpoint | Voids Correct Position
checkpoint | Lifters Correct - Position, Size, Orientation
checkpoint | Fillet is Installed
checkpoint | Check Concrete cover around Reo 30mm
checkpoint | Panel Thickness confirmed
dropdown |  | 300mm
checkpoint | Magnets are 100% Secure
checkpoint | Panel is Clean
checkpoint | Photo Taken
checklist | Installers Checklist
checkpoint | Complete Material "Bucket List"
textbox | Nexus 5T Edge Lifter (T845)
textbox | ID Plate
checkpoint | Flick-out Panel Dimensions & DOUBLE CHECK
checkpoint | Apply bond breaker or wax 1 2 3
checkpoint | Temporary Fix ID Plate to Formwork
checkpoint | Use Timber Form Work on clean Plate. Off Form Finish
checkpoint | Install Reo as-per Shop Drawing Plan
checkpoint | Lifters to be Firm & Square against Formwork
checkpoint | Check Concrete cover around reo 30mm
checkpoint | DOUBLE CHECK EVERYTHING
checkpoint | Finish Required - Smooth Trowel Finish
checkpoint | QA - Final Check of ALL measurerments & Photos
checkpoint | QA - Concrete Mix N40 Panel Mix
checkpoint | QA - Check Concrete mix % before accepting. Allow enough mix time.
checkpoint | CONCRETE TEST TAKEN |  | upload docket?
date | Pour Date
checkpoint | NOT TO BE POURED WITHOUT APPROVAL FROM ENGINEER - NORTHROP |  | signoff?